## PLM Dashboard Data
App ID | APP NAME | Lifecycle State | App Acronym | PDO | LL4+ | LL5+ | LL6 | Architect | SLA | S-Ox | CIA | BMIT | IT Managed | Software Type | LL4 (Org) | LL5 (Org) | Business Skill Team | PDO (EAMS) | Description | Job Count / Report Count / VM Count | Java Apps - Type | Consider (Y/N) | Count | PDO Director | Scope Category | Platform | PDO Timing | Modernization Strategy | Category | Baseline Date | Planned Launch Date | Actual Launch Date | Overall Status | R/Y/G Status | Planned Infra. Decommission Date | Actual Infra. Decommission Date | Infra. Decommission Status | Decom Ticket # | S-Ox Milestone | Architecture Finalized % | Onboarding Pre-Prod % | Code Changes Complete % | UAT % | Onboarding Prod % | Prod Launch Complete % | Dev Sec Ops % | Planned VM for 2025 | Target Platform | Last Modified By | Last Modified | Revision History Date & Comment | PLM program Lead | Comments | Critical App | Platform Consolidation
53108 | Zebra Android Scanner | In Production | ZAS | ISIT | SKING68 | DCLEME13 | ENEWMAN1 | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Enterprise Technology | Industrial System IT | Record placeholder for approved Manufacturing standard Ruggedized handheld smart scanners. See Technology: 7019465 | 1 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
50417 | X-Functional Tire Estimator | Planned | Estimator | ISIT | JPITTERL | CBOHN | HBOYSEN | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | COTS | JPITTERL | CBOHN | Advanced PD and Tech | Industrial System IT | The x-functional tire estimator is a FEA system, which allows the generation of wheel and tire models without strong limitations. It consist of a computing kernel for model creation and a fully parametric model database, which can generate new virtual tire/rim combinations. The estimator can be used as a pre-processor to generate tire/rim models for the requested FEA code formats, e.g. Nastran, Radioss, LS-Dyna, Abaqus. | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
18718 | XUI-Cross Network Messaging User Interface | In Production | XUI | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | Non S-Ox | 111 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | User Interfaces that administratively support the XNet/ICE/RouteOne applications, such as the UI for the Chrome data processing. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Mainframe
18718 | XUI-Cross Network Messaging User Interface | In Production | XUI | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | Non S-Ox | 111 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | User Interfaces that administratively support the XNet/ICE/RouteOne applications, such as the UI for the Chrome data processing. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Version Upgrade | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
13896 | XNET | In Production | XNet | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | Non S-Ox | 222 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | XNet is a centralized global XML message processing system for applications/systems that need to access Ford Credit backend applications in North America, UK, and China. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Mainframe
13896 | XNET | In Production | XNet | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | Non S-Ox | 222 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | XNet is a centralized global XML message processing system for applications/systems that need to access Ford Credit backend applications in North America, UK, and China. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
50417 | X-Functional Tire Estimator | Planned | Estimator | ISIT | JPITTERL | CBOHN | HBOYSEN | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | COTS | JPITTERL | CBOHN | Advanced PD and Tech | Industrial System IT | The x-functional tire estimator is a FEA system, which allows the generation of wheel and tire models without strong limitations. It consist of a computing kernel for model creation and a fully parametric model database, which can generate new virtual tire/rim combinations. The estimator can be used as a pre-processor to generate tire/rim models for the requested FEA code formats, e.g. Nastran, Radioss, LS-Dyna, Abaqus. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
21453 | www.vehdyn.ford.com | In Production | vehdyn | ISIT | OTHERS | SLINDSTR | JVARGA6 | GRAO3 | Silver | Non S-Ox | 211 | Yes | No | In-House | KTROST | SLINDSTR | PD Operations and Quality | - | Web site used for core vehicle dynamics North America, to dissemite methods and tools to other vehicle dynamics organizations. | 6 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51393 | X-Carline Chart | In Production | XCC | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Current technical solution is a SQL-database providing one single data source for all global programs. Future development of the next generation of the X-Carline Chart targets at increased efficiency with further data |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2027 | Modernize to Cloud Databases | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | SQL
667 | WOW | In Production | WOW | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Bronze | Non S-Ox | 221 | No | Yes | In-House |  |  | Advanced PD and Tech | Industrial System IT | WOW! makes it easy to view and manipulate data contained in 'legacy' systems like CMMS, FDVS, GPIRS, GSPAS, Metaphase, MFAL, and WERS. You get full use of the MS Excel toolset which includes sorts, filters, pivots tables; as well as, many popular WOW! tools. Primary Users: Engineering, Finance, Weight, TRMC, Manufacturing, Planning, and Logistics. | 3 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51393 | X-Carline Chart | In Production | XCC | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House |  |  | PD Operations and Quality | Industrial System IT | Current technical solution is a SQL-database providing one single data source for all global programs. Future development of the next generation of the X-Carline Chart targets at increased efficiency with further data |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
21792 | Workforce One (WF1) - Kronos Workforce Central | In Production | WF1 | OCETO | TSWEEN16 | SCHILAKA | JALEXAN3 | MBALAN2 | Silver | S-Ox In Scope | 333 | No | Yes | COTS | DDESAI | SCHILAKA | Human Resources | Staffs IT | The Workforce One application (Kronos Workforce Central suite) includes modules for time and attendance, scheduling, manpower planning, absence management and leaves, labor distribution and activites/work orders in a single integrated workforce management system. | 43 |  | YES | 3 | TSWEEN16 | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  | 2025-06-15 |  | Planned |  | No | [8 empty] | SaaS | [5 empty] | No | VM
53138 | WPX Analytics | Planned | WPX | EPEO | SRUNSON | JROSCINI | DZDROJEW | YKADIYAL | Bronze | Non S-Ox | - | No | Yes | In-House | SRUNSON | JROSCINI | Enterprise Technology | EPEO | Workplace Experience - Workplace Insights and Analytics |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
14945 | WMA | In Production | WMA | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | The WMA Test System is a family of software products designed to store, archive, retrieve, analyze, and report test data (signature analysis) collected from transmission assembly and test stations. This is a quality and test system designed for process optimization and quality prior to shipment through enhanced test data analysis. | 12 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green | 2025-06-15 |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
15727 | WhereNet Yard Management System | In Production | WYMS | ISIT | VVIJAY55 | RADAM10 | PYORK | SSENTH15 | Copper | Non S-Ox | 111 | No | Yes | COTS |  |  | Manufacturing Staffs | Industrial System IT | WhereNet Yard Management Fast Gate, Auto Arrival, Request for shipper | 2 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
858 | Worldwide Integrated Purchasing System | In Production | WIPS | I-ERP | SARAUJO3 | KSYROCKI | SSHITIZ2 | SNAG1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Global Purchasing System used to source and price production and Service parts and materials. |  |  | YES | 3 | TSWEEN16 | PLM | Java Struts | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
858 | Worldwide Integrated Purchasing System | In Production | WIPS | I-ERP | SARAUJO3 | KSYROCKI | SSHITIZ2 | SNAG1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Global Purchasing System used to source and price production and Service parts and materials. |  |  | YES | 3 | TSWEEN16 | PLM | Mainframe | Q4 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
858 | Worldwide Integrated Purchasing System | In Production | WIPS | I-ERP | SARAUJO3 | KSYROCKI | SSHITIZ2 | SNAG1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Global Purchasing System used to source and price production and Service parts and materials. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
663 | Worldwide Engineering Release System | In Production | WERS | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Silver | Non S-Ox | 232 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | The Worldwide Engineering Release System (WERS) is an information system that manages and communicates part information to organizations and downstream systems. WERS facilitates communication between engineering and manufacturing, consolidates worldwide business practices, and eliminates redundant design efforts between regions. |  |  | YES | 4 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | DA
663 | Worldwide Engineering Release System | In Production | WERS | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Silver | Non S-Ox | 232 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | The Worldwide Engineering Release System (WERS) is an information system that manages and communicates part information to organizations and downstream systems. WERS facilitates communication between engineering and manufacturing, consolidates worldwide business practices, and eliminates redundant design efforts between regions. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
663 | Worldwide Engineering Release System | In Production | WERS | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Silver | Non S-Ox | 232 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | The Worldwide Engineering Release System (WERS) is an information system that manages and communicates part information to organizations and downstream systems. WERS facilitates communication between engineering and manufacturing, consolidates worldwide business practices, and eliminates redundant design efforts between regions. |  |  | YES | 4 | BWUNNAVA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
663 | Worldwide Engineering Release System | In Production | WERS | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Silver | Non S-Ox | 232 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | The Worldwide Engineering Release System (WERS) is an information system that manages and communicates part information to organizations and downstream systems. WERS facilitates communication between engineering and manufacturing, consolidates worldwide business practices, and eliminates redundant design efforts between regions. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
11759 | WORKS - Online Reporting and Knowledge System | In Production | WORKS | M&S TECH | FHIRSH | NGIRISH | LSCHLEBA | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | WORKS is the Business Objects tool used by GTS to receive and transmit batch files for vehicle and order status purposes. It is the adhoc reporting tool used by the business team. | 900 |  | YES | 3 | NKANDULA | PLM | BO | Q4 2025 | Migrate to QlikSense | Modernize | 2025-12-30 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | QlikSense | [5 empty] | No | DA
11759 | WORKS - Online Reporting and Knowledge System | In Production | WORKS | M&S TECH | FHIRSH | NGIRISH | LSCHLEBA | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | WORKS is the Business Objects tool used by GTS to receive and transmit batch files for vehicle and order status purposes. It is the adhoc reporting tool used by the business team. |  |  | YES | 3 | NKANDULA | PLM | Oracle | Q4 2027 | Modernize to Cloud Databases | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Oracle
13941 | Warranty Parts Analysis Center | In Production | WPAC | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JDEGUZMA | RMEHTA3 | Quality | Industrial System IT | 10/19/09: Change the app name from WPRC Parts Request System to WPAC. Note 8/17/09: This application is part of the suite that make up Application #13941 (WPRC - Part Request System). This application is marked with decommissioned status to make ITMS/SCRP work easier. Supplement PEARS mainframe application to speed data entry and approval process for WPAC parts requests. Web System allows WPAC customers to type the request. Requests are reviewed and approved by WPAC personnel before loaded into PEARS. - Engineers and Warranty evaluation teams use a web form to order parts for review from the WPRC. - Authorized WPAC personnel use a web form to approve/reject requests. - Approved requests are loaded into PEARS. - Web forms are available on the Ford Intra-net only. Not available on the supplier portal or any computer outside the Ford intra-net. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11515 | Workforce Profile | In Production | WFP | OCETO | TSWEEN16 | SCHILAKA | WPETER58 | MBALAN2 | Silver | Non S-Ox | 311 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | Batch Equal Employment Reporting for Hourly. Bureau of Labor Statistics and Hourly Employment Reports. | 11 |  | YES | 2 | TSWEEN16 | PLM | WebFocus - MF | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
11515 | Workforce Profile | In Production | WFP | OCETO | TSWEEN16 | SCHILAKA | WPETER58 | MBALAN2 | Silver | Non S-Ox | 311 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | Batch Equal Employment Reporting for Hourly. Bureau of Labor Statistics and Hourly Employment Reports. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q2 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Mainframe
21792 | Workforce One (WF1) - Kronos Workforce Central | In Production | WF1 | OCETO | TSWEEN16 | SCHILAKA | JALEXAN3 | MBALAN2 | Silver | S-Ox In Scope | 333 | No | Yes | COTS | DDESAI | SCHILAKA | Human Resources | 333 | The Workforce One application (Kronos Workforce Central suite) includes modules for time and attendance, scheduling, manpower planning, absence management and leaves, labor distribution and activites/work orders in a single integrated workforce management system. |  | Springboot | YES | 3 | TSWEEN16 | PLM | Java < v21 | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2025-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
21792 | Workforce One (WF1) - Kronos Workforce Central | In Production | WF1 | OCETO | TSWEEN16 | SCHILAKA | JALEXAN3 | MBALAN2 | Silver | S-Ox In Scope | 333 | No | Yes | COTS | DDESAI | SCHILAKA | Human Resources | Staffs IT | The Workforce One application (Kronos Workforce Central suite) includes modules for time and attendance, scheduling, manpower planning, absence management and leaves, labor distribution and activites/work orders in a single integrated workforce management system. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2025-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
56466 | VUFORIA STUDIO | Planned | PTC STUDIO | FORD PRO & FCSD TECH | MKAN | DGARANT1 | NHARRIER | MAJAY4 | - | Non S-Ox | - | Yes | No | - |  |  | Ford Customer Service | - | Software used to create augmented reality experiences using Ford 3D CAD images | 1 |  | YES | 1 | RKENNEL | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | SaaS | [5 empty] | No | VM
15910 | Workforce Management | In Production | WFM | FORD CREDIT | IPANKAJ | VSUNDA21 | VSANGEE6 | SMOCK6 | Silver | Non S-Ox | 111 | No | Yes | COTS | IPANKAJ | IPANKAJ | Ford Credit Services | Ford Credit (FMCC) | WFM Workforce application leveraged Verint Workforce Management, Verint Performance Management, Verint Desktop & Process Analytics, Nonvoice products of Verint. eWFM is used to create flexible and efficient agent work schedules, forecast future call volumes, determine the number of agents needed throughout the day and respond immediately to changes in call patterns and agent availability. All the ford credit application data feeds will flow into Verint via eWorkforce application It gives managers the information they need to work with individual agents to help them better adhere to their schedules, makes overall staffing plans more effective. Easily readable desktop windows show how many minutes early or late an agent logs on, when the agent logs out, and when the agent is on break or otherwise unavailable. A status bar constantly compares number of agents scheduled to the number actually logged in and signals when an agent has spent more than a specified amount of time in predetermined activity. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  | 2025-06-15 |  | Planned | [17 empty] | SQL
20071 | VSEM TEAMCENTER | In Production | VSEM TCUA | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | A Global Information Platform with seamless information management of electrical engineering data from Vehicle Feature/Function to ECU S/W & H/W inclusive. The platform will be used to manage electrical content throughout the lifecycle. The information platform will ultimately interface with Ford Blue Oval product definition systems to create a complete PLM solution for electronic/software data management. | 81 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
20431 | Workflow Mainframe Suite | Planned | WF MF | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RMANGAL | Silver | S-Ox In Scope | 211 | No | Yes | - | DTAURO | SKHAN29 | Ford Credit Services | - | The Workflow Mainframe Suite includes all mainframe programs jobs and technical platforms used to support the Ford Credit Workflow business processes. This application was deleted as a standalone app on May 18, 2021 and merged with the parent application (Workflow II FCNA) with app ID 19175. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | Q3 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Mainframe
51013 | Workflow II FAFC | In Production | WFIIFAFC | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 222 | No | Yes | In-House | JCHEN11 | JCHEN11 | Ford Credit Services | - | Provides initiate and routing activities related to Account Service Request, Charge Off, Direct Debit, Financial Change Notice (FCN), New Document Follow-up (NDF), Print Lien Release, Admin and Role Change that are utilized by Shanghai Business Center in China. Includes Server Components and Mainframe compents. |  |  | YES | 3 | SRAISIN1 | PLM | Oracle | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2025-06-15 |  | Planned | [10 empty] | Decommission | [6 empty] | Oracle
50401 | vRealize Orchestrator | Active | vRO | EPEO | LFULCHER | KMAHAJAN | MBRYAN66 | MPEKARSK | Silver | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | Enterprise Technology | ITO | Simplify the automation of complex IT tasks with VMware vRealize Orchestrator, which integrates with vRealize Suite and vCloud Suite to further improve service delivery efficiency, operational management and IT agility. | 10 |  | YES | 2 | SWALIMBE | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | VM
51013 | Workflow II FAFC | In Production | WFIIFAFC | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 222 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | - | Provides initiate and routing activities related to Account Service Request, Charge Off, Direct Debit, Financial Change Notice (FCN), New Document Follow-up (NDF), Print Lien Release, Admin and Role Change that are utilized by Shanghai Business Center in China. Includes Server Components and Mainframe compents. |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2025-06-15 |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
19175 | Workflow II | In Production | WorkflowII | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RPARAME4 | Copper | S-Ox In Scope | 321 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Business Process Management application Workflow to support Account Servicing functions at Ford Credit business centers. |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Mainframe
19175 | Workflow II | In Production | WorkflowII | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RPARAME4 | Copper | S-Ox In Scope | 321 | No | Yes | In-House | DTAURO | DTAURO | Ford Credit Services | Ford Credit (FMCC) | Business Process Management application Workflow to support Account Servicing functions at Ford Credit business centers. |  |  | YES | 3 | SRAISIN1 | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  | 2025-06-15 |  | Planned | [17 empty] | Oracle
50400 | vRealize Automation | Active | vRA | EPEO | LFULCHER | KMAHAJAN | MBRYAN66 | MPEKARSK | Silver | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | Enterprise Technology | ITO | VMware's cloud automation tool - vRealize Automation accelerates the delivery of IT services through automation and pre-defined policies | 6 |  | YES | 2 | SWALIMBE | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | VM
19175 | Workflow II | In Production | WorkflowII | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RPARAME4 | Copper | S-Ox In Scope | 321 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Business Process Management application Workflow to support Account Servicing functions at Ford Credit business centers. |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2025-06-15 |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
13060 | Work Order Request Manager | In Production | WORQ-RM | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | JKOONS | New Model Programs | Industrial System IT | WORQ (Work Order ReQuest) provides the ability to create, submit, and track Engineering Work Order ReQuests (WORQ). This app. supports Powertrain Engineering with electronic work order request forms for the tasks they need performed by the Prototype Build and Manufacturing sites. It also provides Prototype and Manufacturing Engineering with the information needed for managing work performed at a prototype facility. WORQ is used to track all types of work order requests including converter lab, metallurgical investigation, machine shop, tool design, internal work (people and their time), and part changes ... WORQ was originally created in 1995 and was ported to the WEB in 2002. Primary Users: Prototype Product and Manufacturing Engineering and Prototype Build Sites globally. NOTE: This application is replacing the VB3 version, WORQ 3.0, ITMS #775. Production support is billed is part of the WORQ suite currently billed under the prior WORQ application, itms #775. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2025-12-15 |  | Planned |  | No | 50% | 0% | 0% | 0% | 0% | 0% | 0% |  | Decommission | [5 empty] | No | Oracle
253 | IMCS : Inbound Material Carrier System | In Production | EuMP-IMCS | ISIT | JPITTERL | CBOHN | MBONAKDA | SSENTH15 | Bronze | S-Ox In Scope | 231 | No | Yes | In-House | CBOHN | IREINHO3 | Manufacturing Staffs | Industrial System IT | IMCS is the strategic European Ford System for carrier billing (400 Mill. $ p.A. ) tracking for all inbound material in UK and support generation of load lists (Waybill), freight invoicing, statistics and reporting. Main users of the system are Ford's external logistics partners, Ford Global Logistics and MP&L. SBI inclusion into this European application allows carrier invoices to be fed electronically into the Ford Accounts Payables system. |  |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-11-11 | 2024-10-28 | 2024-10-28 | Complete | Blue | 2024-11-30 | 2024-11-25 | Complete |  | Yes | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Decommission | Priya | 2025-03-10 |  |  | There is no STRUTS framework as part of the application architecture at present. The same was eliminated and the corresponding modules were rewritten in Java Springboot | No | Java < v21
54512 | VIN Segment Service | In Production | VinSeg | I-ERP | SVISWANA | VBHOOPAS | LWU14 | LWU14 | Gold | S-Ox In Scope | 233 | No | Yes | In-House | TSWEEN16 | SVISWANA | Finance | - | This service contains global VIN segment information and allows consume to inquire financial segment, such as Ford Blue, Pro, or Model E for a given set of VIN numbers | 8 |  | YES | 3 | TSWEEN16 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
9850 | Work Hours Maintenance System (eWHMS) | In Production | eWHMS | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SBONNICI | SBONNICI | PD Operations and Quality | Industrial System IT | Work Hours Management System - was created to electronically capture and report hours and head count information from hours charged against work orders at build sites and against GPIDs or Categories by the PD engineering community |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2025-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
24608 | Vertex Tax Performance Engine | In Production | Vertex TPE | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Copper | S-Ox In Scope | 331 | No | Yes | Managed by 3rd Party Purchased Service | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Tax Data Warehouse to manage data needed to support global tax processes. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21194 | Work Contract System | In Production | WCS | OCETO | TSWEEN16 | KKOEHLER | WALBERS | MBALAN2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DDESAI | KKOEHLER | Human Resources | Staffs IT | Current View of the Situation: According to the works constitution act the workers council is entitled to be informed and to review any work order in due time before implementation of the work order. Details are outlined in the works agreement (Betriebsvereinbarung) signed on 13-Sep-1991. In this context about 50,000 PNs per year need to be classified, reviewed, analysed and archived. Currently no working IT system is available to support this process. Better View of the Situation: Enable Ford HR and Betriebsrat to process all PNs, by providing a supporting IT system. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2026-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
21194 | Work Contract System | In Production | WCS | OCETO | TSWEEN16 | KKOEHLER | WALBERS | MBALAN2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DDESAI | KKOEHLER | Human Resources | Staffs IT | Current View of the Situation: According to the works constitution act the workers council is entitled to be informed and to review any work order in due time before implementation of the work order. Details are outlined in the works agreement (Betriebsvereinbarung) signed on 13-Sep-1991. In this context about 50,000 PNs per year need to be classified, reviewed, analysed and archived. Currently no working IT system is available to support this process. Better View of the Situation: Enable Ford HR and Betriebsrat to process all PNs, by providing a supporting IT system. |  |  | YES | 4 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  | 2025-06-15 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
23482 | VEME-C&FEE Coastdown | In Production | VEME | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Policy | Industrial System IT | Develop and deploy centralized repository for storing & retrieving information from Aerodynamics, Fuel Economy and C&FEE Coastdown Provide workflow option & e-signature process | 4 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21194 | Work Contract System | In Production | WCS | OCETO | TSWEEN16 | KKOEHLER | WALBERS | MBALAN2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DDESAI | KKOEHLER | Human Resources | Staffs IT | Current View of the Situation: According to the works constitution act the workers council is entitled to be informed and to review any work order in due time before implementation of the work order. Details are outlined in the works agreement (Betriebsvereinbarung) signed on 13-Sep-1991. In this context about 50,000 PNs per year need to be classified, reviewed, analysed and archived. Currently no working IT system is available to support this process. Better View of the Situation: Enable Ford HR and Betriebsrat to process all PNs, by providing a supporting IT system. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2026-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
14945 | WMA | In Production | WMA | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | SKING68 |  | Industrial System IT | The WMA Test System is a family of software products designed to store, archive, retrieve, analyze, and report test data (signature analysis) collected from transmission assembly and test stations. This is a quality and test system designed for process optimization and quality prior to shipment through enhanced test data analysis. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green | 2025-06-15 |  | Planned |  | No | [14 empty] | No | Oracle
14945 | WMA | In Production | WMA | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | The WMA Test System is a family of software products designed to store, archive, retrieve, analyze, and report test data (signature analysis) collected from transmission assembly and test stations. This is a quality and test system designed for process optimization and quality prior to shipment through enhanced test data analysis. |  |  | YES | 3 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green | 2025-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | DA
20804 | Vehicle Financial Systems | In Production | VFS | I-ERP | SFRANCI8 | SDHANAL3 | CSRIRAM | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | COTS | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Application to manage the record of new vehicle prices, create vehicle invoices for finished Vehicles. | 6 |  | YES | 1 | TSWEEN16 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52840 | WLTP Service | In Production | WLTP | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 212 | No | Yes | In-House | RKENNEL | JCHAUSSE | General Management | FCSD Tech | Service accessed via Motorcract to enable EU legislative requirement for vehicel converters to obtain certificate confirming revised C02 and fuel economy data when converting Ford commercial vehicles. |  |  | YES | 2 | RKENNEL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-15 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
22304 | Utility Data Collection System (UDACS) | In Production | Tridium | OCETO | TSWEEN16 | KADOMKAI | JANG | ESTILESK | Copper | Non S-Ox | 111 | No | Yes | COTS | DDESAI | KADOMKAI | Ford Land | Staffs IT | The Utility Data Collection System (UDACS)collects data from various devices, applications or machines transmits the data through a local data transmission appliance to Enterprize Data Center (EDC) The data is inserted into utility database and provides online reporting for the enduser. Additionally the system can recieve direction from a program and adjust control devices it is connected to. The application provides a graphical user interface showing real time information as well as historical. The system allows historical review of systems, their components, and associated infrastructure. This systems provides data for GEARS ITMS# 22195. The current supplier of UDACS is Tridium using the Niagara Software. | 10 |  | YES | 1 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
52840 | WLTP Service | In Production | WLTP | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 212 | No | Yes | In-House |  |  | General Management | FCSD Tech | Service accessed via Motorcract to enable EU legislative requirement for vehicel converters to obtain certificate confirming revised C02 and fuel economy data when converting Ford commercial vehicles. |  | Springboot | YES | 3 | RKENNEL | PLM | Java < v21 | Q3 2026 | Version Upgrade | Modernize | 2026-09-15 | 2026-09-15 |  | Complete | Blue | 2025-06-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | [5 empty] | No | Java < v21
870 | WIPS Ad Hoc Reporting | In Production | Ad Hoc | I-ERP | SARAUJO3 | CBISWADI | JBAJI | CWADE | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | SARAUJO3 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Read-only application supporting downstream applications and adhoc users; provides production-level Purchasing data sourced from WIPS and GSDB. Data contained on the WIPS AdHoc tables are pulled from the WIPS and GSDB databases on a daily basis, excluding inactive and removed parts. Reports can be run against AdHoc using customized queries via MS-Access software. (All canned reports and queries were decommissioned with the front-end as of September 2016.) |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2025-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
870 | WIPS Ad Hoc Reporting | In Production | Ad Hoc | I-ERP | SARAUJO3 | CBISWADI | JBAJI | CWADE | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Read-only application supporting downstream applications and adhoc users; provides production-level Purchasing data sourced from WIPS and GSDB. Data contained on the WIPS AdHoc tables are pulled from the WIPS and GSDB databases on a daily basis, excluding inactive and removed parts. Reports can be run against AdHoc using customized queries via MS-Access software. (All canned reports and queries were decommissioned with the front-end as of September 2016.) |  |  | YES | 3 | TSWEEN16 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
20856 | URL Management Tools | In Production | UMT | EPEO | MCRNKOVI | SPANDRAN | NVIDICAN | NVIDICAN | Copper | Non S-Ox | 111 | No | Yes | - | MCRNKOVI | MCRNKOVI | Enterprise Technology | EPEO | This tool consolidates Vanity URL and URL Shortening functions into one suite of tools. Vanity URL provides redirection of a fully-qualified domain name to a Sharepoint URL. (example: www.one.ford.com => https://comm.sp.ford.com/sites/ONEFordSite/Pages/Default.aspx) Vanity URL is provided via web forms that facilitate the required back-end processes for managing DNS requests. URL Shortening provides a means of shortening any long URL to a shorter string of no more than 5 characters. (example: http://x.ford.com/4 => https://www.tc.ford.com/ts/et/Advanced%20IT/analytics/Lists/Calendar/by_Subj_Workstream_Cal.aspx) URL shortening is provided via web-based forms. | 4 |  | YES | 2 | SWALIMBE | PLM | VM | TBD | EDC CaaS | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | EDC CaaS | [6 empty] | VM
108 | WINS: Wholesale Incentive System | In Production | WINS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Gold | Non S-Ox | 221 | No | Yes | In-House | KHEMANT | RANANDAL | Ford Customer Service | - | The Wholesale incentive systems supports the FCSD automotive service parts after market business. The after market business has long been a major profit center for Ford Motor Co. A key element of the FCSD Business growth strategy is increased wholesale parts sales through US Ford and Lincoln-Mercury dealers. Integral to the strategy is the payment of wholesale incentives on those parts where net pricing constitutes an unacceptable revenue loss. There is no direct interface between WINS and the dealers. Dealers interface with WINS via a second shadow application called 'WINS on the Web' which is administered by Archway. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
108 | WINS: Wholesale Incentive System | In Production | WINS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Gold | Non S-Ox | 221 | No | Yes | In-House | KHEMANT | RANANDAL | Ford Customer Service | - | The Wholesale incentive systems supports the FCSD automotive service parts after market business. The after market business has long been a major profit center for Ford Motor Co. A key element of the FCSD Business growth strategy is increased wholesale parts sales through US Ford and Lincoln-Mercury dealers. Integral to the strategy is the payment of wholesale incentives on those parts where net pricing constitutes an unacceptable revenue loss. There is no direct interface between WINS and the dealers. Dealers interface with WINS via a second shadow application called 'WINS on the Web' which is administered by Archway. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
52722 | Unified Prototype Data Interface | In Production | UPDI | ISIT | JSHANAH1 | SHERBER1 | SDAVIS13 | LPATIL | Bronze | Non S-Ox | 111 | Yes | No | Open Source | JSHANAH1 | SHERBER1 | PD Operations and Quality | - | Used to help groups communicate to get Prototype POs blanket setup, control parts falling into Suspense, and negotiate piece pricing. | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20513 | Wholesale Securitization Backend | In Production | GSWSB | FORD CREDIT | DTAURO | SKHAN29 | APAUL31 | VPOTTIBO | Silver | S-Ox In Scope | 233 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | 233 | Wholesale Securitization, a key funding source for Ford Credit, provides service to asset-backed securities for wholesale accounts in EU and NA. It is also used to move Dealer Credit Lines in and out of a Trust. This application supports Wholesale Securitization application. It is an application developed in-house and supported by Ford Credit IT. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
22235 | Wholesale Securitization | In Production | GSWS | FORD CREDIT | DTAURO | SKHAN29 | APAUL31 | VPOTTIBO | Silver | S-Ox In Scope | 232 | No | Yes | COTS | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Moody's ABS System provides the processing needed to track wholesale asset-based information and translate that asset-based information to produce investor reporting, and accounting and manage Cash Wires of the deals. This application relies on Wholesale Securitization backend processing. It is a vended application, hosted and supported by Ford Credit IT. It also includes My Friend which is a Windows based functionality developed in house to monitor ABS modules like Process Groups, Cash Management, Journal Entry, Calendar, User Roles, and New Deal Setup. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [10 empty] | Decommission | [6 empty] | SQL
51647 | Unified Bill of Material - Electrical | In Production | UniBOM | ISIT | OTHERS | KBERISTA | JPAWLOSK | LPATIL | Copper | Non S-Ox | 111 | Yes | No | In-House | CPAPADOM | KBERISTA | Advanced PD and Tech | - | Manage Data Population of UniBOM database for Electrical | 1 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
54144 | Wholesale Loss Database GDMS | Planned | WhLGDMS | FORD CREDIT | VMADHUSU | TMCCAFFR | SWELCH23 | SWELCH23 | - | S-Ox In Scope | - | Yes | No | COTS | VMADHUSU | TMCCAFFR | Ford Credit Services | - | Global Data Management and Services - Database to write back Wholesale Loss data (FCE) |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Cloud SQL PostgreSQL | [6 empty] | SQL
22746 | UBETestingSuite | In Production | UBEtest | ISIT | OTHERS | JVERHEY2 | EKOEHLE1 | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | In-House | MMAILE1 | JVERHEY2 | PD Operations and Quality | Industrial System IT | The UBE Testing Suite is a distributed application consisting of a SQL database and three frontend tools. The application is globally used within PD (VEV and EESE) to define and manage test scripts for vehicle software tests (Sequence Editor), to coordinate the test execution of those scripts (TMT v3) and to execute those scripts on the test environment (SATA) | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20341 | Wholesale Inventory Audit System-AiM Verify | In Production | IASAV | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | VPOTTIBO | Bronze | Non S-Ox | 211 | No | Yes | COTS | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | AiM Verify U.S. Wholesale Audit System allows AiM(Alliance Inspection Management) to electronically perform a wholesale audit on a dealer's floor plan inventory. The AiM Verify application contains functionality to schedule, perform, reconcile and report inventory audits. Detail audit data is also archived and is retrievable for its retention lifecycle according to GIS1. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Mainframe
15727 | WhereNet Yard Management System | In Production | WYMS | ISIT | VVIJAY55 | RADAM10 | PYORK | SSENTH15 | Copper | Non S-Ox | 111 | No | Yes | COTS | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | WhereNet Yard Management Fast Gate, Auto Arrival, Request for shipper |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
15727 | WhereNet Yard Management System | In Production | WYMS | ISIT | VVIJAY55 | RADAM10 | PYORK | SSENTH15 | Copper | Non S-Ox | 111 | No | Yes | COTS | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | WhereNet Yard Management Fast Gate, Auto Arrival, Request for shipper |  |  | YES | 3 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | DA
20179 | U/SAP - FUS SAP SPM Solution (FCSD) | In Production | Phoenix | I-ERP | SVISWANA | RKAMLAGE | VREDDY5 | MMEHTA5 | Gold | Non S-Ox | 232 | No | Yes | COTS | SVISWANA | RKAMLAGE | Ford Customer Service | FCSD Tech | Standard software 'SAP service parts management (SPM)' to support the US FCSD's SAP Service parts management business.SAP products involved are: ERP 6.18, PI 7.5, CRM 7.14, SCM-SPP 7.14, SCM-EWM 9.4.This is the non-S-Ox part of the SPM solution, whose S-Ox part is under the new number 51062 for the dedicated SAP EWM. | 123 |  | YES | 5 | TSWEEN16 | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
13539 | U/SAP - FoE SAP SPM Solution | In Production | SAP FoE | I-ERP | SVISWANA | RKAMLAGE | VGAUL | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | COTS | SVISWANA | RKAMLAGE | Ford Customer Service | FCSD Tech | Standard software 'SAP service parts management (SPM)' to support the EU FCSD's SAP Service parts management business. This includes the SPRINT business (Vendor managed inventory). Components: ERP 6.05, PI 7.3, CRM 7.02, CRM WCM 7.3, SCM-SPP 7.01, SCM-EWM 7.01, SCM-VMI 7.01. This is the non-S-Ox part of the SPM solution, whose S-Ox part is under the new number 51048 for dedicated SAP FI. | 144 |  | YES | 1 | TSWEEN16 | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
12974 | WERS DB2 Adhoc | In Production | WERSDB2 | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Silver | Non S-Ox | 231 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | WERS DB2 adhoc; To access the WERS DB2 AD-HOC Reporting system, you will need a TSO/RACF user ID. Your RACF Security Officer will be able to provide you with this ID. You will also need to have the DB2 contact listed connect you to the QMF system. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
14516 | Weld Quality Reporting System | In Production | WQR | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | WQR is a database application analytical tool used by plant personnel in their efforts to identify problem areas and improve weld quality by logging weld teardown data, weld surveillance data, and generating reports on the data collected. A weld teardown is a destructive process of pulling apart an assembly. Weld surveillance is a non-destructive process of visually inspecting and pry testing weld assemblies. |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
14516 | Weld Quality Reporting System | In Production | WQR | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | WQR is a database application analytical tool used by plant personnel in their efforts to identify problem areas and improve weld quality by logging weld teardown data, weld surveillance data, and generating reports on the data collected. A weld teardown is a destructive process of pulling apart an assembly. Weld surveillance is a non-destructive process of visually inspecting and pry testing weld assemblies. |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
14516 | Weld Quality Reporting System | In Production | WQR | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | WQR is a database application analytical tool used by plant personnel in their efforts to identify problem areas and improve weld quality by logging weld teardown data, weld surveillance data, and generating reports on the data collected. A weld teardown is a destructive process of pulling apart an assembly. Weld surveillance is a non-destructive process of visually inspecting and pry testing weld assemblies. |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | Q3 2026 | Modernize to Cloud Databases | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [14 empty] | No | SQL
20634 | TWOS Reporting System | In Production | TRS | OCETO | TSWEEN16 | SCHILAKA | JALEXAN3 | MBALAN2 | Bronze | Non S-Ox | 333 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | This is the Business Objects reporting application that reports data from the distributed TWOS application (ITMS #62) | 5 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | SaaS | [5 empty] | No | VM
755 | Certificate of Conformity | In Production | COC | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Bronze | Non S-Ox | 211 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Creation of Certificate of Conformity (CoC) in the National Sales Companies. Used within Ford EU and Ford Otosan. A mainframe Telon Cobol facility that generates CoC VIN data for specific vehicles in line with EU legislative requirements together with feed to central client server application which prints the Certificate of conformity (CoC) in the National Sales Companies. The data held on the system is also used to aid the registration systems. Being enhanced during 2015 to enable Digital Transmission of data via Registration Applications. Cross functionally managed - Business Owner MP&L; Consumption Funding EMS&S; BIT SESE; Project funding dependant on which skill team requests the change and what the change consists of. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Version Upgrade | Modernize | 2025-01-20 | 2024-12-20 | 2024-12-20 | Complete | Blue | 2025-01-20 | 2025-01-20 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Decommission | Priya | 2025-03-06 |  |  | Microservices running on Cloud run. Migration completed in 2024 & Decommission complete in Q1 2025 | No | Java < v21
52651 | Tririga Space Planning | In Production | TSP | OCETO | TSWEEN16 | KADOMKAI | TJACKS13 | ESTILESK | Silver | Non S-Ox | 211 | No | Yes | COTS | DDESAI | KADOMKAI | Ford Land | Staffs IT | Application used by Ford Land for Space Planning and Move Management and Desk Reservations | 32 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
20005 | WEBSPHERE APPLICATION SERVER | Active | WAS | EPEO | LFULCHER | EREYNOL3 | JKADAKIA | JKADAKIA | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | #N/A | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
16383 | WebQuote | In Production | WQ | I-ERP | SARAUJO3 | CBISWADI | TSUNDARA | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | - | Web Quote will electronically send Requests For Quotes (RFQs) from buyers to suppliers, receive quotes from suppliers, and publish the resulting Purchase Orders. It targets the global buying community, including Production and Non-Production buyers. |  |  | YES | 2 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-04-15 |  | In-Progress | Green | 2025-07-14 |  | Planned |  | No | 75% | 100% | 75% | 75% | 50% | 50% | 100% |  | Cloud Run | Praveen | 2025-03-06 |  |  |  | No | Java < v21
16383 | WebQuote | In Production | WQ | I-ERP | SARAUJO3 | CBISWADI | TSUNDARA | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | SARAUJO3 | Supply Chain | - | Web Quote will electronically send Requests For Quotes (RFQs) from buyers to suppliers, receive quotes from suppliers, and publish the resulting Purchase Orders. It targets the global buying community, including Production and Non-Production buyers. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 100% | 75% | 75% | 50% | 50% | 100% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-06 |  |  |  | No | Oracle
22002 | WebFOCUS - Shared | Active | WFOCUS-SE | EPEO | SKULKA52 | MWILLI20 | TCULLER | RMODI2 | Silver | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
623 | TranSend II (DataMyte) | In Production | TranSend | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | This application is used to extract and process measurement data collected by Datamyte data collector that are measuring the margin/flush and fixture data. The application sends the data to WBDM (Web Base Data Management). Transend is a desktop metrology software that is used to program and extract dimensional data from a Datamyte data collector. Transend II is a client/server metrology application | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
50444 | WebEx Teams BOTs and Integrations | In Production | WebExBOTS | EPEO | SRUNSON | PWILL357 | NRAMJI | GSIENKIE | Copper | Non S-Ox | 312 | No | Yes | In-House | SRUNSON | PWILL357 | Enterprise Technology | 211 | This application is to host the BOTs and Integrations developed for WebEx teams. |  | Springboot | YES | 3 | SWALIMBE | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
50444 | WebEx Teams BOTs and Integrations | In Production | WebExBOTS | EPEO | SRUNSON | PWILL357 | NRAMJI | GSIENKIE | Copper | Non S-Ox | 312 | No | Yes | In-House | SRUNSON | PWILL357 | Enterprise Technology | EPEO | This application is to host the BOTs and Integrations developed for WebEx teams. |  |  | YES | 3 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | SQL
15249 | Torque Inspection and Studies System/TPPS | In Production | TISS/TPPS | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | Yes | No | In-House |  |  | Manufacturing Engineering | Industrial System IT | TISS (Torque Inspection and Studies System) and TPPS (Torque Process Potential Studies) capture torque information from the plant floor to be used for inspection purposes. | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
25079 | Webex Portfolio | In Production | Webex | EPEO | SRUNSON | PWILL357 | RSCHUL18 | MLESNAU1 | Platinum | Non S-Ox | 313 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | PWILL357 | Enterprise Technology | EPEO | This is a Cisco collaboration suite enabling teams to collaborate by use of persistent messaging, video conferencing meetings w/screen share, interactive whiteboard, document sharing and integrated UCM calling. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
18817 | ToolsNet | In Production | Tnet | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | Yes | No | Managed by 3rd Party Purchased Service | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | Nutdrivers tork collection AP BMIT_IN_FIPL_ToolsNet | 43 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
12271 | Web Service Modules | In Production | WSMOD | M&S TECH | KHEMANT | KDANDUPA | AKURAMNA | JPOTTE60 | Gold | Non S-Ox | 122 | No | Yes | In-House | KHEMANT | KDANDUPA | Enterprise Technology | - | WSMOD(Web Service Modules) is collection of web services that provides for the retrieval of vehicle related information. Services include VIN Decoding, Genuine Scheduled Maintenance. Web service modules are designed to be re-usable functions that all Ford Trustmark brands and regions use in their consumer/dealer facing web applications and mobile applications. |  |  | YES | 4 | NKANDULA | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | Already done, as part of PCF migration | Yes | Java < v21
12271 | Web Service Modules | In Production | WSMOD | M&S TECH | KHEMANT | KDANDUPA | AKURAMNA | JPOTTE60 | Gold | Non S-Ox | 122 | No | Yes | In-House | KHEMANT | KDANDUPA | Enterprise Technology | - | WSMOD(Web Service Modules) is collection of web services that provides for the retrieval of vehicle related information. Services include VIN Decoding, Genuine Scheduled Maintenance. Web service modules are designed to be re-usable functions that all Ford Trustmark brands and regions use in their consumer/dealer facing web applications and mobile applications. |  |  | YES | 4 | NKANDULA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-02 | Complete | Blue | 2024-12-15 | 2025-01-24 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | Cloud SQL PostgreSQL |  |  |  |  | Already done, as part of PCF migration | Yes | SQL
24485 | TMT | In Production | TMT | ISIT | OTHERS | JVERHEY2 | EKOEHLE1 | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | In-House | MMAILE1 | JVERHEY2 | PD Operations and Quality | Industrial System IT | TMT (Test Management Tool) is an global, Application Server based Application to manage test complexity, test cases and to coordinate the test execution. TMT offers multiple Interfaces to other Tools as VSEM and offers a web based, graphical user interface to manage its data. TMT also offers a SOAP interface to other test relevant tools like Sequence Editor ATX, FTIDE etc. All test information is stored in a standardize ASAM ATX test description format. The Tool is in development until 2018. | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12271 | Web Service Modules | In Production | WSMOD | M&S TECH | KHEMANT | KDANDUPA | AKURAMNA | JPOTTE60 | Gold | Non S-Ox | 122 | No | Yes | In-House | KHEMANT | KDANDUPA | Enterprise Technology | - | WSMOD(Web Service Modules) is collection of web services that provides for the retrieval of vehicle related information. Services include VIN Decoding, Genuine Scheduled Maintenance. Web service modules are designed to be re-usable functions that all Ford Trustmark brands and regions use in their consumer/dealer facing web applications and mobile applications. |  |  | YES | 4 | NKANDULA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | Already done, as part of PCF migration | Yes | Java < v21
12740 | Web Information Systems Request (WebISR) | In Production | IntranetIT | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | Marketing, Sales and Service | There are several IT tools incorporated under this EAMS #. It includes WebISR, Time Tracker and Annual Access Review. The Web ISR is an integrated work flow tool that facilitates the initiation, approval, assignment, reporting, documentation and billing for Information Systems Requests. User roles are defined within the tool to support the various functions within IT. The tool ensures all projects adhere to the ITPM and SDM while also ensuring that documentation and audit requirements are met. As part of the IT intranet services the following sub-application is also included, Annual Access Review. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q1 2027 | Modernize to Cloud Databases | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [14 empty] | No | SQL
62 | Timekeeping and Work Orders (Hourly) | In Production | TWOS | OCETO | TSWEEN16 | SCHILAKA | JALEXAN3 | MBALAN2 | Silver | S-Ox In Scope | 333 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | Timekeeping and Work Orders (Hourly). The TWOS system manages timekeeping, personnel data and changes (moved to HCM 5/9/2022) , and labor distribution for all US and Canadian hourly personnel. TWOS delivers a widely recognized and respected timekeeping service that builds employee satisfaction and adheres to Company | 46 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | SaaS | [5 empty] | No | VM
13229 | Web Compile Tool for Oracle | Active | WCTO | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | - | No | - | - | AFRADKIN | AFRADKIN | Information Technology | Marketing, Sales and Service | WCTO - Web Compile Tool for Oracle is a tool, which provides a web interface to the End Users or Oracle DBAs to automate the validation and compilation of Oracle PL/SQL objects in the respective database. WCTO is formed by combine the Database Change Request system (DBCR) and Database Password Vault (FORDPVLT) applications. |  |  | YES | 1 | TSWEEN16 | PLM | Oracle | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
20504 | Web Based Data Management Website | In Production | WBDM | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | The Web Based Data Management (WBDM) web site (http://www.wbdm.ford.com) is a collection of elements whose function is to provide a means of sending and reporting out on Dimensional Control information at Stamping, Assembly Plants within the Ford enterprise. This project focus on the elements of WBDM that provide Dimensional Control Process Reports to Analysts at many locations globally. The work will focus on development of a process for managing the report files that will result in generation of the interface that will provide users access to these reports. |  |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | Q3 2026 | Modernize to Cloud Databases | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [14 empty] | No | SQL
19620 | TIME WINDOWS (VEHICLE UNLOADING) SPAIN | In Production | TWVU | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Plants | Industrial System IT | Application that controls incoming transport vehicles and monitors the unload of their content in the plant docks especially it keeps track of transport timings. | 4 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
15391 | Web Based Catalyst Packaging Information System | In Production | WCPI | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 221 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | The Web-based Catalyst Packaging System (WCPI) is utilized in the creation, transmittal and storage of Catalyst Packaging Information in support of the analysis and forecasting of the catalyst commodity. It is a web-based functional tool that was created to facilitate the design and procurement of PROTOTYPE catalyst systems. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize | 2024-08-16 | 2024-08-16 | 2024-08-16 | Complete | Blue | 2024-09-30 | 2024-09-25 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Priya | 2025-03-13 |  |  |  | No | SQL
15391 | Web Based Catalyst Packaging Information System | In Production | WCPI | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 221 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | The Web-based Catalyst Packaging System (WCPI) is utilized in the creation, transmittal and storage of Catalyst Packaging Information in support of the analysis and forecasting of the catalyst commodity. It is a web-based functional tool that was created to facilitate the design and procurement of PROTOTYPE catalyst systems. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [9 empty] | Priya |  |  |  |  | No | Java < v21
52683 | ThreatModeler | In Production | ThreatMod | OCETO | PMILLIGA | DZAJAC8 | MDUFFY35 | WJUSTICE | Bronze | Non S-Ox | 321 | No | Yes | COTS | TGEIGER | DZAJAC8 | Enterprise Technology | - | Threat Modeler will improve the vehicle and mobility cyber security management system, including an auditable process to assess risk, track issues, and manage evidence provision to support regulatory requirements placed on our vehicles and mobility products. It will be the Ford global threat model repository for all Ford vehicle and mobility products. | 4 |  | YES | 2 | PMILLIGA | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | SaaS | [5 empty] | No | VM
22327 | WBDO 2.0 | In Production | WBDO 2.0 | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | WBDO 2.0 is 2nd generation of Web Based Dealer Ordering application - a web-based solution for order entry, amendment and cancellation of unscheduled stock and retail orders for US dealers. The user interface is natural language-based, meaning that three-digit sales codes are no longer used to represent desired product content (this is a first step in moving towards a global solution). Instead, dealers are able to choose features via menus, prohibiting the entry of dirty or non-compatible orders. |  |  | YES | 5 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
22327 | WBDO 2.0 | In Production | WBDO 2.0 | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | WBDO 2.0 is 2nd generation of Web Based Dealer Ordering application - a web-based solution for order entry, amendment and cancellation of unscheduled stock and retail orders for US dealers. The user interface is natural language-based, meaning that three-digit sales codes are no longer used to represent desired product content (this is a first step in moving towards a global solution). Instead, dealers are able to choose features via menus, prohibiting the entry of dirty or non-compatible orders. |  |  | YES | 5 | NKANDULA | PLM | Java Struts | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
22327 | WBDO 2.0 | In Production | WBDO 2.0 | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | WBDO 2.0 is 2nd generation of Web Based Dealer Ordering application - a web-based solution for order entry, amendment and cancellation of unscheduled stock and retail orders for US dealers. The user interface is natural language-based, meaning that three-digit sales codes are no longer used to represent desired product content (this is a first step in moving towards a global solution). Instead, dealers are able to choose features via menus, prohibiting the entry of dirty or non-compatible orders. |  |  | YES | 5 | NKANDULA | PLM | SQL | Q3 2026 | Modernize to Cloud Databases | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | SQL
54579 | Threat Assessment Site/Risk Rating | In Production | TAS | OCETO | PMILLIGA | TYOUNG91 | DOREIL11 | WJUSTICE | Copper | Non S-Ox | 321 | No | Yes | In-House |  |  | Enterprise Technology | - | Tool to assess vulnerabilities in code and vehicles | 1 |  | YES | 2 | PMILLIGA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22327 | WBDO 2.0 | In Production | WBDO 2.0 | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | WBDO 2.0 is 2nd generation of Web Based Dealer Ordering application - a web-based solution for order entry, amendment and cancellation of unscheduled stock and retail orders for US dealers. The user interface is natural language-based, meaning that three-digit sales codes are no longer used to represent desired product content (this is a first step in moving towards a global solution). Instead, dealers are able to choose features via menus, prohibiting the entry of dirty or non-compatible orders. |  |  | YES | 5 | NKANDULA | PLM | WAS | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
23936 | WASS - Web Account Statement Solution | In Production | WASS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 222 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Regional applicaton Brazil and Argentina Inform local suppliers the status of invoices that are in the payment process, also available as a lumpsum files that were negotiated between supplier and purchases, in order to support further supplementary invoices. On-line input of supplier Service receip Access to supplier statement Create reports to inform suppliers the balance of retro price adjustments and resumen de entrega |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
24872 | Theorem Compute Clash | In Production | TheoremCC | ISIT | JKOONS | NLAKSHMA | KRAJES33 | GRAO3 | Copper | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | This application is targeted to identify similar assemblies/parts matches, from a large data resource. COTS application is used to provide similar assemblies/parts information based on the attributes identified by COTS application. | 7 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
23936 | WASS - Web Account Statement Solution | In Production | WASS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 222 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Regional applicaton Brazil and Argentina Inform local suppliers the status of invoices that are in the payment process, also available as a lumpsum files that were negotiated between supplier and purchases, in order to support further supplementary invoices. On-line input of supplier Service receip Access to supplier statement Create reports to inform suppliers the balance of retro price adjustments and resumen de entrega |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
13941 | Warranty Parts Analysis Center | In Production | WPAC | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JDEGUZMA | JDEGUZMA | Quality | Industrial System IT | 10/19/09: Change the app name from WPRC Parts Request System to WPAC. Note 8/17/09: This application is part of the suite that make up Application #13941 (WPRC - Part Request System). This application is marked with decommissioned status to make ITMS/SCRP work easier. Supplement PEARS mainframe application to speed data entry and approval process for WPAC parts requests. Web System allows WPAC customers to type the request. Requests are reviewed and approved by WPAC personnel before loaded into PEARS. - Engineers and Warranty evaluation teams use a web form to order parts for review from the WPRC. - Authorized WPAC personnel use a web form to approve/reject requests. - Approved requests are loaded into PEARS. - Web forms are available on the Ford Intra-net only. Not available on the supplier portal or any computer outside the Ford intra-net. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
24813 | TestRail Application | In Production | TR | EVDD | JREYN149 | NFAGEN | MGORDO64 | ECHURCHM | Silver | Non S-Ox | 111 | Yes | No | - | JREYN149 | NFAGEN | Advanced PD and Tech | - | TestRail is agile centric test management tool. It is used by testers, developers and team leads to manage, track and organize software testing efforts. TestRail allows team members to enter test cases, organize test suites, execute test runs and track their results, all from a modern and easy to use web interface. | 1 |  | YES | 1 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | VM
18127 | Warranty Analytical Data Repository | In Production | WADR | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | SSUBRA38 | VRAMASA6 | Silver | S-Ox In Scope | 231 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | Foundation for a consolidated Warranty information asset repository to be used cross brand and cross region for warranty and quality reporting | 1589 |  | YES | 3 | RKENNEL | PLM | Datastage | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [14 empty] | No | DA
18127 | Warranty Analytical Data Repository | In Production | WADR | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | SSUBRA38 | VRAMASA6 | Silver | S-Ox In Scope | 231 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | Foundation for a consolidated Warranty information asset repository to be used cross brand and cross region for warranty and quality reporting | 93 |  | YES | 3 | RKENNEL | PLM | WebFocus | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [14 empty] | No | DA
18127 | Warranty Analytical Data Repository | In Production | WADR | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | SSUBRA38 | VRAMASA6 | Silver | S-Ox In Scope | 231 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | Foundation for a consolidated Warranty information asset repository to be used cross brand and cross region for warranty and quality reporting |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q2 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
54984 | TEST DRIVE SCHEDULER | In Production | TDS | FORD PRO & FCSD TECH | TJUNIPER | AMEIKLE | CHAWKIN9 | HRUSSE26 | Gold | Non S-Ox | 311 | No | Yes | COTS | TJUNIPER | AMEIKLE | Marketing & Sales | Marketing, Sales and Service | Easy online booking system for Test Drive registration and transparency of availability (vehicles and time slots) across dealers/agents providing a consistent test drive experience. | 35 |  | YES | 3 | RKENNEL | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | SaaS | [5 empty] | No | VM
24159 | Warehouse Inventory Next Generation System | In Production | WINGS | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Ford Customer Service | - | Warehouse Management System (WMS) for South America, in replace of Perfit (North Group) and POPIMS (South Group/Brazil). Perform PS&L inventory management for the Region as a transitional solution for any global WMS initiative. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2025-04-30 |  | In-Progress |  | 2025-05-16 |  | Planned |  | No |  | 25% | 25% | 0% | 0% | 0% | 0% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
11486 | TER: Travel & Expense Reporting Online | In Production | TER | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Bronze | S-Ox In Scope | 331 | No | Yes | In-House |  |  | Finance | Staffs IT | TER Online - Web based expense entry, reporting and reimbursement system hosted and managed by Concur Corp. | 3 |  | YES | 5 | TSWEEN16 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24159 | Warehouse Inventory Next Generation System | In Production | WINGS | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Ford Customer Service | - | Warehouse Management System (WMS) for South America, in replace of Perfit (North Group) and POPIMS (South Group/Brazil). Perform PS&L inventory management for the Region as a transitional solution for any global WMS initiative. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2025-04-30 |  | In-Progress |  | 2025-05-16 |  | Planned |  | No |  | 25% | 25% | [5 empty] | Cloud Run | [5 empty] | No | Java < v21
50496 | Warehouse Inventory Next Generation sys- Ordering | In Production | WINGSO | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Ford Customer Service | - | Regional Parts Ordering system for South America. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-04-30 |  | In-Progress |  | 2025-05-16 |  | Planned |  | No |  | 25% | 25% | [5 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
51721 | Technical Assistance Center | In Production | TAC | FORD PRO & FCSD TECH | OTHERS | MKAN | MKUNES | SDHANAS2 | Copper | Non S-Ox | 111 | Yes | No | In-House | SBALZER1 | ETARQUIN | Ford Customer Service | - | Suite of Applications for Global Technical Assistance Centers (Hotlines). It includes the Cost Cap (For US and Canada markets), TACOS, EDP, and internal metrics/personnel management tools | 8 |  | YES | 2 | RKENNEL | PLM | VM | TBD | EDC CaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC CaaS | [5 empty] | No | VM
24209 | Warehouse Inventory Next Generation sys- Account | In Production | WINGSA | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Copper | S-Ox Out of Scope | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Regional FCSD Accounting system in SA |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-04-30 |  | In-Progress |  | 2025-05-16 |  | Planned |  | No |  | 25% | 25% | [5 empty] | SQL | [5 empty] | No | SQL
20562 | Teamcenter Multisite | In Production | MULTISITE | ISIT | JKOONS | NLAKSHMA | KRAJES33 | BAESCHLI | Silver | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | C3PNG multisite - part of Teamcenter. | 3 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
24209 | Warehouse Inventory Next Generation sys- Account | In Production | WINGSA | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Copper | S-Ox Out of Scope | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Regional FCSD Accounting system in SA |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2027 | Rewrite | Modernize | 2027-12-15 | 2025-04-30 |  | In-Progress |  | 2025-05-16 |  | Planned |  | No |  | 25% | 25% | [5 empty] | Cloud Run | [5 empty] | No | Java < v21
22511 | Warehouse Entry System | In Production | WES | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | WES is a data entry system for FCE EDW management reporting. The system also supports budgetary reporting for FCNA. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Mainframe
22511 | Warehouse Entry System | In Production | WES | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | WES is a data entry system for FCE EDW management reporting. The system also supports budgetary reporting for FCNA. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
18033 | WAR - Warranty Datawarehouse | In Production | WAR | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Customer Service | - | Database with warranty information that is used by Service staff to get information and compose some business report. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-07 | Complete | Blue | 2025-06-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | DB Migration completed | No | Oracle
22623 | TeamCenter Cache | In Production | TCCACHE | ISIT | JKOONS | NLAKSHMA | KRAJES33 | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | This application is to create a cache based solution to answer specific queries to Teamcenter application. A Cache (called as TC Cache) will be maintained outside of C3PNG Teamcenter and those specific queries will be answered by the TC Cache. The Cache will contain information of all Items related to Programs (such as Item Id, Owning User, LMD, Item Rev Id, CLI). Subsequent changes/updates in TeamCenter are captured at regular intervals and updated to Cache (Cache Refresh). This will improve the response time to queries and minimize the impact on Teamcenter from usage load. This will also help in monitoring the updates in TeamCenter and data growth in Teamcenter. | 24 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
21483 | Wallstreet Suite | In Production | WS Suite | I-ERP | SFRANCI8 | DSAKAMUR | KMOHAN15 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | Managed by 3rd Party Purchased Service | SFRANCI8 | DSAKAMUR | Finance | Integrated Enterprise Resource Planning (I-ERP) | Global Treasury Management system purchased from Wall Street Systems and externally hosted by ION on the AWS cloud. This application replaced the GTM (15383) application and replaced the Wall Street Classic (15302) application. Current functionality deployed used primarily by the Trading and Funding groups, Treasury Operations, and Treasury Accounting to administer external debt, intercompany debt, and derivatives for Ford Motor Company, Ford Credit, and its affiliates. The system produces cash wire feeds for the global cash system, operational reports, month-end accounting reports and general ledger feeds. WS Suite also reports and provides feeds for various systems used by Financial Strategy and Risk Management. | 151 |  | YES | 1 | TSWEEN16 | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
12096 | W2 Online | In Production | W2 | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | Display W2 online for salaried employees. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
12096 | W2 Online | In Production | W2 | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DDESAI | DDESAI | Finance | Staffs IT | Display W2 online for salaried employees. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 | 2025-01-25 | Complete | Blue | 2025-09-13 |  | Planned |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | GCP Migration is completed for Database. DB VMs decommissioning planned by Q2 2025 due to HRIMS dependency | No | Oracle
13090 | TEAMCENTER | In Production | TC | ISIT | JKOONS | NLAKSHMA | CCHADA | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Teamcenter Engineering is the new CAD data management solution, which combined with TeamCenter Enterprise will be the new strategic solution for C3P. | 166 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
12096 | W2 Online | In Production | W2 | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | Display W2 online for salaried employees. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
54585 | SystemLink Server | In Production | SLS | EVDD | RFRASE15 | ARODR425 | MCARNE15 | MCARNE15 | Gold | Non S-Ox | 111 | Yes | No | COTS | RFRASE15 | ARODR425 | Advanced PD and Tech | - | SystemLink enables teams to accomplish its systems management, asset management, test management, and data management tasks with a variety of software applications and add-ons. | 8 |  | YES | 1 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | VM
20071 | VSEM TEAMCENTER | In Production | VSEM TCUA | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | MNOWICK1 | MNOWICK1 | Advanced PD and Tech | Industrial System IT | A Global Information Platform with seamless information management of electrical engineering data from Vehicle Feature/Function to ECU S/W & H/W inclusive. The platform will be used to manage electrical content throughout the lifecycle. The information platform will ultimately interface with Ford Blue Oval product definition systems to create a complete PLM solution for electronic/software data management. |  |  | YES | 4 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
20071 | VSEM TEAMCENTER | In Production | VSEM TCUA | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | A Global Information Platform with seamless information management of electrical engineering data from Vehicle Feature/Function to ECU S/W & H/W inclusive. The platform will be used to manage electrical content throughout the lifecycle. The information platform will ultimately interface with Ford Blue Oval product definition systems to create a complete PLM solution for electronic/software data management. |  |  | YES | 4 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
53134 | SYNECT-Global | In Production | SYNECT | EVDD | FFRISCHM | PREDLICH | BFRIELIN | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | COTS | FFRISCHM | PREDLICH | Advanced PD and Tech | Industrial System IT | Synect is a tool that visualizes the efficiency of HIL (Hardware in the loop) test equipment. It also provides mechanisms to offload (costly) facility time operations to (cheaper) engineer's PCs. It also manages complexity aspects like configurations for HIL tests. | 8 |  | YES | 2 | MJONE308 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | EDC Hypervisor | [6 empty] | VM
20071 | VSEM TEAMCENTER | In Production | VSEM TCUA | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | A Global Information Platform with seamless information management of electrical engineering data from Vehicle Feature/Function to ECU S/W & H/W inclusive. The platform will be used to manage electrical content throughout the lifecycle. The information platform will ultimately interface with Ford Blue Oval product definition systems to create a complete PLM solution for electronic/software data management. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
20894 | VSEM Portal | In Production | VSEMPortal | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | In-House | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | Website portal for VSEM and IVS |  |  | YES | 2 | BWUNNAVA | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
20894 | VSEM Portal | In Production | VSEMPortal | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | In-House | MNOWICK1 | MNOWICK1 | Advanced PD and Tech | Industrial System IT | Website portal for VSEM and IVS |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
50401 | vRealize Orchestrator | Active | vRO | EPEO | LFULCHER | KMAHAJAN | MBRYAN66 | MPEKARSK | Silver | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | SQL
11417 | Synch. Material Replenishment Trigger (SMART) | In Production | SMART | ISIT | AMEHER1 | ADURSO | MBIJI | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | The SMART system is a line side material delivery system that reduces 4 wall and line side inventory in support of FPS Synch. Material Flow and empower Production Operators to determine when material is needed at line side. Three Process, SMART Card is used globally and store inventory usage by scanning kan-ban cards each cycle; SMART Call, used globally, mechanises the request process, allowing a lineside button press to trigger material replenishment which in turn stores inventory usage; SMART AutoCall, used globally, based on approx. inventory levels at lineside and BoM requirements for each vehicle, triggers SMART Call-style material replenish., again storing usage for analysis. For all three types of SMART, a part can be classified as an eSMART part for these parts, each delivery instance is sent electronically to suppliers via the eSMART. The application does not include primary supplier call-in, and does not deal with financials or purchasing of inventory, or the reporting of inventory levels | 42 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
50400 | vRealize Automation | Active | vRA | EPEO | LFULCHER | KMAHAJAN | MBRYAN66 | MPEKARSK | Silver | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | SQL
51932 | Surface Data Management System | In Production | SDMS | EVDD | IMCLAUGH | CWETZEL | MSHELP | GRAO3 | Silver | Non S-Ox | 322 | Yes | No | In-House | IMCLAUGH | CWETZEL | Advanced PD and Tech | Industrial System IT | Manages Surface change control (eSCR) during product development phase | 6 |  | YES | 2 | MJONE308 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
9887 | VRDB - Vehicle Rptg DB | In Production | EuMP-VRDB | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | VRDB is Vehicle Reporting DataBase and it is used primarily for 'Reporting'. Reports are generated to cover the entire view of both Scheduling and Forecast Data. All reporting is at SFI level, after EOCs have been Solved down to SFIs and then counted by Date of Requirement. It supports SCC Plants for any of the OTD Regions, which are FOE, AP1, AP2, AP3 & EUK Plants. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
14464 | Volumetric Truckload System | In Production | VT | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Parts Ordering for collison parts orders to be entered into the Order Entry Application. |  |  | YES | 2 | RKENNEL | PLM | SQL | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
20328 | Supplier Performance Rating - Global | In Production | SUPER-G | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Bronze | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | This system creates a delivery rating for all suppliers shipping into plants and FCSD sites globally. It provides this info to the Supplier Improvement Metrics (SIM) system for display to suppliers, internal review, and calculation of supplier Q1 score. SuPeR G is in development 2009-2012, planned to replace SDPR for MP&L & FCSD, SPEEDY, and S.A. SCM delivery rating functionality. | 7 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
903 | Volume of Payments (VOP) | In Production | VOP | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | VOP tracks actual payments to suppliers made by S4 Hana, CCAPS and Ford of Europe (GAPS/ERES) and provides extensive reports/data for Diversity (DEI) Suppliers (government requirements) |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q1 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
51795 | Voice of Quality (VoQ) | In Production | VoC | GDIA | KLIDDLE | KARORA4 | NMULIK | KZUREK | Bronze | Non S-Ox | 211 | No | Yes | In-House | KLIDDLE | PJOVANO4 | Enterprise Technology | 211 | Quality Net Promoter Score |  | Springboot | NO | 3 | FRANBELL | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
51795 | Voice of Quality (VoQ) | In Production | VoC | GDIA | KLIDDLE | KARORA4 | NMULIK | KZUREK | Bronze | Non S-Ox | 211 | No | Yes | In-House | KLIDDLE | PJOVANO4 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Quality Net Promoter Score |  |  | NO | 3 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
51795 | Voice of Quality (VoQ) | In Production | VoC | GDIA | KLIDDLE | KARORA4 | NMULIK | KZUREK | Bronze | Non S-Ox | 211 | No | Yes | In-House | KLIDDLE | PJOVANO4 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Quality Net Promoter Score |  |  | NO | 3 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
210 | VOEDIT & Import System | In Production | VOEDIT | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | S-Ox In Scope | 112 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | The VO-EDIT System edits the Vehicle Order Image of new orders and order amendments. The buildable orders will be sent to MP&L. VO-Edit also checks for the maximum plant capacity for buildable orders. VO-Edit also updates all downstream systems with order status. SLA 1, CIA 1,1,2 |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
210 | VOEDIT & Import System | In Production | VOEDIT | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | S-Ox In Scope | 112 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | The VO-EDIT System edits the Vehicle Order Image of new orders and order amendments. The buildable orders will be sent to MP&L. VO-Edit also checks for the maximum plant capacity for buildable orders. VO-Edit also updates all downstream systems with order status. SLA 1, CIA 1,1,2 |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
17119 | VO Program Financial Reporting | In Production | PFR | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | DSHAH1 | Manufacturing Engineering | Integrated Enterprise Resource Planning (I-ERP) | A web based tool used by manufacturing engineers and MBO Analyst from VO/PTO to track Product Spending for vehicle programs. |  |  | YES | 3 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
17119 | VO Program Financial Reporting | In Production | PFR | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Manufacturing Engineering | Integrated Enterprise Resource Planning (I-ERP) | A web based tool used by manufacturing engineers and MBO Analyst from VO/PTO to track Product Spending for vehicle programs. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
17119 | VO Program Financial Reporting | In Production | PFR | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | DSHAH1 | Manufacturing Engineering | Integrated Enterprise Resource Planning (I-ERP) | A web based tool used by manufacturing engineers and MBO Analyst from VO/PTO to track Product Spending for vehicle programs. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
20949 | VO Data Input Screens | In Production | VODIS | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | VODIS Formerly known as (PFIS) has been renamed(4Q2017)to include data input screens from other organizations Stamping, Paint & Assembly. The application allows for customizable quality data input screens used in plant environment for quality reporting. Captures production data which is sent to Web Base Data Management (WBDM) system for reporting results. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
20949 | VO Data Input Screens | In Production | VODIS | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | VODIS Formerly known as (PFIS) has been renamed(4Q2017)to include data input screens from other organizations Stamping, Paint & Assembly. The application allows for customizable quality data input screens used in plant environment for quality reporting. Captures production data which is sent to Web Base Data Management (WBDM) system for reporting results. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | Q3 2026 | Modernize to Cloud Databases | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [14 empty] | No | SQL
20223 | Structured Assumption Language Template - Gen 2 | In Production | SALTGen 2 | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | SALT (Structured Assumptions Language Tempalte) provides a consistent, structured format to capture and communicate product assumptions across the enterprise. Provide a global, cross-program assumptions management process. | 6 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission | 2024-12-15 | 2025-01-15 | 2025-01-06 | Complete | Blue | 2025-01-15 | 2025-01-06 | Complete |  | No | [8 empty] | Decommission | Priya | 2025-03-16 |  |  | App fully Decommissioned | No | VM
19968 | Stamping Production Process Monitoring System | In Production | PPMS | ISIT | OTHERS | AHOROVIT | CGOLDMA4 | TBIRMIN1 | Copper | Non S-Ox | 11 | Yes | No | In-House | AHOROVIT | CGOLDMA4 | Manufacturing Engineering | - | Process Monitoring modules ( Draw Dies, Line Dies, Hot Stamping) Engineering Feedback( Three modules :Dies, Press & Automation, MP&L), Die Room Management (PIST ), QCT, Hard Hit Process, and SOI. Migration to new Data Center planned for Wave 19 | 5 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
17942 | Stamping Business System | In Production | SBS | ISIT | OTHERS | AHOROVIT | CGOLDMA4 | TBIRMIN1 | Copper | Non S-Ox | 111 | Yes | No | In-House | AHOROVIT | CGOLDMA4 | Manufacturing Engineering | - | Support Stamping Business Unit reporting ( FTT, Production Dash Board, Tool & Die DashBoard, Productivity and Downtime reporting). It also supports New Model tracking ( 7207,LQOS, ROC ), Incoming Metal Quality from vendor ( 4 application: Steel, Aluminum, Extrusion, Boron Steel), and One Stop Shop report modules. To ensure that anyone who looks at the architecture framework, they know the Data Center is the ones that manages the server renewal and the business should not be at fault. The comment can read: The SQL S008 server needs upgraded. This is Data Center Managed. Business has no control in timing. Migration planned for Wave 19. | 11 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23997 | VMCWEB | In Production | VMCWEB | ISIT | JPITTERL | CBOHN | MBONAKDA | DNEWTON | Copper | Non S-Ox | 211 | No | Yes | In-House | CBOHN | IREINHO3 | Manufacturing Plants | Industrial System IT | A self developed Java application to support Business operations @ VMC in Cologne. The first release of VMCWEB contains pool car administration, issueing and billing. Enhancing VMCWEB will lead to a strategic step by step Migration of the legacy Software RAMCAM (ITMS 13877) |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
23997 | VMCWEB | In Production | VMCWEB | ISIT | JPITTERL | CBOHN | MBONAKDA | DNEWTON | Copper | Non S-Ox | 211 | No | Yes | In-House | CBOHN | IREINHO3 | Manufacturing Plants | Industrial System IT | A self developed Java application to support Business operations @ VMC in Cologne. The first release of VMCWEB contains pool car administration, issueing and billing. Enhancing VMCWEB will lead to a strategic step by step Migration of the legacy Software RAMCAM (ITMS 13877) |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
21532 | Special Service Support Center Website | In Production | SSSC | FORD PRO & FCSD TECH | OTHERS | EGILLAND | AHUSPEN | ABOBBALA | Gold | Non S-Ox | 221 | Yes | No | In-House | DWILYARD | EGILLAND | Ford Customer Service | - | The mission of the SSSC is to provide their customers with quality information and assistance for Field Service Actions and Customer Service Programs in a timely and professional manner. The SSSC manages web requests and inbound and outbound calls. Requests are related to specific FSA's or CSP's and include general program questions, part order requests, technical assistance, claim review, rental and repair approvals. Renkim and Ford services are closely monitored daily to assure they adhere to the SSSC Service Level Agreement. | 10 |  | YES | 2 | RKENNEL | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
12343 | VMACS - Vehicle Monitoring and Control System | In Production | VMACS (EU) | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | S-Ox In Scope | 231 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Monitoring and Control System. VMACS is the centralized Ford system used in Europe to track the flow of new vehicles from the point of order entry to the point of sale (dealer delivered/retail sold) |  |  | YES | 6 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12343 | VMACS - Vehicle Monitoring and Control System | In Production | VMACS (EU) | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | S-Ox In Scope | 231 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Monitoring and Control System. VMACS is the centralized Ford system used in Europe to track the flow of new vehicles from the point of order entry to the point of sale (dealer delivered/retail sold) |  |  | YES | 6 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
12343 | VMACS - Vehicle Monitoring and Control System | In Production | VMACS (EU) | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | S-Ox In Scope | 231 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Monitoring and Control System. VMACS is the centralized Ford system used in Europe to track the flow of new vehicles from the point of order entry to the point of sale (dealer delivered/retail sold) |  |  | YES | 6 | NKANDULA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
12343 | VMACS - Vehicle Monitoring and Control System | In Production | VMACS (EU) | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | S-Ox In Scope | 231 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Monitoring and Control System. VMACS is the centralized Ford system used in Europe to track the flow of new vehicles from the point of order entry to the point of sale (dealer delivered/retail sold) |  |  | YES | 6 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q2 2027 | Modernize to Cloud Databases | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | SQL
24181 | Sourcing Workplan Tool | In Production | SWT | I-ERP | SARAUJO3 | KSYROCKI | PBUKKAPA | SNAG1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | - | Sourcing WorkPlan Tool (Program Management/Date Tracking Tool) - This tool will be focused on PD and Purchasing Program management. It is a separate tool for simplicity and to provide date tracking and reporting from sourcing workflow for all Global Vehicle Programs and Power Train for each Project Sourcing Action (PSA). This is a Global Tool for no Regional Differences | 4 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12343 | VMACS - Vehicle Monitoring and Control System | In Production | VMACS (EU) | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | S-Ox In Scope | 231 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Monitoring and Control System. VMACS is the centralized Ford system used in Europe to track the flow of new vehicles from the point of order entry to the point of sale (dealer delivered/retail sold) |  |  | YES | 6 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
52496 | Visual Cycle Plan | In Development | VCP | ISIT | SBONNICI | KRAMMOHA | IWEITZER | GRAO3 | Silver | Non S-Ox | - | Yes | No | In-House | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | Vehicle Cycle Plan for upper management (Director/VP Level) |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-04-14 |  | Planned |  | No | 100% | 50% | 25% |  |  |  | 25% |  | Cloud SQL PostgreSQL | Ramesh | 2025-03-11 |  |  | PCF BMIT app in Flight. There is a Possible spill over to Q2 due to Design change. Revised timeline & approval for the date change pending | No | SQL
53392 | Software Change and Release Management | In Production | SWCM | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 212 | No | Yes | In-House | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | Global tool to manage in-vehicle software announcement and health chart. | 10 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12333 | VISTA - New Vehicle Ordering/Tracking (Europe) | In Production | VISTA | M&S TECH | FHIRSH | NSIVASA1 | BRAMA3 | PSATISH2 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | NSIVASA1 | Marketing & Sales | 232 | Vehicle Intranet Services and Tracking - a family of modules for dealer and NSC use such as order management, vehicle locator, contract and retail. VISTA is the primary system for European Ford Dealers to order Ford vehicles, manage the vehicle pipeline and to notify Ford of vehicle contracts and vehicle sales to end customers.. |  | Springboot | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | Java < v21 | Q2 2027 | Version Upgrade | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
12333 | VISTA - New Vehicle Ordering/Tracking (Europe) | In Production | VISTA | M&S TECH | FHIRSH | NSIVASA1 | BRAMA3 | PSATISH2 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Intranet Services and Tracking - a family of modules for dealer and NSC use such as order management, vehicle locator, contract and retail. VISTA is the primary system for European Ford Dealers to order Ford vehicles, manage the vehicle pipeline and to notify Ford of vehicle contracts and vehicle sales to end customers.. |  |  | YES | 5 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
12333 | VISTA - New Vehicle Ordering/Tracking (Europe) | In Production | VISTA | M&S TECH | FHIRSH | NSIVASA1 | BRAMA3 | PSATISH2 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | Vehicle Intranet Services and Tracking - a family of modules for dealer and NSC use such as order management, vehicle locator, contract and retail. VISTA is the primary system for European Ford Dealers to order Ford vehicles, manage the vehicle pipeline and to notify Ford of vehicle contracts and vehicle sales to end customers.. |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | Oracle | Q4 2027 | Modernize to Cloud Databases | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Oracle
12333 | VISTA - New Vehicle Ordering/Tracking (Europe) | In Production | VISTA | M&S TECH | FHIRSH | NSIVASA1 | BRAMA3 | PSATISH2 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Intranet Services and Tracking - a family of modules for dealer and NSC use such as order management, vehicle locator, contract and retail. VISTA is the primary system for European Ford Dealers to order Ford vehicles, manage the vehicle pipeline and to notify Ford of vehicle contracts and vehicle sales to end customers.. |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q4 2027 | Modernize to Cloud Databases | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | SQL | [5 empty] | No | SQL
19167 | SNURK-1 | In Production | SNURK-1 | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 311 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The SNURK is a tool used by Manufacturing Plants, staff MP&L and Controller's Office. In January 2007 the SNURK launched in North America. The SNURK also allows users to compare transactions to promote continuous improvement and the drive for consistent practices. | 5 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20941 | SNURK V.2.0 | In Production | SNURK2 | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 322 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Common global business reporting for manufacturing finance (cars), manufacturing operations (Cost of building cars), capability to do analytics and 100% audit tracking. Reporting Scope: - Plant expense labor and overhead - Industrial Material - Plant accounting (General ledger) - Timekeeping (Hourly and Salary) - Physical presence - Security - badge swipe card as related to payroll and timekeeping - Finished Vehicle accounting - Production Material (FST) - BWS - FAB card charges - Legacy 9270 - Vehicle scheduling | 5 |  | YES | 4 | TSWEEN16 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
56890 | Virtual Training Solutions | Planned | VTS | ISIT | SKING68 | JLYNN1 | KKISIEL | AELANGO | Bronze | S-Ox Classification Pending | 111 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | - | VTS is a 3D virtual Learning Solution to upskill the users in Plant Floor |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q3 2025 | On-Prem | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | SQL
51076 | Smart Parking | In Production | Park | OCETO | TSWEEN16 | KADOMKAI | DSTONE46 | ESTILESK | Copper | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Ford Land | Staffs IT | Accurately determine utilization of a parking facility cameras camerassors | 2 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53323 | Smart Lockers - Hosted Environment | In Production | Vecos | OCETO | TSWEEN16 | KADOMKAI | DSTONE46 | ESTILESK | Bronze | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | DDESAI | KADOMKAI | Ford Land | Staffs IT | Mobile App (Vecos) and Hosted Cloud Solution (Azure) | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
54728 | Virtual Coach | In Production | COACHBOT | M&S TECH | RAHMED33 | JFORBIS | NMUTHUK8 | NMUTHUK8 | Bronze | Non S-Ox | 211 | No | Yes | In-House | APALAZZO | JFORBIS | Enterprise Technology | Marketing, Sales and Service | Virtual Coach Bot for Ford |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-15 | Complete | Blue | 2025-06-13 | 2025-03-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | [5 empty] | No | Java < v21
13586 | VIPER:European Vehicle Inventory Prod Eng Rep | In Production | EuMP-VIPER | ISIT | JPITTERL | CBOHN | MBONAKDA | SSENTH15 | Bronze | Non S-Ox | 211 | No | Yes | In-House | CBOHN | IREINHO3 | Manufacturing Plants | Industrial System IT | This application records the progress of UK Ford owned vehicles, including demonstrators, management roll cars, pool cars and press cars throughout their Ford ownership. It is used by the Dagenham Car Conditioning Centre (Ford Autotech) to record the progress of Company and Contract Direct Sales Vehicles through the garage and provide management-reporting facilities. It is also installed at several satellite locations in the UK to record Company vehicles moving into active service and being returned for disposal. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [13 empty] | TBD, due to Business priorities | No | Java < v21
13586 | VIPER:European Vehicle Inventory Prod Eng Rep | In Production | EuMP-VIPER | ISIT | JPITTERL | CBOHN | MBONAKDA | SSENTH15 | Bronze | Non S-Ox | 211 | No | Yes | In-House | CBOHN | CBOHN | Manufacturing Plants | Industrial System IT | This application records the progress of UK Ford owned vehicles, including demonstrators, management roll cars, pool cars and press cars throughout their Ford ownership. It is used by the Dagenham Car Conditioning Centre (Ford Autotech) to record the progress of Company and Contract Direct Sales Vehicles through the garage and provide management-reporting facilities. It is also installed at several satellite locations in the UK to record Company vehicles moving into active service and being returned for disposal. |  |  | YES | 4 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [13 empty] | TBD, due to Business priorities | No | Oracle
13586 | VIPER:European Vehicle Inventory Prod Eng Rep | In Production | EuMP-VIPER | ISIT | JPITTERL | CBOHN | MBONAKDA | SSENTH15 | Bronze | Non S-Ox | 211 | No | Yes | In-House | CBOHN | IREINHO3 | Manufacturing Plants | Industrial System IT | This application records the progress of UK Ford owned vehicles, including demonstrators, management roll cars, pool cars and press cars throughout their Ford ownership. It is used by the Dagenham Car Conditioning Centre (Ford Autotech) to record the progress of Company and Contract Direct Sales Vehicles through the garage and provide management-reporting facilities. It is also installed at several satellite locations in the UK to record Company vehicles moving into active service and being returned for disposal. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [13 empty] | TBD, due to Business priorities | No | Java < v21
50036 | Siemens Mentor Graphics PCB | In Production | Mentor PCB | ISIT | MNOWICK1 | PBORGAO1 | IAKLEH | GRAO3 | Bronze | Non S-Ox | 111 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | A suite of tools from Siemens Mentor Graphics provides a fully integrated PCB design data management infrastructure, from initial system definition through the design process, to release to manufacturing. It also supports seamless integration between engineering and PLM and ERP systems to provide full lifecycle management of your designs and libraries. | 6 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
18055 | VIP - Ford Dealers Parts Sales and Inventory | In Production | VIP | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | VIP is a common Regional web-based system which the purpose is: -Dealer inventory management Inventory analysis Suggested parts order (auto and manual) Parts locator and inventory balance Standard reports -Dealer Sales and Purchase Analysis Dealer Sales analysis Customer segmentation Dealer Purchase analysis Ad-hoc reporting | 787 |  | YES | 4 | RKENNEL | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
18055 | VIP - Ford Dealers Parts Sales and Inventory | In Production | VIP | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | VIP is a common Regional web-based system which the purpose is: -Dealer inventory management Inventory analysis Suggested parts order (auto and manual) Parts locator and inventory balance Standard reports -Dealer Sales and Purchase Analysis Dealer Sales analysis Customer segmentation Dealer Purchase analysis Ad-hoc reporting |  |  | YES | 4 | RKENNEL | PLM | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
18055 | VIP - Ford Dealers Parts Sales and Inventory | In Production | VIP | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | NBAECKER | Ford Customer Service | FCSD Tech | VIP is a common Regional web-based system which the purpose is: -Dealer inventory management Inventory analysis Suggested parts order (auto and manual) Parts locator and inventory balance Standard reports -Dealer Sales and Purchase Analysis Dealer Sales analysis Customer segmentation Dealer Purchase analysis Ad-hoc reporting |  |  | YES | 4 | RKENNEL | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
20908 | Sequencing and Kitting System | In Production | SKS | ISIT | AMEHER1 | ADURSO | MBIJI | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS |  |  | Manufacturing Staffs | Industrial System IT | Global Sequencing & Kitting System, a module of #12122 Error Proofing - VO. Vendor is CEC Controls. | 11 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
54512 | VIN Segment Service | In Production | VinSeg | I-ERP | SVISWANA | VBHOOPAS | LWU14 | LWU14 | Gold | S-Ox In Scope | 233 | No | Yes | In-House | TSWEEN16 | SVISWANA | Finance | 233 | This service contains global VIN segment information and allows consume to inquire financial segment, such as Ford Blue, Pro, or Model E for a given set of VIN numbers |  | Springboot | YES | 3 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
54512 | VIN Segment Service | In Production | VinSeg | I-ERP | SVISWANA | VBHOOPAS | LWU14 | LWU14 | Gold | S-Ox In Scope | 233 | No | Yes | In-House | TSWEEN16 | SVISWANA | Finance | - | This service contains global VIN segment information and allows consume to inquire financial segment, such as Ford Blue, Pro, or Model E for a given set of VIN numbers |  |  | YES | 3 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
54173 | Seclore EDRM for CyclePlan | In Production | Seclore | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Bronze | Non S-Ox | 332 | No | Yes | COTS | SBONNICI | SBONNICI | PD Operations and Quality | Industrial System IT | Seclore EDRM (Enterprise Digital Rights Management) is a SaaS Solution to protect secret and sensitive documents by Ford Internal Users. Seclore has Client version to be installed in users machine to protect the document. Seclore has 2 independent clients for Windows and Mac OS. Seclore Client software configured to receive auto-update from Vendor Cloud to Ford Windows and Mac OS. | 4 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
9803 | VI&D: Vehicle Invoicing & Drafting | In Production | VI&D | I-ERP | SFRANCI8 | SDHANAL3 | MWARRE10 | LWU14 | Gold | S-Ox In Scope | 233 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | The Vehicle Invoicing & Drafting system provides vehicle invoicing, retail label services, factory gate-release accounting, unit/revenue/sales reporting, funds collection, and joint venture billing or payment services in whole or in part for: North American Assembly plants (invoice & retail labeling services only), U.S. dealers, Ford of Canada (FoC) dealers (no funds collection), Ford of Mexico (FoM) dealers (no funds collection), Ford Trading Company (FTC) dealers (no funds collection), AAI (Auto-Alliance International)(joint venture billing/payment, only), and MAZDA (joint venture billing/payment, only). NOTE: VI&D was launched in the 1960's, but EAMS date field does NOT allow earlier date than Jan 1970. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
755 | Certificate of Conformity | In Production | COC | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Bronze | Non S-Ox | 211 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Creation of Certificate of Conformity (CoC) in the National Sales Companies. Used within Ford EU and Ford Otosan. A mainframe Telon Cobol facility that generates CoC VIN data for specific vehicles in line with EU legislative requirements together with feed to central client server application which prints the Certificate of conformity (CoC) in the National Sales Companies. The data held on the system is also used to aid the registration systems. Being enhanced during 2015 to enable Digital Transmission of data via Registration Applications. Cross functionally managed - Business Owner MP&L; Consumption Funding EMS&S; BIT SESE; Project funding dependant on which skill team requests the change and what the change consists of. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | Q4 2024 | Version Upgrade | Modernize | 2025-01-20 | 2024-12-20 | 2024-12-20 | Complete | Blue | 2025-01-20 | 2025-01-20 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Decommission | Priya | 2025-03-06 |  |  | Microservices running on Cloud run. Migration completed in 2024 & Decommission complete in Q1 2025 | No | Java < v21
53024 | SDE Scout | In Production | SDESC | OCETO | PMILLIGA | SNAMBIVE | DVRABIOI | SGURU8 | Copper | Non S-Ox | 111 | No | Yes | In-House | MCHRIS38 | SNAMBIVE | Enterprise Technology | Technology & Enterprise Services (TES) | An application to provide traceability and auditability for software development ecosystems. | 3 |  | YES | 4 | PMILLIGA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
54766 | VEV Administration | In Production | VEVA | OCETO | DBRIGHEN | BFIGUEI3 | PRENZO | JLUCAS1 | Copper | Non S-Ox | 211 | Yes | No | In-House | AMACHAD4 | BFIGUEI3 | PD Operations and Quality | - | Vehicle Evaluation and Validation (VEV) Administration Application, This is a web application that helps the administrative aspect of the Proving Ground plants. |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
24608 | Vertex Tax Performance Engine | In Production | Vertex TPE | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Copper | S-Ox In Scope | 331 | No | Yes | Managed by 3rd Party Purchased Service | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Tax Data Warehouse to manage data needed to support global tax processes. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
24669 | SDE Portal | In Production | SDEPort | EVDD | AGARBY | NWEBST14 | TNIELSE9 | SGURU8 | Copper | Non S-Ox | 111 | No | Yes | In-House | AGARBY | NWEBST14 | Advanced PD and Tech | - | Portal to store the various SDE process and activities | 3 |  | YES | 2 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | VM
50191 | Verint Call Recording India | In Production | VCR | FORD CREDIT | KDELTA | PBINGI | RGUTOWS3 | SMOCK6 | Bronze | Non S-Ox | 311 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | Application to record contact agent calls with customers |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | SQL
52454 | scs concept - Data touch 3 | In Production | SCS Concep | ISIT | JPITTERL | STHOM124 | AVARADI1 | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | - | JPITTERL | STHOM124 | PD Operations and Quality | - | Records data in the fastener area Dunton UK - Stores on SQL Database | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
50414 | Verint Call Recording Global | In Production | VCR-Global | FORD CREDIT | KDELTA | PBINGI | RGUTOWS3 | SMOCK6 | Silver | Non S-Ox | 311 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | Application to record contact agent calls with customers |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
16727 | SCHNEIDER ION-E | In Production | ION-E | OCETO | TSWEEN16 | JMENDOL1 | GRUTTEN5 | ESTILESK | Copper | Non S-Ox | 11 | Yes | No | COTS |  |  | Ford Land | - | The Schneider Electric ION-e is a hardware/software system providing an 'out-of-the-box' Energy Monitoring System software uses a choice of industry-standard network technologies, including Ethernet and wireless, to automatically collect and store data from key electrical distribution points and physical assets. It forms a layer of energy intelligence across your facility, campus, service area or your entire enterprise, acting as a unified interface to electricity and other consumable resources such as water, compressed air, gas and steam. Web-enabled access gives each user a personalized view to timely, relevant information. | 1 |  | YES | 1 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
52580 | Venezuela EDI (Goanywhere/EDISEC2) | In Production | VenEdi | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Bronze | Non S-Ox | 321 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Gentran/EDISEC2 software support the electronic data file interchange between banks and other institutions for supplier payments, payroll and receive company bank financial statement. This package was purchased in Venezuela through ENIAC supplier, a representative of Sterling Commerce, who is the company that developed the standard UN / EDIFACT, for worldwide use. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2026 | On-Prem | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
51020 | Savanna Location Engine (SLE) | In Production | SLE | ISIT | VVIJAY55 | RADAM10 | PYORK | SSENTH15 | Silver | Non S-Ox | 111 | No | Yes | COTS | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Savanna Location Engine is an integrated software package. Using algorithms and rules engine it derives actionable information and business context from the location data and a common set of outputs to share with applications. Location data is captured by using hardware including sensing, tagging, and mobility technologies, as well as third-party technologies. | 12 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23482 | VEME-C&FEE Coastdown | In Production | VEME | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Policy | Industrial System IT | Develop and deploy centralized repository for storing & retrieving information from Aerodynamics, Fuel Economy and C&FEE Coastdown Provide workflow option & e-signature process |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
17411 | Satellite Digital Audio Radio Services | In Production | SDARS | EVDD | MJAMWAL | VVINOD3 | RDAS9 | DAMARNA3 | Bronze | Non S-Ox | 311 | No | Yes | - |  |  | Advanced PD and Tech | - | Application to manage Satellite Digital Audio Radio Services (SDARS) including but not limited to enahncements to SDARS including delivery of customer data to Sirius, implementation of new data elements and improved data analysis, and inclusion of PAG satellite radio data. | 3 |  | YES | 4 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | VM
23482 | VEME-C&FEE Coastdown | In Production | VEME | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Policy | Industrial System IT | Develop and deploy centralized repository for storing & retrieving information from Aerodynamics, Fuel Economy and C&FEE Coastdown Provide workflow option & e-signature process |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
16532 | Vehicle Visibility | In Production | VVAppl | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Vehicle Visibility: -Provides web-based vehicle status tool containing timely and consistent vehicle status information, complete vehicle order details, and order status history from order entry through sale to a customer. -Consolidate order banks to create Single Order Bank |  |  | YES | 3 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
16532 | Vehicle Visibility | In Production | VVAppl | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Vehicle Visibility: -Provides web-based vehicle status tool containing timely and consistent vehicle status information, complete vehicle order details, and order status history from order entry through sale to a customer. -Consolidate order banks to create Single Order Bank |  |  | YES | 3 | NKANDULA | PLM | Java Struts | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
16532 | Vehicle Visibility | In Production | VVAppl | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Vehicle Visibility: -Provides web-based vehicle status tool containing timely and consistent vehicle status information, complete vehicle order details, and order status history from order entry through sale to a customer. -Consolidate order banks to create Single Order Bank |  |  | YES | 3 | NKANDULA | PLM | Mainframe | Q4 2025 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
13621 | Vehicle Title Document Systems | In Production | EuAS-VTD | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Generate legal documents of ownership (Vehicle Title Documents) for Ford Germany, Ford Spain. |  |  | YES | 2 | TSWEEN16 | PLM | Java Struts | TBD | Rewrite | Modernize |  | 2024-11-24 |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
13621 | Vehicle Title Document Systems | In Production | EuAS-VTD | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Generate legal documents of ownership (Vehicle Title Documents) for Ford Germany, Ford Spain. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
24395 | Vehicle State Services | In Production | VSS | EVDD | MJAMWAL | TPINTO3 | SPATHANJ | TANBUCHE | Platinum | Non S-Ox | 223 | No | Yes | In-House | MJAMWAL | MJAMWAL | Advanced PD and Tech | - | Vehicle state is a consolidated view of the vehicle state information with in the Cloud containing the following: Vehicle details, ECU, Agile Vehicle Data, CV feature capabilities, PID |  |  | YES | 1 | MJONE308 | PLM | Oracle | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Oracle
24395 | Vehicle State Services | In Production | VSS | EVDD | MJAMWAL | TPINTO3 | SPATHANJ | TANBUCHE | Platinum | Non S-Ox | 223 | No | Yes | In-House |  |  | Advanced PD and Tech | - | Vehicle state is a consolidated view of the vehicle state information with in the Cloud containing the following: Vehicle details, ECU, Agile Vehicle Data, CV feature capabilities, PID |  | Springboot | YES | 2 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
839 | GSAR: Global System for Analytics & Reporting-AWS | In Production | GSAR | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | JDEGUZMA | RMEHTA3 | PD Operations and Quality | Industrial System IT | Provides a database of warranty claims and vehicle information that supports common global warranty reporting, analysis, and feedback processes for model years 1991 and forward. Customers have the flexibility to request on-line reports using a wide range of selection criteria and a variety of output formats. Primary Users: Analysts in Quality, Engineering, Finance, Vehicle Operations and Powertrain Plants. |  | Springboot | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | Yes | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | EDC CaaS | Saran | 2025-03-11 |  |  |  | Yes | Java < v21
11539 | CMMS Web-Enabled Direct Data Link | In Production | CMMS eDDL | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | eDDL is a web front-end to the CMMS system and is used by the suppliers to update information needed by Ford analysts to properly manage inventory levels. |  |  | YES | 3 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-12-02 | 2024-12-02 | 2024-12-02 | Complete | Blue | 2025-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
14809 | Vehicle Special Ordering - MPL | In Production | eVSO | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 131 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Unique functionality within CMMS to manage VSO bill of material and order processing. eVSO is the system of record for vehicle special order parts and options only. |  |  | YES | 3 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
53692 | Vehicle Services for Inventory Enrollments | In Production | VSIE | EVDD | RJOHN813 | JDEVER5 | KVIRK1 | JDEVER5 | Gold | Non S-Ox | 221 | No | Yes | Managed by 3rd Party Purchased Service | #N/A | #N/A | Integrated Services | 221 | VEHICLE SERVICES FOR INVENTORY ENROLLMENTS APPLICATION IS AN EVENT-DRIVEN SERVICE THAT AGGREGATES DATA FROM VARIOUS FORD SYSTEMS. FPI_VSIE USES THAT DATA TO AUTOMATE KEY ACTIVITIES SUCH AS ONBOARDING, CONSENT, ENROLLMENT, AND OFFBOARDING FOR FCS DEALER CUSTOMERS. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
16014 | Vehicle Sales Management System | In Production | VSMS | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | VSMS: Vehicle Sales Management System. Scope: Venezuela and Colombia. Main system functionalities: - Vehicle pricing (retail/fleet) - Vehicle invoicing for new and used vehicles - Vehicle distribution process for Dealers - Control of: vehicle inventory, License plates, Gas Kits (GNV) - Vehicles registration control (INTTT) - Back office for Plan Ford program. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
24208 | SATA-DATA | In Production | SATA-DATA | ISIT | RTILLEY | GVANNOYE | GMATHOT | CWADE | Copper | Non S-Ox | 111 | Yes | No | - | RTILLEY | GVANNOYE | Advanced PD and Tech | - | SATA DATA is an Application used to manage in-vehicle software validation tests. It is used by the global Software Validation Fleet and consist of a database, a management tool (SATA DATA) and an execution tool used within the Vehicles (SATA Drive). | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
16014 | Vehicle Sales Management System | In Production | VSMS | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | VSMS: Vehicle Sales Management System. Scope: Venezuela and Colombia. Main system functionalities: - Vehicle pricing (retail/fleet) - Vehicle invoicing for new and used vehicles - Vehicle distribution process for Dealers - Control of: vehicle inventory, License plates, Gas Kits (GNV) - Vehicles registration control (INTTT) - Back office for Plan Ford program. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
21815 | Vehicle Sales Indicators Report South America | In Production | VESIR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | BI application to attend FSAO sales areas. It gets informations of multiple sources to compile the data in reports to Ford Sales, Sales office and dealers. | 204 |  | YES | 4 | TSWEEN16 | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
21815 | Vehicle Sales Indicators Report South America | In Production | VESIR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | BI application to attend FSAO sales areas. It gets informations of multiple sources to compile the data in reports to Ford Sales, Sales office and dealers. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
21351 | SAP Global Components - Portal GRC SM BI SAPGUI | In Production | SAPGlobal | I-ERP | SVISWANA | RKAMLAGE | VREDDY5 | MMEHTA5 | Gold | S-Ox In Scope | 232 | No | Yes | COTS | SVISWANA | RKAMLAGE | Enterprise Technology | FCSD Tech | This is a SAP Global Component site which is used by multiple Ford SAP Applications. Components: - Portal for single sign on to several SAP applications - Governance Risk and Compliance(GRC) - ITSM services (SolMan) - Business intelligence (BI) - QIM (Quality system) in NA (not in EU use in 2016) -- User Experience (SAP Fiori) | 59 |  | YES | 1 | TSWEEN16 | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
21815 | Vehicle Sales Indicators Report South America | In Production | VESIR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | BI application to attend FSAO sales areas. It gets informations of multiple sources to compile the data in reports to Ford Sales, Sales office and dealers. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
20890 | Vehicle Pricing and Invoicing System | In Production | VEPIS | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Finance | - | Brazil Vehicle Pricing & Invoicing application. There is a simulation environment. Avoid many system changes by allowing the users to set up parameters such as taxes, sales modalities, payment conditions, etc. Avoid current user operating workload by simplifying workflow and be oriented to current Ford business model. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-05-30 |  | In-Progress | Green | 2025-06-16 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
20890 | Vehicle Pricing and Invoicing System | In Production | VEPIS | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Finance | - | Brazil Vehicle Pricing & Invoicing application. There is a simulation environment. Avoid many system changes by allowing the users to set up parameters such as taxes, sales modalities, payment conditions, etc. Avoid current user operating workload by simplifying workflow and be oriented to current Ford business model. |  |  | YES | 4 | TSWEEN16 | PLM | SQL | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2025-05-30 |  | In-Progress | Green | 2025-06-16 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | SQL
22008 | Sales Production and Capacity Planning System | In Production | SPCPS | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Silver | S-Ox In Scope | 333 | No | Yes | COTS | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | Sales Production and Capacity Planning System will integrate demand and supply data to make business planning decisions. This application will replace tactical GCRS application. | 14 |  | YES | 2 | NKANDULA | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
20890 | Vehicle Pricing and Invoicing System | In Production | VEPIS | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Finance | - | Brazil Vehicle Pricing & Invoicing application. There is a simulation environment. Avoid many system changes by allowing the users to set up parameters such as taxes, sales modalities, payment conditions, etc. Avoid current user operating workload by simplifying workflow and be oriented to current Ford business model. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-05-30 |  | In-Progress | Green | 2025-06-16 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
53741 | Vehicle Personalization Accessories Life cycle man | In Production | VPALMS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | RSUBRA17 | SDHANAS2 | Silver | Non S-Ox | 311 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | - | VPALMS will used to track an accessory part throughout its lifecycle, right from concept till sales for each vehicle line w/multiple plants and region .It helps to document in Vignettes what region the products will be used. FCSD Vehicle Personalization team currently uses a highly manual process to maintain lifecycle of accessories. MSS RPA DPA team is looking to Simplify and Modernize this process by using Digital Process Automation (DPA). | 15 |  | YES | 1 | RKENNEL | PLM | Datastage | Q4 2024 | Modernize | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | DA
53741 | Vehicle Personalization Accessories Life cycle man | In Production | VPALMS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | RSUBRA17 | SDHANAS2 | Silver | Non S-Ox | 311 | No | Yes | In-House |  |  | Ford Customer Service | - | VPALMS will used to track an accessory part throughout its lifecycle, right from concept till sales for each vehicle line w/multiple plants and region .It helps to document in Vignettes what region the products will be used. FCSD Vehicle Personalization team currently uses a highly manual process to maintain lifecycle of accessories. MSS RPA DPA team is looking to Simplify and Modernize this process by using Digital Process Automation (DPA). |  | Springboot | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
51868 | Vehicle Parameter Repository | In Production | VPR | ISIT | JKOONS | MNOVAK1 | HLIN11 | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | Vehicle Parameter Repository is Mongo DB based repository hosting the Vehicle Parameters required for Systems such as Engine, Chassis, Transmission, High Voltage Battery of ICE and EV vehicles used to perform Fuel Economy and Performance analysis projections. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
56046 | Vehicle Order Contracting Service | Planned | VOCS | M&S TECH | FHIRSH | NSIVASA1 | SJAYAKU3 | PSATISH2 | Gold | Non S-Ox | 311 | No | Yes | In-House | FHIRSH | NSIVASA1 | Marketing & Sales | - | Standardised Vehicle Order Contracting service |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | Q4 2027 | Version Upgrade | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
50255 | Vehicle Key Management System | In Production | KEMAS | ISIT | JPITTERL | CBOHN | MBONAKDA | JLUCAS1 | Copper | Non S-Ox | 211 | No | Yes | COTS | CBOHN | IREINHO3 | PD Operations and Quality | Industrial System IT | The Application allows users to schedule the pickup and delivery of Keys automatically for Prototypes and Fleet Vehicles in Merkenich. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
52938 | Restricted Party Screening System | In Production | REPSSYS | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | DDESAI | KADOMKAI | Policy | Staffs IT | *Privileged and Confidential* Replace current Restricted Party Screening (RPS) system - Accuity mainframe system implemented in 2004 - to mitigate significant legal, business and reputational risk of doing business with a restricted or prohibited party. New system is needed to meet regulatory guidelines for compliance and effective screening and to broaden screening capabilities throughout Ford globally in various skill teams, organizations and regions. Risk if not funded includes significant regulatory penalties, risk to future corporate funding, and reputational harm. | 8 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
12569 | Vehicle Incentives System | In Production | VINCENT | M&S TECH | VMUTHUPA | RANANDAL | PP5 | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Vincent supports Vehicle Incentive payments for North American vehicles. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12569 | Vehicle Incentives System | In Production | VINCENT | M&S TECH | VMUTHUPA | RANANDAL | PP5 | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Vincent supports Vehicle Incentive payments for North American vehicles. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q4 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
20703 | Vehicle Incentive Data Service | In Production | VIDS | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Gold | Non S-Ox | 211 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | The VIDS application provides web service to downstream systems to obtain Vehicle Incentive data |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | Java < v21
20703 | Vehicle Incentive Data Service | In Production | VIDS | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Gold | Non S-Ox | 211 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | The VIDS application provides web service to downstream systems to obtain Vehicle Incentive data |  |  | YES | 5 | NKANDULA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
20703 | Vehicle Incentive Data Service | In Production | VIDS | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Gold | Non S-Ox | 211 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | The VIDS application provides web service to downstream systems to obtain Vehicle Incentive data |  |  | YES | 5 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
20703 | Vehicle Incentive Data Service | In Production | VIDS | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Gold | Non S-Ox | 211 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | The VIDS application provides web service to downstream systems to obtain Vehicle Incentive data |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
642 | Resident Engr. Defects and Concerns Rpting Sys | In Production | REDCRS | ISIT | SKING68 | KBARTHO1 | LMEENAKS | RPRASA22 | Copper | Non S-Ox | 211 | No | Yes | In-House | SKING68 | KBARTHO1 | PD Operations and Quality | Industrial System IT | Used by Powertrain resident engineers at Assenbly plants around the world to report problems and concerns about powertrain products to the manufacturing PTO plant | 8 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
22583 | Vehicle Health & Alerts | In Production | VHA | EVDD | NROTH4 | DRAJESH1 | IPAULMUT | KKANIMO3 | Silver | Non S-Ox | 222 | No | Yes | In-House | #N/A | #N/A | Ford Customer Service | 222 | SDN CLOUD APPLICATION TO MANAGE THE SCHEDULE FOR SENDING THE VEHICLE HEALTH REPORT & ALERTS (VHR) TO CUSTOMERS VIA MOBILE APP AND VIA EMAIL. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
12960 | Research Library Information Systems | In Production | RLIS | EVDD | JDEMAIO | JDEMAIO | LKUDLA1 | JLUCAS1 | Copper | Non S-Ox | 211 | Yes | No | In-House | MJONE308 | JDEMAIO | Advanced PD and Tech | - | Research Library Information Systems Welcome website To search the site, enter your query in the search box at right. To search library materials, click Library Catalog (or click Library Catalog at the top of every RLIS web page) | 2 |  | YES | 2 | MJONE308 | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
50241 | Vehicle Environmental Engineering | In Production | VEE | ISIT | OTHERS | MFUHER | MGUENTHE | TTOBOLSK | Copper | Non S-Ox | 311 | Yes | No | In-House | PHARDIGA | MFUHER | Policy | - | Vehicle Environmental Engineering Data system for preparing information for regulatory compliance. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
13223 | Repository for Diagnostic And Module Configuration | In Production | RDS | FORD PRO & FCSD TECH | OTHERS | KCLARK4 | BSWANSO3 | DFARNIN | Silver | Non S-Ox | 11 | Yes | No | In-House | KDORONY | KCLARK4 | Ford Customer Service | - | Repository for diagnostic and module configuration and programming data used for support of IDS and associated diagnostic and service tools. RDS Exporter is a client app. that interfaces with the RDS SQL database. Exporter uses SQL stored procedures & Local processing to create a proprietary runtime database that is released with each update. & also database update. (DIF) files released | 8 |  | YES | 2 | RKENNEL | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
11539 | CMMS Web-Enabled Direct Data Link | In Production | CMMS eDDL | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | eDDL is a web front-end to the CMMS system and is used by the suppliers to update information needed by Ford analysts to properly manage inventory levels. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-12-02 | 2024-12-02 | 2024-12-02 | Complete | Blue | 2025-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
786 | Vehicle Engineering Database Mgmt. Systems | In Production | VEDMS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Copper | Non S-Ox | 221 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Customer correlation test metadata management system with statistical packages. Customer Correlation group uses VEDMS to determine the optimal durability route for Ford vehicle durability testing. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 25% | [7 empty] | Cloud Run | Ramesh | 2025-03-06 |  |  |  | No | Java < v21
786 | Vehicle Engineering Database Mgmt. Systems | In Production | VEDMS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Copper | Non S-Ox | 221 | No | Yes | In-House | JKOONS | JKOONS | PD Operations and Quality | Industrial System IT | Customer correlation test metadata management system with statistical packages. Customer Correlation group uses VEDMS to determine the optimal durability route for Ford vehicle durability testing. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 25% | [7 empty] | Cloud SQL PostgreSQL | Ramesh | 2025-03-06 |  |  |  | No | Oracle
786 | Vehicle Engineering Database Mgmt. Systems | In Production | VEDMS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Copper | Non S-Ox | 221 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Customer correlation test metadata management system with statistical packages. Customer Correlation group uses VEDMS to determine the optimal durability route for Ford vehicle durability testing. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 25% | [7 empty] | Cloud Run | Ramesh | 2025-03-06 |  |  |  | No | Java < v21
12566 | Vehicle Distribution and Reporting System | In Production | VNAV | M&S TECH | RAHMED33 | GDIAZ1 | ASYRAGAK | IKALUGIN | Gold | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | Marketing, Sales and Service | The Vehicle Distribution Systems support Canadian applications requiring on-line access to Vehicle information. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12566 | Vehicle Distribution and Reporting System | In Production | VNAV | M&S TECH | RAHMED33 | GDIAZ1 | ASYRAGAK | IKALUGIN | Gold | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | Marketing, Sales and Service | The Vehicle Distribution Systems support Canadian applications requiring on-line access to Vehicle information. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
50569 | Vehicle Device Identification Service | In Production | VDIS | EVDD | JWASNIC1 | JWASNIC1 | STHOTTE1 | CSWADLEY | Gold | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 322 | VEHICLE DEVICE IDENTIFICATION SERVICE IDENTIFIES THE VARIOUS DEVICE (TCU, ECG , EPID, IWID & T-BOX) INFORMATION AND IT IS POPULATED TO VEHICLE PROFILE AND ALSO DEVICE REGISTRATION OF JV (CYCLONE, ETC) DEVICES TO VEHICLE PROFILE & TMC IS HANDLED THRU THIS SERVICES. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [5 empty] | No | Java < v21
23947 | Vehicle Data Definition Services Application | In Production | VDDS | EVDD | MMISHR12 | JVEDANAY | CRAMESH5 | JVEDANAY | Copper | Non S-Ox | 311 | No | Yes | In-House | MMISHR12 | JVEDANAY | Advanced PD and Tech | 311 | Holds vehicle data definition information. Will include services to provide data definitions to calling applications. May additionally have capability to decode/encode data from raw to physical representation. |  | Springboot | YES | 2 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [5 empty] | No | Java < v21
23947 | Vehicle Data Definition Services Application | In Production | VDDS | EVDD | MMISHR12 | JVEDANAY | CRAMESH5 | JVEDANAY | Copper | Non S-Ox | 311 | No | Yes | In-House | MMISHR12 | JVEDANAY | Advanced PD and Tech | - | Holds vehicle data definition information. Will include services to provide data definitions to calling applications. May additionally have capability to decode/encode data from raw to physical representation. |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [5 empty] | No | SQL
51417 | Vehicle Cybersecurity Access | In Production | ECUKG | ISIT | MNOWICK1 | PBORGAO1 | SBELSAR1 | GRAO3 | Silver | Non S-Ox | 221 | No | Yes | In-House | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | 221 | Tool and processes for ECU Key Generation requests, approvals, and distribution. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
51417 | Vehicle Cybersecurity Access | In Production | ECUKG | ISIT | MNOWICK1 | PBORGAO1 | SBELSAR1 | GRAO3 | Silver | Non S-Ox | 221 | No | Yes | In-House | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | Tool and processes for ECU Key Generation requests, approvals, and distribution. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
53921 | Remitos Digitales | In Development | REMI | ISIT | OTHERS | JBERGONZ | DYLLA | MPELLEG9 | Gold | Non S-Ox | 211 | Yes | No | In-House | APEREZ12 | JBERGONZ | Manufacturing Plants | - | Digitalizacion de sistema de remitos | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
50062 | Vehicle Customer Order South America | In Production | VECTOR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Provide services to attend South America Sales & Marketing Order Fulfillment process that is based on SAMIS application (mainframe/db2). |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q2 2026 | Modernize to Cloud Databases | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
12894 | QualityWorX | In Production | QWX | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Enterprise Technology | Industrial System IT | In partnership with Manufacturing Engineering, provide IT leadership in support of Sciemetric Meters and QualityWorX installations (former Shadow IT applications). Sciemetric installations utilize signature capture and analysis to provide product testing during assembly. | 46 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
50062 | Vehicle Customer Order South America | In Production | VECTOR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Gold | Non S-Ox | 111 | No | Yes | In-House |  |  | Marketing & Sales | - | Provide services to attend South America Sales & Marketing Order Fulfillment process that is based on SAMIS application (mainframe/db2). |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | PDO team confirmed already on Java v21 | No | Java < v21
50208 | Vehicle Connectivity Enablement Services | In Production | VCES | EVDD | JWASNIC1 | ACHRIS39 | SHOWE | SHOWE | Gold | Non S-Ox | 212 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 212 | COLLECTION OF SERVICES DEVELOPED TO SUPPORT THE FULLY NETWORKED VEHICLE 2.0 (FNV2) PD PROGRAM. THESE SERVICES ENABLE A STANDARDIZED APPROACH FOR THE APPLICATIONS ON ETHERNET CONNECTED ECUS AND FOR DIRECT COMMUNICATION WITH FORD AND THIRD PARTY PROVIDER APPLICATIONS TO RETRIEVE FEATURE SPECIFIC CONTENT AFTER AUTHENTICATION/AUTHORIZATION. THE INITIAL SCOPE OF THIS ENDEAVOR INCLUDES: TOKEN MANAGEMENT, POLICY MANAGEMENT, AND OFF-PEAK WAKE-UP SERVICES IN SUPPORT OF THE IP PASS THROUGH / WIRELESS INTERFACE ROUTER DELIVERABLES. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
231 | Vehicle Commercial Invoice | In Production | VCI | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Silver | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Provides the broker VIN info on vehicles imported into the US, to match against the customs manifest. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q3 2027 | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
53722 | Vehicle as a Service | In Production | VaaS | M&S TECH | TUNDER17 | TUNDER17 | ABOONSTR | SKHANDE1 | Bronze | S-Ox Out of Scope | 311 | No | Yes | In-House | NKANDULA | TUNDER17 | Integrated Services | 311 | PLATFORM FOR TNC DRIVERS TO SUBSCRIBE TO VEHICLES |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
24354 | Vehicle Application & Domain Release | In Production | VADR | EVDD | AGARBY | FGRABOWS | EMARSMAN | MPUNUGU1 | Silver | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 322 | VEHICLE APPLICATION & DOMAIN RELEASE VADR IS AN APPLICATION THAT SUPPORTS THE BUILD AND RELEASE FOR IN VEHICLE SOFTWARE IN ALL FULLY NETWORKED VEHICLE FNV2 VEHICLES USING AUTOMOTIVE ETHERNET. THE APPLICATION WAS DESIGNED AROUND SEVERAL BASE PRINCIPLES IN ORDER TO KEEP FORD MOTOR COMPANY AT THE FOREFRONT OF VEHICLE TECHNOLOGY, ENSURING THAT VEHICLES ARE ABLE TO QUICKLY RECEIVE THE NECESSARY SOFTWARE UPDATES TO KEEP THEM CURRENT. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
11429 | Veh Schedule Control and Installation Record Sys | In Production | 9270 | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Gold | Non S-Ox | 133 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | Veh Sched Control and Install Record Sys (9270). 9270 is a vehicle scheduling system that also maintains production counts on a usage level and determines serialization and plant sourcing for vehicle orders. The official title of the 9270 System is the Vehicle Schedule Control and Installation Record System. Because the official system name is long and somewhat cumbersome it was never accepted and used in the system and user communities. The report output was at one time printed on a form number 9270. Use of this form number to identify the system has become a standard practice over the years. 9270 contains all UCC vehicle usage and forecast counts. | 1 |  | YES | 3 | NKANDULA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11429 | Veh Schedule Control and Installation Record Sys | In Production | 9270 | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Gold | Non S-Ox | 133 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | Veh Sched Control and Install Record Sys (9270). 9270 is a vehicle scheduling system that also maintains production counts on a usage level and determines serialization and plant sourcing for vehicle orders. The official title of the 9270 System is the Vehicle Schedule Control and Installation Record System. Because the official system name is long and somewhat cumbersome it was never accepted and used in the system and user communities. The report output was at one time printed on a form number 9270. Use of this form number to identify the system has become a standard practice over the years. 9270 contains all UCC vehicle usage and forecast counts. |  |  | YES | 3 | NKANDULA | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11429 | Veh Schedule Control and Installation Record Sys | In Production | 9270 | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Gold | Non S-Ox | 133 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | Veh Sched Control and Install Record Sys (9270). 9270 is a vehicle scheduling system that also maintains production counts on a usage level and determines serialization and plant sourcing for vehicle orders. The official title of the 9270 System is the Vehicle Schedule Control and Installation Record System. Because the official system name is long and somewhat cumbersome it was never accepted and used in the system and user communities. The report output was at one time printed on a form number 9270. Use of this form number to identify the system has become a standard practice over the years. 9270 contains all UCC vehicle usage and forecast counts. |  |  | YES | 3 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
13630 | VBS-Portal | In Production | VBS-Portal | ISIT | JKOONS | MMAHIMA | VPRAHALA | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Manufacturing Engineering | Industrial System IT | The VBS-Portal (Manufacturing Web) is a web portal that provides fast and easy access to manufacturing data for Body Construction (e.g. 3D tooling data, Simulations, Documentation, used product parts, etc.) and Stamping. |  |  | YES | 1 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
52570 | Variable Marketing Optimization | In Production | VaMOS | GDIA | EBLOCH | SKATARE | RBHARA29 | MPATEL20 | Silver | Non S-Ox | 311 | No | Yes | In-House | EBLOCH | LDESHPAN | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Enable customer usage of the VM optimization tool for on demand scenarios (more frequent access to GDIA data) for the yield management 2.0 |  |  | NO | 1 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
22242 | Variable Marketing Forecast Essbase | In Production | VMFE | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Asia Pacific Marketing and sales finance system tool to support the Variable Marketing Forecast operation. | 101 |  | YES | 3 | TSWEEN16 | PLM | Datastage | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | DA
22242 | Variable Marketing Forecast Essbase | In Production | VMFE | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Asia Pacific Marketing and sales finance system tool to support the Variable Marketing Forecast operation. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
11440 | QUALITY LEADERSHIP SYSTEM - VEHICLE OPERATIONS | In Production | QLS-VO | ISIT | SKING68 | KBARTHO1 | STOREY | RPRASA22 | Copper | Non S-Ox | 121 | No | Yes | In-House | SKING68 | KBARTHO1 | PD Operations and Quality | Industrial System IT | Quality Leadership System - Vehicle Operations is an application that provides the Assembly Plants with an electronic way to manage their quality data on units manufactured at the plant. The system is highly configurable in allowing the plants to specify what actions/processes occur in what location for various units being built. With this enviornment, it allows the plant to use the electronic, real time data to evaulate current quality processes, evaluate warranty data on units already produced, determine if a unit should be released (i.e. Gate Released) and shipped with respect to Quality, provide valuable data to several plant and corporate Six Sigma projects, provide data for Work Groups and VRT's for evaluating their processes etc. | 10 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
12976 | Variable Data Label System | In Production | VDLS | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Silver | Non S-Ox | 223 | No | Yes | In-House | DKAVITHA | UVIJAYAL | PD Operations and Quality | Industrial System IT | This application provides a mechanized system to capture certification and tire data from upstream engineering processes and generate data for VIN specific labels such as safety certification, tread act, tire pressure, etc. In addition, it provides data verification and auditing, provide timing and milestone tracking and notification and reporting capabilities. |  |  | YES | 5 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-11-28 |  | In-Progress | Green | 2026-02-26 |  | Planned |  | No | 25% | 0% | 0% | 0% | 0% | 0% | 0% |  | Cloud Run | Priya | 2025-03-04 |  |  |  | No | Java < v21
12976 | Variable Data Label System | In Production | VDLS | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Silver | Non S-Ox | 223 | No | Yes | In-House | DKAVITHA | UVIJAYAL | PD Operations and Quality | Industrial System IT | This application provides a mechanized system to capture certification and tire data from upstream engineering processes and generate data for VIN specific labels such as safety certification, tread act, tire pressure, etc. In addition, it provides data verification and auditing, provide timing and milestone tracking and notification and reporting capabilities. |  |  | YES | 5 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-11-28 |  | In-Progress | Green | 2026-02-26 |  | Planned |  | No | 25% | 0% | 0% | 0% | 0% | 0% | 0% |  | Cloud Run | Priya | 2025-03-04 |  |  |  | No | Java < v21
12976 | Variable Data Label System | In Production | VDLS | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Silver | Non S-Ox | 223 | No | Yes | In-House | DKAVITHA | UVIJAYAL | PD Operations and Quality | Industrial System IT | This application provides a mechanized system to capture certification and tire data from upstream engineering processes and generate data for VIN specific labels such as safety certification, tread act, tire pressure, etc. In addition, it provides data verification and auditing, provide timing and milestone tracking and notification and reporting capabilities. |  |  | No | 5 | BWUNNAVA | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [9 empty] | Priya |  |  |  | PDO Confirned there is no Mainframe for this app in the initial assessment meeting. Same captured in MOM & updated in Change log | No | Mainframe
12976 | Variable Data Label System | In Production | VDLS | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Silver | Non S-Ox | 223 | No | Yes | In-House | DKAVITHA | DKAVITHA | PD Operations and Quality | Industrial System IT | This application provides a mechanized system to capture certification and tire data from upstream engineering processes and generate data for VIN specific labels such as safety certification, tread act, tire pressure, etc. In addition, it provides data verification and auditing, provide timing and milestone tracking and notification and reporting capabilities. |  |  | YES | 5 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
11439 | Quality Leadership System - Component Mfg | In Production | QLS-CM | ISIT | SKING68 | KBARTHO1 | CLUND1 | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | SKING68 | KBARTHO1 | Manufacturing Engineering | Industrial System IT | QLS-CM performs automatic quality and as-build data collection as well as a full suite of traceabilty options. QLS-CM also performs schedule creation using the Hiejenken (TPS) method of leveled scheduling via EPLUS interface), schedule execution, transponder management and a Quarantine system that interfaces with plant floor controls to isolate and prevent installation of suspect parts. QLS-CM also includes repair/concern data management. For 6F program, Tranmission solenoid characteristics (TSC) are stored from Bosch and used to compare with supplier product. Finished TSC data is then sent to ECATS, CDC II, and FCSD systems. Repair data collection, and reporting are now available. Symbol WIndows CE app added to provide real time quarantine checks. Interface to upload serialized components to TRACE system is now available. Added in 2012 is replace for message broker communications infrustructure using web services and XML messaging. | 18 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
53465 | Vaccine Registration & COVID Testing | In Production | VR&T | OCETO | TSWEEN16 | KADOMKAI | PPOBURSK | ESTILESK | Gold | Non S-Ox | 322 | No | Yes | In-House | DDESAI | KADOMKAI | Enterprise Technology | Staffs IT | Vaccine registration system and Weekly COVID test upload: Codename Project Snowball |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | SQL
20355 | QNET | In Production | QNET | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | Q-Net is an reporting tool developed by Quantum Information Systems, Inc. used to provide ad-hoc reporting capability to users of all levels of expertise. The web-based tool allows users to create a web-based report containing data from one or more data sources of various types within a site or spanning multiple sites. It is currently installed in Powertrain plants in North America and Europe | 20 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
15258 | PTO - Outbound Logistics | In Production | PTOOBL | ISIT | SKING68 | KBARTHO1 | LMEENAKS | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | SKING68 | KBARTHO1 | Manufacturing Engineering | Industrial System IT | Application and infrastructure to provide engine and transmission traceability from the end of line to final customer destination. | 7 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
13425 | Used Vehicle Information System-UVIS | In Production | UVIS | FORD CREDIT | DTAURO | PBALUSU | LSTARZYK | RPARAME4 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | RMINHAS3 | PBALUSU | Marketing & Sales | Ford Credit (FMCC) | UVIS is the Ford system that manages all processes related to Vehicle Remarketing Inventory and Sales for the US & Canada. | 6221 |  | YES | 4 | SRAISIN1 | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned | [10 empty] | Webfocus 9 | [6 empty] | DA
13425 | Used Vehicle Information System-UVIS | In Production | UVIS | FORD CREDIT | DTAURO | PBALUSU | LSTARZYK | RPARAME4 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DTAURO | SKHAN29 | Marketing & Sales | Ford Credit (FMCC) | UVIS is the Ford system that manages all processes related to Vehicle Remarketing Inventory and Sales for the US & Canada. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Mainframe
15530 | PTDM-LPG Performance | In Production | PTDM-LPG | ISIT | OTHERS | GVANNOYE | GTACKOEN | JLUCAS1 | Silver | Non S-Ox | 111 | Yes | No | In-House | RTILLEY | GVANNOYE | PD Operations and Quality | Industrial System IT | Software used to manage the metadata of performance & special test data at Lommel Proving Ground. The metadata is used to drive a web search engine that enables access to the test data. | 3 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
13425 | Used Vehicle Information System-UVIS | In Production | UVIS | FORD CREDIT | DTAURO | PBALUSU | LSTARZYK | RPARAME4 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DTAURO | SKHAN29 | Marketing & Sales | Ford Credit (FMCC) | UVIS is the Ford system that manages all processes related to Vehicle Remarketing Inventory and Sales for the US & Canada. |  |  | YES | 4 | SRAISIN1 | PLM | WAS | Q3 2027 | Rewrite | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
20856 | URL Management Tools | In Production | UMT | EPEO | MCRNKOVI | SPANDRAN | NVIDICAN | NVIDICAN | Copper | Non S-Ox | 111 | No | Yes | - | MCRNKOVI | MCRNKOVI | Enterprise Technology | EPEO | This tool consolidates Vanity URL and URL Shortening functions into one suite of tools. Vanity URL provides redirection of a fully-qualified domain name to a Sharepoint URL. (example: www.one.ford.com => https://comm.sp.ford.com/sites/ONEFordSite/Pages/Default.aspx) Vanity URL is provided via web forms that facilitate the required back-end processes for managing DNS requests. URL Shortening provides a means of shortening any long URL to a shorter string of no more than 5 characters. (example: http://x.ford.com/4 => https://www.tc.ford.com/ts/et/Advanced%20IT/analytics/Lists/Calendar/by_Subj_Workstream_Cal.aspx) URL shortening is provided via web-based forms. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
22593 | PT CONTROLS SYSTEMS - GTPS | In Production | PCS-GTPS | EVDD | FFRISCHM | SCIBULAS | BPAVLIK1 | BPAVLIK1 | Copper | Non S-Ox | 321 | Yes | No | In-House |  |  | Enterprise Technology | - | A custom tool through which users plan embedded software strategy release timing of vehicle programs (a vehicle program is identified by its Model Year, Nameplate, Engine, Transmission, and Region). Work activities include [1] definition of software and hardware constraints--creating a vehicle program entry, entering emission data for intended markets, specifying the vehicle platform, features/hardware, and categorizing the program change, assigning people to resource roles, entering assumptions, and entering cal tool info; [2] definition of workflow and timing for release of strategy--selecting or keeping the default block timing group, specifying general info, ARD info, comments about the software drivers, and validation details, selecting new task timing or keeping defaults, entering milestone timing, and then, finally, [3] changing status to Complete. | 6 |  | YES | 1 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | VM
11260 | Universal Dealer Locator - Shadow | In Production | UDL | M&S TECH | KHEMANT | VMUTHUPA | SPOTLUR6 | MPINRED1 | Gold | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Enterprise Technology | 111 | UNIVERSAL DEALER LOCATOR IS AN ONLINE SERVICE OFFERED BY MICROSOFT-MULTIMAP AND WAS UPGRADED TO BING MAPS IN OCTOBER/2011. UDL ALLOWS OVER 30 APPLICATIONS TO SEARCH AND EXTRACT DEALER INFORMATION. THE SERVICE OFFERS: - SEARCHING DEALERS BY PROXIMITY (ZIP, CITY/STATE. EX: 30 MILE RADIUS OF 48126) AND NON-PROXIMITY (DEALER NAME) - MAPS - DRIVING DIRECTIONS - SENDING MAPS/DDS TO MOBILE PHONES - DEALER DISTANCE MATRIX - EXTRACTING DEALER'S COORDINATES USING POINT AND CLICK TOOL. THE SERVICE CURRENTLY COLLECTS DEALER INFORMATION FOR THE FOLLOWING BRANDS - - FORD,LINCOLN, - FORD OF CANADA - FCSD (COLLISION CARE, QUICKLANE). THE SERVICE IS MONITORED BOTH BY FORD AOS (SITESCOPE) TEAM AND EXTERNAL PARTNER - KEYNOTE. |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
22644 | PT CONTROLS SYSTEMS - ENGINEERING PROCESS TOOLS | In Production | PCS-EPT | EVDD | FFRISCHM | SCIBULAS | BPAVLIK1 | BPAVLIK1 | Copper | Non S-Ox | 222 | Yes | No | In-House |  |  | Advanced PD and Tech | - | Suite of custom and third-party software for creating a pre-release, uncalibrated, embedded software strategy, with work activities that include [1] managing content about applications, subsystems, and feature versions, using BluePrint; [2] feature development using ClearCase, text editors, Parameter Editor, compilers, linkers, FlexeLint, Feature/BFMT/FSS Bookshelf; [3] building an integrated application using some of the tools named in the previous step plus MakeHex32, MakeSYM, ASAP2Sym, SYM2A2L, CheckType, PD2A2L, AppPreRel, BFMTAppPreRel, producing and delivering a set of strategy application-related files (.H32, .SYM, .A2L, .CSV) to the calibrators. | 6 |  | YES | 1 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | VM
52722 | Unified Prototype Data Interface | In Production | UPDI | ISIT | JSHANAH1 | SHERBER1 | SDAVIS13 | LPATIL | Bronze | Non S-Ox | 111 | Yes | No | Open Source | JSHANAH1 | SHERBER1 | PD Operations and Quality | - | Used to help groups communicate to get Prototype POs blanket setup, control parts falling into Suspense, and negotiate piece pricing. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
22646 | PT CONTROLS SYSTEMS - CALIBRATION RELEASE | In Production | PCS-CALREL | EVDD | FFRISCHM | SCIBULAS | BPAVLIK1 | BPAVLIK1 | Copper | Non S-Ox | 232 | Yes | No | In-House |  |  | Advanced PD and Tech | - | Suite of tools for calibrating, certifying, and releasing an embedded, software strategy application. Work activities include [1] using Calibration File eXecutive (CFX) to create cal project, associate project to cal lists, edit cal data of parameters, resolve compliance issues, request cert sign-off, create image, and then release cal to cert team; [2] certify strategy with the CAlibration Release Tool (CART), signing-off on information about DV, OBD, calibration, transmission, transmission OBD, and transmission dependability; assign 7-character strategy name, and then, with SWDV hand-off certified strategy to the strategy release team; [3] transform object code into formats compatible with memory addressing of target PCMs, with PRISM (Production Release tool for In-Service Modules), make strategy files available in Ford and vendor production release areas (ProdRel), and then notify stakeholders. | 6 |  | YES | 1 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | VM
52722 | Unified Prototype Data Interface | In Production | UPDI | ISIT | JSHANAH1 | SHERBER1 | SDAVIS13 | LPATIL | Bronze | Non S-Ox | 111 | Yes | No | Open Source |  |  | PD Operations and Quality | - | Used to help groups communicate to get Prototype POs blanket setup, control parts falling into Suspense, and negotiate piece pricing. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
52718 | Unified e-Commerce Parts and Accessories | In Production | eComm IAL | M&S TECH | VMUTHUPA | VMUTHUPA | RSWAMINA | MPREETH6 | Platinum | S-Ox Out of Scope | 321 | No | Yes | Managed by 3rd Party Purchased Service | KHEMANT | VMUTHUPA | Enterprise Technology | Marketing, Sales and Service | Unified e-Commerce platform for Ford Parts and Accessories providing B2C and B2B webstores and a 3rd party marketplace store |  |  | YES | 2 | NKANDULA | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | SQL
51470 | Proving Ground Automated Vehicle Operations | In Production | PGAVO | ISIT | OTHERS | JHOLZING | JBICKMAN | JLUCAS1 | Silver | Non S-Ox | 111 | Yes | No | COTS | JSHANAH1 | JHOLZING | PD Operations and Quality | Industrial System IT | An advanced command & control software system for proving ground automation. Testers can create and execute detailed testing events that coordinate multiple unmanned and manned vehicles in the same location or at various locations around a proving ground. | 3 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
52718 | Unified e-Commerce Parts and Accessories | In Production | eComm IAL | M&S TECH | VMUTHUPA | VMUTHUPA | RSWAMINA | MPREETH6 | Platinum | S-Ox Out of Scope | 321 | No | Yes | In-House |  |  | Enterprise Technology | Marketing, Sales and Service | Unified e-Commerce platform for Ford Parts and Accessories providing B2C and B2B webstores and a 3rd party marketplace store |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
15045 | Prototype Vehicle Development Ad-Hoc | In Production | PVD Ad-Hoc | ISIT | OTHERS | CRISTIC | CSELF | ISIDDIQ6 | Silver | Non S-Ox | 311 | Yes | No | In-House | JLANE15 | CRISTIC | New Model Programs | - | Ad-Hoc environment for the New Model Launch related MP&L data. Includes 2 modules, Pre-prod BOM issues tracker and MP&L Cycle Plan Metrics. | 9 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23127 | uDeploy | Active | uDeploy | EPEO | LFULCHER | EREYNOL3 | JKADAKIA | SHAMID1 | Gold | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
20952 | Product Definition and Offering | In Production | PDO | ISIT | MNOWICK1 | LSRINIVA | DCOOMER | JLUCAS1 | Silver | S-Ox In Scope | 233 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | Application includes: Direct Authoring tool, Workflow and Change Mgmt, Market Offering | 102 |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
107 | UDB: Unified Data Base | In Production | UDB | M&S TECH | KPINNU | KHILLERT | GBONUTTI | JHARPER2 | Silver | Non S-Ox | 221 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | Data warehouse of which contains dealership repair order and part inventory information |  |  | YES | 3 | NKANDULA | PLM | Mainframe | Q4 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
107 | UDB: Unified Data Base | In Production | UDB | M&S TECH | KPINNU | KHILLERT | GBONUTTI | JHARPER2 | Silver | Non S-Ox | 221 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | Data warehouse of which contains dealership repair order and part inventory information |  |  | YES | 3 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
107 | UDB: Unified Data Base | In Production | UDB | M&S TECH | KPINNU | KHILLERT | GBONUTTI | JHARPER2 | Silver | Non S-Ox | 221 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | Data warehouse of which contains dealership repair order and part inventory information |  |  | YES | 3 | NKANDULA | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
21179 | uBuild | In Production | uBuild | EA | RRISS | SHE1 | LKESHRI | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | 211 | uBuild is an automated build and test used to assist in application development and testing. |  | Springboot | YES | 3 | GBRAIL | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
21179 | uBuild | In Production | uBuild | EA | RRISS | SHE1 | LKESHRI | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | - | uBuild is an automated build and test used to assist in application development and testing. |  |  | YES | 3 | GBRAIL | PLM | SQL | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | Decommission | [6 empty] | SQL
22749 | Product Definition and Offer - Marketing and Prici | In Production | PDOR2 | ISIT | MNOWICK1 | LSRINIVA | DESPINOS | JLUCAS1 | Silver | Non S-Ox | 222 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | Application includes Market Offering, Change Management and related functionality | 38 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22746 | UBETestingSuite | In Production | UBEtest | ISIT | OTHERS | JVERHEY2 | EKOEHLE1 | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | In-House | MMAILE1 | JVERHEY2 | PD Operations and Quality | Industrial System IT | The UBE Testing Suite is a distributed application consisting of a SQL database and three frontend tools. The application is globally used within PD (VEV and EESE) to define and manage test scripts for vehicle software tests (Sequence Editor), to coordinate the test execution of those scripts (TMT v3) and to execute those scripts on the test environment (SATA) |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
18625 | Product Creation Domain Search Application - PCDS | In Production | PCDS | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Quality | Industrial System IT | Domain Specific Search software, which offers a single user interface to help engineers find corporate knowledge from multiple sources on the intranet such as EKB, eRoom, SetK, E2KS, PeBOD etc. in product creation domain. SLA rating - 3 | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20179 | U/SAP - FUS SAP SPM Solution (FCSD) | In Production | Phoenix | I-ERP | SVISWANA | RKAMLAGE | VREDDY5 | MMEHTA5 | Gold | Non S-Ox | 232 | No | Yes | COTS | SVISWANA | RKAMLAGE | Ford Customer Service | FCSD Tech | Standard software 'SAP service parts management (SPM)' to support the US FCSD's SAP Service parts management business.SAP products involved are: ERP 6.18, PI 7.5, CRM 7.14, SCM-SPP 7.14, SCM-EWM 9.4.This is the non-S-Ox part of the SPM solution, whose S-Ox part is under the new number 51062 for the dedicated SAP EWM. | 214 |  | YES | 5 | TSWEEN16 | PLM | Datastage | Q3 2026 |  | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-11-15 |  | Planned |  | No | [14 empty] | No | DA
20179 | U/SAP - FUS SAP SPM Solution (FCSD) | In Production | Phoenix | I-ERP | SVISWANA | RKAMLAGE | VREDDY5 | MMEHTA5 | Gold | Non S-Ox | 232 | No | Yes | COTS | SVISWANA | RKAMLAGE | Ford Customer Service | FCSD Tech | Standard software 'SAP service parts management (SPM)' to support the US FCSD's SAP Service parts management business.SAP products involved are: ERP 6.18, PI 7.5, CRM 7.14, SCM-SPP 7.14, SCM-EWM 9.4.This is the non-S-Ox part of the SPM solution, whose S-Ox part is under the new number 51062 for the dedicated SAP EWM. |  |  | YES | 5 | TSWEEN16 | PLM | Mainframe | TBD | Move Capabilities to SaaS Solution | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
20179 | U/SAP - FUS SAP SPM Solution (FCSD) | In Production | Phoenix | I-ERP | SVISWANA | RKAMLAGE | VREDDY5 | MMEHTA5 | Gold | Non S-Ox | 232 | No | Yes | COTS | SVISWANA | RKAMLAGE | Ford Customer Service | FCSD Tech | Standard software 'SAP service parts management (SPM)' to support the US FCSD's SAP Service parts management business.SAP products involved are: ERP 6.18, PI 7.5, CRM 7.14, SCM-SPP 7.14, SCM-EWM 9.4.This is the non-S-Ox part of the SPM solution, whose S-Ox part is under the new number 51062 for the dedicated SAP EWM. |  |  | YES | 5 | TSWEEN16 | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
20179 | U/SAP - FUS SAP SPM Solution (FCSD) | In Production | Phoenix | I-ERP | SVISWANA | RKAMLAGE | VREDDY5 | MMEHTA5 | Gold | Non S-Ox | 232 | No | Yes | COTS | SVISWANA | RKAMLAGE | Ford Customer Service | FCSD Tech | Standard software 'SAP service parts management (SPM)' to support the US FCSD's SAP Service parts management business.SAP products involved are: ERP 6.18, PI 7.5, CRM 7.14, SCM-SPP 7.14, SCM-EWM 9.4.This is the non-S-Ox part of the SPM solution, whose S-Ox part is under the new number 51062 for the dedicated SAP EWM. |  |  | YES | 5 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
23716 | Product Attribute Management - PAM | In Production | PAM | ISIT | MNOWICK1 | LSRINIVA | DESPINOS | JLUCAS1 | Bronze | Non S-Ox | 232 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | Product Attribute Management (PAM) seeks to establish a generic capability to manage product attribute data, leveraging the strategic PDO solution as the single-source of truth for feature level product information. | 5 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11830 | Process Configuration | In Production | PRC | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SKING68 | KRAMESH | Manufacturing Engineering | - | PRC has value stream mapping function with stations and equipment. Used by PTO to document process flow for mfg operations. Application supports multibyte language to use regional language. | 16 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
24115 | TypeMaster.Doc | In Production | TypeMaster | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Bronze | Non S-Ox | 112 | No | Yes | COTS | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | TypeMaster is a J2EE web based replacement for CHIP contains structured technical data in order to support the Homologation processes for Whole Vehicle Type Approval (WVTA) homologation processes. Replaces CHIP application a business customizable 3rd party Solution from Supplier T-Systems. |  |  | YES | 1 | BWUNNAVA | PLM | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
20634 | TWOS Reporting System | In Production | TRS | OCETO | TSWEEN16 | SCHILAKA | JALEXAN3 | MBALAN2 | Bronze | Non S-Ox | 333 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | This is the Business Objects reporting application that reports data from the distributed TWOS application (ITMS #62) | 4523 |  | YES | 2 | TSWEEN16 | PLM | BO | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-30 | 2026-12-30 |  | In-Progress | Green | 2027-02-28 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | EXCEPTION BASED. Approval from Tom Culler received to remain on platform until Infra decom. | No | DA
53128 | Privileged Remote Access for Mfg. Plants | In Production | PRA | ISIT | SKING68 | KBARTHO1 | JBARGER | RPRASA22 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SKING68 | KBARTHO1 | Manufacturing Engineering | Industrial System IT | Privileged Remote Access (PRA) is an appliance-based tool that provides remote connectivity to endpoints and enables administrative control, monitoring, management, and auditing of privileged users' access to ICS systems. | 1 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
13760 | TVM Effective Reporting System | In Production | TVM ER | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Provides the capability to report total (design plus non-design) savings by TVM Team. Data is sourced from CRID and NDPC2. |  |  | YES | 1 | TSWEEN16 | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Oracle
17425 | TSO Middleware | In Production | TSO MW | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | JCHAUSSE | Enterprise Technology | FCSD Tech | TSO Middleware is a Java based application residing between Global OASIS (EAMS #99 - Mainframe App) and PTS and other downstream systems. It is a web interface of GOASIS which provides multiple API services for a specific VIN /vehicle attribute. |  |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | 75% | 25% | [6 empty] | Cloud Run | [5 empty] | No | Java < v21
17425 | TSO Middleware | In Production | TSO MW | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | JCHAUSSE | Enterprise Technology | FCSD Tech | TSO Middleware is a Java based application residing between Global OASIS (EAMS #99 - Mainframe App) and PTS and other downstream systems. It is a web interface of GOASIS which provides multiple API services for a specific VIN /vehicle attribute. |  |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | 75% | 25% | [6 empty] | Cloud Run | [5 empty] | No | Java < v21
52678 | TrueSight Orchestration | In Production | TSO | EPEO | RHAMMO57 | JGIES | AMANI1 | GSIENKIE | Silver | Non S-Ox | 223 | No | Yes | COTS | RHAMMO57 | JGIES | Enterprise Technology | EPEO | True Sight Orchestration (TSO) is a BMC Business Process Automation tool. We plan to use this to automate manual/routine ITSM processes. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [5 empty] | No | SQL
51326 | Privacy Protection | In Production | SCA PP | GDIA | CBUCKL19 | VPANDUR1 | UBANDI | MPATEL20 | Silver | Non S-Ox | 321 | No | Yes | In-House | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Privacy Protection application collects and manages CCPA requests | 5 |  | YES | 2 | FRANBELL | PLM | VM | TBD | Will be Decommissioned | Decommission | 2025-03-11 | 2025-03-11 | 2025-03-11 | Complete | Blue | 2025-03-11 | 2025-03-11 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | No VMs shown in SNOW. Marked it as completed | No | VM
20899 | Trucks Ford Service & Ford Protect | In Production | TMAC | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | TMAC is a truck maintenance contract system for the Brazilian Market. This system controls sales of special truck maintenance contracts (MC) for preventive and corrective maintenance of Big Truck Fleet Across the country. Additionally, it enables Ford to improve its competitiveness in the Brazilian heavy truck business. Ford Protect is an additional feature to attend Vehicle ESB. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | PCF migration completed in 2024 | No | Java < v21
20899 | Trucks Ford Service & Ford Protect | In Production | TMAC | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | TMAC is a truck maintenance contract system for the Brazilian Market. This system controls sales of special truck maintenance contracts (MC) for preventive and corrective maintenance of Big Truck Fleet Across the country. Additionally, it enables Ford to improve its competitiveness in the Brazilian heavy truck business. Ford Protect is an additional feature to attend Vehicle ESB. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-11 | Complete | Blue | 2025-06-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | DB Migration completed | No | SQL
50391 | PREEvision | In Production | PREEvision | ISIT | MNOWICK1 | PBORGAO1 | SBELSAR1 | GRAO3 | Silver | Non S-Ox | 221 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Enterprise Technology | Industrial System IT | Electrical & Electronic architecture design tool enables architects to design and evaluate electric & electronic architectures and conduct a holistic analysis to assess the impact to all areas of EESE (Hardware, Software, EDS and NetCom). EE Architecture team currently manually collects data for Feature to functional level decomposition and impact analysis efforts. This tool will enable the future plans/implementation (beyond 2019) for direct interfaces to VSEM, EDS, NetCom, ALM, etc. and provide arch. capability in the Siemens toolset to conduct the impact analysis. This will plug the gap in Siemens' system Engineering landscape. | 17 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
20899 | Trucks Ford Service & Ford Protect | In Production | TMAC | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | TMAC is a truck maintenance contract system for the Brazilian Market. This system controls sales of special truck maintenance contracts (MC) for preventive and corrective maintenance of Big Truck Fleet Across the country. Additionally, it enables Ford to improve its competitiveness in the Brazilian heavy truck business. Ford Protect is an additional feature to attend Vehicle ESB. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | PCF migration completed in 2024 | No | Java < v21
52651 | Tririga Space Planning | In Production | TSP | OCETO | TSWEEN16 | KADOMKAI | TJACKS13 | ESTILESK | Silver | Non S-Ox | 211 | No | Yes | COTS | DDESAI | KADOMKAI | Ford Land | Staffs IT | Application used by Ford Land for Space Planning and Move Management and Desk Reservations |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
13876 | PRC-Parts Recall Centre Management Sys | In Production | PRC | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JDEGUZMA | RMEHTA3 | Quality | Industrial System IT | The programs traces the data from parts stored at the Parts Recall Centres. The users can query the database to retrieve information about parts. There are several reports that give different analysis to the lifeline of concerns and its parts. Some Reports are published on the Ford intranet. The Supplier recall module charges suppliers for faulty parts. | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51589 | Tricentis Tosca | In Production | TOSCA | FORD CREDIT | JMALETZ | SHE1 | KBALAS30 | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | COTS | JMALETZ | NVENKAT2 | Enterprise Technology | - | Tricentis Tosca is a Continuous Testing platform that accelerates testing to keep pace with Agile and DevOps. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q2 2026 | Modernize to Cloud Databases | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned | [16 empty] | No | SQL
50794 | POWERVC | In Production | POWERVC | EPEO | LFULCHER | EREYNOL3 | JAKHOON | JAKHOON | Bronze | Non S-Ox | 111 | No | Yes | In-House |  |  | Enterprise Technology | EPEO | PowerVC is an automation tool to deploy AIX LPARs on pSeries hardware | 1 |  | YES | 1 | SWALIMBE | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | GCP Migration | [5 empty] | No | VM
23975 | Powertrain HIL/SIL Dashboard & Data Mngmt DB | In Production | PT DM-DB | ISIT | JKOONS | MNOVAK1 | HLIN11 | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | The application provide planning and reporting capabilities to show incremental new simulation artifacts needed by upcoming applications. Support for automated creation of virtual controllers. Automatically generate required HIL artifacts for HIL simulation and bench set-up. Organizes and manages critical plant data, controller data parameterization information. Provides a workflow and ease of use optimized for simulation building and delivery. | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
50548 | TrboNet | In Production | TrboNet | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Silver | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | TRBOnet is a suite of professional applications for MOTOTRBO digital two-way radio networks. TRBOnet manages voice and data communication paths across network endpoints. It provides a unified graphical dispatcher workbench interface for the entire range of workforce fleet management tasks. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2027 | On-Prem | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | SQL
54694 | Power Monitoring Expert | In Production | PME | OCETO | TSWEEN16 | KADOMKAI | ESTILESK | ESTILESK | Bronze | Non S-Ox | 111 | Yes | No | COTS | DDESAI | KADOMKAI | Manufacturing Plants | - | Monitoring of all energy devices in Manufacturing Plants | 2 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
19014 | Transport Management System | In Production | TMS | ISIT | JPITTERL | CBOHN | MBONAKDA | SSENTH15 | Silver | Non S-Ox | 212 | Yes | No | In-House | CBOHN | IREINHO3 | Manufacturing Staffs | Industrial System IT | Application to executional plan a logistical transportation network. Main function is to provide trip sheet and pick-up information based on DCI information. Application is operated by the European LLP who's main responsibility is to plan the logistics of the inbound material into all European manufacturing plants. |  |  | NO | 3 | BWUNNAVA | PLM | SQL |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
19014 | Transport Management System | In Production | TMS | ISIT | JPITTERL | CBOHN | MBONAKDA | SSENTH15 | Silver | Non S-Ox | 212 | Yes | No | In-House | CBOHN | IREINHO3 | Manufacturing Staffs | Industrial System IT | Application to executional plan a logistical transportation network. Main function is to provide trip sheet and pick-up information based on DCI information. Application is operated by the European LLP who's main responsibility is to plan the logistics of the inbound material into all European manufacturing plants. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23383 | PORTABLE QUALITY ASSURANCE DEVICE. | In Production | PQAD | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 11 | Yes | No | Managed by 3rd Party Purchased Service |  |  | Enterprise Technology | - | The PQAD (Portable Quality Assurance Device) project requires the use of a handheld computing device which will have an application installed onto it to allow for an Automated Control System to check failures and quality inspections. It will provide Full Vehicle Traceability as it will know exactly which operations have been performed over a specific vehicle. The applications users SMTP MRL to send notifications reports, etc | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51067 | Transformation Enterprise Manager | In Production | TEM | GDIA | CPELTZE1 | MRAFFLE | WHAIDRI | RPOLLO13 | Gold | Non S-Ox | 11 | No | Yes | In-House | MLYONS23 | MJUHASZ | Enterprise Technology | 11 | Sql generator for Transformation and scheduler to run jobs in Hadoop Environment |  | Springboot | NO | 3 | FRANBELL | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
51067 | Transformation Enterprise Manager | In Production | TEM | GDIA | CPELTZE1 | MRAFFLE | WHAIDRI | RPOLLO13 | Gold | Non S-Ox | 11 | No | Yes | In-House | MLYONS23 | MJUHASZ | Enterprise Technology | - | Sql generator for Transformation and scheduler to run jobs in Hadoop Environment |  |  | NO | 3 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
11489 | POLR: Plant On-Line Reporting | In Production | POLR | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Bronze | Non S-Ox | 311 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | - | POLR reports data stored in DLORS database for VO and PTO plants, accessed by Purchasing and Finance Staff. | 8 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
623 | TranSend II (DataMyte) | In Production | TranSend | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | This application is used to extract and process measurement data collected by Datamyte data collector that are measuring the margin/flush and fixture data. The application sends the data to WBDM (Web Base Data Management). Transend is a desktop metrology software that is used to program and extract dimensional data from a Datamyte data collector. Transend II is a client/server metrology application |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
12799 | Plant | In Production | Q-DAS | ISIT | SKING68 | DCLEME13 | TPICKERE | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | The qsSTAT component collects and analyzes process and product related dimensional data to determine whether the process is in statistical control and whether the product conforms to quality specifications. | 23 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
50714 | TRAKA | In Production | TRAKA | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | - | Beyond securing and managing access to keys, Traka solutions can generate unique workflows that support the important processes of your business u2013 require a secondary authorization for master keys, pair key sets to guarantee the lockout of hazardous systems during maintenance, or set curfews which automatically send notifications to administrators, managers or users. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
13296 | PKGINFO Ford B2B hosted | In Production | PKGINFOSUP | I-ERP | OTHERS | TALEXAN4 | TKASPER | MMEHTA5 | Copper | Non S-Ox | 111 | Yes | No | Managed by 3rd Party Purchased Service | BOSTERL1 | TALEXAN4 | Ford Customer Service | - | PS&L Packaging Engineering generates packaging specifications to be used by suppliers. Website supported by Creative Data Inc. Server: eccws547.dearborn.ford.com (DEV) eccws549.dearborn.ford.com (PROD) Vendor contact Glenn LaFever glafeve2 | 5 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
12883 | Training Operations Support Website | In Production | etdc | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Copper | Non S-Ox | 111 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Training Operations Support website is an internal work portal for Retailer Education & Training (RE&T). It is designed to facilitate the development, promotion, delivery and ongoing maintenance of non-technical training and other educational products / services which our department provides for Ford and Lincoln dealership employees in the U.S.; https://www.et.dealerconnection.com/etWeb/home.do |  |  | YES | 3 | NKANDULA | PLM | Java Struts | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-10-15 | 2024-10-15 | Complete | Blue | 2024-12-15 | 2024-10-15 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | This is not partial, app decommissioned fully | No | Java < v21
12883 | Training Operations Support Website | In Production | etdc | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Copper | Non S-Ox | 111 | No | Yes | In-House | FHIRSH | FHIRSH | Customer Experience | Marketing, Sales and Service | Training Operations Support website is an internal work portal for Retailer Education & Training (RE&T). It is designed to facilitate the development, promotion, delivery and ongoing maintenance of non-technical training and other educational products / services which our department provides for Ford and Lincoln dealership employees in the U.S.; https://www.et.dealerconnection.com/etWeb/home.do |  |  | YES | 3 | NKANDULA | PLM | Oracle | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-10-15 | 2024-10-15 | Complete | Blue | 2024-12-15 | 2024-10-15 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Oracle
12883 | Training Operations Support Website | In Production | etdc | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Copper | Non S-Ox | 111 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Training Operations Support website is an internal work portal for Retailer Education & Training (RE&T). It is designed to facilitate the development, promotion, delivery and ongoing maintenance of non-technical training and other educational products / services which our department provides for Ford and Lincoln dealership employees in the U.S.; https://www.et.dealerconnection.com/etWeb/home.do |  |  | YES | 3 | NKANDULA | PLM | WAS | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-10-15 | 2024-10-15 | Complete | Blue | 2024-12-15 | 2024-10-15 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
50045 | TrackLite | In Production | TrackLite | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SBONNICI | SBONNICI | Enterprise Technology | Industrial System IT | TrackLite is the Next Gen tool for eTracker (ITMS No 12408).eTracker tracks issues, tasks, risks and opportunities or anything else that needs tracking eTracker is broken down into individual projects, which can be tailored to suit the team's specific needs. Rather than forcing a user to choose from a vast array of predefined fields, eTracker allows the administrator for each project to define the necessary fields. Most of the input fields can be customized, new fields may be added, and unused fields, removed. The prompts and default lists associated with the fields can also be customized. Additionally, eTracker's reports may be modified to include any fields desired, using nearly any filter and sort method. Reports can be built by customizing those already in the system, or from scratch, and can be made public or private, as the user desires.Tracklite will be using integration like external SMTP for PEGA SaaS |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23029 | Pinnacle - Global Tools Audit | In Production | PINNAUDIT | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Bronze | Non S-Ox | 222 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Global instance for the following Loan Originations applications: Reconciliation Report. | 1 |  | YES | 3 | SRAISIN1 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
50045 | TrackLite | In Production | TrackLite | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SBONNICI | SBONNICI | Enterprise Technology | Industrial System IT | TrackLite is the Next Gen tool for eTracker (ITMS No 12408).eTracker tracks issues, tasks, risks and opportunities or anything else that needs tracking eTracker is broken down into individual projects, which can be tailored to suit the team's specific needs. Rather than forcing a user to choose from a vast array of predefined fields, eTracker allows the administrator for each project to define the necessary fields. Most of the input fields can be customized, new fields may be added, and unused fields, removed. The prompts and default lists associated with the fields can also be customized. Additionally, eTracker's reports may be modified to include any fields desired, using nearly any filter and sort method. Reports can be built by customizing those already in the system, or from scratch, and can be made public or private, as the user desires.Tracklite will be using integration like external SMTP for PEGA SaaS |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
11567 | Traceability: SAVE - Traceability | In Production | TRACE | ISIT | SKING68 | KBARTHO1 | LMEENAKS | RPRASA22 | Gold | Non S-Ox | 121 | No | Yes | In-House | SKING68 | KBARTHO1 | PD Operations and Quality | Industrial System IT | This application accepts input from final area assembly plants coorelating component serial numbers to vins and makes them available to general applications. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
53898 | TPE Billing Helper | In Production | TPE BH | EVDD | JWASNIC1 | VVINOD3 | CJEYAKUM | JMOHAN13 | Silver | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 211 | A SMALL COMPONENT TO HELP ALL THIRD PARTY ENABLEMENT PRODUCTS (NEUTRAL SERVER, VAAS, RSD, LHI/LT, ETC.) TO POST THEIR VIN/DATA USAGE AND GET THE INVOICE RAISED THROUGH SSP API. FEED THIS DATA TO CRM FOR ANY REPORTING AND VISUALIZATION BY BUSINESS. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
15249 | Torque Inspection and Studies System/TPPS | In Production | TISS/TPPS | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | Yes | No | In-House | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | TISS (Torque Inspection and Studies System) and TPPS (Torque Process Potential Studies) capture torque information from the plant floor to be used for inspection purposes. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
16171 | PERCEPTRON AUTOGAUGE | In Production | PERCEPTRON | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House |  |  | Manufacturing Engineering | Industrial System IT | Dimensional Data Management (DDM) is a database of assembly line measurement data from Perceptron scanners. It provides data analysis tools to help identify, trace and sources of process variation. | 1 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
18817 | ToolsNet | In Production | Tnet | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | Yes | No | Managed by 3rd Party Purchased Service | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | Nutdrivers tork collection AP BMIT_IN_FIPL_ToolsNet |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
11482 | PeopleSoft (ASR) AR / BI | In Production | ASR AR | I-ERP | SFRANCI8 | SDHANAL3 | PSATHIS3 | CWADE | Gold | S-Ox In Scope | 332 | No | Yes | COTS | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | PeopleSoft Accounts Receivables module is responsible for the entry of items (outstanding invoices), handling customer payments, dealer statements, managing customer invoices, and creating customer correspondence such as customer statements. PeopleSoft Billing information is used to create invoice, receive billing data from other upstream applications, print invoices and create accounting entries for PeopleSoft General Ledger and Accounts Receivables. | 1 |  | YES | 3 | TSWEEN16 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
24485 | TMT | In Production | TMT | ISIT | OTHERS | JVERHEY2 | EKOEHLE1 | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | In-House | MMAILE1 | JVERHEY2 | PD Operations and Quality | Industrial System IT | TMT (Test Management Tool) is an global, Application Server based Application to manage test complexity, test cases and to coordinate the test execution. TMT offers multiple Interfaces to other Tools as VSEM and offers a web based, graphical user interface to manage its data. TMT also offers a SOAP interface to other test relevant tools like Sequence Editor ATX, FTIDE etc. All test information is stored in a standardize ASAM ATX test description format. The Tool is in development until 2018. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
50102 | PAX-IT | In Production | PAX-IT | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | PAX-IT Is an Image Management Software used for measuring, verifying and storing images of Welds. Joined parts cut and viewed under a microscope in a lab for evaluation. PRAX-IT works with a PRAXCAM camera mounted on a microscope. The images are managed by the software and are also used for reporting documents. | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
24485 | TMT | In Production | TMT | ISIT | OTHERS | JVERHEY2 | EKOEHLE1 | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | In-House | MMAILE1 | JVERHEY2 | PD Operations and Quality | Industrial System IT | TMT (Test Management Tool) is an global, Application Server based Application to manage test complexity, test cases and to coordinate the test execution. TMT offers multiple Interfaces to other Tools as VSEM and offers a web based, graphical user interface to manage its data. TMT also offers a SOAP interface to other test relevant tools like Sequence Editor ATX, FTIDE etc. All test information is stored in a standardize ASAM ATX test description format. The Tool is in development until 2018. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
52446 | TMC Alert Processing and Publishing Service | In Production | TAPPS | EVDD | AGARBY | FGRABOWS | MSHEIKBA | MSHEIKBA | Gold | Non S-Ox | 212 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 212 | TAPPS CONSUMES ALERTS FROM THE TMC FEED TO PROVIDE TO DOWNSTREAM SYSTEMS TO FULFILL VARIOUS BUSINESS NEEDS (E.G. ASUSETTINGS FOR OTA). ALERT DATA IS ALSO STORED AND MAY BE EXPOSED VIA API FOR RETRIEVAL BY FORD SYSTEMS. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
15340 | Part Tracking Management System | In Production | PTMS | ISIT | OTHERS | LJACOBI | SLEVAN | LPATIL | Silver | Non S-Ox | 211 | Yes | No | In-House | DLEHMKUH | LJACOBI | PD Operations and Quality | - | Part Tracking Management System is a workplanning tool to track vehicle program part information. | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
62 | Timekeeping and Work Orders (Hourly) | In Production | TWOS | OCETO | TSWEEN16 | SCHILAKA | JALEXAN3 | MBALAN2 | Silver | S-Ox In Scope | 333 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | Timekeeping and Work Orders (Hourly). The TWOS system manages timekeeping, personnel data and changes (moved to HCM 5/9/2022) , and labor distribution for all US and Canadian hourly personnel. TWOS delivers a widely recognized and respected timekeeping service that builds employee satisfaction and adheres to Company |  |  | YES | 4 | TSWEEN16 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
62 | Timekeeping and Work Orders (Hourly) | In Production | TWOS | OCETO | TSWEEN16 | SCHILAKA | JALEXAN3 | MBALAN2 | Silver | S-Ox In Scope | 333 | No | Yes | In-House | DDESAI | DDESAI | Human Resources | Staffs IT | Timekeeping and Work Orders (Hourly). The TWOS system manages timekeeping, personnel data and changes (moved to HCM 5/9/2022) , and labor distribution for all US and Canadian hourly personnel. TWOS delivers a widely recognized and respected timekeeping service that builds employee satisfaction and adheres to Company |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  | 1900-03-30 |  | Planned |  | No | [14 empty] | No | Oracle
18766 | Part Library II - PLII | In Production | PL-II | ISIT | MNOWICK1 | LSRINIVA | GPIOT1 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | PD Operations and Quality | Industrial System IT | Part Library II is intended to be the next generation of the Part Library application that's currently in production. This application is part of the Global Commodity Management initiative. It will serve as a catalog of technical attribute information for all commodities/parts. | 2 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
62 | Timekeeping and Work Orders (Hourly) | In Production | TWOS | OCETO | TSWEEN16 | SCHILAKA | JALEXAN3 | MBALAN2 | Silver | S-Ox In Scope | 333 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | Timekeeping and Work Orders (Hourly). The TWOS system manages timekeeping, personnel data and changes (moved to HCM 5/9/2022) , and labor distribution for all US and Canadian hourly personnel. TWOS delivers a widely recognized and respected timekeeping service that builds employee satisfaction and adheres to Company |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
19620 | TIME WINDOWS (VEHICLE UNLOADING) SPAIN | In Production | TWVU | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Plants | Industrial System IT | Application that controls incoming transport vehicles and monitors the unload of their content in the plant docks especially it keeps track of transport timings. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
19620 | TIME WINDOWS (VEHICLE UNLOADING) SPAIN | In Production | TWVU | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Plants | Industrial System IT | Application that controls incoming transport vehicles and monitors the unload of their content in the plant docks especially it keeps track of transport timings. |  |  | YES | 4 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23133 | Part Churn Reporting | In Production | CHURN RPT | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Silver | Non S-Ox | 211 | Yes | No | In-House |  |  | PD Operations and Quality | - | Calculates and reports on BOM Part Churn after FDJ. Reports are by program and PMT. | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19620 | TIME WINDOWS (VEHICLE UNLOADING) SPAIN | In Production | TWVU | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Plants | Industrial System IT | Application that controls incoming transport vehicles and monitors the unload of their content in the plant docks especially it keeps track of transport timings. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23728 | PAM Attribute Calculator | In Production | PAM-AC | ISIT | MNOWICK1 | LSRINIVA | DESPINOS | JLUCAS1 | Silver | Non S-Ox | 233 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | Product Attribute Management (PAM) Attribute Calculator. This application provides for calculations on a highly available basis based on PAM data. Related to / interfaces with 23716 Product Attribute Management (PAM) | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20977 | PADB2 | In Production | PADB2 | ISIT | MNOWICK1 | LSRINIVA | VATMAKUR | LPATIL | Silver | Non S-Ox | 111 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | - | The Part Address Database holds mappings of parts to part functions and CPSC II codes, maintaining the CPSC II information standard. | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52683 | ThreatModeler | In Production | ThreatMod | OCETO | PMILLIGA | DZAJAC8 | MDUFFY35 | WJUSTICE | Bronze | Non S-Ox | 321 | No | Yes | COTS | TGEIGER | DZAJAC8 | Enterprise Technology | - | Threat Modeler will improve the vehicle and mobility cyber security management system, including an auditable process to assess risk, track issues, and manage evidence provision to support regulatory requirements placed on our vehicles and mobility products. It will be the Ford global threat model repository for all Ford vehicle and mobility products. |  |  | YES | 2 | PMILLIGA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
12342 | OVS - OPTIMISED VEHICLE SCHEDULING | In Production | OVS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Selects vehicles for scheduling to the manufacturing plants. OVS is a system that schedules on what particular day a vehicle is to be built. | 3 |  | YES | 4 | NKANDULA | PLM | VM | TBD | EDC CaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
56536 | Otosan Fluid Fill Gateway | Planned | FluidGW | ISIT | OTHERS | - | UEMIR1 | UEMIR1 | Silver | Non S-Ox | - | No | Yes | Managed by 3rd Party Purchased Service | OTHERS | #N/A | Manufacturing Staffs | - | As soon as the ECATS tester passes the Beacons for the fluid fill zones, the eCATS tester will start an Ethernet (TCP-IP) communication (telegram) to a transparent gateway server and gateway server will forward telegram to the fluid fill central PC. Based on the telegram data the eCATS tester will send corresponding CAN data to the ABS module through the OBD connector to control the ABS module during the ABS filling process. | 1 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
54153 | On-Prem ESXi Hosting | Active | OPESXiH | EPEO | LFULCHER | KMAHAJAN | GBRADFO3 | GBRADFO3 | Bronze | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | Enterprise Technology | ITO | On-Prem ESXi Hosting | 44 |  | YES | 2 | SWALIMBE | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
54579 | Threat Assessment Site/Risk Rating | In Production | TAS | OCETO | PMILLIGA | TYOUNG91 | DOREIL11 | WJUSTICE | Copper | Non S-Ox | 321 | No | Yes | In-House | TGEIGER | TYOUNG91 | Enterprise Technology | - | Tool to assess vulnerabilities in code and vehicles |  |  | YES | 2 | PMILLIGA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
22901 | ONP - Vehicle Energy Compliance Model | In Production | ONP-VECM | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 321 | No | Yes | In-House | JKOONS | NLAKSHMA | PD Operations and Quality | Industrial System IT | The application will support the source input data processing for the New Compliance Model calculator on Ne National Program. ONP program will enable business process improvements in products/programs cycle planning and compliance reporting process through a comprehensive integrated global IT strategy enabling business teams in developing product scenarios to optimize compliance strategy by managing vehicle and fleet level fuel economy and emissions targets. Provide technological solutions for business capabilities to optimize product mix with technology offerings for future profits and credits as well as meet the stringent regulatory compliance targets | 4 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
54579 | Threat Assessment Site/Risk Rating | In Production | TAS | OCETO | PMILLIGA | TYOUNG91 | DOREIL11 | WJUSTICE | Copper | Non S-Ox | 321 | No | Yes | In-House |  |  | Enterprise Technology | - | Tool to assess vulnerabilities in code and vehicles |  | Springboot | YES | 3 | PMILLIGA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
22828 | OnGuard-The Ford Global Card Access System | In Production | OnGuard | OCETO | TSWEEN16 | BBEEKEL | JWALK257 | ESTILESK | Silver | Non S-Ox | 211 | Yes | No | COTS | MFLEURY | BBEEKEL | Policy | Staffs IT | The Corporate standard application used globally to manage access control (formerly Picture Perfect). This COTS application is provided by Lenel. OnGuard is used in conjunction with NetBadge, #19066, the application that manages access control badges. | 37 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
50288 | Theorem Digital Reality Platform | In Production | TDRP | ISIT | SKING68 | JLYNN1 | KKISIEL | AELANGO | Bronze | Non S-Ox | 311 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Theorem Digital Reality server is used to convert industry standard CAD, JT data to FBX. The server also provides AR/VR/MR client applications for Manufacturing engineering around Ford. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
55026 | Omniverse | Planned | Omniverse | ISIT | SBONNICI | KRAMMOHA | IWEITZER | GRAO3 | Copper | Non S-Ox | 311 | Yes | No | - | SBONNICI | KRAMMOHA | Advanced PD and Tech | - | Nvidia Omniverse is a collaborative tool where users collaboration with design data in different applications. | 1 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
24872 | Theorem Compute Clash | In Production | TheoremCC | ISIT | JKOONS | NLAKSHMA | KRAJES33 | GRAO3 | Copper | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | This application is targeted to identify similar assemblies/parts matches, from a large data resource. COTS application is used to provide similar assemblies/parts information based on the attributes identified by COTS application. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23973 | OBD and DVM Database | In Production | OBD-DVM-DB | ISIT | JKOONS | MNOVAK1 | HLIN11 | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | This application allows PCCN global calibration teams to work with a common standard format for calibration requirements and improve management and distribution of latest calibration guides and DV test procedures. It enables users to generate DVM test procedures manually on demand and auto generated vehicle test configuration files that can achieve fully automated DBD testing using OCTAV on HIL. | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21535 | NX Mfg Tools | In Production | NXMFG | ISIT | JKOONS | MMAHIMA | VPRAHALA | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | COTS | JKOONS | NLAKSHMA | Manufacturing Engineering | Industrial System IT | COTS suite of tools providing a wide range of manufacturing capabilities including: translators, assembly modeling, model editing, visualization, verification, post processing, machine simulation and plant layout. This includes the NX Total Machining and Line Designer Modules. | 5 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
54326 | NVH Workshop Request Center | In Development | MEC-WRC | ISIT | OTHERS | JNAJORK | MKOENIG2 | JLUCAS1 | Bronze | Non S-Ox | - | Yes | No | In-House | KESTIEV1 | JNAJORK | PD Operations and Quality | Industrial System IT | Managing requests and equipment for NVH measurements | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51786 | Texturing Negotiation Tool | In Production | TNT | GDIA | OGUSIKHI | ESTACHOW | RCLAR327 | GCARLSO2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KLIDDLE | RVISWAN1 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Cost Opportunities - Purchasing Analytics - Supply Chain Analytics - GDIA Operations Analytics |  | Springboot | YES | 2 | FRANBELL | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2024-12-15 | 2024-12-15 | 2025-01-15 | Complete | Blue | 2026-03-15 | 2025-01-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | Java < v21
51786 | Texturing Negotiation Tool | In Production | TNT | GDIA | OGUSIKHI | ESTACHOW | RCLAR327 | GCARLSO2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KLIDDLE | RVISWAN1 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Cost Opportunities - Purchasing Analytics - Supply Chain Analytics - GDIA Operations Analytics |  |  | YES | 1 | FRANBELL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-14 | Complete | Blue | 2025-06-13 | 2025-02-14 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | SQL
50118 | North American Sales Analysis & Reporting System | In Production | NASales | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 322 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | North American Sales Analysis & Reporting System (NASales) is a dashboard that provides key Sales & Stock information at all organization levels, right from the business units down to the dealers for the Ford & Lincoln Brands. NorthAmericanSales provides the ability to summarize the sales data for up to 10 yrs. by sales type, vehicle type, Vehicle Line & model years for a day/month/year. Stock information is reported at VIN level with their age (Number of days in lot). Ranking the dealers, reporting sales details/seasonality/period to period analysis, providing the stock details & dealer profile are the other major highlights of this application. | 4 |  | YES | 3 | NKANDULA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
54984 | TEST DRIVE SCHEDULER | In Production | TDS | FORD PRO & FCSD TECH | TJUNIPER | AMEIKLE | CHAWKIN9 | HRUSSE26 | Gold | Non S-Ox | 311 | No | Yes | COTS | TJUNIPER | AMEIKLE | Marketing & Sales | Marketing, Sales and Service | Easy online booking system for Test Drive registration and transparency of availability (vehicles and time slots) across dealers/agents providing a consistent test drive experience. |  |  | YES | 3 | RKENNEL | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
11412 | Non-Design Price Change (NDPC II) | In Production | NDPC II | I-ERP | SARAUJO3 | KSYROCKI | LRUMPTZ | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Non-Design Price Change II (NDPC II)is a web based tool used to report production material cost savings | 8 |  | YES | 3 | TSWEEN16 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
54984 | TEST DRIVE SCHEDULER | In Production | TDS | FORD PRO & FCSD TECH | TJUNIPER | AMEIKLE | CHAWKIN9 | HRUSSE26 | Gold | Non S-Ox | 311 | No | Yes | COTS | TJUNIPER | AMEIKLE | Marketing & Sales | Marketing, Sales and Service | Easy online booking system for Test Drive registration and transparency of availability (vehicles and time slots) across dealers/agents providing a consistent test drive experience. |  |  | YES | 3 | RKENNEL | PLM | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
20501 | Teradata DBMS | Active | Teradata | EPEO | SKULKA52 | MWILLI20 | SYERASI | GARUNAC1 | Bronze | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | SQL
50559 | NMP-RFID | In Production | NMP-RFID | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | JKOONS | TBROWN99 | New Model Programs | Industrial System IT | RFID for New Models Programs. Hybrid SaaS from Lowry Solutions. | 5 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
11486 | TER: Travel & Expense Reporting Online | In Production | TER | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Bronze | S-Ox In Scope | 331 | No | Yes | In-House | DDESAI | DDESAI | Finance | Staffs IT | TER Online - Web based expense entry, reporting and reimbursement system hosted and managed by Concur Corp. |  |  | YES | 5 | TSWEEN16 | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Oracle
11486 | TER: Travel & Expense Reporting Online | In Production | TER | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Bronze | S-Ox In Scope | 331 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | TER Online - Web based expense entry, reporting and reimbursement system hosted and managed by Concur Corp. |  |  | YES | 5 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | BO component migrated to GCP, Security tools integration is pending | No | Java < v21
11486 | TER: Travel & Expense Reporting Online | In Production | TER | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Bronze | S-Ox In Scope | 331 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | TER Online - Web based expense entry, reporting and reimbursement system hosted and managed by Concur Corp. |  |  | YES | 5 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
18483 | NextGen Automated Vehicle Scheduling | In Production | NGAVS | ISIT | AMEHER1 | ADURSO | JLAKATO7 | RPRASA22 | Silver | Non S-Ox | 121 | No | Yes | COTS | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Next Generation Automated Vehicle Scheduling (NGAVS) is a global application that coordinates execution of the vehicle production schedule provided from corporate order management systems for body, paint and the final assembly of the vehicle to ensure that vehicles are built according to schedule. NGAVS provides real-time vehicle build information to operators, suppliers and automation within all areas of the plant. | 6 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green | 1900-03-30 |  | Planned |  | No | [14 empty] | No | VM
11486 | TER: Travel & Expense Reporting Online | In Production | TER | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Bronze | S-Ox In Scope | 331 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | TER Online - Web based expense entry, reporting and reimbursement system hosted and managed by Concur Corp. |  |  | YES | 5 | TSWEEN16 | PLM | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | BO component migrated to GCP, Security tools integration is pending | No | Java < v21
50057 | Technopedia | In Production | TECHNOPD | OCETO | TVASU | MWAWZYSK | SFAN21 | KTRACY8 | Silver | Non S-Ox | 211 | No | Yes | COTS | NSENTHI1 | MWAWZYSK | Enterprise Technology | Technology & Enterprise Services (TES) | Technopedia is a standardized library of IT technologies. It integrates with various systems in the ERP suite and aligns the catalogs and offerings to standard taxonomy. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | Database servers & EAMS Status decommissioned | No | SQL
13867 | Next Gen User Access Mgmt System New | In Production | NGUAMS-NEW | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | This tool creates Users Ids in TeamCenterEngineering (TCe)and assigns car programs, groups, and/or roles to those users. All requests and granted access is tracked in a database for audit purposes. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
19966 | Next Gen eFPA | In Production | eFPA | ISIT | OTHERS | AHOROVIT | CGOLDMA4 | TBIRMIN1 | Copper | Non S-Ox | 111 | Yes | No | In-House | AHOROVIT | CGOLDMA4 | Manufacturing Engineering | - | NextGen eFPA contains modules ( Clay Studio feasability,Stamping New model tooling, Stamping operations, Body in White), Reject Log and Metal finish tracking, LastHit/TCO, and Rack repair tracking. Migration to New Data Center planned for Wave 19 | 6 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19162 | Technical Field Operations Assignment Mgt Sys | In Production | TFOAMS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | TFOAMS is a user-friendly web-based and mobile-compatible system designed for creating, dispatching, and managing assignments for Field Service Engineers (FSEs).This platform empowers FSEs to efficiently handle and update assignments. |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q1 2025 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | There is a delay in the decommission of TFOAMS. They are facing some issues in rolling out capabilities in GTAC, which will be a pre requisite for TFOAMS decommission.Given the delay & the new time line would be in April, so would recommend to have the dates updates to Q2 2025. | No | Mainframe
19162 | Technical Field Operations Assignment Mgt Sys | In Production | TFOAMS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | TFOAMS is a user-friendly web-based and mobile-compatible system designed for creating, dispatching, and managing assignments for Field Service Engineers (FSEs).This platform empowers FSEs to efficiently handle and update assignments. |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
19162 | Technical Field Operations Assignment Mgt Sys | In Production | TFOAMS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Ford Customer Service | FCSD Tech |  |  | Springboot | YES | 3 | RKENNEL | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 0% | [7 empty] | Decommission | [5 empty] | No | Java < v21
51721 | Technical Assistance Center | In Production | TAC | FORD PRO & FCSD TECH | OTHERS | MKAN | MKUNES | SDHANAS2 | Copper | Non S-Ox | 111 | Yes | No | In-House | SBALZER1 | ETARQUIN | Ford Customer Service | - | Suite of Applications for Global Technical Assistance Centers (Hotlines). It includes the Cost Cap (For US and Canada markets), TACOS, EDP, and internal metrics/personnel management tools |  |  | YES | 2 | RKENNEL | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
19066 | NetBadge | In Production | NetBadge | OCETO | TSWEEN16 | BBEEKEL | JWALK257 | ESTILESK | Silver | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | MFLEURY | BBEEKEL | Policy | Staffs IT | NetBadge is a front end to the Ford access control system providing for the request and control of access control badges. NetBadge is used in conjunction with OnGuard, #22828, the application that manages access control. | 8 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
21147 | Teamcenter Visualization Mockup | In Production | TCVIS | ISIT | SBONNICI | KRAMMOHA | RHARIKR2 | GRAO3 | Bronze | Non S-Ox | 111 | No | Yes | COTS | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | View and Markup Tool for C3P NG/FEDE Data: TcVis is a collection of digital prototyping software. TcVis may be used by designers, engineers, and also such groups as marketing, FCSD and finance. TcVis provides the following features: 3D visualization, package design and analysis functions, interference and collision detection, proximity and attribute filtering, and measurement tools. TcVis is ready for production use, and has been released along with the current Ford Image |  |  | YES | 1 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23360 | Teamcenter Services | In Production | TCSVS | ISIT | JKOONS | NLAKSHMA | KSHANMU7 | GRAO3 | Copper | Non S-Ox | 311 | No | Yes | COTS | #N/A | #N/A | Enterprise Technology | 311 | TC SERVICES APPLICATION IS A DCA PLATFORM PRODUCT AND IT IS A WEB SERVICE BASED IN-HOUSE SOLUTION TO CATER THE APPLICATIONS WHICH INTERACTS WITH THE TEAMCENTER. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23315 | NAC-Pivotal Cloud Foundry | Active | PCF | EPEO | SJOHN172 | MHANTON | MAHMED7 | AGERTZ | Copper | Non S-Ox | - | No | Yes | - | SJOHN172 | MHANTON | Enterprise Technology | ITO | Pivotal Cloud Foundry is an open platform as a service, providing a choice of clouds, developer frameworks, and application services. Cloud Foundry makes it faster and easier to build, test, deploy, and scale applications. | 3 |  | YES | 3 | SWALIMBE | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
53278 | Multi-cloud Consumption Dashboard | In Production | MCCD | EPEO | SJOHN172 | SJOHN172 | GGARIMEL | GGARIMEL | Copper | S-Ox Out of Scope | 122 | No | Yes | COTS | SJOHN172 | SJOHN172 | Enterprise Technology | EPEO | External Cloud consumption tracking tool. SaaS Product that supports Cloud Billing | 2 |  | YES | 2 | SWALIMBE | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
22623 | TeamCenter Cache | In Production | TCCACHE | ISIT | JKOONS | NLAKSHMA | KRAJES33 | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS |  |  | Advanced PD and Tech | Industrial System IT | This application is to create a cache based solution to answer specific queries to Teamcenter application. A Cache (called as TC Cache) will be maintained outside of C3PNG Teamcenter and those specific queries will be answered by the TC Cache. The Cache will contain information of all Items related to Programs (such as Item Id, Owning User, LMD, Item Rev Id, CLI). Subsequent changes/updates in TeamCenter are captured at regular intervals and updated to Cache (Cache Refresh). This will improve the response time to queries and minimize the impact on Teamcenter from usage load. This will also help in monitoring the updates in TeamCenter and data growth in Teamcenter. |  | Springboot | YES | 2 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
13090 | TEAMCENTER | In Production | TC | ISIT | JKOONS | NLAKSHMA | CCHADA | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | JKOONS | JKOONS | Advanced PD and Tech | Industrial System IT | Teamcenter Engineering is the new CAD data management solution, which combined with TeamCenter Enterprise will be the new strategic solution for C3P. |  |  | YES | 4 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
13090 | TEAMCENTER | In Production | TC | ISIT | JKOONS | NLAKSHMA | CCHADA | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Teamcenter Engineering is the new CAD data management solution, which combined with TeamCenter Enterprise will be the new strategic solution for C3P. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
13090 | TEAMCENTER | In Production | TC | ISIT | JKOONS | NLAKSHMA | CCHADA | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Teamcenter Engineering is the new CAD data management solution, which combined with TeamCenter Enterprise will be the new strategic solution for C3P. |  |  | YES | 4 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23814 | MSS B2C Global Campaign Foundation (AEM Component) | In Production | GC FDTN | M&S TECH | RKLEINSM | RKLEINSM | KPONNUSW | MPINRED1 | Gold | Non S-Ox | 222 | No | Yes | COTS | RKLEINSM | BMUNIE | Enterprise Technology | Marketing, Sales and Service | AEM foundation (platform) for the Global Campaigns, Reveals and FordPass CMS . | 20 |  | YES | 1 | NKANDULA | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
16748 | TDE Web Site | In Production | TDE_WS | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | - | Official Automatic Transmission Engineering Operations (TDE) Web site |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
14569 | MSDS External Public Website | In Production | MSDS | I-ERP | OTHERS | TWESP | RSCHMI16 | MMEHTA5 | Copper | Non S-Ox | 11 | Yes | No | Managed by 3rd Party Purchased Service | TWILKS2 | TWESP | Ford Customer Service | - | MSDS External Web-site provides information on chemical aftermarket products with Ford/Motorcraft brand. The site contains legally required documentation like Material Safety Data Sheets and Ingredients Data Sheets, as well as a chemical catalog with detailed product/part information. In total 30 global countries with 23 languages are covered. The site is not access controlled and therefore disposable to the world wide web community. | 6 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
24255 | Tasktop | In Production | Tasktop | EA | RRISS | SHE1 | SLOSEY | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | Technology & Enterprise Services (TES) | Integration Tool for maintaining point to point syncing of data |  |  | YES | 2 | GBRAIL | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | SQL
54900 | MPL GSCI EU Reports | In Production | MPL_EUGSCI | ISIT | OTHERS | JSCHULE6 | MMORTSIE | MMORTSIE | Bronze | Non S-Ox | 111 | Yes | No | In-House | AKURIAN | JSCHULE6 | Manufacturing Staffs | - | The application is used to support MPL in their daily work. We create a lot of reports, metrics and calculations, mostly based on CMMS, to support departments within MP&L. | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
21033 | TARDIS Integration Layer | In Production | TARDIS | GDIA | MSPADAF5 | LDESHPAN | RROBI177 | AJOGIYAT | Silver | Non S-Ox | 311 | No | Yes | In-House | EBLOCH | LDESHPAN | Enterprise Technology | - | Consumer integration layer to allow communications between front end applications (e.g.ETIS) and back end applications (e.g. CuPID). |  |  | YES | 2 | FRANBELL | PLM | SQL | Q3 2025 | Will be Decommissioned | Decommission | 2025-08-01 | 2025-08-01 |  | In-Progress | Green | 2025-08-01 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
24476 | MFM MOBILE | In Production | MFM MOBILE | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Silver | Non S-Ox | 222 | No | Yes | COTS |  |  | Manufacturing Staffs | Industrial System IT | Provide users with mobility-based integrated framework that encompasses real-time access to failure information , on-demand, point-of-repair access to maintenance/equipment related information, wireless instantaneous communication of downtime events / meter readings / equipment status, etc | 5 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC CaaS and New EDC Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
23527 | TACCS Online | In Production | EuHR-TONL | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Copper | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Human Resources | Integrated Enterprise Resource Planning (I-ERP) | TACCS Online offers online access to some of the TACCS data for a broad user community. Users can view some of their personal TACCS (ITMS #13598)data. Phase 1: Fuel Card requests and tracking capabilities. Other data are subject to future enhancements. TACCS Online is accessed via HR Online. |  | WAS | YES | 1 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
13598 | TACCS | In Production | EuHR-TACCS | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Gold | Non S-Ox | 311 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Human Resources | Integrated Enterprise Resource Planning (I-ERP) | Taxable benefit calculation for management lease cars and car sales to employees. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q3 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
50273 | MFG Application Enablement Platform | In Production | MFG AEP | ISIT | SKING68 | CSHORTZ | MDENDRIN | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | COTS | SKING68 | CSHORTZ | Manufacturing Engineering | Industrial System IT | The AEP is a platform for ingesting data from manufacturing plant floor devices and integrating data from multiple applications, seamlessly integrating into an analytics solution. | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19238 | METRICS MANAGEMENT SYSTEM | In Production | MMS | ISIT | JKOONS | DMEENAK2 | TLEE7 | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | DMEENAK2 | Enterprise Technology | Industrial System IT | The Metrics Management System (MMS) will enable us to effectively measure and manage these critical and expensive software resources. MMS Reporting Repository enables the company to manage costs as well as assets by monitoring the software usage patterns of engineers by centrally compiling and analyzing relevant usage data. Through analysis of this data, we will be able to identify and correct areas of non-compliance, gaps in inventory versus usage - where cost savings are possible, and opportunities for enterprise license changes that would benefit the company in both the short and the long term. Of similar criticality is the need to identify where a shift in application licenses is needed. For example, some features may be under purchased (Under Purchased) today resulting in unproductive license denials, while other features have been overbought and are therefore not used effectively. | 7 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration |  |  |  |  | 01/22: Reached out to tlee7 via webex and he responded me in mail saying "MS SQL Server DB and MS Report Server (SSRS) will be migrated to EDC New Hypervisor (on-prem). Date=Q2 2026 (Tentatively) , Application Admin portal was moved to GCP Cloud run in 2024. This is the only part of the app that required migration to GCP. | No | VM
20539 | System Center Operations Manager (SCOM) for SCCM | In Production | SCOMSMS | EPEO | SRUNSON | ASTONE31 | CHOSSEIN | BNABOZNY | Bronze | Non S-Ox | 111 | Yes | No | COTS | SRUNSON | ASTONE31 | Enterprise Technology | - | System Center Operations Manager is a Microsoft tool set used for monitoring several enterprise Microsoft products. In this particular situation it is monitoring the global System Center Configuration Manager environment. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
20420 | MAXIMO FOR MAINTENANCE | In Production | MFM | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Silver | S-Ox In Scope | 222 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Staffs | Industrial System IT | Enables plant and equipment maintenance at our manufacturing facilities. Replacement for TEM 4. Based on Maximo 7.6.X | 39 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC CaaS | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
21216 | System Center Configuration Manager | In Production | SCCM 2012 | EPEO | SRUNSON | ASTONE31 | CHOSSEIN | BNABOZNY | Copper | Non S-Ox | 212 | No | Yes | COTS | SRUNSON | ASTONE31 | Enterprise Technology | EPEO | SCCM 2012 is the replacement version for System Management Server 2007 (SCCM 2007) which is the strategic direction for software delivery solutions. This applicaiton suite replaces all legacy software delivery tools globally for Windows clients and servers. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
23824 | MaterialCenter | In Production | MatCen | ISIT | JPITTERL | CBOHN | HBOYSEN | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | JPITTERL | CBOHN | Advanced PD and Tech | Industrial System IT | MSC's MaterialCenter is a Material Lifecycle Management System for materials data & process management. MaterialCenter supports CAE and Material Engineering work streams. | 11 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
901 | Sys for NonProd On-Line Order Processing | In Production | SNOOPIE | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | - | European Purchasing system for FM & SP. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
53134 | SYNECT-Global | In Production | SYNECT | EVDD | FFRISCHM | PREDLICH | BFRIELIN | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | COTS | FFRISCHM | PREDLICH | Advanced PD and Tech | Industrial System IT | Synect is a tool that visualizes the efficiency of HIL (Hardware in the loop) test equipment. It also provides mechanisms to offload (costly) facility time operations to (cheaper) engineer's PCs. It also manages complexity aspects like configurations for HIL tests. |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
18469 | Mass Autosave | In Production | MDT | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Engineering | - | The AutoSave programmable device support software is a change management and storage system for the plants automation device programs. It features full documentation support, program history, access control, and full integration with programming application software packages for Schneider PL7/Unity, Indramat MTC200 and other controllers presently running in the plants. | 16 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
11417 | Synch. Material Replenishment Trigger (SMART) | In Production | SMART | ISIT | AMEHER1 | ADURSO | MBIJI | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | GHERMAN | Manufacturing Staffs | Industrial System IT | The SMART system is a line side material delivery system that reduces 4 wall and line side inventory in support of FPS Synch. Material Flow and empower Production Operators to determine when material is needed at line side. Three Process, SMART Card is used globally and store inventory usage by scanning kan-ban cards each cycle; SMART Call, used globally, mechanises the request process, allowing a lineside button press to trigger material replenishment which in turn stores inventory usage; SMART AutoCall, used globally, based on approx. inventory levels at lineside and BoM requirements for each vehicle, triggers SMART Call-style material replenish., again storing usage for analysis. For all three types of SMART, a part can be classified as an eSMART part for these parts, each delivery instance is sent electronically to suppliers via the eSMART. The application does not include primary supplier call-in, and does not deal with financials or purchasing of inventory, or the reporting of inventory levels |  |  | YES | 4 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
11417 | Synch. Material Replenishment Trigger (SMART) | In Production | SMART | ISIT | AMEHER1 | ADURSO | MBIJI | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | The SMART system is a line side material delivery system that reduces 4 wall and line side inventory in support of FPS Synch. Material Flow and empower Production Operators to determine when material is needed at line side. Three Process, SMART Card is used globally and store inventory usage by scanning kan-ban cards each cycle; SMART Call, used globally, mechanises the request process, allowing a lineside button press to trigger material replenishment which in turn stores inventory usage; SMART AutoCall, used globally, based on approx. inventory levels at lineside and BoM requirements for each vehicle, triggers SMART Call-style material replenish., again storing usage for analysis. For all three types of SMART, a part can be classified as an eSMART part for these parts, each delivery instance is sent electronically to suppliers via the eSMART. The application does not include primary supplier call-in, and does not deal with financials or purchasing of inventory, or the reporting of inventory levels |  |  | YES | 4 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11417 | Synch. Material Replenishment Trigger (SMART) | In Production | SMART | ISIT | AMEHER1 | ADURSO | MBIJI | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | The SMART system is a line side material delivery system that reduces 4 wall and line side inventory in support of FPS Synch. Material Flow and empower Production Operators to determine when material is needed at line side. Three Process, SMART Card is used globally and store inventory usage by scanning kan-ban cards each cycle; SMART Call, used globally, mechanises the request process, allowing a lineside button press to trigger material replenishment which in turn stores inventory usage; SMART AutoCall, used globally, based on approx. inventory levels at lineside and BoM requirements for each vehicle, triggers SMART Call-style material replenish., again storing usage for analysis. For all three types of SMART, a part can be classified as an eSMART part for these parts, each delivery instance is sent electronically to suppliers via the eSMART. The application does not include primary supplier call-in, and does not deal with financials or purchasing of inventory, or the reporting of inventory levels |  |  | YES | 4 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
53858 | Manufacturing Inventory Management System | In Production | MIMS | ISIT | SKING68 | KBARTHO1 | JBARGER | RPRASA22 | Bronze | Non S-Ox | 311 | No | Yes | COTS | SKING68 | KBARTHO1 | Manufacturing Engineering | Industrial System IT | Manufacturing Inventory Management System (MIMS) tracks Manufacturing IT and Industrial Controls Systems using a BMC Helix Infrastructure. | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
20693 | Symantec Anti-Malware (SEP) | Planned | AntiMalwar | EPEO | NOKEEFE | VNACHIMU | PFREILE | WJUSTICE | Silver | Non S-Ox | 211 | No | Yes | - | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | Corporate Anti-Malware (Virus and Spyware Protection) Solution - Symantec. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
23820 | MagicDraw Teamwork Server | In Production | MDRAWTWORK | ISIT | MNOWICK1 | PBORGAO1 | JYANDOO1 | GRAO3 | Copper | Non S-Ox | 311 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | Teamwork Cloud is a collaboration server that houses SysML models created using the MagicDraw client (COTS products). MD is used to engineer features and define architecture for platform systems at multiple, traceable abstraction levels through models. System design tasks in MD/TWC include definition of use cases, detailed system requirements, interface definition that turns into FIDL and APIs, FMEA and Functional safety. System design then feeds software development | 15 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
51038 | M/ECAD | In Production | M/ECAD | ISIT | MNOWICK1 | PBORGAO1 | IAKLEH | GRAO3 | Bronze | Non S-Ox | - | Yes | No | In-House | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | - | M/ECAD is a comprehensive project that is focused on looking for the most optimal way to address the current and future business changes for the EDS Core department; this solution was designed to support the most recent engineering platforms CAD The Master and the upcoming FSS. Project: M/ECAD includes a series of functional components such as 3D PMI, DTSync, MCI 2.0, FFA2, EDS Checklist, WGO and a series of ECAD Inputs. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
11034 | Suspension Orders | In Production | SORP | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DDESAI | DDESAI | Policy | Staffs IT | Suspension Orders: increases the effectiveness of Suspension Orders by providing an on-line application that allows for authoring, searching, viewing and reporting of Suspension Orders for all those who work at Ford globally. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | APP and DB component migrated to GCP, Security tools integration is pending | No | Oracle
53191 | Lutron - Quantum + Hyperion | In Production | Lutron | OCETO | TSWEEN16 | JBLOUIN1 | CTHOM368 | ESTILESK | Copper | Non S-Ox | 11 | Yes | No | COTS | JDOBLESK | JBLOUIN1 | Ford Land | - | Hyperion is a part of the Quantum Software application. This software takes into account the weather and sensor information to reduce glare and automatically adjust the window shades accordingly. | 2 |  | YES | 1 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
51932 | Surface Data Management System | In Production | SDMS | EVDD | IMCLAUGH | CWETZEL | MSHELP | GRAO3 | Silver | Non S-Ox | 322 | Yes | No | In-House | IMCLAUGH | CWETZEL | Advanced PD and Tech | Industrial System IT | Manages Surface change control (eSCR) during product development phase |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
13782 | LPG Internal Web Site | In Production | EuPV-LPGW | ISIT | OTHERS | GVANNOYE | GTACKOEN | JLUCAS1 | Silver | Non S-Ox | 211 | Yes | No | In-House | RTILLEY | GVANNOYE | PD Operations and Quality | Industrial System IT | Intranet Web site hosting information about Lommel Proving Ground. The site consists of static (HTML) and dynamic (ASP,ASPX) content. | 5 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
51932 | Surface Data Management System | In Production | SDMS | EVDD | IMCLAUGH | CWETZEL | MSHELP | GRAO3 | Silver | Non S-Ox | 322 | Yes | No | In-House |  |  | Advanced PD and Tech | Industrial System IT | Manages Surface change control (eSCR) during product development phase |  | Springboot | YES | 3 | MJONE308 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
910 | Supply On-Line Management Information System | In Production | SOLMIS | OCETO | TVASU | KBALAS13 | CBHARGAV | KTRACY8 | Gold | Non S-Ox | 233 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | Mainframe application responsible for Electronic Data Interchange (EDI) data from ALL Ford plants (vis CMMS) to the GEC Hub (a 2nd N.A. EDI system) where all Trading Partners (suppliers, transporation carriers, Health Care Providers, customers, etc.). SOLMIS is the connection point for most internal applications doing EDI with external trading partners and exists concert with the GEC Hub environment. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
12781 | SUPPLIER WARRANTY REPORTING | In Production | SWR | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | A tool that collects data from various systems throughout the enterprise, calculates warranty metrics by supplier, and communicates the metric to both suppliers & internal stakeholders in the SIM application. |  | Java Struts | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-01-15 | 2025-01-15 | Complete | Blue | 2025-01-15 | 2025-01-15 | Complete |  | No | [8 empty] | Decommission | Praveen | 2025-03-05 |  |  |  | No | Java < v21
12781 | SUPPLIER WARRANTY REPORTING | In Production | SWR | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | SARAUJO3 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | A tool that collects data from various systems throughout the enterprise, calculates warranty metrics by supplier, and communicates the metric to both suppliers & internal stakeholders in the SIM application. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-01-15 | 2025-01-15 | Complete | Blue | 2025-01-30 | 2025-01-30 | Complete |  | No | [8 empty] | Decommission | Praveen | 2025-03-05 |  |  |  | No | Oracle
20328 | Supplier Performance Rating - Global | In Production | SUPER-G | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Bronze | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | This system creates a delivery rating for all suppliers shipping into plants and FCSD sites globally. It provides this info to the Supplier Improvement Metrics (SIM) system for display to suppliers, internal review, and calculation of supplier Q1 score. SuPeR G is in development 2009-2012, planned to replace SDPR for MP&L & FCSD, SPEEDY, and S.A. SCM delivery rating functionality. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
20328 | Supplier Performance Rating - Global | In Production | SUPER-G | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Bronze | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | This system creates a delivery rating for all suppliers shipping into plants and FCSD sites globally. It provides this info to the Supplier Improvement Metrics (SIM) system for display to suppliers, internal review, and calculation of supplier Q1 score. SuPeR G is in development 2009-2012, planned to replace SDPR for MP&L & FCSD, SPEEDY, and S.A. SCM delivery rating functionality. |  |  | YES | 4 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23265 | LPG Electronic Workflow | In Production | eDocs | ISIT | OTHERS | GTACKOEN | FBOMANS | JLUCAS1 | Silver | Non S-Ox | 111 | Yes | No | In-House | GVANNOYE | GTACKOEN | PD Operations and Quality | Industrial System IT | Web- and SQL server infrastructure to host a Web based workflow system to process PD forms. | 9 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20328 | Supplier Performance Rating - Global | In Production | SUPER-G | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Bronze | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | This system creates a delivery rating for all suppliers shipping into plants and FCSD sites globally. It provides this info to the Supplier Improvement Metrics (SIM) system for display to suppliers, internal review, and calculation of supplier Q1 score. SuPeR G is in development 2009-2012, planned to replace SDPR for MP&L & FCSD, SPEEDY, and S.A. SCM delivery rating functionality. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23142 | LPG BUSINESS ADMINISTRATION WEB | In Production | LPGBAW | ISIT | OTHERS | GTACKOEN | FBOMANS | JLUCAS1 | Silver | Non S-Ox | 211 | Yes | No | In-House | GVANNOYE | GTACKOEN | PD Operations and Quality | Industrial System IT | To improve the efficiency of the business administration and the transparency of the LPG operation, all data should only be entered once into a central database using standardized forms and reports. . Through a global portal, specific users will be allowed to retrieve specific data in line with the company guidelines. The system should include the possibility to collect the same data from agency and hired persons that are under Ford supervision. | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52868 | Supplier Part Data Quality System | In Production | SPDQS | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House |  |  | Quality | Industrial System IT | SPDQS is Web application that provides Quality engineers with functionalities to manage/ visualize the different Supplier data feed formats, PD nominal data availability/ status and SPC Quality reports . |  | Springboot | YES | 2 | BWUNNAVA | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
20565 | Supplier Improvement Metrics | In Production | SIM | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | This is the Next Generation Supplier Improvement Metrics application replacing the current Supplier Improvement Metrics system. SIM NG will serve as the data infrastructure for Ford's common, globally integrated supplier quality management processes that ecompass sourcing, launch, and on-going production. Taking input from SUPER G, CMMS, and other systems to calculate key Supplier metrics such as PPM and Q1 Rating. In development 2008 - 2012, SIM Next Gen is planned to replace the existing Supplier Improvement Metrics application. NOTE: as of Nov 11, 2013 this version of SIM will become Q1 scoring System of Record | 1446 |  | YES | 6 | TSWEEN16 | PLM | Datastage | Q2 2025 |  | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 75% | 100% | 75% | 100% |  | QlikSense | Praveen | 2025-03-21 |  |  |  | No | DA
20565 | Supplier Improvement Metrics | In Production | SIM | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | This is the Next Generation Supplier Improvement Metrics application replacing the current Supplier Improvement Metrics system. SIM NG will serve as the data infrastructure for Ford's common, globally integrated supplier quality management processes that ecompass sourcing, launch, and on-going production. Taking input from SUPER G, CMMS, and other systems to calculate key Supplier metrics such as PPM and Q1 Rating. In development 2008 - 2012, SIM Next Gen is planned to replace the existing Supplier Improvement Metrics application. NOTE: as of Nov 11, 2013 this version of SIM will become Q1 scoring System of Record | 170 |  | YES | 6 | TSWEEN16 | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
20565 | Supplier Improvement Metrics | In Production | SIM | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | This is the Next Generation Supplier Improvement Metrics application replacing the current Supplier Improvement Metrics system. SIM NG will serve as the data infrastructure for Ford's common, globally integrated supplier quality management processes that ecompass sourcing, launch, and on-going production. Taking input from SUPER G, CMMS, and other systems to calculate key Supplier metrics such as PPM and Q1 Rating. In development 2008 - 2012, SIM Next Gen is planned to replace the existing Supplier Improvement Metrics application. NOTE: as of Nov 11, 2013 this version of SIM will become Q1 scoring System of Record |  |  | YES | 6 | TSWEEN16 | PLM | Java Struts | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-31 |  | In-Progress | Green | 2025-04-15 |  | Planned |  | No | 100% | 100% | 75% | 75% | 100% | 75% | 100% |  | Cloud Run | Praveen | 2025-03-05 |  |  |  | No | Java < v21
20565 | Supplier Improvement Metrics | In Production | SIM | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | This is the Next Generation Supplier Improvement Metrics application replacing the current Supplier Improvement Metrics system. SIM NG will serve as the data infrastructure for Ford's common, globally integrated supplier quality management processes that ecompass sourcing, launch, and on-going production. Taking input from SUPER G, CMMS, and other systems to calculate key Supplier metrics such as PPM and Q1 Rating. In development 2008 - 2012, SIM Next Gen is planned to replace the existing Supplier Improvement Metrics application. NOTE: as of Nov 11, 2013 this version of SIM will become Q1 scoring System of Record |  |  | YES | 6 | TSWEEN16 | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 75% | 100% | 75% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
50145 | Loan Origination Services | In Production | LOS | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | Non S-Ox | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | This application hosts all the micro services related to Pinnacle Loan Origination. Services are either called from Pinnacle Loan Origination or they expose data from Pinnacle Loan Origination tables. | 3 |  | YES | 4 | SRAISIN1 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
20565 | Supplier Improvement Metrics | In Production | SIM | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | This is the Next Generation Supplier Improvement Metrics application replacing the current Supplier Improvement Metrics system. SIM NG will serve as the data infrastructure for Ford's common, globally integrated supplier quality management processes that ecompass sourcing, launch, and on-going production. Taking input from SUPER G, CMMS, and other systems to calculate key Supplier metrics such as PPM and Q1 Rating. In development 2008 - 2012, SIM Next Gen is planned to replace the existing Supplier Improvement Metrics application. NOTE: as of Nov 11, 2013 this version of SIM will become Q1 scoring System of Record |  |  | YES | 6 | TSWEEN16 | PLM | WAS | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-31 |  | In-Progress | Green | 2025-04-15 |  | Planned |  | No | 100% | 100% | 75% | 75% | 100% | 75% | 100% |  | GCP Migration | Praveen | 2025-03-05 |  |  |  | No
12442 | Supplier Directory | In Production | SD | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Copper | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Manufacturing Staffs | Marketing, Sales and Service | The Supplier Directory (SD) is the central repository for Supplier contact information: specfically the Supplier Account Manager and Capacity Planner. Presently, the SD primarly supports the capacity planning applciations, MCPV and CPV2. SD also sends emails to suppliers as requested by the MCPV and CPV2 applications. The SD shares the same databases as the CMMS contact screen: FBBA. |  |  | YES | 1 | NKANDULA | PLM | Java Struts | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
12002 | Supplier Direct Ship | In Production | SDS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | Supplier Direct Ship System allows the submission and tracking of orders for parts that are not stocked in the PS&L depot network. These parts are built by suppliers as needed and shipped directly to the ordering dealer. | 3 |  | YES | 2 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
12002 | Supplier Direct Ship | In Production | SDS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | Supplier Direct Ship System allows the submission and tracking of orders for parts that are not stocked in the PS&L depot network. These parts are built by suppliers as needed and shipped directly to the ordering dealer. |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12002 | Supplier Direct Ship | In Production | SDS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | S-Ox In Scope | 232 | No | Yes | In-House |  |  | Ford Customer Service | FCSD Tech | Supplier Direct Ship System allows the submission and tracking of orders for parts that are not stocked in the PS&L depot network. These parts are built by suppliers as needed and shipped directly to the ordering dealer. |  | Springboot | YES | 3 | RKENNEL | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13729 | LIMS: Laboratory Information Management System | In Production | EuVP_LIMS | ISIT | JKOONS | CBOHN | MZIRWES1 | JLUCAS1 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | This LIMS is a full-featured Client Server Laboratory Information Management System that is integrated into Windows environment for the European Materials Laboratory developed by LABWARE Association. The system manages all projects e.g. workload test protocol and results cost controlling reporting. The system is concepted to be variable to the various business requirements. | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
20627 | Supplier APQP Assessment System | In Production | eAPQP | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 321 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Automated Supplier APQP Assessment System is a key enabler for integration of suppliers into GPDS and the company global platform strategies. Suppliers all over the world will be producing common parts for common vehicle architectures. Supplier status information must be communicated and analyzed by different parties in different regions at the same time. Progra m decisionmaking will require accurate information from suppliers in an efficient and timely manner. It also supports one of the key components of the Global Product Development System (GPDS), which is the Supplier Engagement Process. The Supplier Engagement Process defines the disciplined set of work activities from the point of sourcing to Job1. This work activity ensures ontime part readiness at the desired quality levels. | 304 |  | YES | 5 | TSWEEN16 | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
20627 | Supplier APQP Assessment System | In Production | eAPQP | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 321 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Automated Supplier APQP Assessment System is a key enabler for integration of suppliers into GPDS and the company global platform strategies. Suppliers all over the world will be producing common parts for common vehicle architectures. Supplier status information must be communicated and analyzed by different parties in different regions at the same time. Progra m decisionmaking will require accurate information from suppliers in an efficient and timely manner. It also supports one of the key components of the Global Product Development System (GPDS), which is the Supplier Engagement Process. The Supplier Engagement Process defines the disciplined set of work activities from the point of sourcing to Job1. This work activity ensures ontime part readiness at the desired quality levels. |  |  | YES | 5 | TSWEEN16 | PLM | Java Struts | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-14 | Complete | Blue | 2025-03-15 | 2025-02-14 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Praveen | 2025-03-04 |  |  |  | No | Java < v21
20627 | Supplier APQP Assessment System | In Production | eAPQP | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 321 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Automated Supplier APQP Assessment System is a key enabler for integration of suppliers into GPDS and the company global platform strategies. Suppliers all over the world will be producing common parts for common vehicle architectures. Supplier status information must be communicated and analyzed by different parties in different regions at the same time. Progra m decisionmaking will require accurate information from suppliers in an efficient and timely manner. It also supports one of the key components of the Global Product Development System (GPDS), which is the Supplier Engagement Process. The Supplier Engagement Process defines the disciplined set of work activities from the point of sourcing to Job1. This work activity ensures ontime part readiness at the desired quality levels. |  |  | YES | 5 | TSWEEN16 | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-04-15 |  | In-Progress | Green | 2025-07-14 |  | Planned |  | No | 100% | 100% | 75% | 50% | 50% |  | 75% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-06 |  |  |  | No | SQL
25080 | Lead Access Platform (LEAP) | In Production | LEAP | FORD PRO & FCSD TECH | TJUNIPER | GRIST | SRAVI6 | AJOGIYAT | Silver | Non S-Ox | 321 | No | Yes | COTS | TJUNIPER | GRIST | Marketing & Sales | Marketing, Sales and Service | Track Leads from point of initiation to fulfilment including activities by dealers agnostic of DMS | 2 |  | YES | 1 | RKENNEL | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
20627 | Supplier APQP Assessment System | In Production | eAPQP | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 321 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Automated Supplier APQP Assessment System is a key enabler for integration of suppliers into GPDS and the company global platform strategies. Suppliers all over the world will be producing common parts for common vehicle architectures. Supplier status information must be communicated and analyzed by different parties in different regions at the same time. Progra m decisionmaking will require accurate information from suppliers in an efficient and timely manner. It also supports one of the key components of the Global Product Development System (GPDS), which is the Supplier Engagement Process. The Supplier Engagement Process defines the disciplined set of work activities from the point of sourcing to Job1. This work activity ensures ontime part readiness at the desired quality levels. |  |  | YES | 5 | TSWEEN16 | PLM | WAS | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-14 | Complete | Blue | 2025-06-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Praveen | 2025-03-04 |  |  | App migration completed on 14 Feb, yet to decommission | No | Java < v21
399 | Supercube | In Production | EuMP-SCUBE | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Gold | Non S-Ox | 111 | No | Yes | - | SROYCHOU | RADAM10 | Manufacturing Plants | Industrial System IT | SuperCube monitors the movements of SuperCube trailers, carrying Inter-Company shipments of production material between British and Continental European plants. It operates on trailer level and provides details of vessel journeys and intermediate location movements. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q4 2025 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
23730 | Subscription Services Platform | In Production | SSP | M&S TECH | RAHMED33 | MRICHA62 | AWILHOI1 | SNETHAJI | Gold | Non S-Ox | 221 | No | Yes | In-House | #N/A | #N/A | Integrated Services | 221 | SUBSCRIPTIONS SERVICES PLATFORM IS AN INTEGRATED SET OF SUBSCRIPTION AND PAYMENT CAPABILITIES. IT PROVIDES COMMON TECHNOLOGY PATTERNS ACROSS CHANNELS TO ENABLE GLOBAL EXPERIENCES AND INCREASE CUSTOMER ENGAGEMENT, LOYALTY AND REVENUE. |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | Q2 2025 | Version Upgrade | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | Java 17 |  |  |  |  | Some APIs have already been upgraded to 3.x.x. Remaining APIs are targeting Q2 2025 | No | Java < v21
50696 | Knock Down LOT Set Order Management System | In Production | KDLOTSOM | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Knock Down LOT Set Order Management System (KDLOTSOM) manages KD Lot-Set Kit orders for both confirmed and forecast period. KD Kits can be ordered in user defined quantities (Lots) to support KD Kit assembly at a non-CMMS enabled 3rd party destination (Partner). This application enables KD Lot-Set program planning, KD Lot-Set order management and KD Lot-Set order tracking. It interacts with PDO upstream system to get the buildability at WERS level and CMMS downstream by providing KD order details at WERS level to drive supplier material release. Other Key functionalities: 1. Orders are driven based on SPCPS Sales allocations & CMMS OP Plan. 2. Triggers Dealer order creation in GOALS 3. Facilitates Physical VIN generation using PVG & communicates to Partner, MVP, NGAVS, GEVIS. 4. Communicates order details to NGAVS to drive PFS related functionalities at partner end. 5. Receives Vehicle Assembly Order Status from Partner systems & communicates to GEVIS. 6. Order Status Tracking from Forecast to Wholesale. | 2 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20223 | Structured Assumption Language Template - Gen 2 | In Production | SALTGen 2 | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | SALT (Structured Assumptions Language Tempalte) provides a consistent, structured format to capture and communicate product assumptions across the enterprise. Provide a global, cross-program assumptions management process. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission | 2024-12-15 | 2025-01-15 | 2025-01-06 | Complete | Blue | 2025-01-15 | 2025-01-06 | Complete |  | No | [8 empty] | Decommission | Priya | 2025-03-16 |  |  | App fully Decommissioned | No | SQL
12855 | Just-in-time Execution and Delivery Initiative | In Production | JEDI | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Silver | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | The JEDI application is a decision support tool used by Stamping plants to efficiently schedule the parts being produced at the plant. | 13 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | Priya | 2025-03-05 |  |  |  | No | VM
20223 | Structured Assumption Language Template - Gen 2 | In Production | SALTGen 2 | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | SALT (Structured Assumptions Language Tempalte) provides a consistent, structured format to capture and communicate product assumptions across the enterprise. Provide a global, cross-program assumptions management process. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission | 2024-12-15 | 2025-01-15 | 2025-01-06 | Complete | Blue | 2025-01-15 | 2025-01-06 | Complete |  | No | [8 empty] | Decommission | Priya | 2025-03-16 |  |  | App fully Decommissioned | No | Java < v21
53223 | Stripe Customer Mapping Service | In Production | SCMS | FORD CREDIT | DTAURO | MVENKA15 | CDWYER6 | ROBRIEN3 | Gold | Non S-Ox | 323 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 323 | THE APPLICATION PROVIDES AN ABSTRACTION LAYER FOR PAYMENTS. APPLICATION PROVIDES A UI COMPONENT TO INCLUDE IN FORD PAYMENT WORK FLOWS AND ALSO PROVIDES BACKEND SERVICES. SOLUTION ABSTRACTS PAYMENT PROVIDER INTEGRATION. PROVICES GLOBAL SOLUTION WITH LOCATIONIZATION. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q3 2027 | Version Upgrade | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
23489 | JIRA | In Production | JIRA | EVDD | AGARBY | NWEBST14 | NWHITEH8 | SGURU8 | Bronze | Non S-Ox | 321 | Yes | No | Managed by 3rd Party Purchased Service | AGARBY | NWEBST14 | Advanced PD and Tech | - | JIRA is a defect tracking tool used as part of an agile s/w development environment within the R&A EESE organization. | 9 |  | YES | 2 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
50835 | IVI-C Watchdog | In Production | IVIC-WD | EVDD | JREYN149 | NFAGEN | MGORDO64 | ECHURCHM | Bronze | Non S-Ox | 111 | Yes | No | - | JREYN149 | NFAGEN | Advanced PD and Tech | - | Metrics, Software Release Reports and Quality Scorecard along with other web based tools used by IVI-C to manage software development | 6 |  | YES | 2 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
53666 | STORAGE DATA PROTECTION SERVICE | Active | DPAAS | EPEO | LFULCHER | RMANNING | ACHALME4 | RCLAFFEY | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | RMANNING | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 3 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
51784 | Issuetrak - APTL | In Production | IAPTL | ISIT | KCHRIST2 | KCHRIST2 | JCICOTTE | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | Issuetrak COTS solution for test issue managment | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
53666 | STORAGE DATA PROTECTION SERVICE | Active | DPAAS | EPEO | LFULCHER | RMANNING | ACHALME4 | RCLAFFEY | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | RMANNING | #N/A | ITO | #N/A |  |  | YES | 3 | SWALIMBE | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
22077 | iqs Gauge Calibration Management | In Production | iqs GCM | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | SKING68 | DCLEME13 | Quality | Industrial System IT | iqs-GCM (Gauge Calibration Management), is the Globally approved software module that is used to schedule and manage gauge certifications. The iqs-GCM solution provides quality management personnel with valid, actionable process data, and reporting. Without reliable device management protocols, manufacturers may increase the risk of unknowingly producing nonconforming items, which can delay time-to-market objectives. In the worst-case scenario, invalid process data resulting from inaccurate equipment gages can lead to defective products reaching the open market. A commercial description can be found at: http://www.iqs.de/en-Inspection-equipment-Management.html | 7 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
16088 | Stock Administration Web Site | In Production | SAWS | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Bronze | S-Ox Out of Scope | 331 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | The Incentive Compensation Office (ICO) utilizes SAWS to maintain the history of annual grants and special grants. The application is also used to administer new grants. Participant information and Grants information is transmitted to Morgan Stanley (MS) who administers the exercise, by participants, of the options granted, and who ultimately becomes the master source for all stock award information. |  |  | YES | 5 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
16088 | Stock Administration Web Site | In Production | SAWS | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Bronze | S-Ox Out of Scope | 331 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | The Incentive Compensation Office (ICO) utilizes SAWS to maintain the history of annual grants and special grants. The application is also used to administer new grants. Participant information and Grants information is transmitted to Morgan Stanley (MS) who administers the exercise, by participants, of the options granted, and who ultimately becomes the master source for all stock award information. |  |  | YES | 5 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
16088 | Stock Administration Web Site | In Production | SAWS | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Bronze | S-Ox Out of Scope | 331 | No | Yes | In-House | DDESAI | DDESAI | Human Resources | Staffs IT | The Incentive Compensation Office (ICO) utilizes SAWS to maintain the history of annual grants and special grants. The application is also used to administer new grants. Participant information and Grants information is transmitted to Morgan Stanley (MS) who administers the exercise, by participants, of the options granted, and who ultimately becomes the master source for all stock award information. |  |  | YES | 5 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
51806 | Interactive Platform for Data Analytics | In Development | IPDA | ISIT | JKOONS | MNOVAK1 | HBOYSEN | GRAO3 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JPITTERL | CBOHN | Advanced PD and Tech | Industrial System IT | A platform to merge Ford internal CAE and physical crash test data in a single database. The database also includes external, publicly available test crash data (i.e. NHTSA, IIHS). The system applies data analytics methods on the different data sources to identify success factors. An interactive frontend platform allows data analysis and supports virtual/physical data correlation. | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
16088 | Stock Administration Web Site | In Production | SAWS | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Bronze | S-Ox Out of Scope | 331 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | The Incentive Compensation Office (ICO) utilizes SAWS to maintain the history of annual grants and special grants. The application is also used to administer new grants. Participant information and Grants information is transmitted to Morgan Stanley (MS) who administers the exercise, by participants, of the options granted, and who ultimately becomes the master source for all stock award information. |  |  | YES | 5 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
21632 | SteelHead | In Production | SteelHead | FORD PRO & FCSD TECH | OTHERS | LCAMAJ | MMELVIL2 | ABOBBALA | Copper | Non S-Ox | 311 | Yes | No | In-House | KDORONY | LCAMAJ | Ford Customer Service | - | Steelhead is a project management application for SEO Upstream Program Managers to track new vehicle program launch milestones and deliverables across the company. |  |  | YES | 2 | RKENNEL | PLM | SQL | Q4 2026 | On-Prem | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
20419 | INTEGRATED SOURCING MANUFACTURING & DESIGN | In Production | ISMD | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Production Implementation of Big Bang Project from Research & Advanced Engineering. Define, develop, and implement upfront design tools that integrate product attribute, sourcing, and manufacturing considerations to achieve weight & cost savings. Modules Include: GMUD, MATREC, TECHSELECT, DAWN & CET-FTI Batch Process Integrator | 8 |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
16204 | STARS2 Reporting Module (WebFocus) | In Production | STARS RPTS | FORD PRO & FCSD TECH | OTHERS | LCAMAJ | PALLENRI | JHARPER2 | Bronze | Non S-Ox | 211 | Yes | No | In-House | KDORONY | LCAMAJ | Ford Customer Service | - | STARS Reporting | 1395 |  | YES | 4 | RKENNEL | PLM | WebFocus - MF | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-30 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | 25% | 0% | 0% | 0% | 0% | 0% | 0% |  | Webfocus 9 |  |  |  |  | EXCEPTION BASED. Approval from Product Owner, Tom Culler, received to remain on platform until Infra decom. Contract renewals underway. | No | DA
16204 | STARS2 Reporting Module (WebFocus) | In Production | STARS RPTS | FORD PRO & FCSD TECH | OTHERS | LCAMAJ | PALLENRI | JHARPER2 | Bronze | Non S-Ox | 211 | Yes | No | In-House | KDORONY | LCAMAJ | Ford Customer Service | - | STARS Reporting | 1395 |  | YES | 4 | RKENNEL | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
16204 | STARS2 Reporting Module (WebFocus) | In Production | STARS RPTS | FORD PRO & FCSD TECH | OTHERS | LCAMAJ | PALLENRI | JHARPER2 | Bronze | Non S-Ox | 211 | Yes | No | In-House | KDORONY | LCAMAJ | Ford Customer Service | - | STARS Reporting |  |  | YES | 4 | RKENNEL | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
16204 | STARS2 Reporting Module (WebFocus) | In Production | STARS RPTS | FORD PRO & FCSD TECH | OTHERS | LCAMAJ | PALLENRI | JHARPER2 | Bronze | Non S-Ox | 211 | Yes | No | In-House | KDORONY | LCAMAJ | Ford Customer Service | - | STARS Reporting |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
106 | STARS: Standardized Training and Resource System | In Production | STARS106 | M&S TECH | NKANDULA | JLEWIS10 | PCHERUK2 | JHARPER2 | Silver | Non S-Ox | 321 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | STARS is a Learning Management System used by dealer personnel globally. Learners can register for classes, look up their training history, and view their certification planner that informs them of their training gap based on their declared job specialty. STARS helps deliver on the divisional goals of fix it right the first time. |  |  | YES | 4 | NKANDULA | PLM | Java Struts | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-02-02 | 2025-02-02 | Complete | Blue | 2025-02-28 | 2025-02-28 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | PDO just launched our modernized STARS app last week. We will start the activities to decommission legacy STARS Struts application end of this month and will complete decommission by mid-March, 2025. This is PCF Decom and PDO still use APP ID 106. | No | Java < v21
106 | STARS: Standardized Training and Resource System | In Production | STARS106 | M&S TECH | NKANDULA | JLEWIS10 | PCHERUK2 | JHARPER2 | Silver | Non S-Ox | 321 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | STARS is a Learning Management System used by dealer personnel globally. Learners can register for classes, look up their training history, and view their certification planner that informs them of their training gap based on their declared job specialty. STARS helps deliver on the divisional goals of fix it right the first time. |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q4 2027 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
106 | STARS: Standardized Training and Resource System | In Production | STARS106 | M&S TECH | NKANDULA | JLEWIS10 | PCHERUK2 | JHARPER2 | Silver | Non S-Ox | 321 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | STARS is a Learning Management System used by dealer personnel globally. Learners can register for classes, look up their training history, and view their certification planner that informs them of their training gap based on their declared job specialty. STARS helps deliver on the divisional goals of fix it right the first time. |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
106 | STARS: Standardized Training and Resource System | In Production | STARS106 | M&S TECH | NKANDULA | JLEWIS10 | PCHERUK2 | JHARPER2 | Silver | Non S-Ox | 321 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | STARS is a Learning Management System used by dealer personnel globally. Learners can register for classes, look up their training history, and view their certification planner that informs them of their training gap based on their declared job specialty. STARS helps deliver on the divisional goals of fix it right the first time. |  |  | YES | 4 | NKANDULA | PLM | WAS | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-02-02 | 2025-02-02 | Complete | Blue | 2025-02-28 | 2025-02-28 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | PDO just launched our modernized STARS app last week. We will start the activities to decommission legacy STARS Struts application end of this month and will complete decommission by mid-March, 2025. This is PCF Decom and PDO still use APP ID 106. | No | Java < v21
21366 | STARS - PTT Automation System | In Production | EuPD-STARS | ISIT | JPITTERL | STHOM124 | AVARADI1 | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | COTS | JPITTERL | STHOM124 | PD Operations and Quality | - | STARS as a real time system is imbedded in the key testing facilities of Powertrain Testing (PTT). It verifies new engine designs, conduct engine and transmission durability tests, establish engine performance, and develop engine, transmission and power train calibrations. It is a purchased system (COTS). |  |  | YES | 1 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
15664 | Standard Equipment Retail Label | In Production | SERL | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Copper | Non S-Ox | 111 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | SERL is a web-based application that facilitates the input, review, approval, and implementation of window label standard equipment. SERL can be access directly: www.serl.ford.com or through the Market Offering Change Management (MOCM) web site: http://www.workflow.ford.com/metro. When accessing SERL directly, anyone with a valid Ford single web logon ID can view standard equipment. Access to edit standard equipment is available in MOCM to ensure that only the VLMMs have update capability. MOCM compares the valid VLMM CDS ID with the valid vehicle lines and passes the authorization to SERL. The Data Dictionary section within SERL houses standard equipment descriptions by Sales Division. The Data Dictionary assists with providing accurate and consistent descriptions across vehicle lines within each Sales Division. SERL uses the MOCM security table to identify valid VLMM CDS IDs and authorize changes and additions. The VLMM accesses the Data Dictionary directly from the SERL home page (www.serl.ford.com). |  |  | YES | 1 | NKANDULA | PLM | WAS | Q2 2027 | Rewrite | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
188 | Standard Cost | In Production | stancost | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 232 | No | Yes | In-House | DNANDAN | DWIERZBI | Finance | FCSD Tech | The purpose of this read-only system is to distribute standard cost for all FCSD parts sold, manufactured and packaged in NA. The system also provides standard cost data to other systems including financial inventory tracking system and customer billing system | 1 |  | YES | 3 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
188 | Standard Cost | In Production | stancost | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 232 | No | Yes | In-House | NBAECKER | DWIERZBI | Finance | FCSD Tech | The purpose of this read-only system is to distribute standard cost for all FCSD parts sold, manufactured and packaged in NA. The system also provides standard cost data to other systems including financial inventory tracking system and customer billing system |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
188 | Standard Cost | In Production | stancost | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 232 | No | Yes | In-House | NBAECKER | DWIERZBI | Finance | FCSD Tech | The purpose of this read-only system is to distribute standard cost for all FCSD parts sold, manufactured and packaged in NA. The system also provides standard cost data to other systems including financial inventory tracking system and customer billing system |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
11665 | Stamping Tooling Analysis and Mfg Plan Sys | In Production | Stamps | ISIT | SKING68 | JRICH264 | RCHANDA | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | RTHIRUV1 | Manufacturing Engineering | Industrial System IT | Tracks status of diesets for SBU from PDN to Prod plant shipping |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
11665 | Stamping Tooling Analysis and Mfg Plan Sys | In Production | Stamps | ISIT | SKING68 | JRICH264 | RCHANDA | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | Tracks status of diesets for SBU from PDN to Prod plant shipping |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
11665 | Stamping Tooling Analysis and Mfg Plan Sys | In Production | Stamps | ISIT | SKING68 | JRICH264 | RCHANDA | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | RTHIRUV1 | Manufacturing Engineering | Industrial System IT | Tracks status of diesets for SBU from PDN to Prod plant shipping |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
23481 | Integral Translation System(ITS) | In Production | ITS | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Application to support Interaction & Ergonomics department for the translation specification management | 4 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51833 | Stamping Quality Manager | In Production | SQM | ISIT | SKING68 | DCLEME13 | MIVES6 | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Manufacturing Plants | 111 | ABILITY TO LOG DEFECTS, TRACK PARTS FROM INSPECTIONS ON TEST PANELS, SIGN OFFS, AND REPORT OUT ABILITY |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-06-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Priya | 2025-03-03 |  |  | PCF services is stopped. This app is dependent on the parent App 50273- Manf AEP for decommission of the PCF Org | No | Java < v21
19968 | Stamping Production Process Monitoring System | In Production | PPMS | ISIT | OTHERS | AHOROVIT | CGOLDMA4 | TBIRMIN1 | Copper | Non S-Ox | 11 | Yes | No | In-House | AHOROVIT | CGOLDMA4 | Manufacturing Engineering | - | Process Monitoring modules ( Draw Dies, Line Dies, Hot Stamping) Engineering Feedback( Three modules :Dies, Press & Automation, MP&L), Die Room Management (PIST ), QCT, Hard Hit Process, and SOI. Migration to new Data Center planned for Wave 19 |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51300 | INFORMATICA MDM | Active | Infa-MDM | EPEO | SKULKA52 | MWILLI20 | MMAES | RPOLLO13 | Gold | S-Ox In Scope | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | ITO | This is a PLACEHOLDER EAMS entry, per the 'IT Application Portfolio Management' guidelines. Customers of this service are required to raise their own EAMS entries, complete GRC App Assessments, etc. as required. ITO Shared environment featuring Informatica's MDM product suite. | 32 |  | YES | 4 | SWALIMBE | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
12482 | ACS: Automated Certification System | In Production | ACSPD | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Copper | Non S-Ox | 211 | No | Yes | In-House | DKAVITHA | DKAVITHA | Policy | Industrial System IT | ACS allows users to process and maintain the necessary data to produce emission certification data for the EPA and the California Air Resources Board (CARB) and submit electronic transactions to both agencies. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | Q4 2024 | Will be Decommissioned | Decommission | 2025-01-21 | 2025-01-21 | 2025-01-21 | Complete | Blue | 2025-01-21 | 2025-01-21 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Priya | 2025-03-03 |  |  | App fully Decommissioned | No | Oracle
50039 | Informatica for GCCT | Active | GCCTInfo | M&S TECH | RAHMED33 | DPOOVATH | DJAIN6 | MSCHOLT3 | Gold | Non S-Ox | - | No | Yes | - | APALAZZO | nashraf3 | Customer Experience | Marketing, Sales and Service | Informatica is a middleware to build batch and real-time integrations between Ford and Cloud Systems. This instance is dedicated to the GCCT implementation of MS Dynamics 365 | 10 |  | YES | 2 | NKANDULA | PLM | VM | TBD | EDC CaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
17942 | Stamping Business System | In Production | SBS | ISIT | OTHERS | AHOROVIT | CGOLDMA4 | TBIRMIN1 | Copper | Non S-Ox | 111 | Yes | No | In-House | AHOROVIT | CGOLDMA4 | Manufacturing Engineering | - | Support Stamping Business Unit reporting ( FTT, Production Dash Board, Tool & Die DashBoard, Productivity and Downtime reporting). It also supports New Model tracking ( 7207,LQOS, ROC ), Incoming Metal Quality from vendor ( 4 application: Steel, Aluminum, Extrusion, Boron Steel), and One Stop Shop report modules. To ensure that anyone who looks at the architecture framework, they know the Data Center is the ones that manages the server renewal and the business should not be at fault. The comment can read: The SQL S008 server needs upgraded. This is Data Center Managed. Business has no control in timing. Migration planned for Wave 19. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23242 | India Tax Register Solution | In Production | ITRS | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Silver | S-Ox Out of Scope | 221 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | ITRS system has an invoicing solution which would be used to generate and print miscellaneous and service invoices for various shipment types. ITRS will provide an option to maintain price for Service Billings, Other Parts. The ITRS system will have the master data for the TAX rates based on the HSN/SAC. On successful generation of invoice, ITRS will post the invoice details to PSGL/ AR system It would also act as Sales and Purchase register for India Market and would be used as base to file the GST tax returns | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
14060 | Stackup Online Analysis Tool | In Production | eStackup | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | This is a web-based application that captures comprehensive knowledge on all major stackup types and facilitates access to all available standards. It centralizes analysis results and is integrated with PIM system (APDM). It uses automated e-mail capability to enhance the communications required for the engineering approval process |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
14060 | Stackup Online Analysis Tool | In Production | eStackup | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | This is a web-based application that captures comprehensive knowledge on all major stackup types and facilitates access to all available standards. It centralizes analysis results and is integrated with PIM system (APDM). It uses automated e-mail capability to enhance the communications required for the engineering approval process |  |  | YES | 3 | BWUNNAVA | PLM | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
14060 | Stackup Online Analysis Tool | In Production | eStackup | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | JKOONS | Advanced PD and Tech | Industrial System IT | This is a web-based application that captures comprehensive knowledge on all major stackup types and facilitates access to all available standards. It centralizes analysis results and is integrated with PIM system (APDM). It uses automated e-mail capability to enhance the communications required for the engineering approval process |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
53816 | STA Competency eScorecard | In Production | eSTACS | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Manage & assess the competencies for the STA personnel. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-02-14 | 2025-02-14 | Complete | Blue | 2025-03-01 | 2025-03-01 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-04 |  |  |  | No | SQL
13181 | IN VEHICLE SOFTWARE SYSTEM | In Production | IVS | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 221 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | In Vehicle Software System combined is a high level customization for implementation of IVS TeamCenter Enterprise Application. | 22 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
53816 | STA Competency eScorecard | In Production | eSTACS | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House |  |  | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Manage & assess the competencies for the STA personnel. |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-14 | Complete | Blue | 2025-03-15 | 2025-01-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Praveen | 2025-03-04 |  |  |  | No | Java < v21
51482 | SRE Observability Platform | In Production | SRE | EPEO | RHAMMO57 | MBRUM | KTELLER1 | NKAUSHAL | Silver | Non S-Ox | 112 | No | Yes | Managed by 3rd Party Purchased Service | #N/A | #N/A | Enterprise Technology | 112 | A LIGHTWEIGHT SET OF OPEN SOURCE MONITORING, AGGREGATING AND ALERTING TOOLS FOR MAINTAINING YOUR PCF BASED PRODUCT. |  | Springboot | YES | 1 | SWALIMBE | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2025-01-31 | 2025-01-31 | Complete | [17 empty] | Java < v21
19353 | SQLServer | Active | SQLServer | EPEO | SKULKA52 | NSHAH43 | DPATEL43 | NVAIDYAN | Copper | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
56158 | IN VEHICLE SOFTWARE NEXT GEN | In Development | IVSNG | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | - | No | Yes | - | MNOWICK1 | PBORGAO1 | Enterprise Technology | - | In Vehicle Software System combined is a high level customization for implementation of IVS TeamCenter Application. | 36 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
24309 | SQL User Utility Process | In Production | SUUP | EPEO | SKULKA52 | CGIACOBB | VMANDELL | VMANDELL | Copper | Non S-Ox | 121 | No | Yes | In-House |  |  | Enterprise Technology | EPEO | The SQL User Utility Process is the automation to obtain permissions and execute DB2 queries. |  | MF - WAS Liberty | YES | 1 | SWALIMBE | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
52487 | SQL Server Password Expiration Notification | In Production | SQLPEN | EPEO | SKULKA52 | NSHAH43 | DPATEL43 | NVAIDYAN | Copper | S-Ox In Scope | 111 | Yes | No | - | CMIRABIT | NSHAH43 | Enterprise Technology | - | The SQL Server PEN- Password Expiration Notification process collects data from all of the supported SQL instances globally. This allows email notifications to customers when the passwords for their SQL Server authenticated logins will expire. This process is required to enforce the Access Control policies documented in the ISP (Information Security Policy). |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
20900 | In Plant Module Flashing | In Production | IPF | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Silver | Non S-Ox | 111 | Yes | No | In-House | SKING68 | DCLEME13 | Manufacturing Engineering | - | Application is used to flash Powertrain Control Modules (PCM)and other modules in vehicles while they are traveling through the assembly line process. A flashing tool inserted into the OBD-II connection in the vehicle will receive PCM configuration information from eCATS via a wireless interface connection and will use the configuration information to flash the PCM module. Results of the flashing process will be sent back to the eCATS application. | 9 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
50921 | I-ERP Platform | Active | IERP | I-ERP | SVISWANA | SVISWANA | MMOORE41 | MMOORE41 | Gold | S-Ox In Scope | - | No | Yes | - | SVISWANA | PNARAYAN | Enterprise Technology | - | This is the IERP SAP application infrastructure and license management project | 479 |  | YES | 3 | TSWEEN16 | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
53577 | SQL Server 2019 Standard | Planned | SQL | EVDD | PFRIEDMA | PFRIEDMA | PBLANCH3 | JTARDIFF | Silver | Non S-Ox | - | No | Yes | - | MJONE308 | PFRIEDMA | Advanced PD and Tech | - | Upload laboratory test data to web-based server for processing |  |  | YES | 1 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
11147 | SPRITE V1.4 | In Production | SPRITE | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Silver | Non S-Ox | 221 | No | Yes | In-House | GHERMAN | GHERMAN | PD Operations and Quality | Industrial System IT | SPRITE - Safety Processing Realtime Integrated Testing Environment. SPRITE Request Manager (web) has 1 database instance. SPRITE Test Stand(Client) has 17 installations on PCs. SPRITE also include KT Test, Test Stand Control System and FARO CMM System. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | Q4 2027 | On-Prem | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Oracle
52469 | I-ERP Material Master | In Production | IERPMAT | I-ERP | SVISWANA | SVISWANA | DMCAULI3 | MJOHN873 | Gold | S-Ox In Scope | 322 | No | Yes | COTS | TSWEEN16 | SVISWANA | Enterprise Technology | Integrated Enterprise Resource Planning (I-ERP) | I-ERP Material Master | 1 |  | YES | 3 | TSWEEN16 | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
11147 | SPRITE V1.4 | In Production | SPRITE | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Silver | Non S-Ox | 221 | No | Yes | In-House |  |  | PD Operations and Quality | Industrial System IT | SPRITE - Safety Processing Realtime Integrated Testing Environment. SPRITE Request Manager (web) has 1 database instance. SPRITE Test Stand(Client) has 17 installations on PCs. SPRITE also include KT Test, Test Stand Control System and FARO CMM System. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
51755 | I-ERP Cost and Inventory Accounting | In Production | IERPCIA | I-ERP | SFRANCI8 | AKANSKI | AKANSKI | LWU14 | Gold | S-Ox In Scope | 232 | No | Yes | COTS |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | Planning costs and establishing material prices, aiding in estimating the cost of goods managing and monitoring inventories, while providing information on movements, inventories and work in process. | 6 |  | YES | 1 | TSWEEN16 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
25082 | HR Middleware | In Production | HRMW | OCETO | TSWEEN16 | NMUTHUK2 | PVENKA12 | MBALAN2 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | HR Middleware(ITMS#25082) Informatica Cloud - is an integration platform to facilitate HR data need for all HCM ERP interfaces(Payroll and Non-Payroll, MDM and Non-HR applications). | 12 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
25069 | Specification Translator | In Production | SPECTR | M&S TECH | FHIRSH | NSIVASA1 | BRAMA3 | PSATISH2 | Gold | Non S-Ox | 222 | No | Yes | In-House | #N/A | #N/A | Marketing & Sales | 222 | SPECTR PROVIDE SERVICES TO TRANSLATE VEHICLE SPECIFICATIONS ACROSS VARIOUS CODES (E.G, WERS, EOC, USC ETC) |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | Q2 2026 | Version Upgrade | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
54256 | Specification Rationalization | In Production | SpecRat | GDIA | AMADDULA | RVISWAN1 | VKRISH34 | KMARATH1 | Copper | Non S-Ox | 211 | No | Yes | In-House | AFRADKIN | ELOTITO | Enterprise Technology | Global Data Insight and Analytics (GDIA) | SpecRat is one of Reductive Design application, and its is an application helps the engineering teams in revising KLT test requirement leveraging historical weather data and connected vehicle data. |  | Springboot | YES | 1 | FRANBELL | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-10-31 | 2025-10-31 |  | Not Started |  | 2025-10-31 |  | Planned |  | No | [14 empty] | No | Java < v21
21532 | Special Service Support Center Website | In Production | SSSC | FORD PRO & FCSD TECH | OTHERS | EGILLAND | AHUSPEN | ABOBBALA | Gold | Non S-Ox | 221 | Yes | No | In-House | DWILYARD | EGILLAND | Ford Customer Service | - | The mission of the SSSC is to provide their customers with quality information and assistance for Field Service Actions and Customer Service Programs in a timely and professional manner. The SSSC manages web requests and inbound and outbound calls. Requests are related to specific FSA's or CSP's and include general program questions, part order requests, technical assistance, claim review, rental and repair approvals. Renkim and Ford services are closely monitored daily to assure they adhere to the SSSC Service Level Agreement. |  |  | YES | 2 | RKENNEL | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
23731 | GPL (CVision - Purchasing) | In Production | GPL | I-ERP | SARAUJO3 | SCRANFOR | GALONSO6 | SNAG1 | Bronze | Non S-Ox | 111 | Yes | No | In-House | ASMYTH3 | SCRANFOR | Supply Chain | - | EMC software that enables OCR of scanned documents and integration with EDMS. This is a Purchasing skill team solution. | 6 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
12268 | Special Requests Navis Mini | In Production | VS-SRNM | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | North American Sales Reporting - Special Requests Activity. Analysts develop special reports utilizing NAVIS and other key sales reporting applications with short turn-around timing. Requests submitted through Web Site: http://www.mso.ford.com/mss/css/special/request.html. Supports in excess of 500 requests annually. Key customers include: OGC, Brand, Fleet, Assembly Plants, Vehicle Sales Divisions, Engineering,Compliance, etc. |  |  | YES | 1 | NKANDULA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
51541 | South America OTD | In Production | SOTD | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | 111 | Collect orders to South America |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | PDO team confirmed already on Java v21 | No | Java < v21
51541 | South America OTD | In Production | SOTD | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Collect orders to South America |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
12764 | Global Vehicle Programming | In Production | GVP | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Silver | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | Global Vehicle Programming - US Based - reporting of Actual and Forecast volume and mix rate data from North American operational systems (CPV2, 9270, Pseudo Order). | 4 |  | YES | 3 | NKANDULA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
17927 | South America Free of Charge (ARPW) | In Production | ARPW | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | S-Ox Out of Scope | 211 | No | Yes | - | DBRIGHEN | DBRIGHEN | Ford Customer Service | - | This system controls the delivery of parts free of charge to the Dealer when the vehicle repaired is in warranty period. Also controls that these parts are involved in a warranty claim submitted by the Dealer after the repair. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-03 | Complete | Blue | 2025-06-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | DB Migration completed | No | Oracle
24281 | Global Vehicle Management System | In Production | GVMS | EVDD | MJAMWAL | TPINTO3 | BCHITTI | CSUBHA1 | Platinum | Non S-Ox | 223 | No | Yes | In-House | MJAMWAL | TPINTO3 | Advanced PD and Tech | - | Global Vehicle Management System | 4 |  | YES | 4 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
51540 | South America Direct Sales | In Production | SADS | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | 311 | Manage Direct Sales for South America. |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
51540 | South America Direct Sales | In Production | SADS | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Manage Direct Sales for South America. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
22701 | Global User Experience - Europe | In Production | GUX-EU | FORD PRO & FCSD TECH | TJUNIPER | AMEIKLE | AMACLEA1 | JCOY3 | Silver | Non S-Ox | 223 | No | Yes | Managed by 3rd Party Purchased Service | TJUNIPER | AMEIKLE | Marketing & Sales | Marketing, Sales and Service | Consumer facing (B2C) website platform application for Ford Of Europe. Part of the Global UX initiative. | 19 |  | YES | 1 | RKENNEL | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50791 | South America Customs API | In Production | CustomsAPI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | 111 | Provide communication between legacy applications and OneSource Global Trade solution (50790). It manages data transformation to attend all requirements related to customs data need for Ford applications and for OneSource controls. |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
50791 | South America Customs API | In Production | CustomsAPI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | Provide communication between legacy applications and OneSource Global Trade solution (50790). It manages data transformation to attend all requirements related to customs data need for Ford applications and for OneSource controls. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | SQL
53431 | Global Trading Partner Community Management | In Production | GTPCM | OCETO | TVASU | KBALAS13 | CBHARGAV | KTRACY8 | Silver | Non S-Ox | 232 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | This website is used by Data Exchange customers to request/change connections, view status of request/transactions, maintain credential and use other information required to establish data exchange to support their business need. | 10 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | EDC CaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC CaaS | [5 empty] | No | VM
54219 | South America Active Call | In Production | SAAC | OCETO | DBRIGHEN | NMORALE7 | PDELMOND | NMORALE7 | Bronze | Non S-Ox | 311 | No | Yes | - | DBRIGHEN | NMORALE7 | Ford Customer Service | - | Platform that manage Active Call process, which include an online monitoring of Vehicle Health Alerts (VHA) in real time, so Call Center can contact and support customers and provide proactive support |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is decommissioned already | No | Java < v21
24181 | Sourcing Workplan Tool | In Production | SWT | I-ERP | SARAUJO3 | KSYROCKI | PBUKKAPA | SNAG1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | 211 | Sourcing WorkPlan Tool (Program Management/Date Tracking Tool) - This tool will be focused on PD and Purchasing Program management. It is a separate tool for simplicity and to provide date tracking and reporting from sourcing workflow for all Global Vehicle Programs and Power Train for each Project Sourcing Action (PSA). This is a Global Tool for no Regional Differences |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-01 | Complete | Blue | 2025-03-15 | 2025-01-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Praveen | 2025-03-05 |  |  |  | No | Java < v21
24181 | Sourcing Workplan Tool | In Production | SWT | I-ERP | SARAUJO3 | KSYROCKI | PBUKKAPA | SNAG1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | - | Sourcing WorkPlan Tool (Program Management/Date Tracking Tool) - This tool will be focused on PD and Purchasing Program management. It is a separate tool for simplicity and to provide date tracking and reporting from sourcing workflow for all Global Vehicle Programs and Power Train for each Project Sourcing Action (PSA). This is a Global Tool for no Regional Differences |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-02-14 | 2025-02-14 | Complete | Blue | 2025-03-01 | 2025-03-01 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-05 |  |  |  | No | SQL
51005 | Global Trade in Valuation | In Production | GTIV | M&S TECH | RKLEINSM | MMILBOC1 | EGRIFF38 | SRUDENK2 | Gold | Non S-Ox | 221 | No | Yes | In-House | RKLEINSM | MMILBOC1 | Enterprise Technology | Marketing, Sales and Service | Global Trade In Valuation is an online Trade-In solution for all vehicle makes and models for up to 15 model years. It is a standalone application, which is intended to exist within the eCommerce experience, but can also be integrated with other internal applications. The Trade In Valuation experience is orchestrated through a series of web service calls to both internal and external APIs. The application has been generalized as much as possible to ensure consistency across regions, but has features that are specific to each region. | 4 |  | YES | 2 | NKANDULA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13190 | Sourcing for Quality | In Production | SFQ | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | The eQ1MSA part of SFQ application, is to automate the enhanced Q1 Manufacturing Site Assessment process to reduce the amount of manual data entry from Suppliers and STA Engineers. The eQ1MSA part of SFQ application, will allow Suppliers and STA Engineers to enter, view and analyze assessment data electronically. The global web-based application will also receive feeds from the upstream systems, such as FDS, GSDB, SMAP, WIPS AdHoc, WIPS & SIM-NG. eQ1MSA part of SFQ application will also provide Data feeds to SIM-NG and WCT. The application works with J2EE platform with Struts framework, HTML and Java script for the data entry user interface, with Oracle 11.x Database. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-02-15 | 2025-02-15 | Complete | Blue | 2025-02-15 | 2025-02-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Praveen | 2025-03-05 |  |  |  | No | Java < v21
13190 | Sourcing for Quality | In Production | SFQ | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | The eQ1MSA part of SFQ application, is to automate the enhanced Q1 Manufacturing Site Assessment process to reduce the amount of manual data entry from Suppliers and STA Engineers. The eQ1MSA part of SFQ application, will allow Suppliers and STA Engineers to enter, view and analyze assessment data electronically. The global web-based application will also receive feeds from the upstream systems, such as FDS, GSDB, SMAP, WIPS AdHoc, WIPS & SIM-NG. eQ1MSA part of SFQ application will also provide Data feeds to SIM-NG and WCT. The application works with J2EE platform with Struts framework, HTML and Java script for the data entry user interface, with Oracle 11.x Database. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-02-15 | 2025-02-15 | Complete | Blue | 2025-04-01 | 2025-03-02 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-05 |  |  | Migration completed. Decom in progress. | No | Oracle
13190 | Sourcing for Quality | In Production | SFQ | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | The eQ1MSA part of SFQ application, is to automate the enhanced Q1 Manufacturing Site Assessment process to reduce the amount of manual data entry from Suppliers and STA Engineers. The eQ1MSA part of SFQ application, will allow Suppliers and STA Engineers to enter, view and analyze assessment data electronically. The global web-based application will also receive feeds from the upstream systems, such as FDS, GSDB, SMAP, WIPS AdHoc, WIPS & SIM-NG. eQ1MSA part of SFQ application will also provide Data feeds to SIM-NG and WCT. The application works with J2EE platform with Struts framework, HTML and Java script for the data entry user interface, with Oracle 11.x Database. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-31 | 2025-01-10 | Complete | Blue | 2025-04-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Praveen | 2025-03-05 |  |  | Migration completed. Decom in progress. | No | Java < v21
22796 | SonarQube | In Production | SonarQube | EA | RRISS | SHE1 | LKESHRI | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | - | SonarQube is an open source quality management platform, dedicated to continuously analyze and measure technical quality, from project portfolio to method. |  |  | YES | 2 | GBRAIL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
526 | Global Tooling System/variset | In Production | GTSV | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Engineering | - | GTSV allows for the entry and storage of all tooling information required for effective tool management in a single application. Goal is to reduce production costs by controlling tool usage, inventory, rework and purchases. Key Features Include: Tool life monitoring Inventory tracking Cutter grind management Tool pre-setter interface Central data repository Rework tracking and mgmt Tool presetting & gauge interface | 13 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
50392 | Software Release Portal | In Production | SRP | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | In-House | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | Global tool to manage in-vehicle software release and change management process. |  |  | YES | 1 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50392 | Software Release Portal | In Production | SRP | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | In-House |  |  | Advanced PD and Tech | Industrial System IT | Global tool to manage in-vehicle software release and change management process. |  | Springboot | YES | 2 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
50179 | Software Licensing Asset Manager | In Production | SLAM | EPEO | SKULKA52 | CGIACOBB | 0 | GSIENKIE | Copper | Non S-Ox | 111 | No | Yes | In-House |  |  | Enterprise Technology | EPEO | A tool that provides an inventory of all mainframe installed software products, as well as the licenses for these products. |  | MF - WAS Liberty | YES | 1 | SWALIMBE | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
53392 | Software Change and Release Management | In Production | SWCM | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 212 | No | Yes | In-House | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | 212 | Global tool to manage in-vehicle software announcement and health chart. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
53392 | Software Change and Release Management | In Production | SWCM | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 212 | No | Yes | In-House | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | Global tool to manage in-vehicle software announcement and health chart. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
20295 | Global Test Data Management System | In Production | GTDM | ISIT | JKOONS | TBROWN99 | SPILLA12 | JLUCAS1 | Bronze | Non S-Ox | 222 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | GTDM is a global application adopting the industry standard ASAM-ODS (Open Data Service) to manage and enable efficient central storage, provide global data access, data retention management, global data sharing/analysis of high quality physical test data which will help engineers to make a quick and good decision on product. It currently manages Engine Dyno Data, Vehicle Durability, Emission, Powertrain Control and Calibration, Body Interior, Safety Crash and NVH data | 105 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
16544 | SOF Releases | In Production | SOFRELS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Single Order Filter will combine three major areas of functionality and six legacy systems to create a single application that selects and schedules orders. SOF will streamline, simplify, and enhance the scheduling business processes and supporting systems within the Marketing & Sales and Material Planning & Logistics organizations. |  |  | YES | 6 | NKANDULA | PLM | Java Struts | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
16544 | SOF Releases | In Production | SOFRELS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Single Order Filter will combine three major areas of functionality and six legacy systems to create a single application that selects and schedules orders. SOF will streamline, simplify, and enhance the scheduling business processes and supporting systems within the Marketing & Sales and Material Planning & Logistics organizations. |  |  | YES | 6 | NKANDULA | PLM | Mainframe | Q1 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
16544 | SOF Releases | In Production | SOFRELS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Single Order Filter will combine three major areas of functionality and six legacy systems to create a single application that selects and schedules orders. SOF will streamline, simplify, and enhance the scheduling business processes and supporting systems within the Marketing & Sales and Material Planning & Logistics organizations. |  |  | YES | 6 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
16544 | SOF Releases | In Production | SOFRELS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Single Order Filter will combine three major areas of functionality and six legacy systems to create a single application that selects and schedules orders. SOF will streamline, simplify, and enhance the scheduling business processes and supporting systems within the Marketing & Sales and Material Planning & Logistics organizations. |  |  | YES | 6 | NKANDULA | PLM | SQL | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
21376 | Global S&R Paynter | In Production | GSRP | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | PD Operations and Quality | Industrial System IT | This application will provide program teams in NVH the ability to create dashboards and paynter charts on programs based on input from plants ( VO and VE development Teams ) on S&R issues. | 4 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
16544 | SOF Releases | In Production | SOFRELS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Single Order Filter will combine three major areas of functionality and six legacy systems to create a single application that selects and schedules orders. SOF will streamline, simplify, and enhance the scheduling business processes and supporting systems within the Marketing & Sales and Material Planning & Logistics organizations. |  |  | YES | 6 | NKANDULA | PLM | WAS | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
19518 | SOE Amendment and Search | In Production | SAMS | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | CKEMPSKI | Bronze | Non S-Ox | 122 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | SAMS is an application developed within the SOE Project. It provides order amendment functionality. |  |  | YES | 2 | NKANDULA | PLM | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
19518 | SOE Amendment and Search | In Production | SAMS | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | CKEMPSKI | Bronze | Non S-Ox | 122 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | SAMS is an application developed within the SOE Project. It provides order amendment functionality. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q4 2026 | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
19167 | SNURK-1 | In Production | SNURK-1 | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 311 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The SNURK is a tool used by Manufacturing Plants, staff MP&L and Controller's Office. In January 2007 the SNURK launched in North America. The SNURK also allows users to compare transactions to promote continuous improvement and the drive for consistent practices. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
9087 | Global OnLine Dealer Database | In Production | GOLDD | M&S TECH | NKANDULA | JLEWIS10 | CVOGLER1 | JHARPER2 | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | The Global OnLine Dealer Database (GOLDD) is Ford Motor Company's worldwide repository for all retailers of Ford Motor Company products and services. | 12 |  | YES | 6 | NKANDULA | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20941 | SNURK V.2.0 | In Production | SNURK2 | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 322 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Common global business reporting for manufacturing finance (cars), manufacturing operations (Cost of building cars), capability to do analytics and 100% audit tracking. Reporting Scope: - Plant expense labor and overhead - Industrial Material - Plant accounting (General ledger) - Timekeeping (Hourly and Salary) - Physical presence - Security - badge swipe card as related to payroll and timekeeping - Finished Vehicle accounting - Production Material (FST) - BWS - FAB card charges - Legacy 9270 - Vehicle scheduling | 785 |  | YES | 4 | TSWEEN16 | PLM | Datastage | Q2 2025* |  | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | [8 empty] | QlikSense | [5 empty] | No | DA
20941 | SNURK V.2.0 | In Production | SNURK2 | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 322 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Common global business reporting for manufacturing finance (cars), manufacturing operations (Cost of building cars), capability to do analytics and 100% audit tracking. Reporting Scope: - Plant expense labor and overhead - Industrial Material - Plant accounting (General ledger) - Timekeeping (Hourly and Salary) - Physical presence - Security - badge swipe card as related to payroll and timekeeping - Finished Vehicle accounting - Production Material (FST) - BWS - FAB card charges - Legacy 9270 - Vehicle scheduling |  |  | YES | 4 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
20941 | SNURK V.2.0 | In Production | SNURK2 | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 322 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Common global business reporting for manufacturing finance (cars), manufacturing operations (Cost of building cars), capability to do analytics and 100% audit tracking. Reporting Scope: - Plant expense labor and overhead - Industrial Material - Plant accounting (General ledger) - Timekeeping (Hourly and Salary) - Physical presence - Security - badge swipe card as related to payroll and timekeeping - Finished Vehicle accounting - Production Material (FST) - BWS - FAB card charges - Legacy 9270 - Vehicle scheduling |  |  | YES | 4 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
21669 | Global Market Equation Analysis Tool | In Production | MEAT | I-ERP | SFRANCI8 | AKANSKI | RDAVIES6 | LWU14 | Silver | Non S-Ox | 221 | No | Yes | In-House |  |  | Marketing & Sales | Integrated Enterprise Resource Planning (I-ERP) | MEAT is a global tool to consolidate and analyse marketing and finance data (including price positions, shares, financials, favourable opinion, etc.) in a structural and consistent way, to support decision making and to comply with global reporting requirements. | 2 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
9088 | SMARTS/MOCA - Sales Mgmnt Analysis & Rptg Tool | In Production | SMARTS | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Data warehouse & toolset for the analysis / reporting of sales & stock information for Ford brand across the European markets. Data held within SMARTS is derived from the GENERIC EXTRACT which is updated every night. Data is held according to European business rules. Includes EMSS-MOCA (Market Offering Complexity Analysis) module which provides reports on top-selling entity/option mixes across Europe. Previous ITMS entry for MOCA (13328) now deleted and input merged with this (9088) | 63 |  | YES | 5 | NKANDULA | PLM | BO | Q1 2025 | Already Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
9088 | SMARTS/MOCA - Sales Mgmnt Analysis & Rptg Tool | In Production | SMARTS | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | Data warehouse & toolset for the analysis / reporting of sales & stock information for Ford brand across the European markets. Data held within SMARTS is derived from the GENERIC EXTRACT which is updated every night. Data is held according to European business rules. Includes EMSS-MOCA (Market Offering Complexity Analysis) module which provides reports on top-selling entity/option mixes across Europe. Previous ITMS entry for MOCA (13328) now deleted and input merged with this (9088) |  |  | YES | 5 | NKANDULA | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
9088 | SMARTS/MOCA - Sales Mgmnt Analysis & Rptg Tool | In Production | SMARTS | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Data warehouse & toolset for the analysis / reporting of sales & stock information for Ford brand across the European markets. Data held within SMARTS is derived from the GENERIC EXTRACT which is updated every night. Data is held according to European business rules. Includes EMSS-MOCA (Market Offering Complexity Analysis) module which provides reports on top-selling entity/option mixes across Europe. Previous ITMS entry for MOCA (13328) now deleted and input merged with this (9088) |  |  | YES | 5 | NKANDULA | PLM | Mainframe | TBD | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9088 | SMARTS/MOCA - Sales Mgmnt Analysis & Rptg Tool | In Production | SMARTS | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Data warehouse & toolset for the analysis / reporting of sales & stock information for Ford brand across the European markets. Data held within SMARTS is derived from the GENERIC EXTRACT which is updated every night. Data is held according to European business rules. Includes EMSS-MOCA (Market Offering Complexity Analysis) module which provides reports on top-selling entity/option mixes across Europe. Previous ITMS entry for MOCA (13328) now deleted and input merged with this (9088) |  |  | YES | 5 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
17408 | Global Lending Analysis System-GLAS | In Production | GLAS | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 322 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | This system is a dealer lending platform that automates the process of creating dealer credit ratings across the globe and facilitates credit package creation and approval process for wholesale lines, dealers loans etc. The system is also used for ongoing risk monitoring and mitigation action documentation. | 7 |  | YES | 5 | SRAISIN1 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
9088 | SMARTS/MOCA - Sales Mgmnt Analysis & Rptg Tool | In Production | SMARTS | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | In-House |  |  | Marketing & Sales | Marketing, Sales and Service | Data warehouse & toolset for the analysis / reporting of sales & stock information for Ford brand across the European markets. Data held within SMARTS is derived from the GENERIC EXTRACT which is updated every night. Data is held according to European business rules. Includes EMSS-MOCA (Market Offering Complexity Analysis) module which provides reports on top-selling entity/option mixes across Europe. Previous ITMS entry for MOCA (13328) now deleted and input merged with this (9088) |  | Springboot | YES | 6 | NKANDULA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50768 | Smart Wall Box | In Production | SWB | EVDD | JWOOD38 | RDEBSHAL | SSHAILAJ | PSENTH40 | Silver | Non S-Ox | 223 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 223 | SMART WALL BOX - PROVIDE A PLATFORM THAT ENHANCES CUSTOMER EXPERIENCE THROUGH AN INTEGRATED IN-HOME CHARGING SOLUTION: INTERFACES WITH FORD ECOSYSTEM FOR ANALYTICS AND FEATURE DEVELOPMENT; REMOTE OPERATIONS: TURN ON OR OFF CHARGING, RESPOND TO 3RD PARTY REMOTE REQUESTS AND RESPOND TO LOCAL REQUESTS FOR ENERGY MANAGEMENT; MANAGE USER ACCESS AND NUMBER OF USERS THAT CAN USE THE BOX; ENABLE CAPABILITY TO UPGRADE OR ENHANCE OPERATION REMOTELY OR OVER THE AIR (OTA) UPDATES; REAL TIME AND HISTORICAL INFO FROM THE BOX; WALL BOX SYSTEM INFORMATION ON REQUEST; MATCH CUSTOMER AND WALL BOX |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
19221 | Smart VINCENT 2 | In Production | SV2 | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Supports dealership sales process by providing VIN eligibility for incentives, saving information in an online deal, reporting the sale, and claiming incentives. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-04-30 |  | In-Progress | Green | 2025-07-29 |  | Planned |  | No | 100% | 25% | [6 empty] | Java 21 |  |  |  |  | confirmed with PDO. Rewrite is in progress and will be completed on or before Q2 | No | Java < v21
19221 | Smart VINCENT 2 | In Production | SV2 | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Supports dealership sales process by providing VIN eligibility for incentives, saving information in an online deal, reporting the sale, and claiming incentives. |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q4 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
19221 | Smart VINCENT 2 | In Production | SV2 | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Supports dealership sales process by providing VIN eligibility for incentives, saving information in an online deal, reporting the sale, and claiming incentives. |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
19221 | Smart VINCENT 2 | In Production | SV2 | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Supports dealership sales process by providing VIN eligibility for incentives, saving information in an online deal, reporting the sale, and claiming incentives. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-04-30 |  | In-Progress | Green | 2025-07-29 |  | Planned |  | No | 100% | 25% | [6 empty] | GCP Migration |  |  |  |  | confirmed with PDO. Rewrite is in progress and will be completed on or before Q2 | No | Java < v21
51076 | Smart Parking | In Production | Park | OCETO | TSWEEN16 | KADOMKAI | DSTONE46 | ESTILESK | Copper | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Ford Land | Staffs IT | Accurately determine utilization of a parking facility cameras camerassors |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
21988 | Global Interior Quietness Paynter | In Production | GIQP | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | PD Operations and Quality | Industrial System IT | This application will provide program teams in NVH the ability to create dashboards and paynter charts on programs based on input from plants (VO and VE development Teams) on Interior Quietness (IQ)issues. | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53323 | Smart Lockers - Hosted Environment | In Production | Vecos | OCETO | TSWEEN16 | KADOMKAI | DSTONE46 | ESTILESK | Bronze | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | DDESAI | KADOMKAI | Ford Land | Staffs IT | Mobile App (Vecos) and Hosted Cloud Solution (Azure) |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
18579 | GLOBAL FORENSICS INFRASTRUCTURE | Active | GCFI | OCETO | PMILLIGA | PLUBAS | RKLOMAN | VPOTTIBO | Copper | Non S-Ox | - | No | Yes | - | PMILLE12 | PLUBAS | Enterprise Technology | - | This application is a place holder for the two Technology records in GRC ( 7015890 and 7009210). Encase enables the Company to collect digital evidence in support of internal and external investigation requests that is timely, cost effective, and in a manner that permits the collected data to be used in a court of law. | 3 |  | YES | 1 | PMILLIGA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
55030 | SLP Supplement | Planned | SLPS | I-ERP | SARAUJO3 | CBISWADI | DGLOVE26 | SNAG1 | - | Non S-Ox | 11 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Supplemental application for Ariba SLP application which handles supplier onboarding, qualification, and maintenance |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
14217 | SLD Website - Dearborn Safety Lab Test Data | In Production | SLD WS | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | The Safety Lab Website provides vehicle crash results. This site provides the following information: digital images, digital videos instrumentation data, film analysis plots, test reports, test log info QAT Reports, and HDF files (complete and GPP compatible). This website was developed and launched before 1999. |  |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
52879 | Global DV Data Processor | In Development | GDDP | EVDD | NDIMMITT | GKAUR19 | RMENDO42 | JLUCAS1 | Silver | Non S-Ox | 111 | Yes | No | In-House | SHAKIM2 | NDIMMITT | Advanced PD and Tech | - | An application that will connect to external tools to fetch data, process it based on the necessary test level. The tool will map the high level test cases to low level test cases to be run manually or automatically, providing all necessary data | 6 |  | YES | 3 | MJONE308 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
11591 | SLA: Service Loss Analysis | In Production | SLA | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Bronze | Non S-Ox | 111 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | The Service Loss Assignment system's main goal is to determine the reason for service loss (i.e., local fill & system fill loss) for PDC stocked parts in N.A. The SLA output data will be used as the basis for applying operational or system changes to help improve fill. SLA fill calculations were designed to match the currently used PA0012PR Fill report from MMP Network12 & will provide drill-down capability into the data. The reason for all service loss will be gauged by probing the entire supply chain (from supplier shipment to final PDC stockkeep transaction) to show where a process may have been over standard. SLA will use data processed by the IMAS application to decide the cause for service loss. IT Architecture: SLA information is staged on DB2 to facilitate DB2 table lookups & then stored on Teradata & accessed via both interactive web screens & a data analysis-reporting tool called Business Objects. Business Criticality: Med-H Additional Outage Impact includes: Impact to Financial Results. | 15 |  | YES | 4 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11591 | SLA: Service Loss Analysis | In Production | SLA | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Bronze | Non S-Ox | 111 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | The Service Loss Assignment system's main goal is to determine the reason for service loss (i.e., local fill & system fill loss) for PDC stocked parts in N.A. The SLA output data will be used as the basis for applying operational or system changes to help improve fill. SLA fill calculations were designed to match the currently used PA0012PR Fill report from MMP Network12 & will provide drill-down capability into the data. The reason for all service loss will be gauged by probing the entire supply chain (from supplier shipment to final PDC stockkeep transaction) to show where a process may have been over standard. SLA will use data processed by the IMAS application to decide the cause for service loss. IT Architecture: SLA information is staged on DB2 to facilitate DB2 table lookups & then stored on Teradata & accessed via both interactive web screens & a data analysis-reporting tool called Business Objects. Business Criticality: Med-H Additional Outage Impact includes: Impact to Financial Results. |  |  | YES | 4 | RKENNEL | PLM | Mainframe | Q3 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11591 | SLA: Service Loss Analysis | In Production | SLA | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Bronze | Non S-Ox | 111 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | The Service Loss Assignment system's main goal is to determine the reason for service loss (i.e., local fill & system fill loss) for PDC stocked parts in N.A. The SLA output data will be used as the basis for applying operational or system changes to help improve fill. SLA fill calculations were designed to match the currently used PA0012PR Fill report from MMP Network12 & will provide drill-down capability into the data. The reason for all service loss will be gauged by probing the entire supply chain (from supplier shipment to final PDC stockkeep transaction) to show where a process may have been over standard. SLA will use data processed by the IMAS application to decide the cause for service loss. IT Architecture: SLA information is staged on DB2 to facilitate DB2 table lookups & then stored on Teradata & accessed via both interactive web screens & a data analysis-reporting tool called Business Objects. Business Criticality: Med-H Additional Outage Impact includes: Impact to Financial Results. |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
50119 | Global DAT TDM system | In Production | DTDM | ISIT | OTHERS | MKEES | KZARSE | GRAO3 | Silver | Non S-Ox | 111 | Yes | No | In-House | SPAFFRA2 | MKEES | Advanced PD and Tech | Industrial System IT | For the development of advanced driver assistance systems (ADAS), a global test data management system is required to manage files from ADAS test drives and to provide meta data storage and search capabilities. | 6 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
18607 | Global Commodity Hub | In Production | GCH | ISIT | MNOWICK1 | LSRINIVA | GPIOT1 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | This is the Global Commodity Management Hub workstream A. It is an application designed to expose the engineering, purchasing, financial, and manufacturing data necessary to create commodity business plans. The application is being developed with an outside vendor, Endeca. | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
13746 | Single Order Edit | In Production | SOE | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Single Order Edit (SOE) commonizes NA vehicle order editing rules among engineering, marketing, and manufacturing. SOE data services & rules are used throughout Order Fulfillment (order entry & mgmt, amendments, scheduling, & some post-release processes). |  |  | YES | 4 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
13746 | Single Order Edit | In Production | SOE | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Manufacturing Staffs | Marketing, Sales and Service | Single Order Edit (SOE) commonizes NA vehicle order editing rules among engineering, marketing, and manufacturing. SOE data services & rules are used throughout Order Fulfillment (order entry & mgmt, amendments, scheduling, & some post-release processes). |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13746 | Single Order Edit | In Production | SOE | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Manufacturing Staffs | Marketing, Sales and Service | Single Order Edit (SOE) commonizes NA vehicle order editing rules among engineering, marketing, and manufacturing. SOE data services & rules are used throughout Order Fulfillment (order entry & mgmt, amendments, scheduling, & some post-release processes). |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q4 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
13746 | Single Order Edit | In Production | SOE | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Manufacturing Staffs | Marketing, Sales and Service | Single Order Edit (SOE) commonizes NA vehicle order editing rules among engineering, marketing, and manufacturing. SOE data services & rules are used throughout Order Fulfillment (order entry & mgmt, amendments, scheduling, & some post-release processes). |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
53068 | Single Interface Experience customeR Request Appli | In Production | SIERRA | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 311 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | 311 | Application that allows agents to receive and process requests to serve customers in a single working environment (Single Pane of Glass) being able to see, execute and track the satisfactory completion of the requests |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
53068 | Single Interface Experience customeR Request Appli | In Production | SIERRA | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 311 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Application that allows agents to receive and process requests to serve customers in a single working environment (Single Pane of Glass) being able to see, execute and track the satisfactory completion of the requests |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
21468 | Global Color Management System | In Production | GCMS | ISIT | VVIJAY55 | ABANSA15 | VBHATT | ABANSA15 | Gold | Non S-Ox | 221 | No | Yes | In-House | BGANESH | AFINK4 | Advanced PD and Tech | Industrial System IT | GCMS is the next gen ColorTrax application. The goal of GCMS is to streamline the Color Harmony, Color Release, Design Mastering and Design Quality process. Currently the process depends heavily on manual data entry, subject matter expertise and gaining Ford information from suppliers. GCMS will streamline the color release process by automatically and seamlessly pulling and updating information from upstream systems eliminating the redundant data entry that exists today and providing advanced analytical capabilities to identity gaps/issues earlier in the GPDS process. GCMS will serve as a single global repository for color and materials mastering and appearance item approval tracking and reporting. | 11 |  | YES | 5 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53358 | Single Complete Actionable view of the Vehicle Plu | Planned | scav+ | EVDD | HHUANGJI | YZHOU159 | JSHAN | WJIN12 | Gold | Non S-Ox | - | No | Yes | - | TSWEEN16 | HHUANGJI | Advanced PD and Tech | - | This is the platform to store the vehicle related data as business needs. |  |  | YES | 1 | MJONE308 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
14995 | SIN - Sales Incentive System | In Production | SIN | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | The SIN System is the application that is responsible for control the incentives for Ford Dealers, through of the creation, simulation and approval incentives sales programs. The Ford Dealers are able to search the incentives received by VIN Number. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
14995 | SIN - Sales Incentive System | In Production | SIN | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | The SIN System is the application that is responsible for control the incentives for Ford Dealers, through of the creation, simulation and approval incentives sales programs. The Ford Dealers are able to search the incentives received by VIN Number. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q3 2026 | Modernize to Cloud Databases | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Oracle
11395 | Global Capacity Planning System | In Production | GCP | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | Computer application designed to aid in the planning of Capacity requirements for Ford Motor Company. It is a global process that calculates part volumes for assembly plant end items. | 6 |  | YES | 3 | NKANDULA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
14995 | SIN - Sales Incentive System | In Production | SIN | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | The SIN System is the application that is responsible for control the incentives for Ford Dealers, through of the creation, simulation and approval incentives sales programs. The Ford Dealers are able to search the incentives received by VIN Number. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
53180 | SimManager(SimManager | In Development | SimManager | ISIT | JKOONS | MNOVAK1 | BTHOMA47 | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | COTS | JKOONS | JKOONS |  | Industrial System IT | MSC's SimManager is a Simulation Management System for simulation data & process management. MSCONE Licensing |  |  | YES | 1 | BWUNNAVA | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
53277 | GFT_Labtronics | In Production | Labtronics | ISIT | JPITTERL | STHOM124 | AVARADI1 | JLUCAS1 | Bronze | Non S-Ox | 222 | Yes | No | COTS | JPITTERL | STHOM124 | PD Operations and Quality | Industrial System IT | Component testing test bench application | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51218 | GFT_Jedox-BI | In Production | Jedox | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SFRANCI8 | AKANSKI | Manufacturing Plants | - | Datawarehousing solution for financial reporting and planning | 7 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11952 | Shipping Instructions | In Production | ShipInst | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | SROYCHOU | Manufacturing Staffs | Industrial System IT | Shipping Instructions is the Global Logistics shipping instructions website to develop and distribute shipping instructions to internal and external users. Logistics providers send data to SI, which in turn sends route information to CMMS3 (HMRSII, WIP6, Supplier Performance), Cass freight payment and premium, and OFM Data Warehouse. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
11952 | Shipping Instructions | In Production | ShipInst | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Shipping Instructions is the Global Logistics shipping instructions website to develop and distribute shipping instructions to internal and external users. Logistics providers send data to SI, which in turn sends route information to CMMS3 (HMRSII, WIP6, Supplier Performance), Cass freight payment and premium, and OFM Data Warehouse. | 8 |  | YES | 3 | BWUNNAVA | PLM | WebFocus | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
14104 | General Plotting Package | In Production | GPP | ISIT | JPITTERL | CBOHN | HBOYSEN | GRAO3 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JPITTERL | CBOHN | Advanced PD and Tech | Industrial System IT | General Purpose Plotting package and math toolkit for CAE and Test data analysis. | 4 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19622 | SHC Resource Center | In Production | SHC-RC | EPEO | LFULCHER | EREYNOL3 | JKADAKIA | MMACKE16 | Silver | Non S-Ox | 111 | No | Yes | In-House | LFULCHER | EREYNOL3 | Enterprise Technology | EPEO | Central repository for servers and applications managed by Hosting Services. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
653 | GEMSS (Global Engineering Management Support Sys) | In Production | GEMSS | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Bronze | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | GEMSS Global Engineering Management Support Sys GEMSS is a personal computer application that generates graphs and printed reports of selected Programs and Activities using data extracted daily from WERS Worldwide Engineering Release System. | 7 |  | YES | 5 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
57426 | GDIA CREDIT CITRIX | In Production | GDIA_CTRX | FORD CREDIT | RMINHAS3 | SSINGH14 | SASIF | VBHUPATH | Silver | Non S-Ox | 111 | Yes | No | In-House |  |  | Ford Credit Services | - | This Solution is used to support GDI&A Credit teams to work faster by decreasing the latency | 1 |  | YES | 1 | SRAISIN1 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
53115 | GDIA - Informatica (ADM)(INFA-ADM) | Active | INFA-ADM | EPEO | SKULKA52 | MWILLI20 | MMAES | RPOLLO13 | Bronze | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | This is a PLACEHOLDER EAMS entry, per the 'IT Application Portfolio Management' guidelines. Customers of this service are required to raise their own EAMS entries, complete GRC App Assessments, etc. as required. This tool covers the 'GDIA - Informatica Tools (23779)' Engineering/Development environment used by GDIA. This tool covers data management, and self-service solutions for GDIA. Includes the following components: Big Data Management (BDM), Enterprise Data Catalog (EDC) and Data Privacy Management (DPM). This is not an 'Application'. This EAMS record is required to manage server ownership, and other contact information needed by Server Hosting. | 50 |  | YES | 2 | SWALIMBE | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
53268 | SERVICE XP PLATFORM | In Production | SXP | M&S TECH | KPINNU | KMURALIK | SGUMUDA1 | PANTONI6 | Gold | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | KPINNU | KMURALIK | Customer Experience | Marketing, Sales and Service | The Ford Service Experience Platform (ServiceXP) provides the foundation for customer and dealer experiences (CX/DX) supporting our Service Customer Journey end-to-end. ServiceXP is based on Pega and will provide CX/DX related products and services such as Reservations, Global Uptime, Mobile Service. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
51998 | FVEXDATA | In Production | FVEXDATA | M&S TECH | NKANDULA | TBRYANS1 | PRAO2 | RFERMAN1 | Bronze | Non S-Ox | 222 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Marketing & Sales | - | SQL database that holds lead information | 3 |  | YES | 2 | NKANDULA | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
53268 | SERVICE XP PLATFORM | In Production | SXP | M&S TECH | KPINNU | KMURALIK | SGUMUDA1 | PANTONI6 | Gold | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | KPINNU | KMURALIK | Customer Experience | Marketing, Sales and Service | The Ford Service Experience Platform (ServiceXP) provides the foundation for customer and dealer experiences (CX/DX) supporting our Service Customer Journey end-to-end. ServiceXP is based on Pega and will provide CX/DX related products and services such as Reservations, Global Uptime, Mobile Service. |  |  | YES | 3 | NKANDULA | PLM | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
9912 | Service Vehicle Info System (SERVIS2) | In Production | SERVIS2 | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SDEENAD1 | SDHANAS2 | Silver | S-Ox Out of Scope | 222 | No | Yes | In-House | RKENNEL | RKENNEL | Ford Customer Service | FCSD Tech | SERVIS2 is the regional Warranty application for Asia Pacific. It replaced a warranty process that was largely manual and paper based. It provides the dealers with greater access to relevant vehicle data to enable them to drive customer satisfaction. The timely submission of data reduces the cycle time for feedback to quality teams via the interface to the global Analytical Warranty System (AWS). SERVIS2 is hosted in Dearborn. |  |  | YES | 5 | RKENNEL | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
9912 | Service Vehicle Info System (SERVIS2) | In Production | SERVIS2 | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SDEENAD1 | SDHANAS2 | Silver | S-Ox Out of Scope | 222 | No | Yes | In-House | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | SERVIS2 is the regional Warranty application for Asia Pacific. It replaced a warranty process that was largely manual and paper based. It provides the dealers with greater access to relevant vehicle data to enable them to drive customer satisfaction. The timely submission of data reduces the cycle time for feedback to quality teams via the interface to the global Analytical Warranty System (AWS). SERVIS2 is hosted in Dearborn. | 369 |  | YES | 5 | RKENNEL | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
9912 | Service Vehicle Info System (SERVIS2) | In Production | SERVIS2 | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SDEENAD1 | SDHANAS2 | Silver | S-Ox Out of Scope | 222 | No | Yes | In-House | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | SERVIS2 is the regional Warranty application for Asia Pacific. It replaced a warranty process that was largely manual and paper based. It provides the dealers with greater access to relevant vehicle data to enable them to drive customer satisfaction. The timely submission of data reduces the cycle time for feedback to quality teams via the interface to the global Analytical Warranty System (AWS). SERVIS2 is hosted in Dearborn. |  |  | YES | 5 | RKENNEL | PLM | Java Struts | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
50878 | FORDMATE (DcOF) | In Production | FMATEDCOF | FORD CREDIT | JBENITO | SHODGSO9 | VFERRARO | AJOGIYAT | Silver | Non S-Ox | 221 | Yes | No | Managed by 3rd Party Purchased Service | JBENITO | SHODGSO9 | Marketing & Sales | - | FORDMATE 14600 DCoF Migration. FORD MATE is Ford of Italy's version of the Dealer Portal used for communicating to Dealers. It a part of the Standard European Portal Rollout. | 9 |  | YES | 2 | SRAISIN1 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | GCP Migration | [5 empty] | No | VM
9912 | Service Vehicle Info System (SERVIS2) | In Production | SERVIS2 | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SDEENAD1 | SDHANAS2 | Silver | S-Ox Out of Scope | 222 | No | Yes | In-House | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | SERVIS2 is the regional Warranty application for Asia Pacific. It replaced a warranty process that was largely manual and paper based. It provides the dealers with greater access to relevant vehicle data to enable them to drive customer satisfaction. The timely submission of data reduces the cycle time for feedback to quality teams via the interface to the global Analytical Warranty System (AWS). SERVIS2 is hosted in Dearborn. |  |  | YES | 5 | RKENNEL | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
14851 | Service Purchasing Bill of Material | In Production | SPBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | Creates a service purchasing bill of material to track costs of purchased service parts vs production part prices for use by buyers to facilitate purchasing efficiencies. | 2 |  | YES | 4 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
14851 | Service Purchasing Bill of Material | In Production | SPBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Creates a service purchasing bill of material to track costs of purchased service parts vs production part prices for use by buyers to facilitate purchasing efficiencies. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | [5 empty] | No | Java < v21
14851 | Service Purchasing Bill of Material | In Production | SPBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Creates a service purchasing bill of material to track costs of purchased service parts vs production part prices for use by buyers to facilitate purchasing efficiencies. |  |  | YES | 4 | RKENNEL | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
14851 | Service Purchasing Bill of Material | In Production | SPBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Creates a service purchasing bill of material to track costs of purchased service parts vs production part prices for use by buyers to facilitate purchasing efficiencies. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-29 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | [5 empty] | No | Java < v21
19341 | Service OVID | In Production | SOVID | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | S-Ox In Scope | 221 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Corporate Repository for European vehicle information |  |  | YES | 2 | RKENNEL | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
19341 | Service OVID | In Production | SOVID | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | S-Ox In Scope | 221 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Corporate Repository for European vehicle information |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
50806 | FordLabs - Shared | Planned | FLABS | M&S TECH | SVIJAI1 | SVIJAI1 | LSREERAM | COCONN33 | - | Non S-Ox | - | No | Yes | - | APALAZZO | JFORBIS | Enterprise Technology | Marketing, Sales and Service | This is an ITMS # to bin any shared infrastructure or other assets that need to be tracked that are owned by FordLabs as a whole. FordLabs isn't actually an application. But, may Ford processes require you to establish an application before you can provision any infrastructure. FordLabs often works on experiments that preceed the definition and identificaiton of applications. | 1 |  | YES | 3 | NKANDULA | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
11063 | Service Appointment Tracking System (SATS) | In Production | SATS | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | Service Appointment Tracking system |  |  | YES | 1 | NKANDULA | PLM | SQL | Q4 2027 | Modernize to Cloud Databases | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | SQL
11063 | Service Appointment Tracking System (SATS) | In Production | SATS | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House |  |  | Human Resources | Marketing, Sales and Service | Service Appointment Tracking system |  | Springboot | YES | 2 | NKANDULA | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
20908 | Sequencing and Kitting System | In Production | SKS | ISIT | AMEHER1 | ADURSO | MBIJI | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | GHERMAN | GHERMAN | Manufacturing Staffs | Industrial System IT | Global Sequencing & Kitting System, a module of #12122 Error Proofing - VO. Vendor is CEC Controls. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
54523 | FORDKIT | Planned | FORDKIT | EVDD | MMONALIS | JMILOSER | MVANN10 | MVANN10 | Bronze | Non S-Ox | - | No | Yes | - |  |  | Advanced PD and Tech | - | Vehicle SDK for upfitters | 1 |  | YES | 1 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
15429 | Sequencer - Valencia Plant Floor | In Production | EuPFS-Sequ | ISIT | JPITTERL | STHOM124 | RRUIZMAR | RPRASA22 | Bronze | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | JPITTERL | STHOM124 | Manufacturing Plants | Industrial System IT | Sequencer controls the production line mix by generating the next sequence to be built. There are two instances running on the same server infrastructure: Sequencer for Trim, and Sequencer for Chassis. Both modules generates the best sequence (car) that will be taken from the buffers into the production lines at each of those points. The Trim Sequencer considers the AS/RS warehouse cars, selects the best unit towards Trim or PreTrim, and also inserts PreTrim units -once finished- into the Trim flow. The Chassis version takes into consideration the Pre-Chassis buffer cars to select the best unit towards the Chassis lines. In all cases taking into account the following principles: Principle 1: To maintain a regular and stable production sequence. Principle 2: To separate the Regularity concept from constraints. Principle 3: To produce based on a good Master Sequence, to modify it by including a new improved Dynamic Sequence only when an Exception arises, to return to the Master Sequence as soon as p |  |  | YES | 1 | BWUNNAVA | PLM | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
20670 | Sell-out reporting | In Production | SOR | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | The Sell-out reporting application (formerly named Wholesale sell-out reporting WSR) provides reporting on dealer sell-out channels related sell data (independent repairers & bodyshops, fleets, authorized Ford repairers, etc). | 625 |  | YES | 6 | NKANDULA | PLM | Datastage | Q2 2025 |  | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | [11 empty] | Need to get the dates from PDO team | No | DA
20670 | Sell-out reporting | In Production | SOR | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | THE SELL-OUT REPORTING APPLICATION (FORMERLY NAMED WHOLESALE SELL-OUT REPORTING WSR) PROVIDES REPORTING ON DEALER SELL-OUT CHANNELS RELATED SELL DATA (INDEPENDENT REPAIRERS & BODYSHOPS, FLEETS, AUTHORIZED FORD REPAIRERS, ETC). | 5031 |  | YES | 6 | NKANDULA | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
20670 | Sell-out reporting | In Production | SOR | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | The Sell-out reporting application (formerly named Wholesale sell-out reporting WSR) provides reporting on dealer sell-out channels related sell data (independent repairers & bodyshops, fleets, authorized Ford repairers, etc). |  |  | YES | 6 | NKANDULA | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | Need to get the dates from PDO team | No | Java < v21
20670 | Sell-out reporting | In Production | SOR | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | The Sell-out reporting application (formerly named Wholesale sell-out reporting WSR) provides reporting on dealer sell-out channels related sell data (independent repairers & bodyshops, fleets, authorized Ford repairers, etc). |  |  | YES | 6 | NKANDULA | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | [6 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
13015 | Ford Pro: AccuQuote / Commercial Truck Tools | In Production | CTT / CVT | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | ATRIPAT9 | Copper | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | RKENNEL | PJEFFRE5 | General Management | Ford Pro | AccuQuote / Commercial Truck (Vehicle) Tools is a web based stand system developed to provide Ford dealers a Medium Duty Truck sales tool. The system has the capability to do sales presentations as well as spec'ing and quoting trucks. The software was developed by vendor Chrome Data / Autodata / JD Power. They were selected and funded by the Ford Commercial Truck Brand Org. The system works in tandem with CTOPS (#12871), the backend, which feeds the US Order Fulfillment systems. CIA 2,1,1 Vendor Chrome Data | 8 |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20670 | Sell-out reporting | In Production | SOR | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | The Sell-out reporting application (formerly named Wholesale sell-out reporting WSR) provides reporting on dealer sell-out channels related sell data (independent repairers & bodyshops, fleets, authorized Ford repairers, etc). |  |  | YES | 6 | NKANDULA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
9092 | SEER - Sales Eurovis Extract Reporter | In Production | SEER | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | 211 | Analysis tool used by the following Central Business Groups: Ford of Europe (FoE), Middle East and Africa (MEA), The Americas, European Direct Markets (EDM) and Asia Pacific Africa (AP) to analyse sales & stock information at market level and below. Data held within SEER is derived from the GENERIC EXTRACT which is updated every night. It contains sales data for each market, from the point of order receipt to retail sale + history. This data can be used to find specific vehicles, spot delays, monitor dealer performance or perform sales analyses. As a result this tool is used for sales reporting & operational purposes. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
9092 | SEER - Sales Eurovis Extract Reporter | In Production | SEER | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | Analysis tool used by the following Central Business Groups: Ford of Europe (FoE), Middle East and Africa (MEA), The Americas, European Direct Markets (EDM) and Asia Pacific Africa (AP) to analyse sales & stock information at market level and below. Data held within SEER is derived from the GENERIC EXTRACT which is updated every night. It contains sales data for each market, from the point of order receipt to retail sale + history. This data can be used to find specific vehicles, spot delays, monitor dealer performance or perform sales analyses. As a result this tool is used for sales reporting & operational purposes. |  |  | YES | 3 | NKANDULA | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
50424 | Ford Pro Marketplace | In Production | FFM | FORD PRO & FCSD TECH | SKOVACIC | ESHANKS2 | RRENGASW | AMARYNOV | Gold | Non S-Ox | 323 | No | Yes | In-House | JSING180 | JJACO130 | General Management | Ford Pro | Part of FordPro. Tool customers use to enroll/unenroll their fleet of vehicles in products. | 6 |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
54243 | Security Look Up Portal | In Production | SLP | OCETO | PMILLIGA | TYOUNG91 | DOREIL11 | WJUSTICE | Bronze | Non S-Ox | 312 | No | Yes | In-House | TGEIGER | TYOUNG91 | Enterprise Technology | - | Cybersecurity incident investigation tool |  |  | YES | 1 | PMILLIGA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
54141 | Security Camera Streaming Services | In Development | SCSS | EVDD | JWOOD38 | JBRIDGE6 | AHOWE1 | AJONES25 | Gold | Non S-Ox | - | No | Yes | In-House | #N/A | #N/A | Integrated Services | - | THIS RECORD COVERS THE VIDEO STREAMING APPLICATIONS. SCSS IS AN APPLICATION LAYER WHICH SUPPORTS LIVE STREAMING AND STILL PICTURES FROM COMMERCIAL VEHICLES USING CANOPY HARDWARE, WITH IMAGES AND VIDEOS HOSTED IN CANOPY CLOUD. ISC USES FORD'S ONBOARD CAMERAS AND TMC. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
22745 | Security Access Management System | In Production | SAMS | EPEO | SKULKA52 | CGIACOBB | VMANDELL | VMANDELL | Silver | S-Ox In Scope | 121 | No | Yes | In-House |  |  | Enterprise Technology | EPEO | Automation to collect RACF data access approval and implementation. |  | MF - WAS Liberty | YES | 1 | SWALIMBE | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
14840 | Secured Password Management | In Production | PwdMgmt | EPEO | NOKEEFE | MSNYDER5 | DDALKOVS | GSIENKIE | Silver | Non S-Ox | 222 | Yes | No | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Ford's complex, heterogeneous computing environment needs a simple way to manage multiple passwords. The P-Synch software simplifies multi-system password management by providing users, generic ID owners, and help desk operators with a web interface for managing their Active Directory password. Additionally, the P-Synch software provides a transparent password synchronization across different systems. Those systems are Active Directory (ICR #: 2005-1744), RACF (ICR #: 2003-1926_ and IBM Lighthouse (ICR #: 2013-1). P-Synch will enable Ford to strengthen and manage password authentication and reduce administration and help desk costs by: 1. Allowing all user passwords on registered Target Applications (i.e., Active Directory, RACF Mainframe Systems, IBM Lighthouse, etc...) to be changed to a single value simultaneously. 2. Enforcing a centralized password policy and history. 3. Allowing users to reset their own passwords via various self-service options (e.g., Q&A, Alternate Email, etc...) reducing |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
14550 | Ford Performance System 2000 | In Production | TFRS2K | FORD PRO & FCSD TECH | OTHERS | MIGNATOW | AKUCUKAR | VPUNDAMA | Bronze | Non S-Ox | 311 | Yes | No | In-House | MGRUEBE2 | MIGNATOW | Ford Customer Service | - | Ford Performance Parts (ERP) Application supports: Product Development Purchasing Order Entry Sales Data Warehouse & Inventory management. Product development data is used to populate FPP Website Content | 9 |  | YES | 2 | RKENNEL | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13533 | Ford Performance Parts | In Production | FPP | FORD PRO & FCSD TECH | OTHERS | MIGNATOW | AKUCUKAR | VPUNDAMA | Copper | Non S-Ox | 321 | Yes | No | In-House | MGRUEBE2 | MIGNATOW | Ford Customer Service | - | Business-to-Consumer brand site for Ford Performance Parts. The website is designed for Brand Enthusiasts to engage and obtain information about parts, check part availability, place part orders, and check part order status. The Ford Performance Parts website is hosted in the Dearborn Data Center. (formerly Ford Racing Performance Parts - FRPP) | 10 |  | YES | 2 | RKENNEL | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
25089 | SecOps User WebTools | In Production | SecOpTools | EPEO | NOKEEFE | MSNYDER5 | ZZHAN106 | GSIENKIE | Silver | Non S-Ox | 211 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Security Operations Tools website for Customer self-service solutions |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | SQL
50355 | FORD LAND MAINTENANCE MANAGEMENT SYSTEM | In Production | FLMMS | ISIT | SKING68 | KRAMESH | VGARIMEL | ESTILESK | Copper | S-Ox Out of Scope | 211 | No | Yes | COTS | SKING68 | KRAMESH | Ford Land | Industrial System IT | Facilities Maintenamce and Asset Management application used by Ford Land | 8 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC CaaS | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
52721 | Ford Land Data Hub | In Production | FLDH | OCETO | TSWEEN16 | KADOMKAI | TJACKS13 | ESTILESK | Bronze | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Ford Land | Staffs IT | Information Integration Hub to enable data transfer between Ford Land systems, other corporate system, and other Ford data hubs. | 5 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11331 | SDPR: Supplier Delivery Performance Rating | In Production | SDPR:11331 | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Bronze | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | NBAECKER | Ford Customer Service | FCSD Tech | SDPR functionality migrated to Super G Application. SDPR is just an interface to SIM and Super G with supplier ASN information. The SDPR data (ASN, Releases) is gathered on the mainframe from various modules of MMP. The data is then DRDA downloaded to an Oracle server sent to SIM (Supplier Improvement Metrics), and then made available to suppliers via the B2B server. No Web Module available, it is just an interface running on Mainframe |  |  | YES | 3 | RKENNEL | PLM | Oracle | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Oracle
11331 | SDPR: Supplier Delivery Performance Rating | In Production | SDPR:11331 | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Bronze | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | SDPR functionality migrated to Super G Application. SDPR is just an interface to SIM and Super G with supplier ASN information. The SDPR data (ASN, Releases) is gathered on the mainframe from various modules of MMP. The data is then DRDA downloaded to an Oracle server sent to SIM (Supplier Improvement Metrics), and then made available to suppliers via the B2B server. No Web Module available, it is just an interface running on Mainframe |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q2 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11331 | SDPR: Supplier Delivery Performance Rating | In Production | SDPR:11331 | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Bronze | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | SDPR functionality migrated to Super G Application. SDPR is just an interface to SIM and Super G with supplier ASN information. The SDPR data (ASN, Releases) is gathered on the mainframe from various modules of MMP. The data is then DRDA downloaded to an Oracle server sent to SIM (Supplier Improvement Metrics), and then made available to suppliers via the B2B server. No Web Module available, it is just an interface running on Mainframe |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
51869 | SDNLookup | In Production | SDNLookup | EVDD | JWASNIC1 | MBOMMANA | SPRADHAN | SPRADHAN | Gold | Non S-Ox | 222 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 222 | TO LOOKUP THE SDN TYPE FOR THE CLIENT TO CALL FOR A VIN |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | Java < v21
51292 | SDE Utilities | In Production | SDE | EA | RRISS | SHE1 | LKESHRI | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | In-House | RRISS | SHE1 | Enterprise Technology | 211 | Utility Infrastructure to support SDE applications |  | Springboot | YES | 2 | GBRAIL | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | Java < v21
23259 | Ford Immobilizer Codes Online - 2 | In Production | FIMCO 2.0 | EVDD | JREYN149 | TPINTO3 | BCHITTI | CSUBHA1 | Silver | Non S-Ox | 322 | No | Yes | In-House | WFRANTZ | CRAJA1 | Advanced PD and Tech | - | PD Engineers and Supplier Testers will use this application interface to get the Key Values to unlock the ECU Modules so that they can update them or run tests on them. | 4 |  | YES | 3 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
53024 | SDE Scout | In Production | SDESC | OCETO | PMILLIGA | SNAMBIVE | DVRABIOI | SGURU8 | Copper | Non S-Ox | 111 | No | Yes | In-House | MCHRIS38 | SNAMBIVE | Enterprise Technology | Technology & Enterprise Services (TES) | An application to provide traceability and auditability for software development ecosystems. | 91 |  | YES | 4 | PMILLIGA | PLM | WebFocus | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-30 | 2024-12-30 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Already Migrated |  |  |  |  | Do not recognize this as a WebFOCUS app, not in my tracker. (KW 3-14-25) | No | DA
53024 | SDE Scout | In Production | SDESC | OCETO | PMILLIGA | SNAMBIVE | DVRABIOI | SGURU8 | Copper | Non S-Ox | 111 | No | Yes | In-House | MCHRIS38 | SNAMBIVE | Enterprise Technology | 111 | An application to provide traceability and auditability for software development ecosystems. |  | Springboot | YES | 4 | PMILLIGA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
53024 | SDE Scout | In Production | SDESC | OCETO | PMILLIGA | SNAMBIVE | DVRABIOI | SGURU8 | Copper | Non S-Ox | 111 | No | Yes | In-House | MCHRIS38 | SNAMBIVE | Enterprise Technology | Technology & Enterprise Services (TES) | An application to provide traceability and auditability for software development ecosystems. |  |  | YES | 4 | PMILLIGA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
13559 | Ford Fulfillment System | In Production | FFS | M&S TECH | OTHERS | AHROMCO | ELIDDELL | RFERMAN1 | Copper | Non S-Ox | 222 | Yes | No | In-House | GHEDDERM | AHROMCO | Marketing & Sales | - | This is Fulfillment System for Ford and Lincoln. The application is used and maintained by the Agency. The application is hosted in the B2B environment. | 9 |  | YES | 2 | NKANDULA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24669 | SDE Portal | In Production | SDEPort | EVDD | AGARBY | NWEBST14 | TNIELSE9 | SGURU8 | Copper | Non S-Ox | 111 | No | Yes | In-House | AGARBY | NWEBST14 | Advanced PD and Tech | - | Portal to store the various SDE process and activities |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50055 | Ford Energy Rewards | In Production | FER | EVDD | JWOOD38 | RDEBSHAL | JMANKIN | SCOUPER | Bronze | Non S-Ox | 211 | No | Yes | In-House | JWOOD38 | RDEBSHAL | Advanced PD and Tech | - | Ford Energy Rewards (aka SmartGrid) connects electric utility companies with Ford to manage grid integrations. | 4 |  | YES | 3 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
52454 | scs concept - Data touch 3 | In Production | SCS Concep | ISIT | JPITTERL | STHOM124 | AVARADI1 | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | - | JPITTERL | STHOM124 | PD Operations and Quality | - | Records data in the fastener area Dunton UK - Stores on SQL Database |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
52628 | FORD DRIVE: NETWORK OPTIMIZATION AND CAPACITY PLAN | Archived | NOCAP | ISIT | AHAAS3 | AHAAS3 | MZHANG3 | RBALAS21 | - | Non S-Ox | - | No | Yes | In-House |  |  | Enterprise Technology | - | Tool to aid AV Fleet Management decision making | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
22162 | SCRA -Servicemembers Civil Relief Act | In Production | SCRA | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | Non S-Ox | 311 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The SCRA application collects Active Duty Military status data from the US Dept of Defense for use in the handling of 'adverse events' (e.g., charge-offs and repossessions) by Ford Credit applications. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | Q3 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50809 | Font Management System | In Production | Fontera | ISIT | JKOONS | CDODD7 | SJAIMES | JLUCAS1 | Copper | Non S-Ox | 211 | Yes | No | - | JKOONS | NLAKSHMA | Advanced PD and Tech | - | A font management system for global vehicle programs | 3 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12065 | Scopus Case Management | In Production | SCOPUS | OCETO | TSWEEN16 | NABBAS | MKOMATH1 | MBALAN2 | Bronze | Non S-Ox | 321 | No | Yes | In-House | DDESAI | DDESAI | Human Resources | - | Case Management Software System which supports the HR Benefits Office |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | Database servers & EAMS Status decommissioned | No | Oracle
21580 | FOA Historical Vehicle Sales | In Production | FOA-HVS | M&S TECH | RAHMED33 | DPOOVATH | SPARVESH | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | In-House | APALAZZO | DPOOVATH | Ford Customer Service | - | Database to capture historical vehicle sales data for the Australian Market | 5 |  | YES | 2 | NKANDULA | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24202 | SCOM for Directory Services (SCOM - DS) | In Production | SCOMDS | EPEO | NOKEEFE | MSNYDER5 | CQI | GSIENKIE | Silver | Non S-Ox | 111 | Yes | No | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Microsoft System Center Operations Manager (SCOM) implemented for Directory Services Environment that supports integrated event management. MS-SCOM version 20xx with SCOM agent and recommended management packs installed is the monitoring solution of choice for Ford Directory Services Infrastructure. MS-SCOM 20xx is an application and server management solution capable of monitoring the availability, performance and security of Directory Services servers and utility servers. SCOM also gathers performance counter used to generate metrics. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
51903 | FNV2 Test Automation Analytics | In Production | TANALYTICS | EVDD | NDIMMITT | DCHAMB77 | AAVALOS7 | AAVALOS7 | Copper | Non S-Ox | 111 | Yes | No | In-House | NDIMMITT | DCHAMB77 | Advanced PD and Tech | - | FNV2 (Fully Network Vehicle) test automation analytics is a data science and machine learning project. The objective of this project is to gather automated software verification data from hundreds of Jenkins slave machines that are verifying the software quality in each dev pull request made on Ford GITHUB. The end goal is to gather the metadata and use them for data science and machine learning. Some examples are as follows: Predict software quality trends based on millions of data-point, generate heatmap on problem areas in production code that happens 1 in a million, resource planning based on data insight, monitor lab fleet dynamically using a data-driven Dashboard. | 2 |  | YES | 2 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
24109 | FNV2 Release Engineering System | In Production | JenkinsSil | EVDD | JREYN149 | MCHATTE1 | GSEGAL | VVEINOTT | Silver | Non S-Ox | 221 | Yes | No | In-House | JREYN149 | MCHATTE1 | Advanced PD and Tech | - | The FNV2 Release Engineering System includes continuous integration and other tools that support the build and release of the FNV2 software components via a highly configurable and fully automated s/w build environment. | 2 |  | YES | 1 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
50584 | Scheduled Remote Services Manager | In Production | SRSm | EVDD | JWASNIC1 | JVEDANAY | MMOYAL | PKALIYAP | Silver | Non S-Ox | 222 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 222 | SERVICE TO SCHEDULE REMOTE COMMANDS FOR CONNECTED VEHICLES |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
9890 | SCC/Emerging Markets Forecasting & Scheduling | In Production | EuMP-SCC | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | SCC stands for SFI CUM COUNTER. It receives CMF from OVS, offline & captive sequence file from Plant as inputs. It creates 3 bridge files - Year to Date CUM file, Lineup & offline file & sends to CMMS3 to maintain inventory counts, daily call in & current day offline information. It supports AP & FOE regions. EMFS stands for Emerging Markets Forecasting and Scheduling. It receives Forecast, Lineup & Offline file as input from QAD/Master system. It creates 4 bridge files - Forecast file, Year to Date CUM file, Lineup file & offline file and sends to CMMS3 application to maintain forecast counts, inventory counts used, daily call in and current day offline information. It supports Taiwan and FAB regions. WSR stands for Weighted Spring Release. It caters release of correct spring parts based on total weight of vehicle for balance and ride height Optimization. Daily solve generates solves (SFIs) using GPAM load modules for unique EOC specification for all EOCs that are used in previous run of all MP&L systems. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
22496 | SCA-Vehicle | In Production | SCA-V | GDIA | MLYONS23 | CDEBASHI | JJOHN998 | KMARATH1 | Bronze | Non S-Ox | 321 | No | Yes | In-House | DTERPST1 | JFERNSLE | Enterprise Technology | 321 | SCA-V is a back end application that collects, receives and stores vehicle data from all sources so that it can be made available to enterprise teams for analytical purposes. Project also encompasses data discovery environment for analytic purposes. |  | Springboot | YES | 3 | FRANBELL | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2025-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
22496 | SCA-Vehicle | In Production | SCA-V | GDIA | MLYONS23 | CDEBASHI | JJOHN998 | KMARATH1 | Bronze | Non S-Ox | 321 | No | Yes | In-House | DTERPST1 | JFERNSLE | Enterprise Technology | Global Data Insight and Analytics (GDIA) | SCA-V is a back end application that collects, receives and stores vehicle data from all sources so that it can be made available to enterprise teams for analytical purposes. Project also encompasses data discovery environment for analytic purposes. |  |  | YES | 3 | FRANBELL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-01-15 | 2025-01-15 | 2025-01-15 | Complete | Blue | 2025-01-15 | 2025-01-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
24564 | FNV Automated Testing | In Production | FNV TAT | EVDD | NDIMMITT | DCHAMB77 | AAVALOS7 | AAVALOS7 | Copper | Non S-Ox | 111 | Yes | No | In-House | NDIMMITT | DCHAMB77 | Advanced PD and Tech | - | FNV2 (Fully Networked Vehicle) involves 3 main components: SYNC4 (infotainment console), TCU (mobile radio), and ECG (Enhanced Central Gateway). Objective is to develop and execute automated testing for these components. The testing includes the following: Pre-submit: tests whenever a software developer submits a code change Sanity: daily testing to ensure main features are functional Stability: long duration testing to verify mean time between failures | 9 |  | YES | 2 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
23063 | SCA-Customer | In Production | SCA-C | GDIA | CBUCKL19 | SPATIBAN | NTHAYANI | MPATEL20 | Silver | S-Ox In Scope | 322 | No | Yes | Managed by 3rd Party Purchased Service | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | It provides the ability to understand the interaction between enterprise actions (inc. Ford & Partners) and the customer lifecycle, determine which actions maximize the benefit to the customer and the enterprise and then track the actions through completion in a closed loop. |  |  | YES | 5 | FRANBELL | PLM | Datastage | Q4 2025 |  | Modernize | 2025-12-15 | 2025-07-31 |  | In-Progress | Green | 2025-07-31 |  | Planned |  | No | [14 empty] | No | DA
23063 | SCA-Customer | In Production | SCA-C | GDIA | CBUCKL19 | SPATIBAN | NTHAYANI | MPATEL20 | Silver | S-Ox In Scope | 322 | No | Yes | Managed by 3rd Party Purchased Service | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | It provides the ability to understand the interaction between enterprise actions (inc. Ford & Partners) and the customer lifecycle, determine which actions maximize the benefit to the customer and the enterprise and then track the actions through completion in a closed loop. |  |  | YES | 5 | FRANBELL | PLM | Mainframe | Q2 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
23063 | SCA-Customer | In Production | SCA-C | GDIA | CBUCKL19 | SPATIBAN | NTHAYANI | MPATEL20 | Silver | S-Ox In Scope | 322 | No | Yes | Managed by 3rd Party Purchased Service | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | It provides the ability to understand the interaction between enterprise actions (inc. Ford & Partners) and the customer lifecycle, determine which actions maximize the benefit to the customer and the enterprise and then track the actions through completion in a closed loop. |  |  | YES | 5 | FRANBELL | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-07-30 | 2025-07-01 |  | In-Progress | Green | 2025-07-01 |  | Planned |  | No | [14 empty] | No | SQL
24435 | FNV Analytics | In Production | FNVA | EVDD | GJABLONS | PZU1 | RMAURICE | DMOOR349 | Copper | Non S-Ox | 211 | No | Yes | In-House | GJABLONS | GJABLONS | Advanced PD and Tech | - | SYNC Analytics is an device/server application that Product Development will be using to help us understand HOW users are using the SYNC module and also capture software failure data to improve quality of the module before release. | 8 |  | YES | 3 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
23063 | SCA-Customer | In Production | SCA-C | GDIA | CBUCKL19 | SPATIBAN | NTHAYANI | MPATEL20 | Silver | S-Ox In Scope | 322 | No | Yes | Managed by 3rd Party Purchased Service | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | It provides the ability to understand the interaction between enterprise actions (inc. Ford & Partners) and the customer lifecycle, determine which actions maximize the benefit to the customer and the enterprise and then track the actions through completion in a closed loop. |  | WAS | YES | 5 | FRANBELL | PLM | WAS | Q1 2026 | Version Upgrade | Modernize | 2026-03-15 | 2027-06-29 |  | Not Started | Green | 2027-06-29 |  | Planned |  | No | [14 empty] | No | Java < v21
51273 | SCAC Strategic Data Environment | In Production | SCAC SDE | GDIA | CBUCKL19 | KJINNA | RKODEESW | NDEVI3 | Silver | Non S-Ox | 311 | No | Yes | In-House | EBLOCH | SKOWDLE | Enterprise Technology | Global Data Insight and Analytics (GDIA) | SCAC SDE system contains holistic customer centric data to support Campaigning, Decisioning, Reporting, Modeling, and Analytics functions for global Ford/ FMCC/ other Ford centric organizations |  | Springboot | YES | 2 | FRANBELL | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 | 2025-01-31 | Complete | Blue | 2026-03-15 | 2025-01-31 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | Java < v21
23451 | FEDEBOM | In Production | FEDEBOM | ISIT | MNOWICK1 | LSRINIVA | HKUMAR7 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | FEDEBOM is a solution to Product Development D&R Engineers to author Vehicle Bill Of Material and planned to replace AVBOM2 and will support Engineers out WERS. | 59 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23697 | SCA-C Consumer Account Profile | In Production | SCA-C CAP | GDIA | EBLOCH | KKB | PSIRISIN | SDUTTA9 | Gold | Non S-Ox | 322 | No | Yes | COTS | EBLOCH | KKB | Enterprise Technology | 322 | Provides access to Consumer Account Profile data on demand to consumers regardless of their geographic location and stores the data within the SCA-Customer environment.Note: Please see the Tech07 and CBID documents for the most current list of regions and interfaces. |  | Springboot | NO | 3 | FRANBELL | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
23697 | SCA-C Consumer Account Profile | In Production | SCA-C CAP | GDIA | EBLOCH | KKB | PSIRISIN | SDUTTA9 | Gold | Non S-Ox | 322 | No | Yes | COTS | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Provides access to Consumer Account Profile data on demand to consumers regardless of their geographic location and stores the data within the SCA-Customer environment.Note: Please see the Tech07 and CBID documents for the most current list of regions and interfaces. |  |  | NO | 3 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
20330 | FEDE Workbench | Planned | FEDEWB | ISIT | JKOONS | NLAKSHMA | KRAJES33 | GRAO3 | Silver | S-Ox Classification Pending | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | PD Systems Engineering initiatives | 16 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50717 | SCA Consent Platform | In Production | CP | GDIA | CBUCKL19 | KKB | PSIRISIN | SDUTTA9 | Silver | Non S-Ox | 212 | No | Yes | In-House | EBLOCH | KKB | Enterprise Technology | 212 | Manage and service Consumer Consents |  | Springboot | YES | 3 | FRANBELL | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 | 2025-01-15 | Complete | Blue | 2026-03-15 | 2025-01-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | Java < v21
50717 | SCA Consent Platform | In Production | CP | GDIA | CBUCKL19 | KKB | PSIRISIN | SDUTTA9 | Silver | Non S-Ox | 212 | No | Yes | In-House | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Manage and service Consumer Consents |  |  | YES | 3 | FRANBELL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-15 | Complete | Blue | 2025-06-13 | 2025-01-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
54913 | FC India Architecture Research | In Development | FCINDArch | FORD CREDIT | IPANKAJ | VGA | RPARAME4 | RPARAME4 | Copper | Non S-Ox | - | No | Yes | In-House | IPANKAJ | VGA | Ford Credit Services | - | GCP Development Platform for Architects - for POC's only | 1 |  | YES | 1 | SRAISIN1 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
104 | SBOM: Service Bill of Material | In Production | SBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Web based software tool designed to help engineering community manage the service part release business in WERS |  |  | YES | 4 | RKENNEL | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
104 | SBOM: Service Bill of Material | In Production | SBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Web based software tool designed to help engineering community manage the service part release business in WERS |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
104 | SBOM: Service Bill of Material | In Production | SBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | NBAECKER | Ford Customer Service | FCSD Tech | Web based software tool designed to help engineering community manage the service part release business in WERS |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-29 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
56919 | FAFC Communication Messaging System | Planned | FAFCCMS | FORD CREDIT | JCHEN11 | CYANG63 | YFU33 | YZHU86 | Silver | Non S-Ox | 321 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | FAFC Communication Messaging System - China provides the technical resources for triggering messaging notifications to Ford Credit customers. | 1 |  | YES | 1 | SRAISIN1 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | VM
104 | SBOM: Service Bill of Material | In Production | SBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House |  |  | Ford Customer Service | FCSD Tech | Web based software tool designed to help engineering community manage the service part release business in WERS |  | Springboot | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | Q2 2026 | Version Upgrade | Modernize | 2026-06-15 | 2026-06-15 | 2025-01-31 | Complete | Blue | 2026-09-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 21 | [5 empty] | No | Java < v21
52967 | SBDO Service | In Production | SBDO | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | - | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | - | Service accessed via PTS to enable symptom based diagnostics and repair of vehicles |  | Springboot | YES | 3 | RKENNEL | PLM | Java < v21 | Q3 2026 | Version Upgrade | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
52967 | SBDO Service | In Production | SBDO | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | - | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Service accessed via PTS to enable symptom based diagnostics and repair of vehicles |  |  | YES | 3 | RKENNEL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | Decom Completed | No | SQL
13682 | FACTS: Ford And Competitor Technology System | In Production | EuVP_FACTS | ISIT | MNOWICK1 | LSRINIVA | RSTOCKTO | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | - | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | FACTS is a software which is provided and maintained by a company called A2Mac1. This will provide a central database for storage and retrieval of Ford teardown information and Ford attribute, commodity and component data including photos. | 16 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
89 | SAVE: Single Access to Vehicle | In Production | SAVE | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | AGREWAL6 | Silver | S-Ox In Scope | 221 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Comprised of six modules: Table maintenance, I/O, SOA, Service OVID, Catalog vendor daily extract processing and vehicle data mart |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
89 | SAVE: Single Access to Vehicle | In Production | SAVE | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | AGREWAL6 | Silver | S-Ox In Scope | 221 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Comprised of six modules: Table maintenance, I/O, SOA, Service OVID, Catalog vendor daily extract processing and vehicle data mart |  |  | YES | 4 | RKENNEL | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
89 | SAVE: Single Access to Vehicle | In Production | SAVE | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | AGREWAL6 | Silver | S-Ox In Scope | 221 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Comprised of six modules: Table maintenance, I/O, SOA, Service OVID, Catalog vendor daily extract processing and vehicle data mart |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
89 | SAVE: Single Access to Vehicle | In Production | SAVE | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | AGREWAL6 | Silver | S-Ox In Scope | 221 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Comprised of six modules: Table maintenance, I/O, SOA, Service OVID, Catalog vendor daily extract processing and vehicle data mart |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
51020 | Savanna Location Engine (SLE) | In Production | SLE | ISIT | VVIJAY55 | RADAM10 | PYORK | SSENTH15 | Silver | Non S-Ox | 111 | No | Yes | COTS | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Savanna Location Engine is an integrated software package. Using algorithms and rules engine it derives actionable information and business context from the location data and a common set of outputs to share with applications. Location data is captured by using hardware including sensing, tagging, and mobility technologies, as well as third-party technologies. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
22310 | FACTON - Enterprise Product Costing | In Production | FACTON EPC | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 211 | No | Yes | COTS | SFRANCI8 | AKANSKI | PD Operations and Quality | Integrated Enterprise Resource Planning (I-ERP) | Cost Estimating Application that enables cross CBG estimate comparisons. This tool will replace the legacy CAPE tool. | 22 |  | YES | 3 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
17411 | Satellite Digital Audio Radio Services | In Production | SDARS | EVDD | MJAMWAL | VVINOD3 | RDAS9 | DAMARNA3 | Bronze | Non S-Ox | 311 | No | Yes | - | MJAMWAL | VVINOD3 | Advanced PD and Tech | - | Application to manage Satellite Digital Audio Radio Services (SDARS) including but not limited to enahncements to SDARS including delivery of customer data to Sirius, implementation of new data elements and improved data analysis, and inclusion of PAG satellite radio data. |  |  | YES | 4 | MJONE308 | PLM | Java Struts | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | Java < v21
17411 | Satellite Digital Audio Radio Services | In Production | SDARS | EVDD | MJAMWAL | VVINOD3 | RDAS9 | DAMARNA3 | Bronze | Non S-Ox | 311 | No | Yes | - | MJAMWAL | MJAMWAL | Advanced PD and Tech | - | Application to manage Satellite Digital Audio Radio Services (SDARS) including but not limited to enahncements to SDARS including delivery of customer data to Sirius, implementation of new data elements and improved data analysis, and inclusion of PAG satellite radio data. |  |  | YES | 4 | MJONE308 | PLM | Oracle | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
21865 | EZ Budget Tracking System | In Production | EZB | ISIT | MNOWICK1 | LSRINIVA | ESATISH | JLUCAS1 | Copper | Non S-Ox | 211 | Yes | No | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | - | EZ Budget Tracking System for Powertrain FNA. | 5 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
17411 | Satellite Digital Audio Radio Services | In Production | SDARS | EVDD | MJAMWAL | VVINOD3 | RDAS9 | DAMARNA3 | Bronze | Non S-Ox | 311 | No | Yes | - | MJAMWAL | VVINOD3 | Advanced PD and Tech | - | Application to manage Satellite Digital Audio Radio Services (SDARS) including but not limited to enahncements to SDARS including delivery of customer data to Sirius, implementation of new data elements and improved data analysis, and inclusion of PAG satellite radio data. |  |  | YES | 4 | MJONE308 | PLM | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
24208 | SATA-DATA | In Production | SATA-DATA | ISIT | RTILLEY | GVANNOYE | GMATHOT | CWADE | Copper | Non S-Ox | 111 | Yes | No | - | RTILLEY | GVANNOYE | Advanced PD and Tech | - | SATA DATA is an Application used to manage in-vehicle software validation tests. It is used by the global Software Validation Fleet and consist of a database, a management tool (SATA DATA) and an execution tool used within the Vehicles (SATA Drive). |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
11850 | Exhaust Emissions Measurement System | In Production | EEMS | ISIT | KCHRIST2 | KCHRIST2 | JCICOTTE | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | In-House | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | The EEMS application is utilized to divert production vehicles to the APTL test facility for testing. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
186 | SAS: Sales Agreement System | In Production | SAS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | Sales agreement is an agreement that FCSD will sell specific parts and quantities to a customer at other than dealer net or discounts allowed for customer's distribution channel. |  |  | YES | 1 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
53514 | EV DevOps | In Development | EV DevOps | EVDD | RJOHN813 | SLYTLE | LKINNAIR | LKINNAIR | Bronze | Non S-Ox | - | No | Yes | - | RJOHN813 | SLYTLE | Advanced PD and Tech | - | EV DevOps Placeholder | 1 |  | YES | 2 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | VM
19139 | ETS - Engineering Translation Services | In Production | ETS | ISIT | JKOONS | NLAKSHMA | KRAJES33 | BAESCHLI | Silver | Non S-Ox | 311 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Engineering Translation Services application is used for interop between various CAD tools and TCe. Main components of ETS are 1. Translation Server Toolkit 2. ETS toolkit | 31 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
24774 | SAS RDM Middleware China | In Production | SASRDMMWCH | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | Non S-Ox | 233 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 233 | CHINA - SAS RDM MIDDLEWARE IS A WEB SERVICE APP USED TO CONVERT MAINFRAME TO WEB SERVICE TO PASS PINNACLE LOAN ORIGINATIONS TRANSACTIONS TO SAS RDM. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [16 empty] | No | Java < v21
22326 | SAS RDM Middleware | In Production | SASRDMMID | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | TSAILESH | Silver | Non S-Ox | 333 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | 333 | SAS RDM Middleware is a web service app used to convert mainframe to web service to pass Pinnacle Loan Originations transactions to SAS RDM. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [16 empty] | No | Java < v21
22326 | SAS RDM Middleware | In Production | SASRDMMID | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | TSAILESH | Silver | Non S-Ox | 333 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | SAS RDM Middleware is a web service app used to convert mainframe to web service to pass Pinnacle Loan Originations transactions to SAS RDM. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | SQL
53442 | ETR Cloud Adoption | In Development | ETRCA | EPEO | MPATIL1 | MPATIL1 | BTOY1 | STALLUR2 | Copper | Non S-Ox | - | No | Yes | Managed by 3rd Party Purchased Service | MPATIL1 | MPATIL1 | Enterprise Technology | EPEO | This application is to host GCP POC related tools to enable application assessments. | 3 |  | YES | 1 | SWALIMBE | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
13128 | Ethernet Broadcast | In Production | EBC | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Copper | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Ethernet Based Broadcast System. Utilized in broadcasting vehicle build information to plant floor operators, displays, computers, and interfaces. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [7 empty] | 4 | EDC Hypervisor | Priya | 2025-03-05 |  |  |  | No | VM
14993 | SAMIS - Sales & Marketing System | In Production | SAMIS | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | SAMIS (WA-WE-WM-MJ-WL-TV) - Sales & Marketing Systems. Main functionalities: Model catalogue admin, Order tracking, Pricing, Invoincing, Yard Control, Harbor Control. |  |  | YES | 1 | TSWEEN16 | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
22008 | Sales Production and Capacity Planning System | In Production | SPCPS | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Silver | S-Ox In Scope | 333 | No | Yes | COTS | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | Sales Production and Capacity Planning System will integrate demand and supply data to make business planning decisions. This application will replace tactical GCRS application. | 96 |  | YES | 2 | NKANDULA | PLM | Datastage | Q4 2025 |  | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | DA
12122 | Error Proofing - VO | In Production | EP - CEC | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | Yes | No | Managed by 3rd Party Purchased Service | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | In-Station process control for DC nutrunners | 22 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
52489 | Sales Exchanging Information System | In Production | SEIS | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Marketing & Sales | 211 | SEIS receives from dealers all information related to retail and delivery vehicle information. Brazil knows it as CVVG information (Carta de venda varejo e garantia) and, Argentina, Chile, Peru and Colombia as TAE. |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
52489 | Sales Exchanging Information System | In Production | SEIS | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Marketing & Sales | - | SEIS receives from dealers all information related to retail and delivery vehicle information. Brazil knows it as CVVG information (Carta de venda varejo e garantia) and, Argentina, Chile, Peru and Colombia as TAE. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | SQL
52851 | ePolicy Orchestrator | In Production | ePO | ISIT | SKING68 | KBARTHO1 | JBARGER | RPRASA22 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SKING68 | KBARTHO1 | Manufacturing Engineering | Industrial System IT | Trellix ePolicy Orchestrator (ePO) is a Centralized security Management Tool to help orchestrate and manage your endpoints. | 5 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
9959 | Sales Daily/Monthly | In Production | SLS | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Silver | S-Ox In Scope | 332 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The North American Sales Reporting system processes all North America-sourced new vehicle sales, transfers, cancellations and customer name and address change transactions supporting all North American dealers of Ford and Lincoln Mercury brands. |  |  | YES | 1 | NKANDULA | PLM | Mainframe | TBD | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11466 | Salary Timekeeping (NETSUS) | In Production | NETSUS | OCETO | TSWEEN16 | PTOCCO | LSUYAK | LWU14 | Gold | S-Ox Out of Scope | 333 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | U.S. salaried timekeeping system |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11466 | Salary Timekeeping (NETSUS) | In Production | NETSUS | OCETO | TSWEEN16 | PTOCCO | LSUYAK | LWU14 | Gold | S-Ox Out of Scope | 333 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | U.S. salaried timekeeping system |  |  | YES | 2 | TSWEEN16 | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
6304 | EPAS - European Property Accounting System | In Production | EuAS-EPAS | OCETO | TSWEEN16 | KKOEHLER | MRAUTERK | LWU14 | Copper | Non S-Ox | 131 | No | Yes | COTS | DDESAI | KKOEHLER | Finance | Staffs IT | EPAS (European Property Accouting System)is used to maintain fixed assets/special tool records in a standardized System (SAP FI/AA module). After the launch of PCAM the scope of European Property Accounting System (EPAS) had been reduced. EPAS primary serves as data repository for asset information prior to PCAM launch | 2 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
51857 | SA Vehicle Subscription | In Production | SAVS | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | 311 | South America Vehicle Subscription Platform |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
51857 | SA Vehicle Subscription | In Production | SAVS | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | South America Vehicle Subscription Platform |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | GCP Migration is completed for Database and VMs are decommissioned | No | SQL
56379 | ENTERPRISE TESTING | In Development | ENT-TEST | FORD CREDIT | IPANKAJ | VNAVEEN1 | SARAVI17 | RMANGAL | Bronze | Non S-Ox | - | No | Yes | - |  |  | Ford Credit Services | Ford Credit (FMCC) | Enterprise Testing | 1 |  | YES | 1 | SRAISIN1 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
24155 | SA Smart Mobility Data Hub | In Production | SMDH | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Integrated Services | 311 | Cloud Hub to capture Data from Smart Mobility experiments. The clients would be IOT, Mobile applications, or other sources sending data to support Fleet Management, Active Call and Enterprise Values development |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
24155 | SA Smart Mobility Data Hub | In Production | SMDH | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Integrated Services | - | Cloud Hub to capture Data from Smart Mobility experiments. The clients would be IOT, Mobile applications, or other sources sending data to support Fleet Management, Active Call and Enterprise Values development |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-08 | Complete | Blue | 2025-04-30 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | DB Migration completed | No | SQL
20388 | Enhanced Laboratory Management Systems | In Production | ELMS | ISIT | OTHERS | JLOPORTO | JNG | JLUCAS1 | Silver | Non S-Ox | 312 | Yes | No | In-House | JSHANAH1 | JLOPORTO | PD Operations and Quality | - | ELMS (Enhanced Laboratory Management System) aids in the management of work flow, test scheduling and resource allocation for a given labaoratory or support group and customers. It will be used by Powertrain labs in North America, by the VEV org in PD. This is a Non-SOX application. VEV is providing day-to-day support of the application software including training. It provides tools to assign tests to facilities and personnel, monitors facility status, and provides performance metrics, and provides access to best practices. | 14 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
14258 | Emission non-sensitive VETS 9000 | In Production | APTL VETS | ISIT | KCHRIST2 | KCHRIST2 | JCICOTTE | JLUCAS1 | Copper | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | The Vehicle Emission Test System (VETS) application is wholly developed by Horiba. The Vehicle Emission Test System (VETS) software is used to control a computerized vehicle emissions test system. It is designed to control and document tests measuring the mass of certain compounds emitted by a vehicle under controlled conditions. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
54342 | SA Payments API | In Production | SA Payment | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NMORALE7 | Gold | S-Ox In Scope | 331 | No | Yes | In-House | #N/A | #N/A | Finance | 331 | SA PAYMENTS IS AN API INITIATIVE TO MAKE EASIER TO IMPLEMENT PAYMENTS INTO FORD SOLUTIONS. |  | Springboot | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
13194 | Electronic Powertrain Program Planning | In Production | e3P | ISIT | MNOWICK1 | LSRINIVA | ESATISH | JLUCAS1 | Bronze | Non S-Ox | 311 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | e3P (Electronic Powertrain Program Planning) is a web-based application for authoring, approval and documentation of Powertrain engineering assumptions and related documents. The Assumption module is used for the authoring, approval and documentation of engineering assumption needed to support Powertrain programs. The 5 Panel module is used for the authoring and documentation of 5 Panel sheets needed to support Powertrain programs. The PTBOM (Powertrain Bill of Material) module is an easy to use tool to view and compare different BOMs (WERS, CMMS and CAD). It also enables the users to manage the Complexity Matrix and audit the Bill of Material. e3P is therefore the central repository of engineering assumptions and CPMT 5 Panel sheets. These are accessible via the Ford internal web with access control. Engineering assumptions are Ford proprietary and 5 Panel are Ford confidential information. | 3 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52801 | SA Invoicing | In Production | SAI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | 211 | South America Invoicing application |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
52801 | SA Invoicing | In Production | SAI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | South America Invoicing application |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | SQL | [5 empty] | No | SQL
13541 | EESE ELECTRICAL DATA MANAGEMENT | In Production | EESEDATA | ISIT | OTHERS | KBERISTA | JPAWLOSK | GRAO3 | Copper | Non S-Ox | 111 | Yes | No | In-House | CPAPADOM | KBERISTA | Advanced PD and Tech | - | management of electrical BOM data. Includes Web interface to existing electrical databases (UniBOM). | 7 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
23330 | SA Fleet Control System | In Production | Fleec | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Customer Service | - | Manage company fleet vehicle processes : order placement and tracking, documentation, release, maintenance, fines and rental payment, fuel consumption, incidents and sale. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | SQL
12418 | eDB: Electronic Document Base | In Production | EuFA-eDB | I-ERP | SFRANCI8 | AKANSKI | RDAVIES6 | LWU14 | Silver | Non S-Ox | 11 | No | Yes | In-House | SFRANCI8 | AKANSKI | Enterprise Technology | Integrated Enterprise Resource Planning (I-ERP) | eDB is a J-EE based program that runs in WAS Liberty on CAAS. It connects to an Oracle database where it stores application screen definitions, application role based security data and application database connection credentials (Passwords Encrypted). eDB is accessed via web browser. eDB hosts several applications, whereby the users of each application visits the EDB website, plus two URL parameters, Site ID and Screen No. eDB retrieves the requested screen definition from its database using these parameters, and in conjunction with the users CDS ID, dynamically renders the appropriate application screen. The screen will include controls that retrieve application data from the applications database (eDB database does not contain any business data). | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
23330 | SA Fleet Control System | In Production | Fleec | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Customer Service | - | Manage company fleet vehicle processes : order placement and tracking, documentation, release, maintenance, fines and rental payment, fuel consumption, incidents and sale. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
21275 | SA FCSD Executive Dashboard | In Production | FEDB | OCETO | DBRIGHEN | DBRIGHEN | RLOPES3 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Ford Customer Service | - | South America dashboard for FCSD as a bridge solution to the Global FCSD dashboard (UDB/e-React). The regional dashboard is to cover key metrics for FCSD area (Service, PS&L, Marketing). |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q3 2026 | Modernize to Cloud Databases | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
50765 | eCommerce Marketplace Portal | In Production | EMP | M&S TECH | RKLEINSM | MMILBOC1 | TKOPCZY1 | MPINRED1 | Bronze | Non S-Ox | 222 | No | Yes | Managed by 3rd Party Purchased Service | RKLEINSM | MMILBOC1 | Marketing & Sales | Marketing, Sales and Service | eCommerce Marketplace Portal supports Ford's eCommerce program by facilitating delear onboarding and eCommerce order management | 4 |  | YES | 3 | NKANDULA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21275 | SA FCSD Executive Dashboard | In Production | FEDB | OCETO | DBRIGHEN | DBRIGHEN | RLOPES3 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Ford Customer Service | - | South America dashboard for FCSD as a bridge solution to the Global FCSD dashboard (UDB/e-React). The regional dashboard is to cover key metrics for FCSD area (Service, PS&L, Marketing). |  |  | YES | 3 | TSWEEN16 | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
51355 | SA Dev Enablement Hub | In Production | SA API HUB | OCETO | DBRIGHEN | NMORALE7 | RMARQU65 | NMORALE7 | Copper | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Enterprise Technology | 111 | SA DEV ENABLEMENT HUB IS A SET OF COMMON TOOLS AND APIS TO ENABLE SOUTH AMERICA TEAM TO BOOST PRODUCTIVITY WHEN DEVELOPING NEW SOLUTIONS. THIS SET OF TOOLS IS AN ENABLER TO MOVE FROM LEGACY SYSTEMS AND INTEROPERABILITY MODELS TO LATEST STANDARDS |  | Springboot | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
53224 | SA Credit Limit app | In Production | SACIM | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NMORALE7 | Gold | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | 221 | South America application to whosale financing control |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
53224 | SA Credit Limit app | In Production | SACIM | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NMORALE7 | Gold | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | South America application to whosale financing control |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q2 2026 | Modernize to Cloud Databases | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
21254 | eCATS Centralized Reporting & Data Repository | In Production | eCATS-RL | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 221 | Yes | No | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | eCATS is vend-suppt. sys used by veh.assy plants to program/config/check/record the ECUs in each vehicle & test the veh.fns those ECUs ctrl. Has ReportLogiq(RL) web-reporting, but also feeds corp.sys's for supporting/by vehs in service. Prod.process uses per-plant config of plant floor stns & local plant file/app.svr. Latter acts as receiver of stns' veh.results +/- a distrib&archive of veh.build-specs fr. other systems that steer eCATS stns' veh.procs. Plant hosting aids prod.process resilience. RL & corp.feeds hosted on svrs often at Dearborn unless WAN-perf. &/ JV-rules dictate regional / plant-located. eCATS 2.0 into some plants 2016+ brings unmanned 'Mini' stns for more progr. of ECUs, initially only upstream of existing eCATS areas. W/o user interf. for oper/maint, mgmt of Minis uses plant-based web/service fn AdminLogiq(AL). NB: eCATS often called End-Of-Line - but term neither limited to eCATS nor role. ECU progr. also called flashing - but InPlant Flash is name of NA-only sys w different technol | 59 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
17370 | RULES | In Production | RULES | EPEO | SKULKA52 | CGIACOBB | VMANDELL | GSIENKIE | Copper | S-Ox In Scope | 121 | No | Yes | In-House |  |  | Enterprise Technology | EPEO | Generates passwords to restricted ids, allows users to check out the accounts. Alerts id owners that passwords have been generated. Regenerates passwords on checkin - for selected environments. |  | MF - WAS Liberty | YES | 1 | SWALIMBE | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
9976 | RTOM : Real Time Order Management System | In Production | RTOM | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | RTOM is a web/mainframe system that allocates vehicle and commodity production volumes from the market level to dealer level and produces Vehicle and Commodity Wholesale Guides for North American Dealers. |  |  | YES | 5 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
9976 | RTOM : Real Time Order Management System | In Production | RTOM | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | RTOM is a web/mainframe system that allocates vehicle and commodity production volumes from the market level to dealer level and produces Vehicle and Commodity Wholesale Guides for North American Dealers. |  |  | YES | 5 | NKANDULA | PLM | Mainframe | Q4 2026 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9976 | RTOM : Real Time Order Management System | In Production | RTOM | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | RTOM is a web/mainframe system that allocates vehicle and commodity production volumes from the market level to dealer level and produces Vehicle and Commodity Wholesale Guides for North American Dealers. |  |  | YES | 5 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
9976 | RTOM : Real Time Order Management System | In Production | RTOM | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | RTOM is a web/mainframe system that allocates vehicle and commodity production volumes from the market level to dealer level and produces Vehicle and Commodity Wholesale Guides for North American Dealers. |  |  | YES | 5 | NKANDULA | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
20811 | ECAD - Zuken E3 | In Production | ECAD E3 | ISIT | MNOWICK1 | PBORGAO1 | IAKLEH | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | Application for ECAD - Zuken E3 Project (19057)Zuken E3 is a complete and open CAD solution for design and documentation of electrical and automation systems. It also includes integrated logic-oriented functionality for the creation of cabling and harnesses. Zuken E3 is based upon common component database and symbol libraries and ensures a unique representation of all elements of the circuit diagrams, to produce accurate and error-free documentation. It also allows for creation of block diagrams, under logic control, that provide an overview of all electrical and electronic elements. Connections between functional modules can be achieved using individual conductors, shielded or twisted cables or bundled cables. | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
21558 | RSW - Resource Staffing & Workload Hyperion | In Production | RSWHYP | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | SBONNICI | SBONNICI | PD Operations and Quality | Industrial System IT | RSW [Resource, Staffing and Workload] Hyperion is an internally hosted web application that supports common business practices / collaboration as a single source of information ensuring the right resources, at the right time (increasing resource utilization), integration of estimation models into a resource management solution and proactively detect, avoid cost overruns, and budget reconciliation to manage workload and program resources globally. | 942 |  | YES | 5 | BWUNNAVA | PLM | Datastage | Q3 2026 |  | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-11-15 |  | Planned |  | No | [14 empty] | No | DA
21558 | RSW - Resource Staffing & Workload Hyperion | In Production | RSWHYP | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | SBONNICI | SBONNICI | Enterprise Technology | Industrial System IT | RSW [Resource, Staffing and Workload] Hyperion is an internally hosted web application that supports common business practices / collaboration as a single source of information ensuring the right resources, at the right time (increasing resource utilization), integration of estimation models into a resource management solution and proactively detect, avoid cost overruns, and budget reconciliation to manage workload and program resources globally. |  |  | YES | 5 | BWUNNAVA | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
21558 | RSW - Resource Staffing & Workload Hyperion | In Production | RSWHYP | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | SBONNICI | SBONNICI | PD Operations and Quality | Industrial System IT | RSW [Resource, Staffing and Workload] Hyperion is an internally hosted web application that supports common business practices / collaboration as a single source of information ensuring the right resources, at the right time (increasing resource utilization), integration of estimation models into a resource management solution and proactively detect, avoid cost overruns, and budget reconciliation to manage workload and program resources globally. |  |  | YES | 5 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50994 | Dynetics EOL CADET Electrical Test System | In Production | EOL Sys | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Silver | Non S-Ox | 112 | Yes | No | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | - | Dynetics EOL CADET Electrical Test System is a specialized application intended to allow for vehicle ECU programming, configuration, diagnostics, and other functional tests. It utilizes an HMI, custom PC-oriented hardware and software, CAN communications, digital I/O, and network communications to facilitate testing, generate test results, and providing reporting | 5 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
21558 | RSW - Resource Staffing & Workload Hyperion | In Production | RSWHYP | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | SBONNICI | SBONNICI | PD Operations and Quality | Industrial System IT | RSW [Resource, Staffing and Workload] Hyperion is an internally hosted web application that supports common business practices / collaboration as a single source of information ensuring the right resources, at the right time (increasing resource utilization), integration of estimation models into a resource management solution and proactively detect, avoid cost overruns, and budget reconciliation to manage workload and program resources globally. |  |  | YES | 5 | BWUNNAVA | PLM | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23174 | RSA Archer GRC Platform | In Production | ArcherGRC | EPEO | NOKEEFE | NOKEEFE | VVENKA40 | WJUSTICE | Silver | Non S-Ox | 322 | No | Yes | COTS | UARJUNAN | NOKEEFE | Enterprise Technology | EPEO | The RSA Archer GRC application for Cyber Defense Center (CDC) for Case Management. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
51710 | Dynamic Central | In Production | DYNCEN | ISIT | AMEHER1 | ADURSO | RHOPKIN4 | RPRASA22 | Bronze | Non S-Ox | 111 | No | Yes | COTS | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Centrally managed application that pushes images to Displaydata displays, it can receive data from external sources through either an API-driven or data-driven interface. It tracks update success, display temperature, and battery life for displays. it also tracks displays tied to dynamic communicators for each location. | 30 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
51356 | DYNA Santorin AVL Puma | In Production | DYNA AVL | ISIT | OTHERS | JLOPORTO | JQUOZIEN | JLUCAS1 | Bronze | Non S-Ox | 122 | Yes | No | Managed by 3rd Party Purchased Service | JLOPORTO | RDANES1 | PD Operations and Quality | - | Compehensive test cell environement aquisition software | 7 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
57190 | RS&W PLANISWARE / OPERATING PLAN | In Production | RSWPLW | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Silver | Non S-Ox | 332 | No | Yes | COTS | SBONNICI | SBONNICI | PD Operations and Quality | - | RS&W Planisware / Operating Plan [Resource, Staffing and Workload] is an internally hosted web application that supports common business practices / collaboration as a single source of information ensuring the right resources, at the right time (increasing resource utilization), integration of estimation models into a resource management solution and proactively detect, avoid cost overruns, and budget reconciliation to manage workload and program resources globally. |  |  | YES | 2 | BWUNNAVA | PLM | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
54544 | Risk Scoring Origination NA | In Production | RiskNA | FORD CREDIT | JMALETZ | PBALUSU | JMADDEN5 | JMANI | Silver | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 322 | FCNA - FUNCTIONALITY INCLUDES THE SCORING PIECE OF THE ORIGINATION SYSTEMS. BUSINESS CRITICALITY HIGH. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | Java < v21
23040 | Risk Scoring Analysis | In Production | RSA | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | Risk Scoring Analysis for GLO China |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
54156 | RICOH Data Transformation Layer | In Production | RDTL | FORD CREDIT | PTABOR5 | VSUNDA21 | VSANGEE6 | ROBRIEN3 | Silver | Non S-Ox | 211 | No | Yes | In-House | PTABOR5 | IPANKAJ | Ford Credit Services | Ford Credit (FMCC) | Suite of Ford Credit APIs used to transform data into and from Ricoh. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
16385 | RFQ - REQUEST FOR QUOTATION | In Production | RFQ | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Supply Chain | - | RFQ Request for Quotation. Application controls requests for suppliers quotation. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
52120 | Driver Score | In Production | DSAPI | EVDD | RJOHN813 | GNANDURI | DSING103 | GNANDURI | Bronze | Non S-Ox | 211 | No | Yes | In-House | SSURYAN3 | GNANDURI | Integrated Services | Enterprise Connectivity - PDO | Develop a consistent, reliable scoring methodology to rate a driver's performance based on telematics data | 3 |  | YES | 3 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
16385 | RFQ - REQUEST FOR QUOTATION | In Production | RFQ | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Supply Chain | - | RFQ Request for Quotation. Application controls requests for suppliers quotation. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
18861 | Reval | In Production | Reval | I-ERP | SFRANCI8 | DSAKAMUR | KMOHAN15 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | Managed by 3rd Party Purchased Service | SFRANCI8 | DSAKAMUR | Finance | Integrated Enterprise Resource Planning (I-ERP) | Externally hosted application (Application Service Provider model) to be used for effectiveness testing and hedge accounting for FAS 133. Application contains debt, derivative, foreign exchange and commodity data from Wall Street Suite. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
11838 | Disputed Excess Transportation Charges | In Production | DETC | ISIT | VVIJAY55 | RADAM10 | PYORK | SSENTH15 | Copper | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | The DETC system uses data from Cass Premium processing and user input to assist the MP&L personnel with resolving supplier disputes regarding premium freight charges. Outside suppliers have limited access to read-only functions of the system. Application is build in Unix , Perl , Shell scripting & Oracle | 6 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23863 | Retirement Data Archive (Open Text) | In Production | RDA | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Copper | Non S-Ox | 311 | Yes | No | Managed by 3rd Party Purchased Service | DDESAI | NMUTHUK2 | Human Resources | - | Data Archive Application. Internally hosted vendor application to store historical retirement records |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
54846 | Dimensional Planning & Validation | Planned | DPV | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | - | Yes | No | COTS | OTHERS | #N/A | Advanced PD and Tech | - | Tecnomatix Dimensional Planning and Validation (DPV) helps to collect, manage, dimensionally analyze, and report the quality measurement information. It is a quality management solution that can integrate into Teamcenter environment. | 11 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
53807 | Retail Network Information Bridge | Planned | RNIB | M&S TECH | NKANDULA | JLEWIS10 | TMCKEE2 | JHARPER2 | - | Non S-Ox | - | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | Data processing asset used to bridge information between the retail network transactional systems and the Dealer Franchising Portal (DFP) | 0 |  | YES | 3 | NKANDULA | PLM | Datastage | Q3 2025 | Migrate to CP4D | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | DA
53807 | Retail Network Information Bridge | Planned | RNIB | M&S TECH | NKANDULA | JLEWIS10 | TMCKEE2 | JHARPER2 | - | Non S-Ox | - | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | Data processing asset used to bridge information between the retail network transactional systems and the Dealer Franchising Portal (DFP) |  |  | YES | 3 | NKANDULA | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | SQL
53891 | Digital Thread Platform | In Production | DTP | ISIT | JKOONS | NLAKSHMA | CCHADA | BAESCHLI | Silver | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | - | Digital Thread is a complete Digitalization and Integration across the work streams: Product Design, Suppliers, Plants, and Vehicle, and Customers, with single authoritative source of truth for all content in any given program. | 25 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
9079 | Retail Identification Program/Sign Ordering System | In Production | RIP/SOS | M&S TECH | NKANDULA | JLEWIS10 | KMICHALE | JHARPER2 | Silver | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Retail Identification Program Sign Ordering System (RIP/SOS) is the control system for all company approved exterior signs at franchised Ford and Lincoln dealerships within U.S. under the Retail identification Program. The group responsible for administering this program is the Retail Identification Activity (RIA). The RIA consists of one Ford Manager and his staff located in Dearborn with additional non-Ford Order Administrators located at the Sign Vendors. The Ford RIA is responsible for maintaining the SOS database of orderable sign models and associated pricing. The Vendors will be responsible for Order management and fulfilment. The Web platform allows for the partnering of Ford with the Sign Vendors to improve the process of timely completion Dealer Sign Orders. |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q4 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9079 | Retail Identification Program/Sign Ordering System | In Production | RIP/SOS | M&S TECH | NKANDULA | JLEWIS10 | KMICHALE | JHARPER2 | Silver | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Retail Identification Program Sign Ordering System (RIP/SOS) is the control system for all company approved exterior signs at franchised Ford and Lincoln dealerships within U.S. under the Retail identification Program. The group responsible for administering this program is the Retail Identification Activity (RIA). The RIA consists of one Ford Manager and his staff located in Dearborn with additional non-Ford Order Administrators located at the Sign Vendors. The Ford RIA is responsible for maintaining the SOS database of orderable sign models and associated pricing. The Vendors will be responsible for Order management and fulfilment. The Web platform allows for the partnering of Ford with the Sign Vendors to improve the process of timely completion Dealer Sign Orders. |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
9079 | Retail Identification Program/Sign Ordering System | In Production | RIP/SOS | M&S TECH | NKANDULA | JLEWIS10 | KMICHALE | JHARPER2 | Silver | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Retail Identification Program Sign Ordering System (RIP/SOS) is the control system for all company approved exterior signs at franchised Ford and Lincoln dealerships within U.S. under the Retail identification Program. The group responsible for administering this program is the Retail Identification Activity (RIA). The RIA consists of one Ford Manager and his staff located in Dearborn with additional non-Ford Order Administrators located at the Sign Vendors. The Ford RIA is responsible for maintaining the SOS database of orderable sign models and associated pricing. The Vendors will be responsible for Order management and fulfilment. The Web platform allows for the partnering of Ford with the Sign Vendors to improve the process of timely completion Dealer Sign Orders. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
20687 | Diesel Software Development Environment | In Production | DSWDE | EVDD | FFRISCHM | JDADAJ | LHATFIEL | GRAO3 | Silver | Non S-Ox | 222 | Yes | No | COTS | FFRISCHM | SCIBULAS | Advanced PD and Tech | - | The Diesel Software Development Environment comprises: an Accurev configuration management server to manage Engine management software, a build server to develop software releases and a Web server to support AccuRev Web Interface. | 28 |  | YES | 1 | MJONE308 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
9079 | Retail Identification Program/Sign Ordering System | In Production | RIP/SOS | M&S TECH | NKANDULA | JLEWIS10 | KMICHALE | JHARPER2 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Customer Experience | Marketing, Sales and Service | Retail Identification Program Sign Ordering System (RIP/SOS) is the control system for all company approved exterior signs at franchised Ford and Lincoln dealerships within U.S. under the Retail identification Program. The group responsible for administering this program is the Retail Identification Activity (RIA). The RIA consists of one Ford Manager and his staff located in Dearborn with additional non-Ford Order Administrators located at the Sign Vendors. The Ford RIA is responsible for maintaining the SOS database of orderable sign models and associated pricing. The Vendors will be responsible for Order management and fulfilment. The Web platform allows for the partnering of Ford with the Sign Vendors to improve the process of timely completion Dealer Sign Orders. |  | Springboot | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
20510 | Retail and Lease Securitization | In Production | GSRLS | FORD CREDIT | DTAURO | SKHAN29 | HMANDA | VPOTTIBO | Silver | S-Ox In Scope | 233 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Retail and Lease securitization, a key funding source for Ford Credit, is an application to create and service asset-backed securities for retail and lease accounts in China, EU, and NA. It is an application developed in-house and supported by Ford Credit IT. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20510 | Retail and Lease Securitization | In Production | GSRLS | FORD CREDIT | DTAURO | SKHAN29 | HMANDA | VPOTTIBO | Silver | S-Ox In Scope | 233 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Retail and Lease securitization, a key funding source for Ford Credit, is an application to create and service asset-backed securities for retail and lease accounts in China, EU, and NA. It is an application developed in-house and supported by Ford Credit IT. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
51140 | DevOps Command Center | In Production | DCC | EVDD | JREYN149 | NFAGEN | TARUNAC1 | STANIKEL | Copper | Non S-Ox | 111 | No | Yes | In-House | JREYN149 | TCARMEAN | Advanced PD and Tech | Enterprise Connectivity - PDO | Portal For System Tool Access | 2 |  | YES | 2 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
52938 | Restricted Party Screening System | In Production | REPSSYS | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | DDESAI | KADOMKAI | Policy | 322 | *Privileged and Confidential* Replace current Restricted Party Screening (RPS) system - Accuity mainframe system implemented in 2004 - to mitigate significant legal, business and reputational risk of doing business with a restricted or prohibited party. New system is needed to meet regulatory guidelines for compliance and effective screening and to broaden screening capabilities throughout Ford globally in various skill teams, organizations and regions. Risk if not funded includes significant regulatory penalties, risk to future corporate funding, and reputational harm. |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | PDO planning to migrate for java 21 by Q2 | No | Java < v21
52938 | Restricted Party Screening System | In Production | REPSSYS | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | DDESAI | KADOMKAI | Policy | Staffs IT | *Privileged and Confidential* Replace current Restricted Party Screening (RPS) system - Accuity mainframe system implemented in 2004 - to mitigate significant legal, business and reputational risk of doing business with a restricted or prohibited party. New system is needed to meet regulatory guidelines for compliance and effective screening and to broaden screening capabilities throughout Ford globally in various skill teams, organizations and regions. Risk if not funded includes significant regulatory penalties, risk to future corporate funding, and reputational harm. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
57002 | Detailed Risk Assessment Report Application | Planned | DRA Report | OCETO | PMILLIGA | FWANG38 | DWEITZMO | DWEITZMO | Copper | Non S-Ox | - | Yes | No | In-House | PMILLIGA | FWANG38 | Enterprise Technology | Technology & Enterprise Services (TES) | This application is used to create visualizations from Enterprise Archer GRC Detailed Risk Assessment. In order to support Management awareness and approval process for Detailed Risk Assessments. | 4 |  | YES | 2 | PMILLIGA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
15863 | Resource Management Group-RMG | In Production | RMG | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Copper | Non S-Ox | 311 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | RMG receives receivable systems determinant values (from various receivable systems and MAPS) and actual headcount information from payroll and then calculations Authorized/Allocated headcount for branches, service centers, and central office. Personnel cost data is passed to the Op Cost system. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
642 | Resident Engr. Defects and Concerns Rpting Sys | In Production | REDCRS | ISIT | SKING68 | KBARTHO1 | LMEENAKS | RPRASA22 | Copper | Non S-Ox | 211 | No | Yes | In-House | SKING68 | SKING68 | PD Operations and Quality | Industrial System IT | Used by Powertrain resident engineers at Assenbly plants around the world to report problems and concerns about powertrain products to the manufacturing PTO plant |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
23931 | Dealer Marketing Platform (ex-UACE) | In Production | DMP | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | COTS | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | New campaign engine for unified customer contacts in FCSD and potential REACT replacement. The application uses the Adobe Marketing cloud, specifically Adobe Campaign and Adobe Analytics premium. | 4 |  | YES | 4 | NKANDULA | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
13362 | Dealer Information Systems Net Enabled | In Production | DISNE | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | DISNE (Dealer Information System InterNet Enabled) is the database of record for Dealer, Commercial and Specialty Product information. Information stored in DISNE is used by various Ford Credit applications, Ford Motor Company systems and vended applications primarily to facilitate processing of wholesale, retail, lease, dealer loan business and Commercial Line Of Credit. There are also numerous downstream systems that use DISNE data for a variety of reasons including risk analysis, marketing programs, Salesforce and MAPS reporting. | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
12960 | Research Library Information Systems | In Production | RLIS | EVDD | JDEMAIO | JDEMAIO | LKUDLA1 | JLUCAS1 | Copper | Non S-Ox | 211 | Yes | No | In-House | MJONE308 | JDEMAIO | Advanced PD and Tech | - | Research Library Information Systems Welcome website To search the site, enter your query in the search box at right. To search library materials, click Library Catalog (or click Library Catalog at the top of every RLIS web page) |  |  | YES | 2 | MJONE308 | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
13223 | Repository for Diagnostic And Module Configuration | In Production | RDS | FORD PRO & FCSD TECH | OTHERS | KCLARK4 | BSWANSO3 | DFARNIN | Silver | Non S-Ox | 11 | Yes | No | In-House | KDORONY | KCLARK4 | Ford Customer Service | - | Repository for diagnostic and module configuration and programming data used for support of IDS and associated diagnostic and service tools. RDS Exporter is a client app. that interfaces with the RDS SQL database. Exporter uses SQL stored procedures & Local processing to create a proprietary runtime database that is released with each update. & also database update. (DIF) files released |  |  | YES | 2 | RKENNEL | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
53359 | Dealer Franchising Portal | In Development | DFP | M&S TECH | NKANDULA | JLEWIS10 | CVOGLER1 | JHARPER2 | Silver | Non S-Ox | 333 | No | Yes | COTS | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | DFP is used by the US Market Representation Team, including the regional and market area teams, franchising, representation planning, business management and retail operations to receive and process dealer change requests (aka transactions), manage/create/update dealer contracts, and track the progress of those requests through the different approval and signature chains. The final contract documents produced by the system will be stored and available internally in a document repository within the application. The application will allow Dealers to engage with Ford, upload necessary documentation, and sign the contracts electronically within the application. The system tracks all changes and it allows the team to monitor obligations and standards compliance, and provides metrics to support reporting and planning. The platform is a no code platform that allows custom configurations and scalability to other teams and processes to provide an holistic view of Dealer Information. | 9 |  | YES | 2 | NKANDULA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
13399 | Repo Website | In Production | Repo | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RPARAME4 | Bronze | Non S-Ox | 222 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Internet Website that Ford Financial Repossession Contractors use to enter account information and interface with the Repossession Workflow |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [16 empty] | No | Java < v21
12684 | Remotely Accessed Parts Info System IP | In Production | RAPID IP | FORD PRO & FCSD TECH | CHURLEY3 | FTUERCK | ABUCHHOL | MMEHTA5 | Silver | Non S-Ox | 212 | No | Yes | In-House | AHOFFM15 | FTUERCK | Ford Customer Service | - | Provide IP communications to the RAPID online parts ordering system. The user community includes European dealers, Export dealers, some suppliers & Ford Users. External access will be via Public Internet using SSL. |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Decommission |  |  |  | Complete |  |  |  | Complete |  | No | [8 empty] | Decommission |  |  |  |  | In EAMS as well in Servicenow its already decomissioned. | No | Mainframe - DB2
12684 | Remotely Accessed Parts Info System IP | In Production | RAPID IP | FORD PRO & FCSD TECH | CHURLEY3 | FTUERCK | ABUCHHOL | MMEHTA5 | Silver | Non S-Ox | 212 | No | Yes | In-House | AHOFFM15 | FTUERCK | Ford Customer Service | - | Provide IP communications to the RAPID online parts ordering system. The user community includes European dealers, Export dealers, some suppliers & Ford Users. External access will be via Public Internet using SSL. |  |  | YES | 2 | RKENNEL | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Complete |  |  |  | Complete |  | No | [8 empty] | Decommission |  |  |  |  | In EAMS as well in Servicenow its already decomissioned. | No | Mainframe
52532 | Remote Start Limiter | In Production | RSL | EVDD | JWASNIC1 | JVEDANAY | MMOYAL | PKALIYAP | Gold | Non S-Ox | 122 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 122 | KEEPS TRACK OF THE NUMBER OF REMOTE STARTS EXECUTED BY A GIVEN VEHICLE SO THAT REMOTE START COMMANDS ARE BLOCKED BY THE CLOUD LAYER (TMC/MCG) WHEN NEEDED. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | Java < v21
53050 | Remote Services FI | In Production | RSFI | EVDD | JWASNIC1 | JVEDANAY | MMOYAL | PKALIYAP | Gold | Non S-Ox | 222 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 222 | REMOTE SERVICES FI HOUSES THE BUSINESS LOGIC FOR PREP MY VEHICLE FEATURES, INCLUDING REMOTE CLIMATE CONTROL. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | Java < v21
53921 | Remitos Digitales | In Development | REMI | ISIT | OTHERS | JBERGONZ | DYLLA | MPELLEG9 | Gold | Non S-Ox | 211 | Yes | No | In-House | APEREZ12 | JBERGONZ | Manufacturing Plants | - | Digitalizacion de sistema de remitos |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
21504 | DDVPM Data Management | In Production | DDVPM-DM | ISIT | SBONNICI | SBONNICI | ABANSA15 | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SBONNICI | SBONNICI | Enterprise Technology | Industrial System IT | Application to store and manage digital appearance assets captured from physical materials using appearance capture devices. Also has provision to capture metadata about the verification status of the captured material . Acronym meaning: Design Digital Validation of Physical Material. | 9 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
50552 | Relativity | In Production | Relativity | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | Non S-Ox | 321 | No | Yes | COTS | DDESAI | KADOMKAI | Policy | Staffs IT | Relativity contains the latest in advanced searching, analytics, machine learning and visualizations built into the application and is utilized by the majority of law firms and eDiscovery vendors used by OGC Litigation team. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
50701 | Data Aggregator | In Production | DataAg | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | Data Aggregator is a Java batch application and it updates Salesforce.com with DISNE and EDW data on a daily basis. | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
51181 | Regulatory User Interface | In Production | RegUI | FORD CREDIT | IPANKAJ | PSRIKIR1 | RMRINAL2 | NKALE | Bronze | Non S-Ox | 323 | No | Yes | Open Source | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | FCE Regulatory User Interface is utility to enter data that is not available in the source for FCE regulatory and liquidity monitoring & reporting |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
50588 | Cycletool | In Production | Cycletool | ISIT | JKOONS | MNOVAK1 | HLIN11 | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | Cycletool is application to populate and screen data and displays report for vehicle energy management engineering. | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
51181 | Regulatory User Interface | In Production | RegUI | FORD CREDIT | IPANKAJ | PSRIKIR1 | RMRINAL2 | NKALE | Bronze | Non S-Ox | 323 | No | Yes | Open Source |  |  | Ford Credit Services | Ford Credit (FMCC) | FCE Regulatory User Interface is utility to enter data that is not available in the source for FCE regulatory and liquidity monitoring & reporting |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | Java < v21
18111 | REGISTRY (VOPISO) | In Production | Registry | ISIT | JDEGUZMA | RMEHTA3 | RJAMBUNA | ISIDDIQ6 | Silver | Non S-Ox | 111 | No | Yes | In-House | JDEGUZMA | RMEHTA3 | PD Operations and Quality | Industrial System IT | Registry is a WEB-based system to publish the required quality management system documentation in line with the general system requirements of the ISO 9001 for Global Business use. All necessary information can be stored and provided to all Business Units & departments affected. The Registry provides each department the possibility to create its own Master Document List (MDL), one of the five pillars of the quality management system. This application was migrated to IT Compliant infrastructure on 20-May-2014. Formerly known as VOPISO = Vehicle Operations Manufacturing Engineering ISO Homepage. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
18111 | REGISTRY (VOPISO) | In Production | Registry | ISIT | JDEGUZMA | RMEHTA3 | RJAMBUNA | ISIDDIQ6 | Silver | Non S-Ox | 111 | No | Yes | In-House | JDEGUZMA | RMEHTA3 | PD Operations and Quality | Industrial System IT | Registry is a WEB-based system to publish the required quality management system documentation in line with the general system requirements of the ISO 9001 for Global Business use. All necessary information can be stored and provided to all Business Units & departments affected. The Registry provides each department the possibility to create its own Master Document List (MDL), one of the five pillars of the quality management system. This application was migrated to IT Compliant infrastructure on 20-May-2014. Formerly known as VOPISO = Vehicle Operations Manufacturing Engineering ISO Homepage. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
54112 | CX-Hub | In Production | CX-HUB | M&S TECH | RAHMED33 | DPOOVATH | AROSS76 | MSCHOLT3 | Silver | Non S-Ox | 222 | No | Yes | COTS |  |  | Customer Experience | Marketing, Sales and Service | Assist Customer - CX-Hub is a solution that includes Microsoft Dynamics 365 as the core CRM used for Case Management, and integrates with several Azure services (blob storage, Azure SQL, Cognitive Services, etc.) and multiple internal applications (SAVE-IO, SCA-C, etc.) as well as various third-party applications (BBB, Agero Roadside Assistance, etc.) | 8 |  | YES | 1 | NKANDULA | PLM | VM | TBD | Complete Migration to SaaS | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
50453 | CV Integration Data and Device Management | In Production | CVDDM | EVDD | NDIMMITT | DCHAMB77 | SCUNNIN8 | SCUNNIN8 | Copper | Non S-Ox | 111 | No | Yes | In-House | NDIMMITT | DCHAMB77 | Advanced PD and Tech | - | This system provides Data Management service, Device Management service, Data Validation Service and Health Checkup for Test Data Setup Core systems in lower environment | 2 |  | YES | 3 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
23474 | CV Business and Operations Portal | In Production | CVBOP | EVDD | JWASNIC1 | ACHRIS39 | VMARIUCC | JBENNER6 | Gold | Non S-Ox | 322 | No | Yes | In-House | JWASNIC1 | ACHRIS39 | Advanced PD and Tech | - | Connected Vehicle Portal and Dashboard will act as a common platform to configure vehicles (via RDR, CARMON, PARSED, FOTA Etc.) for vehicle diagnostic/rich vehicle data collection at vehicle and individual module level via common APIs. view Data and Reports / Dashboard / Feature KPIs / advanced analytics. Querying any vehicle record to address vehicle operations issues. | 5 |  | YES | 3 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
51913 | REDIRECT SERVICES | In Production | RS | M&S TECH | RKLEINSM | RKLEINSM | KPONNUSW | JPOTTE60 | Copper | Non S-Ox | 12 | No | Yes | In-House | RKLEINSM | RKLEINSM | Enterprise Technology | Marketing, Sales and Service | Redirects vanity urls to point to ford.com etc. |  |  | YES | 2 | NKANDULA | PLM | WAS | Q1 2026 | Version Upgrade | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
52850 | CRM for Third Party Enablement | In Production | TPE CRM | EVDD | JWASNIC1 | RBUITEWE | ABIANC15 | WESTES6 | Silver | Non S-Ox | 111 | No | Yes | COTS | JWASNIC1 | RBUITEWE | Advanced PD and Tech | - | The Developer Marketplace team in Model e use MS Dynamics 365 solutions to manage the activities related to User management, Marketing, Sales (Lead and Account) management and Case management. This application as global CRM system helps to coordinate customer partnerships, people, processes and technologies to render the ultimate mobility customer experience. | 2 |  | YES | 2 | MJONE308 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
12348 | Recognition and Anniversary Award (Engage2Excel) | In Production | Empl Award | OCETO | TSWEEN16 | NABBAS | ALAVANY3 | MBALAN2 | Copper | Non S-Ox | 311 | Yes | No | Managed by 3rd Party Purchased Service | DDESAI | NABBAS | Human Resources | - | External, purchased services to administer the Corporate Reward & Recognition Program. Also includes processing on the Ford IT side to receive taxation informatio on the awards and provide to Payroll/HRIMS system for processing. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
51553 | Recall Investigative VIN Attribute tool | In Production | RIVAT | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | KAMIT4 | SDHANAS2 | Gold | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | RIVAT is an accounting (Tracking and Monitoring) database and Information Review Tool for the accounting and completion of Takata Airbag recalls as per NHTSA guidelines. The tool will be used to identify, control and maintain supplemental vehicle and owner data obtained from designated internal and external sources and vendors. Application has integration like smtp | 610 |  | YES | 4 | RKENNEL | PLM | Datastage | Q4 2024 |  | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | DA
51553 | Recall Investigative VIN Attribute tool | In Production | RIVAT | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | KAMIT4 | SDHANAS2 | Gold | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | RIVAT is an accounting (Tracking and Monitoring) database and Information Review Tool for the accounting and completion of Takata Airbag recalls as per NHTSA guidelines. The tool will be used to identify, control and maintain supplemental vehicle and owner data obtained from designated internal and external sources and vendors. Application has integration like smtp |  |  | YES | 4 | RKENNEL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | Already decommisioned due to migration on SaaS | No | SQL
22161 | Crash Designer 2.9.1 | In Production | CLCD | ISIT | JPITTERL | MZIRWES1 | RKAREN | JLUCAS1 | Bronze | Non S-Ox | 211 | Yes | No | In-House | CBOHN | MZIRWES1 | PD Operations and Quality | Industrial System IT | Crash Designer is a software application for data acquisition purpose in crash testing from vendor Kistler. It is separated in two parts. The first part is management of test equipment (sensors and measurement devices) and preparation of test sequences. The second part manages the execution of tests and provides measurement results in various formats. | 9 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
51553 | Recall Investigative VIN Attribute tool | In Production | RIVAT | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | KAMIT4 | SDHANAS2 | Gold | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | RIVAT is an accounting (Tracking and Monitoring) database and Information Review Tool for the accounting and completion of Takata Airbag recalls as per NHTSA guidelines. The tool will be used to identify, control and maintain supplemental vehicle and owner data obtained from designated internal and external sources and vendors. Application has integration like smtp |  |  | YES | 4 | RKENNEL | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-29 | 2025-01-31 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | Already decommisioned due to migration on SaaS | No | Java < v21
483 | CPV Consensus | In Production | CPV | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | Forecasts rates for different vehicle options before Job #1. | 8 |  | YES | 1 | NKANDULA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
12739 | React Retail Event Analysis & Customer Targeting | In Production | REACT | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | REACT! is the aftermarket CRM tool providing Ford with internal and dealer business analysis feature and pro-active customer contact (PACC) facility. Collects Invoice Data from Dealers for Management / Dealer Reports and Proactiv Customer Contact | 1324 |  | YES | 2 | NKANDULA | PLM | Datastage | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
12739 | React Retail Event Analysis & Customer Targeting | In Production | REACT | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SBAILE17 | SBAILE17 | Marketing & Sales | Marketing, Sales and Service | REACT! is the aftermarket CRM tool providing Ford with internal and dealer business analysis feature and pro-active customer contact (PACC) facility. Collects Invoice Data from Dealers for Management / Dealer Reports and Proactiv Customer Contact |  |  | YES | 2 | NKANDULA | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
51052 | RE&T Ford Lincoln Dealer Product Info AEM Tenant | In Production | eSB Tenant | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Copper | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | 211 | Product information repository and workflow validation tool. The application will also enable publishing of product information to Ford and Lincoln sales consultants, sales managers, etc. The 'Next Gen' platform will replace the current Ford eSourceBook and Lincoln Mercury ProductPortfolio websites. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-25 | 2025-03-15 | Complete | Blue | 2025-06-23 | 2025-03-15 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
51052 | RE&T Ford Lincoln Dealer Product Info AEM Tenant | In Production | eSB Tenant | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Copper | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Product information repository and workflow validation tool. The application will also enable publishing of product information to Ford and Lincoln sales consultants, sales managers, etc. The 'Next Gen' platform will replace the current Ford eSourceBook and Lincoln Mercury ProductPortfolio websites. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-03-12 | Complete | Blue | 2025-06-13 | 2025-03-12 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | SQL
20162 | Cost Reduction Idea Database 2 | In Production | CRID2 | ISIT | MNOWICK1 | LSRINIVA | RSTOCKTO | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | A system for managing cost-reducing ideas for current model vehicles. First version will target design ideas on current-model vehicles (0-18 months) | 7 |  | YES | 4 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  | 2025-03-12 | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22338 | RAPTOR | In Production | RAPTOR | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | JMANI | Bronze | Non S-Ox | 221 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit pricing platform for New and Used US Standard Retail rates. It delivers pricing rates to the PARMS application. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
22338 | RAPTOR | In Production | RAPTOR | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | JMANI | Bronze | Non S-Ox | 221 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit pricing platform for New and Used US Standard Retail rates. It delivers pricing rates to the PARMS application. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53463 | Cost Analysis | In Production | COSTSCAN | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | RSRINI38 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | - | DPA project to perform parts price comparison | 3 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
22338 | RAPTOR | In Production | RAPTOR | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | JMANI | Bronze | Non S-Ox | 221 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit pricing platform for New and Used US Standard Retail rates. It delivers pricing rates to the PARMS application. |  |  | YES | 4 | SRAISIN1 | PLM | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | Java < v21
14545 | Rapid Referrals | In Production | RAPID | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | Emergency backorders are sent to OE Connection for dealer inventory fill. Note: This process has been re-branded as 'D2D Express'. Set to In Production 1/22/08 by Andrea Pruitt per Christina Schulz. |  |  | YES | 1 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
53590 | Rapid Embedded Deployment | In Production | RED | EVDD | AGARBY | FGRABOWS | MSHEIKBA | JMONTICE | Bronze | Non S-Ox | 223 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 223 | IDENTIFIES A TARGET VEHICLES SOFTWARE AND TRIGGERS THE DEPLOYMENT OF UPDATED SOFTWARE TO THAT VEHICLE. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | Java < v21
226 | Rail Car Tracking | In Production | TRRIPS | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Silver | Non S-Ox | 112 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | TRRIPS. Tracks railcar shipment involving Ford location and enables Ford and it suppliers to efficiently manage rail shipment between facilities. / Old Acronym : RCT |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-03-31 |  | Planned | REQ0097769, REQ0052434, REQ000007857752, REQ000006144415, REQ0116265, REQ0116265, INC1034751 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Priya | 2025-03-04 |  |  | App on target for Decommission. Validation in progress. Tickets for DB Decommission, Stop running Jobs, Remove RACF profile, request for Mainframe Billing consulting raised by PDO | No | Mainframe
54374 | RACF Password Reset | In Production | RPWR | EPEO | SKULKA52 | CGIACOBB | VMANDELL | GSIENKIE | Gold | Non S-Ox | 331 | No | Yes | In-House |  |  | Enterprise Technology | EPEO | RACF Password Reset will be an external facing application which will provide all users of the Ford Mainframe a common entry point for managing the password for their RACF ID. |  | MF - WAS Liberty | YES | 1 | SWALIMBE | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | Java < v21
24524 | Quick Lane Canada Dealer Applications Website | In Production | FOCQL | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Ford Customer Service | Marketing, Sales and Service | Dealer Facing Quick Lane co-op automation tool to help manage and track co-op payments related to Quick Lane Sales and Marketing. |  |  | YES | 3 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
24524 | Quick Lane Canada Dealer Applications Website | In Production | FOCQL | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Ford Customer Service | Marketing, Sales and Service | Dealer Facing Quick Lane co-op automation tool to help manage and track co-op payments related to Quick Lane Sales and Marketing. |  |  | YES | 3 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q2 2026 | Modernize to Cloud Databases | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
21555 | Corporate knowledge Wiki | In Production | CKW | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JKOONS | NLAKSHMA | Quality | Industrial System IT | Wiki based on Confluence-(Atlassian-vendor). Designed to store corporate knowledge using the power of Wiki. Initially to store Quality Procedures and allow organic growth across the company. | 7 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
12894 | QualityWorX | In Production | QWX | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Enterprise Technology | Industrial System IT | In partnership with Manufacturing Engineering, provide IT leadership in support of Sciemetric Meters and QualityWorX installations (former Shadow IT applications). Sciemetric installations utilize signature capture and analysis to provide product testing during assembly. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
24129 | Confluence (EESEWiki) | In Production | EESEWiki | EVDD | JREYN149 | JREYN149 | MCHATTE1 | VVEINOTT | Copper | Non S-Ox | 311 | Yes | No | COTS | MJONE308 | JREYN149 | Advanced PD and Tech | - | Confluence is the current tool used for collaboration for EC projects. It is a rich wiki environment that supports creating pages, blog posts, questions, diagrams etc. | 9 |  | YES | 2 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [16 empty] | No | VM
11414 | Quality Reject Version II (QR 2) | In Production | QR2 | ISIT | SKING68 | KBARTHO1 | LMEENAKS | RPRASA22 | Silver | Non S-Ox | 211 | No | Yes | In-House | SKING68 | KBARTHO1 | PD Operations and Quality | Industrial System IT | QR2 enables plants to capture rejected parts (including cause, qty, etc.), escalate the quality problems to Purchasing STA & suppliers, and recoup rework costs from suppliers. Data sent to SIM (Supplier Information Metrics) is used to calculate supplier Q1 rating. Also known as Quality Reporting or Material Quality System. |  |  | YES | 2 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11414 | Quality Reject Version II (QR 2) | In Production | QR2 | ISIT | SKING68 | KBARTHO1 | LMEENAKS | RPRASA22 | Silver | Non S-Ox | 211 | No | Yes | In-House | SKING68 | KBARTHO1 | PD Operations and Quality | Industrial System IT | QR2 enables plants to capture rejected parts (including cause, qty, etc.), escalate the quality problems to Purchasing STA & suppliers, and recoup rework costs from suppliers. Data sent to SIM (Supplier Information Metrics) is used to calculate supplier Q1 rating. Also known as Quality Reporting or Material Quality System. | 7 |  | YES | 2 | BWUNNAVA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11440 | QUALITY LEADERSHIP SYSTEM - VEHICLE OPERATIONS | In Production | QLS-VO | ISIT | SKING68 | KBARTHO1 | STOREY | RPRASA22 | Copper | Non S-Ox | 121 | No | Yes | In-House | SKING68 | KBARTHO1 | PD Operations and Quality | Industrial System IT | Quality Leadership System - Vehicle Operations is an application that provides the Assembly Plants with an electronic way to manage their quality data on units manufactured at the plant. The system is highly configurable in allowing the plants to specify what actions/processes occur in what location for various units being built. With this enviornment, it allows the plant to use the electronic, real time data to evaulate current quality processes, evaluate warranty data on units already produced, determine if a unit should be released (i.e. Gate Released) and shipped with respect to Quality, provide valuable data to several plant and corporate Six Sigma projects, provide data for Work Groups and VRT's for evaluating their processes etc. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
11440 | QUALITY LEADERSHIP SYSTEM - VEHICLE OPERATIONS | In Production | QLS-VO | ISIT | SKING68 | KBARTHO1 | STOREY | RPRASA22 | Copper | Non S-Ox | 121 | No | Yes | In-House | SKING68 | SKING68 | PD Operations and Quality | Industrial System IT | Quality Leadership System - Vehicle Operations is an application that provides the Assembly Plants with an electronic way to manage their quality data on units manufactured at the plant. The system is highly configurable in allowing the plants to specify what actions/processes occur in what location for various units being built. With this enviornment, it allows the plant to use the electronic, real time data to evaulate current quality processes, evaluate warranty data on units already produced, determine if a unit should be released (i.e. Gate Released) and shipped with respect to Quality, provide valuable data to several plant and corporate Six Sigma projects, provide data for Work Groups and VRT's for evaluating their processes etc. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
251 | Component Data Collection II (Traceability) | In Production | CDC-II | ISIT | SKING68 | KBARTHO1 | LMEENAKS | RPRASA22 | Copper | Non S-Ox | 121 | No | Yes | In-House | SKING68 | KBARTHO1 | Enterprise Technology | Industrial System IT | Traceability of component serial numbers and the VIN of the vehicle in which the components were installed. Current components traced include front and side air bags, engines, transmissions, keycodes, fuel tanks, and tires. | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
11439 | Quality Leadership System - Component Mfg | In Production | QLS-CM | ISIT | SKING68 | KBARTHO1 | CLUND1 | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | QLS-CM performs automatic quality and as-build data collection as well as a full suite of traceabilty options. QLS-CM also performs schedule creation using the Hiejenken (TPS) method of leveled scheduling via EPLUS interface), schedule execution, transponder management and a Quarantine system that interfaces with plant floor controls to isolate and prevent installation of suspect parts. QLS-CM also includes repair/concern data management. For 6F program, Tranmission solenoid characteristics (TSC) are stored from Bosch and used to compare with supplier product. Finished TSC data is then sent to ECATS, CDC II, and FCSD systems. Repair data collection, and reporting are now available. Symbol WIndows CE app added to provide real time quarantine checks. Interface to upload serialized components to TRACE system is now available. Added in 2012 is replace for message broker communications infrustructure using web services and XML messaging. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
11439 | Quality Leadership System - Component Mfg | In Production | QLS-CM | ISIT | SKING68 | KBARTHO1 | CLUND1 | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | SKING68 | KBARTHO1 | Manufacturing Engineering | Industrial System IT | QLS-CM performs automatic quality and as-build data collection as well as a full suite of traceabilty options. QLS-CM also performs schedule creation using the Hiejenken (TPS) method of leveled scheduling via EPLUS interface), schedule execution, transponder management and a Quarantine system that interfaces with plant floor controls to isolate and prevent installation of suspect parts. QLS-CM also includes repair/concern data management. For 6F program, Tranmission solenoid characteristics (TSC) are stored from Bosch and used to compare with supplier product. Finished TSC data is then sent to ECATS, CDC II, and FCSD systems. Repair data collection, and reporting are now available. Symbol WIndows CE app added to provide real time quarantine checks. Interface to upload serialized components to TRACE system is now available. Added in 2012 is replace for message broker communications infrustructure using web services and XML messaging. |  |  | YES | 3 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
50092 | Compliance Accounting and Reporting Environment | In Production | CARE | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Bronze | Non S-Ox | 232 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | - | ICS, RAPS, PS GL GAPS and ERES delivers monthly data feeds to this tool. CARE was developed during an external German customs audit and is part of the GDIA database. This project is to transform the existing CARE tool to have automated feeds from source applications, create Data integration layer, IT compliant and scalable solution, which could be launched to GDIA Production environment and will be supported by IT team | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
50993 | Quality Early Detection | In Production | QED | GDIA | KLIDDLE | BJOHNS69 | SSOMISET | KZUREK | Bronze | Non S-Ox | 111 | No | Yes | In-House | KLIDDLE | PJOVANO4 | Enterprise Technology | 111 | QED is a recommendation system to provide guidance with respect to the cause of quality issues, e.g. feature, manufacturing, supplier, geographic & design |  | Springboot | NO | 2 | FRANBELL | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50993 | Quality Early Detection | In Production | QED | GDIA | KLIDDLE | BJOHNS69 | SSOMISET | KZUREK | Bronze | Non S-Ox | 111 | No | Yes | In-House | KLIDDLE | PJOVANO4 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | QED is a recommendation system to provide guidance with respect to the cause of quality issues, e.g. feature, manufacturing, supplier, geographic & design |  |  | NO | 2 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
19519 | Quality Center ALM | In Production | QC ALM | FORD CREDIT | JMALETZ | SHE1 | KBALAS30 | SGURU8 | Bronze | Non S-Ox | 111 | No | Yes | COTS | JMALETZ | NVENKAT2 | Enterprise Technology | - | Micro Focus ALM/Quality Center is a comprehensive, unified, flexible and extensible application lifecycle management product. It provides the teams with visibility across all enterprise projects and the complete application lifecycle. It establishes consistent, repeatable processes for managing requirements, tests, and business components, effectively increasing speed, improving quality and reducing cost. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q2 2026 | Modernize to Cloud Databases | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned | [17 empty] | SQL
22365 | Company Vehicle Inventory | In Production | CVIS | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Finance | Marketing, Sales and Service | Application used by Company Vehicle Headquarters, Human Resources, Company Vehicle Reps, and Financial Services to administer all aspects of company-use vehicle inventory. | 12 |  | YES | 1 | NKANDULA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11770 | Quality Analysis and Reporting System | In Production | QARSPD | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Silver | Non S-Ox | 221 | No | Yes | COTS | JDEGUZMA | JDEGUZMA | Quality | Industrial System IT | Quality Analysis and Reporting Systems (QARS) provide web based Quality Analysis capability; and standardized Quality Reporting for PD, VO organizations (Common Metrics). The Quality Analysis Data Cubes provide real-time, web-based analytical functions, using a common interface for Warranty, Market Research and other data. The analyst interacts with the Data Cubes directly, allowing continuity of thought during the analysis process, as well as permitting 'What if?' questions to be answered immediately. Warranty analysis can be performed on data from North America, Europe, Australia and Mazda (Thailand), and Market Research information is available for North America and Europe. Primary Users: Analysts in Quality, Engineering, Finance, Market Research, 6-Sigma Black Belts, Vehicle Operations and Powertrain Plants. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
565 | Common Security Interface | In Production | CSI | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 222 | No | Yes | In-House | SKING68 | KRAMESH | Manufacturing Staffs | - | Common Security Interface (CSI)- for Plant Floor Systems. Provides for a single User ID & Password to use all plant applications integrated into utilizing CSI Authentication and Authorization APIs and screens. Allows the plant security administrator one User Profile administration application for all applications integrated into utilizing CSI User Ids. | 43 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned | [16 empty] | No | VM
15288 | QRM - Quantitative Risk Management | In Production | QRM | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | S-Ox In Scope | 231 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | The QRM application is a vended application that Ford Treasury Risk Management analysts use to assess Ford Credit's risk exposure. Risk Management analysts use QRM to assess the Company's interest rate risk, profit volatility and to calculate market values for all on- and off-balance sheet instruments. In Ford Treasury and Ford Credit Finance use QRM to forecast the Company's borrowing cost. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
14874 | CMMS3 Datamart | In Production | CMMS DMR | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Datamart for CMMS that is refreshed daily from selected CMMS3 tables. Users/applications connect directly to Datamart to obtain data/generate reports. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
15477 | Capture-IT | In Production | Capture-IT | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Copper | Non S-Ox | 211 | Yes | No | In-House | SARAUJO3 | CBISWADI | Supply Chain | - | STA owned application containing stop ship and field action information - high level only for reporting to SIM as supplier responsible. | 3 |  | YES | 1 | TSWEEN16 | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
56855 | Capital Harness Systems for CE1 | In Development | CHS | ISIT | MNOWICK1 | PBORGAO1 | IAKLEH | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | - | Siemens COST application used by Electic CAD CE1 engineers to design wire harnesses | 6 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
24095 | QPR (Quality System and Supplier Documents) | In Production | QPR | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Bronze | Non S-Ox | 111 | Yes | No | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Application used by suppliers and purchasing STA team to view user guides and reference material |  |  | YES | 2 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
20355 | QNET | In Production | QNET | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | Q-Net is an reporting tool developed by Quantum Information Systems, Inc. used to provide ad-hoc reporting capability to users of all levels of expertise. The web-based tool allows users to create a web-based report containing data from one or more data sources of various types within a site or spanning multiple sites. It is currently installed in Powertrain plants in North America and Europe |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
52460 | CAE specific data analysis with splunk | In Production | CAESDAWS | ISIT | JKOONS | MNOVAK1 | HBOYSEN | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | In-House | JPITTERL | CBOHN | Enterprise Technology | Industrial System IT | CAE specific data analysis with splunk | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | Partial Migration to GCP | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
56984 | Cadence Orcad PCB | In Development | Cadence | ISIT | MNOWICK1 | PBORGAO1 | IAKLEH | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | - | Design and build Printed Circuit Boards (PCBs) used by the Global eDrive Systems team. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
53997 | Qlik Replicate | In Production | GDIA-Repl | GDIA | CPELTZE1 | ASANKA30 | CRAJAGHA | RPOLLO13 | Bronze | Non S-Ox | 111 | No | Yes | COTS | CPELTZE1 | SS348 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Data Replication Application for Data Factory |  |  | YES | 2 | FRANBELL | PLM | SQL | Q1 2027 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-12-15 |  | In-Progress | Green | 2027-01-15 |  | Planned |  | No | [14 empty] | No | SQL
23002 | CAD Release Information System | In Production | CADRIS | ISIT | MNOWICK1 | LSRINIVA | HKUMAR7 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | CAD Release Information System would store Parts claim data which would be used by other applications to view, update Part information during its release progression. In the context of a vehicle program CAD Supervisors, CAD Lead, CAD Designers would have the capability to claim parts, update claimed parts, transfer claimed parts , update Causal Factors , CAD Remarks along with other comments related to release statuses which would be stored in the CAD Release Information System. | 5 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11756 | C3P-NG(NG) | Active | NG | ISIT | JKOONS | NLAKSHMA | CCHADA | GRAO3 | Silver | Non S-Ox | - | No | Yes | - | SBONNICI | KRAMMOHA | Advanced PD and Tech | - | C3P NG is a program that delivers the next level of digital product capabilities for all brand partners in Ford Motor Company, to effectively conduct enterprise-wide vehicle and technology product creation. Ford moved to C3P NG to achieve efficiencies in Product Creation that will enable it to bring products to market faster by (a)Moving to a central CAD solution (b)Negotiating Not to Exceed pricing for C3P NG tools (c)Providing Visualization access. This ITMS is used as a financial holding for operating expenses of a variety of applications in the C3P suite | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
21808 | QAD Archival Tool | In Production | QAT | I-ERP | SFRANCI8 | RJAYAKU2 | RSRIRA18 | LWU14 | Silver | Non S-Ox | 311 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | - | Application to store, view and create reports of QAD data.This application will hold QAD data post QAD Exit. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q2 2027 | Modernize to Cloud Databases | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | SQL
13868 | C3P Central Authentication System | In Production | CCAS | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | 111 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | C3P Central Authentication System is the user authentication wrapper aroud TcEng. CCAS forces login to TcEng to go through the WSL authentication before access to TcEng is allowed. CCAS is developed as a generic function to be used for future C3P tools that do not meet Ford password strength requirements. | 16 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
51597 | Business Intelligence for Global Cost | Planned | BIGC | ISIT | OTHERS | MSTOECKL | MFRANIA1 | MQAZI1 | Bronze | Non S-Ox | - | Yes | No | In-House | BGUBING | MSTOECKL | Manufacturing Engineering | - | BMIT Database for BI data around the Global Cost processes. | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
18038 | Purchasing Technology Services | In Production | TSP | I-ERP | SARAUJO3 | CBISWADI | TSUNDARA | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | #N/A | #N/A | Supply Chain | - | Purchasing Technology Services is a shared web service bundle application for Purchasing. It includes following services. 1. Purchasing Document Service 2. Purchasing Security Service 3. Purchasing Reporting It feeds Web Quote and CMBP applications. |  |  | YES | 1 | TSWEEN16 | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
18286 | Purchasing Quality Security System | In Production | PQS | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | It provides request for user access, work flow approvals and AAR for Purchasing Quality Applications. |  |  | YES | 1 | TSWEEN16 | PLM | Oracle | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-04-15 |  | In-Progress | Green | 2025-07-14 |  | Planned |  | No | [8 empty] | Decommission | Praveen | 2025-03-06 |  |  |  | No | Oracle
20848 | Purchasing Portfolio Services (Web Service Bundle) | In Production | PPS | I-ERP | SARAUJO3 | CBISWADI | TSUNDARA | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | #N/A | #N/A | Supply Chain | - | Collection of reusable web services created by Purchasing applications used by multiple applications across Purchasing 1. Purchasing Notification Service 2. GSDB Service 3. Attachment Service |  |  | YES | 1 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 75% | 100% | 75% | 75% | 50% | 50% | 100% |  | Cloud Run | Praveen | 2025-03-06 |  |  |  | No | Java < v21
18531 | Purchasing Datahub (PUB) | In Production | PUB | I-ERP | SARAUJO3 | CBISWADI | JBAJI | CWADE | Bronze | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | PUB is a data warehouse for global Purchasing data. It is the repository for all historical data, facilitating analytical queries/reporting needs. The aim of PUB is to consolidate functionality and data of many disparate strategic solutions into one place. Goals: 1 - Provide analytical capabilities/reporting across all Purchasing functions 2 - Support interfaces where appropriate to reduce transactional load on source systems 3 - Interconnect with other enterprise wide analytical layers 4 - Provide security and controls in line with ITPM/GIS 5 - Provide framework to allow for expansion in line with the ability of the source systems 6 - Promote reusable nature for extracting/manipulating/loading information to analytical/reporting environment 7 - Use the Purchasing Logical Object Model. PUB has two parts: 1) Data warehouse for current/historical data 2) ODS (Operation Data Store) for current data to support transactional applications. | 2532 |  | YES | 2 | TSWEEN16 | PLM | Datastage | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | DA
18531 | Purchasing Datahub (PUB) | In Production | PUB | I-ERP | SARAUJO3 | CBISWADI | JBAJI | CWADE | Bronze | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | PUB is a data warehouse for global Purchasing data. It is the repository for all historical data, facilitating analytical queries/reporting needs. The aim of PUB is to consolidate functionality and data of many disparate strategic solutions into one place. Goals: 1 - Provide analytical capabilities/reporting across all Purchasing functions 2 - Support interfaces where appropriate to reduce transactional load on source systems 3 - Interconnect with other enterprise wide analytical layers 4 - Provide security and controls in line with ITPM/GIS 5 - Provide framework to allow for expansion in line with the ability of the source systems 6 - Promote reusable nature for extracting/manipulating/loading information to analytical/reporting environment 7 - Use the Purchasing Logical Object Model. PUB has two parts: 1) Data warehouse for current/historical data 2) ODS (Operation Data Store) for current data to support transactional applications. | 599 |  | YES | 2 | TSWEEN16 | PLM | WebFocus | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
15978 | PURCHASING ANNUAL ACCESS REVIEW SYSTEM | In Production | PAARS | I-ERP | SARAUJO3 | CBISWADI | TSUNDARA | SNAG1 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SARAUJO3 | SARAUJO3 | Supply Chain | - | Purchasing Annual Access Review System |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  | 1900-03-30 |  | Planned |  | No | [14 empty] | No | Oracle
20891 | Business Intelligence for Digital Innovation App | In Development | BIDI | ISIT | MNOWICK1 | LSRINIVA | RSTOCKTO | JMATHEWS | Copper | Non S-Ox | 211 | Yes | No | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | - | Not really an application. A placeholder for non-Prod data studies supporting Business Intelligence for DI | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
15978 | PURCHASING ANNUAL ACCESS REVIEW SYSTEM | In Production | PAARS | I-ERP | SARAUJO3 | CBISWADI | TSUNDARA | SNAG1 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | - | Purchasing Annual Access Review System |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  | 1900-03-30 |  | Planned |  | No | [14 empty] | No | Java < v21
17992 | PUR - Purchasing Datawarehouse | In Production | PUR | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Supply Chain | - | Database with Purchase information that is used by Purchasing staff to get information and compose some business report. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
51592 | BrakeLab Connect | In Production | BLC | ISIT | OTHERS | KESTIEV1 | HOBERKIR | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | In-House | MMAILE1 | KESTIEV1 | PD Operations and Quality | Industrial System IT | The system manages Brake Lab Processes i.e. Warehousing test parts, Dynometer Configuration File Management, Reporting. | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22265 | Brake Analysis and Calculation Info System | In Production | BASIC | ISIT | OTHERS | BAESCHLI | GRAO3 | GRAO3 | Bronze | Non S-Ox | 122 | Yes | No | In-House | LLANE10 | BAESCHLI | Advanced PD and Tech | Industrial System IT | Chassis Engineering has developed a new Matlab based application to replace the currently in use Excel sheets with Makros to simulate, calculate and analyse new break systems. NAS Site: \\FMC9040181\ola2_beamng_prod8337 Group: ESA\USWF-NAS-ola2_beamng_prod8337 | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24451 | Public Wifi Self-Help Tool | In Production | PWSHT | EPEO | MCRNKOVI | SSOLTANI | SSASINOW | ASALOWI1 | Copper | Non S-Ox | 121 | No | Yes | In-House | MCRNKOVI | SSOLTANI | Enterprise Technology | EPEO | This is a web-based tool which allows public wifi users the capability to reset their public wifi passwords. |  |  | YES | 2 | SWALIMBE | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
14648 | PTO Manufacturing Engineering Home Page | In Production | MEWEB | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Bronze | Non S-Ox | 111 | Yes | No | In-House | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | The Main PTO Manufacturing Engineering (ME) Web page. This Web site encompasses all the non-dynamic web sites within the global ME organization. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
14648 | PTO Manufacturing Engineering Home Page | In Production | MEWEB | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Bronze | Non S-Ox | 111 | Yes | No | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | The Main PTO Manufacturing Engineering (ME) Web page. This Web site encompasses all the non-dynamic web sites within the global ME organization. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
56133 | BoC AMR - ABB | Planned | AMR-ABB | ISIT | AMEHER1 | ADURSO | MBIJI | RPRASA22 | Silver | Non S-Ox | - | Yes | No | COTS | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | ABB AMR (Autonomous Mobile Robot) (similar to AGV) deployment at Blue Oval City Body Shop to handle all material transportation to workstations. | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
492 | PTO Focus Reporting | In Production | PTO Focus | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 211 | No | Yes | In-House | SKING68 | KRAMESH | Finance | - | Various PTO Focus reports. This application is for the Power Train Controller's Office user. PTO Focus application gathers data from Corporate Systems Applications-AIS, CCAPS, CPARS, PCPAS, TWOS and CMMS. Major functions include: tracking Mfg expense, CMMS Scrap reporting, CMMS Mfg Analysis, CCAPS Mfg Cost Analysis, CPARS Mfg Cost Reporting, Plant Project Status reporting. | 31 |  | YES | 1 | BWUNNAVA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
23910 | PTO Calibration Complexity Matrix | In Production | CCM | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Copper | Non S-Ox | 233 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | 233 | Calibration Complexity matrix is a Ford Internal application, to convert the retrieved buildable combination for each power pack from PDO into Calibration Complexity Matrix with the required fields that drives a calibration. CCM applications involves two major group: PTIM Powertrain Integration and Project Management and PCCN Powertrain Controls, Calibration and NVH . The current CCMs are created on excel sheet and shared with group via SharePoint, which makes hard to track. Now CCM will be located in one central database, and approvals will be secured, electronic and stored in database to ensure greater consistency. CCM application also helps in maintaining a standard matrix to record and sort the calibrations for each power pack. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23910 | PTO Calibration Complexity Matrix | In Production | CCM | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Copper | Non S-Ox | 233 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | Calibration Complexity matrix is a Ford Internal application, to convert the retrieved buildable combination for each power pack from PDO into Calibration Complexity Matrix with the required fields that drives a calibration. CCM applications involves two major group: PTIM Powertrain Integration and Project Management and PCCN Powertrain Controls, Calibration and NVH . The current CCMs are created on excel sheet and shared with group via SharePoint, which makes hard to track. Now CCM will be located in one central database, and approvals will be secured, electronic and stored in database to ensure greater consistency. CCM application also helps in maintaining a standard matrix to record and sort the calibrations for each power pack. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
24235 | BMC IT Connect SmartIT | In Production | ITConnect | EPEO | RHAMMO57 | JGIES | SMAYO6 | GSIENKIE | Silver | Non S-Ox | 223 | No | Yes | COTS | RHAMMO57 | JGIES | Enterprise Technology | EPEO | Ford's IT ticketing system, including the customer user interface (IT Connect), and the IT support team user interface (SmartIT). This is a COTS application from the vendor BMC. | 8 |  | YES | 1 | SWALIMBE | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
15258 | PTO - Outbound Logistics | In Production | PTOOBL | ISIT | SKING68 | KBARTHO1 | LMEENAKS | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | Application and infrastructure to provide engine and transmission traceability from the end of line to final customer destination. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
19836 | Bill of Material Foundation | In Production | BOMF | ISIT | MNOWICK1 | LSRINIVA | VATMAKUR | LPATIL | Silver | Non S-Ox | 211 | No | Yes | - | MNOWICK1 | LSRINIVA | Advanced PD and Tech | - | This application is expected to become the BOM Foundation database within Ford Motor Company; it is part of the BOM Convergence & Transformaton project. It is initially expected to replace AVBOM starting in 2009 and serve as the kernel for a BOM Foundation platform. BOM Foundation is a repository for BOM & Part data and includes a set of web services to the Process Driven BOM (PDB) tool in a way that allows the AVBOM application to no longer be necessary. BOM Foundation establishes a robust, scalable platform that will enable future unification of BOM and Parts databases from other Ford applications (e.g., WERS, CMMS3). | 5 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50781 | PTNVH Process Tools | In Production | PTNVH-TRS | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | In House process software to manage business process and run estimation tools. |  |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
21040 | Battery Cell Innovation Lab | In Production | BCIL | ISIT | KCHRIST2 | KCHRIST2 | JCICOTTE | JLUCAS1 | Silver | Non S-Ox | 211 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | Provide a comprehensive test environment for battery cell technology. Arrays of Battery Cycling Instruments and Test Cells have been installed to accommodate testing battery cell packaging ranging from single cells to multi-cell pack configurations. These testing instruments are capable of performing thermally controlled and automated test procedures, defined by test engineers. Test configuration, data capture, and data storage/data management is being supplied by a comprehensive AVL software solution. This software solution employs a client-server model architecture, where the client side will be a supplied and configured by AVL, and the server side component will be provisioned and managed by Ford IT residing in the corporate data center. | 7 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
50781 | PTNVH Process Tools | In Production | PTNVH-TRS | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Bronze | Non S-Ox | 111 | no | No | In-House |  |  | PD Operations and Quality | Industrial System IT | In House process software to manage business process and run estimation tools. |  | Springboot | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
54148 | AW and Indexing | In Production | AWINDEX | ISIT | JKOONS | NLAKSHMA | KRAJES33 | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | - | Active Workspace is an user interface for an improved Teamcenter user experience. | 63 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
22560 | PT Prototype Lifecycle System | In Production | PTPLS | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Gold | Non S-Ox | 311 | No | Yes | In-House | JKOONS | MNOVAK1 | Enterprise Technology | 311 | The Powertrain Prototype Lifecycle application will capture and record powertrain prototype test data. Eliminate Engineers manually tracking down engine test results in different locations. Data/Results Electronically Available Immediately for Engineers to Review. Electronically Track Engines and Parts. Making The Process of Inputting Data More Time Efficient and Accurate (i.e. e-inspection). Linking Engineering, BDTC, EMDO, and DYNO. |  | Springboot | YES | 2 | BWUNNAVA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
22560 | PT Prototype Lifecycle System | In Production | PTPLS | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Gold | Non S-Ox | 311 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | The Powertrain Prototype Lifecycle application will capture and record powertrain prototype test data. Eliminate Engineers manually tracking down engine test results in different locations. Data/Results Electronically Available Immediately for Engineers to Review. Electronically Track Engines and Parts. Making The Process of Inputting Data More Time Efficient and Accurate (i.e. e-inspection). Linking Engineering, BDTC, EMDO, and DYNO. |  |  | YES | 2 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
54513 | AutoHitch_DAT_AIML_Pipeline | In Development | AH_DAT_PL | EVDD | OTHERS | DROGAN4 | SSHAR137 | VKOSURI | Silver | Non S-Ox | - | No | Yes | In-House | JSHAW52 | DROGAN4 | Advanced PD and Tech | - | An MLOps pipeline to automate AI/ML model development and training | 1 |  | YES | 1 | MJONE308 | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | VM
13096 | ATS - Automated Test System | In Production | ATS App | M&S TECH | OTHERS | JSTRIEGE | KSHRABLE | JHARPER2 | Bronze | Non S-Ox | 111 | Yes | No | Managed by 3rd Party Purchased Service | AVIETOR | JJACO146 | Marketing & Sales | Marketing, Sales and Service | A purchased package for storing and distributing test modules. | 9 |  | YES | 2 | NKANDULA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
50888 | ArchDev | In Development | ArchDev | OCETO | PMILLIGA | CSMYTH5 | WMYLES4 | WMYLES4 | Bronze | Non S-Ox | 11 | No | Yes | - | DZAJAC8 | CSMYTH5 | Enterprise Technology | - | Product Description Ver 0.1 - Enterprise API/App Central aggregates enterprise data leveraging hour glass architecture with the intent of automating all business operations within 'SOA framework' constrained by 'API Strategy', 'Moving at Speed of Business', and 'Platform Enablement' as its chief design principals | 3 |  | YES | 1 | PMILLIGA | PLM | VM | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
16525 | PS&L Info Center | In Production | PSLIC | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | Provides environment for business users to perform adhoc FOCUS queries against extracts of operational data. | 22 |  | YES | 3 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
16525 | PS&L Info Center | In Production | PSLIC | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Provides environment for business users to perform adhoc FOCUS queries against extracts of operational data. |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q4 2025 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
16525 | PS&L Info Center | In Production | PSLIC | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Provides environment for business users to perform adhoc FOCUS queries against extracts of operational data. |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
53526 | ArcGIS Enterprise | Planned | ArcGIS | OCETO | TSWEEN16 | KADOMKAI | DSTONE46 | ESTILESK | Copper | Non S-Ox | - | No | Yes | COTS | DDESAI | KADOMKAI | Marketing & Sales | - | ArcGIS provides contextual tools for mapping and spatial reasoning so you can explore data and share location based insights | 5 |  | YES | 1 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
9982 | APA TH EAGLE | In Production | EAGLE | I-ERP | SFRANCI8 | - | CSUTHANA | NCHAIHUA | Silver | Non S-Ox | 311 | Yes | No | COTS | PCHANTAK | BBUNYANO | Finance | - | System for Time Attendance, Payroll, ePayslip, PA on client, website, mobile app for AAT JV employee. | 2 |  | YES | 1 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
12926 | APA AU Total Vehicle Database (TVDB) | In Production | TVDB | ISIT | SBONNICI | KTONG1 | JAGATI | PSATISH2 | Copper | Non S-Ox | 211 | Yes | No | In-House | SBONNICI | KTONG1 | Marketing & Sales | - | SQL database containing retail history and vehicle orders for Ford Australia, used to drive reporting within M&S and Finance functional areas. | 6 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13864 | AMA - Authorization | In Production | APS -AuthZ | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Gold | S-Ox In Scope | 233 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | AMA aka APS Authorization provides various run time authorization services and standard process for defining, administering access control policies. Powered by industry leading Authorization engine - PDP by Axiomatics. It is cloud native service and full supports Attribute Based Access Control (ABAC). Supports XACML Policy editor, Policy Auditing and Reporting tools, policy publishing lifecycle | 5 |  | YES | 5 | SWALIMBE | PLM | VM | TBD | Complete Migration to GCP (Both App & DB) | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | GCP Migration | [5 empty] | No | VM
19245 | Provider Website for Add-Ons | In Production | ProvideWeb | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RPARAME4 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | This application will allow external providers/administrators of add-ons (insurance warranty maintenance etc.) to provide Ford Credit with a refund quote to be applied to the customers account at the time of repossession charge-off, early payoff, total loss, rewrite etc. |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [16 empty] | No | Java < v21
15045 | Prototype Vehicle Development Ad-Hoc | In Production | PVD Ad-Hoc | ISIT | OTHERS | CRISTIC | CSELF | ISIDDIQ6 | Silver | Non S-Ox | 311 | Yes | No | In-House | JLANE15 | CRISTIC | New Model Programs | - | Ad-Hoc environment for the New Model Launch related MP&L data. Includes 2 modules, Pre-prod BOM issues tracker and MP&L Cycle Plan Metrics. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23280 | AE VM Share | In Production | AEVM | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | Provides gauging engineers the ability to manage gauging programs and access gauging reports from the AE NAS drive without interruption to production and providing a higher level of program consistency across common programs. | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
11012 | ProPrima FDB | In Production | FDB | I-ERP | SFRANCI8 | AKANSKI | RDAVIES6 | LWU14 | Gold | Non S-Ox | 222 | No | Yes | In-House | SFRANCI8 | AKANSKI | Marketing & Sales | Integrated Enterprise Resource Planning (I-ERP) | Central mainframe repository for ProPrima, incorporating the Finance Database (FDB). ProPrima allows pricing and brand team analysts to position current and planned Ford products against their competition in terms of both specification and price. Supports the development of price positioning strategy, and enables the impact assessment of product actions on profitability. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
16794 | ProPrima - Competitive Data Engine | In Production | CDE | I-ERP | SFRANCI8 | AKANSKI | RDAVIES6 | LWU14 | Bronze | Non S-Ox | 221 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Marketing & Sales | Integrated Enterprise Resource Planning (I-ERP) | The ProPrima Competitive Data Engine (CDE) is the repository of CDD (Competitive Data Derived) -sourced Competitor Product Definition loaded by Business users and used within the ProPrima price-setting application. The pricing community then uses this competitive data through the ProPrima Global Client (PGC) desktop application for product/price analysis and the production of pricing papers within Ford. The URL of the CDE application: https://www.edbcaas1.ford.com/edb3/web?site=34 |  |  | YES | 1 | TSWEEN16 | PLM | Oracle | Q3 2026 | Modernize to Cloud Databases | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Oracle
16794 | ProPrima - Competitive Data Engine | In Production | CDE | I-ERP | SFRANCI8 | AKANSKI | RDAVIES6 | LWU14 | Bronze | Non S-Ox | 221 | No | Yes | In-House |  |  | Marketing & Sales | Integrated Enterprise Resource Planning (I-ERP) | The ProPrima Competitive Data Engine (CDE) is the repository of CDD (Competitive Data Derived) -sourced Competitor Product Definition loaded by Business users and used within the ProPrima price-setting application. The pricing community then uses this competitive data through the ProPrima Global Client (PGC) desktop application for product/price analysis and the production of pricing papers within Ford. The URL of the CDE application: https://www.edbcaas1.ford.com/edb3/web?site=34 |  | Springboot | YES | 2 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
56092 | Advanced Supply Chain Enablement for N-tier | In Production | ASCENT | ISIT | VVIJAY55 | SDESHPA5 | MKOMPELL | SNAIR16 | Gold | Non S-Ox | 211 | No | Yes | COTS | SROYCHOU | SDESHPA5 | Supply Chain | Industrial System IT | A Collaboration SaaS solution for Global Supply Chain visibility and supplier collaboration. | 4 |  | YES | 1 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
54356 | Promotional Law | In Production | ARPL | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Finance | 111 | THIS APPLICATION SUPPORTS PROMOTIONAL LAW PROCESS IN ARGENTINA |  | Springboot | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
12785 | CMMS3 Empress - Commodity Audit | In Production | CMMS EMP | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Empress is a suite of Web based audit tools that validates the CMMS assembly bills of material (BOM) identifies differences with the WERS engineering BOM and provides the infrastructure/mechanism to manage the resolution of the differences. An extensive set of web screens Excel downloads and reports are provided to the users to enable them to determine the cause of the errors. |  |  | YES | 3 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-09-22 | 2024-12-15 | 2024-12-08 | Complete | Blue | 2024-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
21751 | Acronis Advanced Workstation | In Production | Acronis | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Engineering | - | Acronis Advanced Workstation is the global standard Industrial PC Imaging and Backup software used throughout Manufacturing. | 14 |  | YES | 3 | BWUNNAVA | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
12785 | CMMS3 Empress - Commodity Audit | In Production | CMMS EMP | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Empress is a suite of Web based audit tools that validates the CMMS assembly bills of material (BOM) identifies differences with the WERS engineering BOM and provides the infrastructure/mechanism to manage the resolution of the differences. An extensive set of web screens Excel downloads and reports are provided to the users to enable them to determine the cause of the errors. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-09-22 | 2024-12-15 | 2024-12-08 | Complete | Blue | 2024-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
54020 | Prognostics | In Production | AIM-PAE | EVDD | RJOHN813 | VSVIDENK | VTHYAHAR | MSANT429 | Silver | Non S-Ox | 211 | Yes | No | In-House | RJOHN813 | VSVIDENK | Advanced PD and Tech | 211 | Analytics Insights and Modeling (AIM) Effortless Maintenance & Repair (EM&R) Prognostics |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
20423 | Prognosis IP Telephony Manager | Active | UCIPTM | EPEO | SRUNSON | PWILL357 | DPETRIE | CFINLE13 | Copper | Non S-Ox | - | No | Yes | - | SRUNSON | PWILL357 | ENTERPRISE TECHNOLOGY | - | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53400 | Account Receivable Workflow | In Production | ARWORKFLOW | I-ERP | SFRANCI8 | SDHANAL3 | PSATHIS3 | LWU14 | Bronze | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | - | AR workflow is a third-party application which enables automation of Collection & Cash application processes.AI enabled payment predictor provides early warning alerts on potential delays - helps prioritize 'customer base' requiring attn/ follow-up.Process is automated ilo current process i.e. moving from dependent on human judgement to data based follow-up prioritization.AI based remittance capture from Checks, Emails, EDIs and Websites & Invoice Matching process which enable automatic cash application.Handling/ response to customer queries is automated across languages with in-built translation capabilities..AI payment predictor helps avoid customer follow-ups with a good payment track-record.Worklist Prioritization, repository of customer, follow Ups and ability to track customer queries and timely response by team members.Automated metrics/reports ex: customer ageing, daily sales outstanding, cash flow forecast etc | 8 |  | YES | 2 | TSWEEN16 | PLM | VM | TBD | EDC New Hypervisor | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
13063 | Professional Technician System | In Production | PTS | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | QBROWN4 | BGHANTA | Gold | Non S-Ox | 222 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | PTS is the technical portal for internal FORD users and dealership employees globally. Includes SPECS, Service Advisor Portal and Newfordtech. |  |  | YES | 2 | RKENNEL | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
23402 | ABC Scale and Commodity Planning | In Production | ABC Scale | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Copper | Non S-Ox | 311 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | Complexity Management Tool that facilitates the creation of Modular Toolkits, ABC Complexity Charts and basic Chess Board Reports. Pre Program Engineering can create a Toolkit of Commodity Variants, A Variant being the Base followed by High and Low variants A1, B, B1 etc. | 7 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
20952 | Product Definition and Offering | In Production | PDO | ISIT | MNOWICK1 | LSRINIVA | DCOOMER | JLUCAS1 | Silver | S-Ox In Scope | 233 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | Application includes: Direct Authoring tool, Workflow and Change Mgmt, Market Offering |  |  | YES | 4 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
20952 | Product Definition and Offering | In Production | PDO | ISIT | MNOWICK1 | LSRINIVA | DCOOMER | JLUCAS1 | Silver | S-Ox In Scope | 233 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | Application includes: Direct Authoring tool, Workflow and Change Mgmt, Market Offering |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50522 | 2018-372 AP AU BMIT JOYTECH CO., LTD. | In Production | Joytech | ISIT | MFOUNTA1 | AWILDEY1 | ACAJDIN | ACAJDIN | Copper | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | MFOUNTA1 | AWILDEY1 | Advanced PD and Tech | - | The supplier Joytech (GSDB: HG9BA) is IMG VA Package seating Buck / Property build supplier. IMG PD VA team being use Joytech since 2015 for building various program package buck and future product. Ford require to send Confidential 3D CAD data and Joytech to store the data during the project engagement. We are using TCE and SharePoint for the data transmit. Supplier stores the data on a desktop. The desktop links to the milling machine. The supplier will delete all Ford confidential data (CAD / email / data / pictures / etc.) after the delivery and close of the PO. | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | TBD | Will be Decommissioned | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
20952 | Product Definition and Offering | In Production | PDO | ISIT | MNOWICK1 | LSRINIVA | DCOOMER | JLUCAS1 | Silver | S-Ox In Scope | 233 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | Application includes: Direct Authoring tool, Workflow and Change Mgmt, Market Offering |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
22749 | Product Definition and Offer - Marketing and Prici | In Production | PDOR2 | ISIT | MNOWICK1 | LSRINIVA | DESPINOS | JLUCAS1 | Silver | Non S-Ox | 222 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | Application includes Market Offering, Change Management and related functionality |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23936 | WASS - Web Account Statement Solution | In Production | WASS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 222 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Regional applicaton Brazil and Argentina Inform local suppliers the status of invoices that are in the payment process, also available as a lumpsum files that were negotiated between supplier and purchases, in order to support further supplementary invoices. On-line input of supplier Service receip Access to supplier statement Create reports to inform suppliers the balance of retro price adjustments and resumen de entrega | 4 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
22749 | Product Definition and Offer - Marketing and Prici | In Production | PDOR2 | ISIT | MNOWICK1 | LSRINIVA | DESPINOS | JLUCAS1 | Silver | Non S-Ox | 222 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | Application includes Market Offering, Change Management and related functionality |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
18625 | Product Creation Domain Search Application - PCDS | In Production | PCDS | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Quality | Industrial System IT | Domain Specific Search software, which offers a single user interface to help engineers find corporate knowledge from multiple sources on the intranet such as EKB, eRoom, SetK, E2KS, PeBOD etc. in product creation domain. SLA rating - 3 |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
12333 | VISTA - New Vehicle Ordering/Tracking (Europe) | In Production | VISTA | M&S TECH | FHIRSH | NSIVASA1 | BRAMA3 | PSATISH2 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Intranet Services and Tracking - a family of modules for dealer and NSC use such as order management, vehicle locator, contract and retail. VISTA is the primary system for European Ford Dealers to order Ford vehicles, manage the vehicle pipeline and to notify Ford of vehicle contracts and vehicle sales to end customers.. | 28 |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
18625 | Product Creation Domain Search Application - PCDS | In Production | PCDS | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Quality | Industrial System IT | Domain Specific Search software, which offers a single user interface to help engineers find corporate knowledge from multiple sources on the intranet such as EKB, eRoom, SetK, E2KS, PeBOD etc. in product creation domain. SLA rating - 3 |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23716 | Product Attribute Management - PAM | In Production | PAM | ISIT | MNOWICK1 | LSRINIVA | DESPINOS | JLUCAS1 | Bronze | Non S-Ox | 232 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | 232 | Product Attribute Management (PAM) seeks to establish a generic capability to manage product attribute data, leveraging the strategic PDO solution as the single-source of truth for feature level product information. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23716 | Product Attribute Management - PAM | In Production | PAM | ISIT | MNOWICK1 | LSRINIVA | DESPINOS | JLUCAS1 | Bronze | Non S-Ox | 232 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | Product Attribute Management (PAM) seeks to establish a generic capability to manage product attribute data, leveraging the strategic PDO solution as the single-source of truth for feature level product information. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51466 | VisionPro | In Production | VISIONPRO | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | GHERMAN | ADURSO | Manufacturing Staffs | - | PowerFleet provides you all the essential, best-practice function you need to manage your industrial vehicles and the personnel who operate them. This solution scope covers the key features required by your business to achieve the best ROI while improving your company's overall safety practices. | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2027 | Complete Migration to SaaS | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
11830 | Process Configuration | In Production | PRC | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SKING68 | SKING68 | Manufacturing Engineering | - | PRC has value stream mapping function with stations and equipment. Used by PTO to document process flow for mfg operations. Application supports multibyte language to use regional language. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
20890 | Vehicle Pricing and Invoicing System | In Production | VEPIS | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Finance | - | Brazil Vehicle Pricing & Invoicing application. There is a simulation environment. Avoid many system changes by allowing the users to set up parameters such as taxes, sales modalities, payment conditions, etc. Avoid current user operating workload by simplifying workflow and be oriented to current Ford business model. | 4 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2025-05-30 |  | In-Progress | Green | 2025-06-16 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
16385 | RFQ - REQUEST FOR QUOTATION | In Production | RFQ | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Supply Chain | - | RFQ Request for Quotation. Application controls requests for suppliers quotation. | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
17992 | PUR - Purchasing Datawarehouse | In Production | PUR | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Supply Chain | - | Database with Purchase information that is used by Purchasing staff to get information and compose some business report. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
13566 | Privilege Club - UK | In Production | EuHRPrivUK | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 321 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | Online application for employee discounted vehicle sales |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13566 | Privilege Club - UK | In Production | EuHRPrivUK | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 321 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | Online application for employee discounted vehicle sales |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Oracle | Q4 2027 | Modernize to Cloud Databases | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Oracle
50384 | NGAVS-Schedule Execution | In Production | NGAVS-SE | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Platinum | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | NGAVS-SE provides the capabilities to execute daily order schedule, providing tracking and production status of vehicle, provide broadcast data to downstream systems, communicate order data to industrial controls/automation and provide critical reports to in-plant personnel | 9 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2027 | EDC CaaS | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [8 empty] | EDC CaaS | Priya | 2025-03-05 |  |  | Migration to EDC CaaS for a single site (DCP) Completed. | No | VM
13566 | Privilege Club - UK | In Production | EuHRPrivUK | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 321 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | Online application for employee discounted vehicle sales |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
51326 | Privacy Protection | In Production | SCA PP | GDIA | CBUCKL19 | VPANDUR1 | UBANDI | MPATEL20 | Silver | Non S-Ox | 321 | No | Yes | In-House | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Privacy Protection application collects and manages CCPA requests |  | Springboot | YES | 3 | FRANBELL | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 | 2025-01-18 | Complete | Blue | 2026-03-15 | 2025-01-18 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | Java < v21
51326 | Privacy Protection | In Production | SCA PP | GDIA | CBUCKL19 | VPANDUR1 | UBANDI | MPATEL20 | Silver | Non S-Ox | 321 | No | Yes | In-House | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Privacy Protection application collects and manages CCPA requests |  |  | YES | 2 | FRANBELL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 | 2025-01-18 | Complete | Blue | 2026-03-15 | 2025-01-18 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | SQL
13784 | NAC EBS - EMSS Build System | Active | EBS | M&S TECH | FHIRSH | NSIVASA1 | BRAMA3 | LRODR205 | Copper | Non S-Ox | - | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | - | Build & Deploy application for vista, smarts, seer, execnet, penta, and Afrl. Running on Solaris and a good target for modernisation. | 4 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
6383 | PRIMAS | In Production | EuAS-PRIMA | I-ERP | SFRANCI8 | AKANSKI | RDAVIES6 | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | AKANSKI | Marketing & Sales | Integrated Enterprise Resource Planning (I-ERP) | Price Maintenance System. PRIMAS is a price database and online price maintenance system used for all sales from Ford companies on the European continent to markets in Europe and all over the world. The main purpose is to provide EUROVAC with the information required for the invoicing process, such as prices for models and options, standard features and descriptions which have to be printed on the invoices. This information is kept in local languages and currencies. Only the price maintenance for a few national sales companies is done in EUROVAC and transferred for interco price calculation to PRIMAS. PRIMAS has the functionality to print internal price list and to do any pre-calculations of prices in terms of tax, vat, dealer margin or interco margin changes.All histories of prices are stored within the PRIMAS system. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
14902 | Price Protection Entry System | In Production | PPES | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Dealers enter claims for price protection credit when the price of the vehicle increased from the time of order to the time of delivery. The information received is validated to ensure payment has not already been made and any credits due are processed through Dealer Payment System. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
54026 | PreQual | In Production | PQL | FORD CREDIT | NJOSHI21 | ASAPEHIA | VDATLA | ASAXENA8 | Silver | Non S-Ox | 321 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 321 | PREQUALIFICATION EXPERIENCE DESIGNED TO TARGET THE NEW TO FORD/FORD CREDIT SHOPPING CONSUMER. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50391 | PREEvision | In Production | PREEvision | ISIT | MNOWICK1 | PBORGAO1 | SBELSAR1 | GRAO3 | Silver | Non S-Ox | 221 | No | Yes | COTS | MNOWICK1 | MNOWICK1 | Enterprise Technology | Industrial System IT | Electrical & Electronic architecture design tool enables architects to design and evaluate electric & electronic architectures and conduct a holistic analysis to assess the impact to all areas of EESE (Hardware, Software, EDS and NetCom). EE Architecture team currently manually collects data for Feature to functional level decomposition and impact analysis efforts. This tool will enable the future plans/implementation (beyond 2019) for direct interfaces to VSEM, EDS, NetCom, ALM, etc. and provide arch. capability in the Siemens toolset to conduct the impact analysis. This will plug the gap in Siemens' system Engineering landscape. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
21493 | Global ESB System | In Production | GESB | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | JBROADW4 | RKADAM1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | Global system to support the creation and management of Extended Service Plans using common global processes. | 39 |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q4 2027 | Partial Migration to GCP | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13876 | PRC-Parts Recall Centre Management Sys | In Production | PRC | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JDEGUZMA | JDEGUZMA | Quality | Industrial System IT | The programs traces the data from parts stored at the Parts Recall Centres. The users can query the database to retrieve information about parts. There are several reports that give different analysis to the lifeline of concerns and its parts. Some Reports are published on the Ford intranet. The Supplier recall module charges suppliers for faulty parts. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
17419 | FSN - Ford Suppliers Network (South America) | In Production | FSN SA | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Supply Chain | - | Application controls suppliers website portal where suppliers check payment dates among other supplier related information. | 4 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
12468 | PPM Audit | In Production | EuCR-PPMAu | ISIT | JKOONS | NLAKSHMA | CCHADA | GRAO3 | Bronze | Non S-Ox | 212 | No | Yes | In-House | NLAKSHMA | cchada | Advanced PD and Tech | - | This product is used to facilitate the global release of engineering drawings in electronic image file format. Function Extract drawing attributes from the current drawing and use these attributes as indexing information for global release.Create image file for the drawing. Launch a web-based PPM Audit Tool GUI with prepopulated indexing information. Also extracts attributes from PMI parts and sends data to PPM AUDIT server for releasing. Provides electronic signoff by Gatekeepers, Engineers and PPM Analysts. Distributes drawings to required Ford Archive. |  | Springboot | YES | 1 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
17780 | Finance documents control management | In Production | MIG | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Scope: Venezuela, Colombia Main system functionalities: - Generates vehicle credit notes - Generates and approval process for accounting notes for all Andina local systems - Documents Issuance Control(sequence): Invoices, 3040 | 5 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
23975 | Powertrain HIL/SIL Dashboard & Data Mngmt DB | In Production | PT DM-DB | ISIT | JKOONS | MNOVAK1 | HLIN11 | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | The application provide planning and reporting capabilities to show incremental new simulation artifacts needed by upcoming applications. Support for automated creation of virtual controllers. Automatically generate required HIL artifacts for HIL simulation and bench set-up. Organizes and manages critical plant data, controller data parameterization information. Provides a workflow and ease of use optimized for simulation building and delivery. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
17971 | FIN - Finance DataWarehouse | In Production | FIN | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Finance Data Warehouse that it is used by Finance Staff to take information and compose some business report concerning Finance requirements. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
23975 | Powertrain HIL/SIL Dashboard & Data Mngmt DB | In Production | PT DM-DB | ISIT | JKOONS | MNOVAK1 | HLIN11 | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | The application provide planning and reporting capabilities to show incremental new simulation artifacts needed by upcoming applications. Support for automated creation of virtual controllers. Automatically generate required HIL artifacts for HIL simulation and bench set-up. Organizes and manages critical plant data, controller data parameterization information. Provides a workflow and ease of use optimized for simulation building and delivery. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
22686 | Powertrain Development Verification | In Production | PTDV | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 311 | COMPUTER AIDED ENGINEERING PROGRAM MANAGEMENT: IS A PROCESS FROM WHICH ANALYTICAL RESULTS AND ENGINE PROGRAM ASSUMPTIONS AND OTHER SIGNIFICANT INPUT ATTRIBUTES CAN BE EXTRACTED FOR THE PURPOSE OF DRIVING ENGINE DESIGN AND ASSISTS IN DETERMINING ASSUMPTIONS FOR NEW ENGINE TECHNOLOGIES. CAE PM INFRASTRUCTURE INCLUDES FUNCTIONALITY TO STORE DISCRETE AND COMPLEX RESULTS AS DATA, STORE DISCRETE AND COMPLEX INFLUENCING FACTORS, AND PROVIDES CROSS REFERENCE DATA THROUGH STRUCTURED PROGRAM NAMING CONVENTION BY GPDS TIMING AND RELATED BILL OF MATERIAL. CAE PM CAN STAGE REQUESTS, PROVIDE HEALTH TO TIMING, PROVIDE HEALTH TO TARGET, AND IS THE FILE STORAGE LOCATION FOR REPORTS AND ASSOCIATED CAE INPUT FILES. CAE PM IS SECURE TO A SPECIFIC USER LIST EMPLOYING IN-SYSTEM USER ACCESS BY JOB DUTIES, ADMINISTRATIVE FUNCTIONS, WITH STRUCTURE AND ULTIMATE ACCESS TIED TO THE CDSID. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
15658 | Powertrain Control Module Interface Spec | In Production | PCM Spec | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Copper | Non S-Ox | 221 | Yes | No | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | - | The website is a live source of information detailing the electrical interfaces between the powertrain control module (PCM) and vehicle sensors and actuators. The PCM is currently made by Visteon and Motorola. In the future other PCM manufactures will begin working with Ford and will need access to the specifications |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23641 | ePAYS S America electronic Payment Solution - ePAY | In Production | ePAYS | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | South America electronic Payment Solution ePAYS to support non-prod account payments, in such way that the miscellaneous account payment process is mechanized in the region. The solution will support Argentina, Brazil, Ford Credit Brazil and National Sales Companies Chile, Colombia, Peru markets. | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
50291 | PowerCurve Originations | In Production | PCO | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Bronze | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Consumer Credit Scoring Application |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
22605 | eMIS - Miscellaneous Invoicing System | In Production | eMIS | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Perform issuance of Miscellaneous invoices (Notas Fiscais) for all Ford Brazil plants | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
50113 | PowerBroker PAM | In Production | PBPAM | EPEO | NOKEEFE | MSNYDER5 | GGEARY | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | COTS | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | PowerBroker Password Safe is an automated password and privileged session management solution offering secure access control, auditing, alerting and recording for any privileged account Planned replacement product for TPAM. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
18008 | CEPS User Access Review (TVS) | In Production | TVS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Supply Chain | - | O sistema TVS eh um sistema utilizado para fazer a revisao de acesso de outros sistemas (mainframe, web ou clientserver). Ele possui a facilidade dos coordenadores de sistemas e executivos utilizarem a propria intranet para fazer o processo de revisao de acesso. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
54694 | Power Monitoring Expert | In Production | PME | OCETO | TSWEEN16 | KADOMKAI | ESTILESK | ESTILESK | Bronze | Non S-Ox | 111 | Yes | No | COTS | DDESAI | KADOMKAI | Manufacturing Plants | - | Monitoring of all energy devices in Manufacturing Plants |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
22590 | Bank Accounts Reconciliation System (BARS) | In Production | BARS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Bank Accounts Reconciliation. The purpose of BARS application is performing bank accounts reconciliation of Accounting items (PeopleSoft GL) and bank statement. | 6 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
16474 | Portfolio Transfer Application | In Production | PTA | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Silver | Non S-Ox | 121 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | An Intranet application designed to initiate the transactions that will transfer dealer and customer accounts from a closing branch to one or more receiving branches. Three types of transactions can be created. 1.) Full Branch Transfer - Where the entire portfolio of a closing branch is transferred to a single receiving branch. 2.) Partial Branch Transfer - Where the portfolio of a closing branch is being transferred to 2 or more receiving branches. 3.) Liquidating Branch Transfer - Where the accounts of branches closed prior to PTA are merged with the dealers previously created in the new branch. On-line and batch reports will also be created to provide the branches with a cross reference of the old dealer number (ex. ABA100) and the new dealer number (ex. AKA100). Dealer Web services functionalities are provided to FCNA down streams to extract dealer data. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
16474 | Portfolio Transfer Application | In Production | PTA | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Silver | Non S-Ox | 121 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | An Intranet application designed to initiate the transactions that will transfer dealer and customer accounts from a closing branch to one or more receiving branches. Three types of transactions can be created. 1.) Full Branch Transfer - Where the entire portfolio of a closing branch is transferred to a single receiving branch. 2.) Partial Branch Transfer - Where the portfolio of a closing branch is being transferred to 2 or more receiving branches. 3.) Liquidating Branch Transfer - Where the accounts of branches closed prior to PTA are merged with the dealers previously created in the new branch. On-line and batch reports will also be created to provide the branches with a cross reference of the old dealer number (ex. ABA100) and the new dealer number (ex. AKA100). Dealer Web services functionalities are provided to FCNA down streams to extract dealer data. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
17847 | Arg. Foreign Payment (Pagos al Exterior) (PE) | In Production | ARPE | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | This system prepares all documentation requested by Argentinian Banco Central to perform a Payment to a foreign supplier. Receives information of all Ford Argentina Imports and, based on suppliers payment condition and Banco Central Regulations, determines payment dates and prepare information to send to the Banks for payments. | 6 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
51772 | Portable Personal Profile | Planned | PPP | EVDD | JWASNIC1 | MBOMMANA | SPRADHAN | SPRADHAN | - | Non S-Ox | 221 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 221 | ALLOWS USERS TO CONFIGURE THEIR VEHICLE PREFERENCES FROM A MOBILE APP OR WEBSITE FOR THEIR RECENTLY PURCHASED VEHICLE AND APPLY THOSE PREFERENCES TO THE VEHICLE UPON ARRIVAL |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
11315 | POPS: Part Order Processing System | In Production | POPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | POPS: Part Order Processing System. Includes several modules that fall within the Part Order Entry, Order Processing, Supplier Direct Ship, and Part Return areas. This is one of the companies top 10 critical applications. Secondary outage impacts are 'Impact to Financial Results' and 'Impact to Productivity'. | 6 |  | YES | 3 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11315 | POPS: Part Order Processing System | In Production | POPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | POPS: Part Order Processing System. Includes several modules that fall within the Part Order Entry, Order Processing, Supplier Direct Ship, and Part Return areas. This is one of the companies top 10 critical applications. Secondary outage impacts are 'Impact to Financial Results' and 'Impact to Productivity'. |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
11315 | POPS: Part Order Processing System | In Production | POPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | POPS: Part Order Processing System. Includes several modules that fall within the Part Order Entry, Order Processing, Supplier Direct Ship, and Part Return areas. This is one of the companies top 10 critical applications. Secondary outage impacts are 'Impact to Financial Results' and 'Impact to Productivity'. |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
11489 | POLR: Plant On-Line Reporting | In Production | POLR | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Bronze | Non S-Ox | 311 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | - | POLR reports data stored in DLORS database for VO and PTO plants, accessed by Purchasing and Finance Staff. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Oracle
17855 | Arg. Export invoice hub to PS AR (Black Box) (BB) | In Production | ARBB | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This system receives billing data from the argentinian billing systems (Popims, VH and T&C) and creates an outbound file for PeopleSoft Accounts Receivable known as Open Items interface. This systems also maintains conversion tables in order to translate different values from one system to another. | 4 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
23711 | POLICY PORTAL - DOCUMENTUM D2 | In Production | PolicyMgmt | I-ERP | SFRANCI8 | SFRANCI8 | AKANSKI | LWU14 | Copper | Non S-Ox | 222 | No | Yes | COTS | TSWEEN16 | TSWEEN16 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Policy Portal - Documentum D2 tool for Corporate Policy Management |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
22523 | APMEA Statutory Interface & Registration Database | In Production | APMEA SIRD | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | The APMEA Statutory Interface and Registration Database (APMEA SIRD) supports the registration of vehicles with local governments and external interfaces in the AP and MEA regions | 5 |  | YES | 3 | NKANDULA | PLM | VM | Q4 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23711 | POLICY PORTAL - DOCUMENTUM D2 | In Production | PolicyMgmt | I-ERP | SFRANCI8 | SFRANCI8 | AKANSKI | LWU14 | Copper | Non S-Ox | 222 | No | Yes | COTS | TSWEEN16 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Policy Portal - Documentum D2 tool for Corporate Policy Management |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
16012 | Accounts Receivable | In Production | CXC | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Account Receivable Perfit system Scope: Venezuela, Colombia Main system functionalities: - Generates vehicle and parts e-collections client statements - Maintains a repository of all local automated and manual journals that are transmitted daily to PS GL. - Generates several VAT Tax Books of Sales for tax reporting purposes. - Generates dealer statement for Regional Publicity Fund from installments deducted from vehicle invoices. - Interfaces with vehicle/parts billing systems to automatically journalize sales - Calculates and journalizes different types of interest charges such as interests on vehicle financing and on overdue parts balances. - Receive and journalize interface file of installment payments - Backoffice for Planford Consortium Website Portal | 4 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
267 | Plant Vehicle Sched. | In Production | EuPFS-PVS | ISIT | AMEHER1 | ADURSO | RHOPKIN4 | RPRASA22 | Copper | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | PVS is a Plant Vehicle Scheduling system used for the following purposes : a)Tracking vehicles at various stages of production like Underbody, Exit Body, Exit Paint, Assembly Offline & CAIOK b)Broadcasting to varies in-plant devices as roboters,skillet conveyors, VIN-machines, Andon-boards, operators, and to suppliers at Supplier Park and Visteon for making and delivering the parts. |  |  | YES | 1 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
12799 | Plant | In Production | Q-DAS | ISIT | SKING68 | DCLEME13 | TPICKERE | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | COTS | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | The qsSTAT component collects and analyzes process and product related dimensional data to determine whether the process is in statistical control and whether the product conforms to quality specifications. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
12799 | Plant | In Production | Q-DAS | ISIT | SKING68 | DCLEME13 | TPICKERE | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | The qsSTAT component collects and analyzes process and product related dimensional data to determine whether the process is in statistical control and whether the product conforms to quality specifications. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
16011 | Accounts Payable | In Production | CXP | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Account Payable Perfit system Scope: Venezuela, Colombia Main system functionalities: - Payment disbursement for CCAPS (production material and Non-production payments). - Payment processing for spare parts billed by the P&A Parts and Accessories System. - Issues checks on preprinted check formats. - Generates tax adjustments and other tax reporting including VAT tax Book of Purchases. - Generates a withholding tax declaration file in Seniat format for electronic uploading. - Generates miscellaneous payments for items not handled by corporate systems. | 8 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | VM
15327 | Accounting - Dealer EFT | In Production | DEFT | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | ROBRIEN3 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | KDELTA | MVENKA15 | Ford Credit Services | Ford Credit (FMCC) | US & Canada - Electronically moves funds between Dealers bank accounts and Ford/Ford Credit bank accounts. | 3 |  | YES | 5 | SRAISIN1 | PLM | VM | Q4 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
13296 | PKGINFO Ford B2B hosted | In Production | PKGINFOSUP | I-ERP | OTHERS | TALEXAN4 | TKASPER | MMEHTA5 | Copper | Non S-Ox | 111 | Yes | No | Managed by 3rd Party Purchased Service | BOSTERL1 | TALEXAN4 | Ford Customer Service | - | PS&L Packaging Engineering generates packaging specifications to be used by suppliers. Website supported by Creative Data Inc. Server: eccws547.dearborn.ford.com (DEV) eccws549.dearborn.ford.com (PROD) Vendor contact Glenn LaFever glafeve2 |  |  | YES | 2 | TSWEEN16 | PLM | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50513 | Pinnacle Table Maintenance Application | In Production | TMA | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | ROBRIEN3 | Silver | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Enterprise Technology | Ford Credit (FMCC) | TMA is an application that business will use to view and update business tables. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50513 | Pinnacle Table Maintenance Application | In Production | TMA | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | ROBRIEN3 | Silver | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Enterprise Technology | Ford Credit (FMCC) | TMA is an application that business will use to view and update business tables. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q1 2027 | Rewrite | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | Java < v21
50619 | Pinnacle Security - China | In Production | SecChina | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Copper | Non S-Ox | 333 | No | Yes | In-House | JCHEN11 | CXUE7 | Ford Credit Services | Ford Credit (FMCC) | Security and admin for Pinnacle GLO - China. This includes application related to Pinnacle Security 1) Global Pinnacle Security 2) Pinnacle Audit |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
13378 | Pinnacle Security | In Production | Security | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | Non S-Ox | 223 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Security and admin for Pinnacle LO |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
13378 | Pinnacle Security | In Production | Security | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | Non S-Ox | 223 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Security and admin for Pinnacle LO |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
13370 | Pinnacle Loan Origination | In Production | PinnacleLO | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Functionality built under the PINLO label. Functionality includes Credit Analysis - system to analyze credit applications, and online CA reports. Discounting (includes MD&R)- Application is used to discount credit applications. This is an SLA1 making business criticality High. Calculator and online LO reports. | 1 |  | YES | 3 | SRAISIN1 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned | [17 empty] | DA
13370 | Pinnacle Loan Origination | In Production | PinnacleLO | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Functionality built under the PINLO label. Functionality includes Credit Analysis - system to analyze credit applications, and online CA reports. Discounting (includes MD&R)- Application is used to discount credit applications. This is an SLA1 making business criticality High. Calculator and online LO reports. |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
13370 | Pinnacle Loan Origination | In Production | PinnacleLO | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Functionality built under the PINLO label. Functionality includes Credit Analysis - system to analyze credit applications, and online CA reports. Discounting (includes MD&R)- Application is used to discount credit applications. This is an SLA1 making business criticality High. Calculator and online LO reports. |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
50618 | Pinnacle Common Logon - China | In Production | LogonChina | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 333 | No | Yes | In-House | JCHEN11 | CXUE7 | Ford Credit Services | Ford Credit (FMCC) | Logon for all Pinnacle Applications and various other FC server apps. in China |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
13376 | Pinnacle Common Logon | In Production | Logon | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | Non S-Ox | 223 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Logon for all Pinnacle Applications and various other FC server apps. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
13376 | Pinnacle Common Logon | In Production | Logon | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | Non S-Ox | 223 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Logon for all Pinnacle Applications and various other FC server apps. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
20090 | Pinnacle Add-On Dealer Report | In Production | PinnDPR | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Copper | Non S-Ox | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Facility for dealers to access the Ford Credit Add-On Products and Forms from the fmcDealer website. Provides a real-time report to dealers which lets them know the approved Programs, Providers, Insurers, and Forms for Add-Ons. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20090 | Pinnacle Add-On Dealer Report | In Production | PinnDPR | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Copper | Non S-Ox | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Facility for dealers to access the Ford Credit Add-On Products and Forms from the fmcDealer website. Provides a real-time report to dealers which lets them know the approved Programs, Providers, Insurers, and Forms for Add-Ons. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
15289 | Pinnacle Account Servicing Batch | In Production | PASMF | FORD CREDIT | NJOSHI21 | HBRUMLEV | VCECCARE | ROBRIEN3 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | The Pinnacle Account Servicing Mainframe Suite is a S-OX classified suite of programs responsible for passing Pinnacle DB2 Data to/from the Pinnacle Account Servicing application and for Account Servicing batch processes. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
51127 | Pinnacle Account Servicing - China | In Production | PinASVChn | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CXUE7 | Ford Credit Services | Ford Credit (FMCC) | There are 2 separate applications that make up the Pinnacle Account Servicing Suite for China, they are Customer Service (CS) and Table Maintenance Application (TMA). These are used in all FAFC locations. It interfaces with LA Receivables, Debt Manager, Account Manager, Workflow and IVR to provide the user with customer account information (e.g., account balance and customer contact history, etc.). It provides for documenting of customer interactions and submitting transactions to the Receivables system and external Vendors for processing. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
51127 | Pinnacle Account Servicing - China | In Production | PinASVChn | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CXUE7 | Ford Credit Services | Ford Credit (FMCC) | There are 2 separate applications that make up the Pinnacle Account Servicing Suite for China, they are Customer Service (CS) and Table Maintenance Application (TMA). These are used in all FAFC locations. It interfaces with LA Receivables, Debt Manager, Account Manager, Workflow and IVR to provide the user with customer account information (e.g., account balance and customer contact history, etc.). It provides for documenting of customer interactions and submitting transactions to the Receivables system and external Vendors for processing. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
13883 | Pinnacle Account Servicing | In Production | PinnacleAS | FORD CREDIT | NJOSHI21 | HBRUMLEV | VCECCARE | ROBRIEN3 | Silver | S-Ox In Scope | 233 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | There are six separate applications that make up the Pinnacle Account Servicing Suite, they are Customer Service (CS), Correspondence Letter Library (COR), Administration (Admin), Payments, Disbursements,and Table Maintenance Application (TMA). These are used in all Ford Financial locations in North America and satellite locations. It interfaces with LA Receivables, Debt Manager, Account Manager, Workflow and IVR to provide the user with customer account information (e.g., account balance and customer contact history, etc.). It provides for documenting of customer interactions and submitting transactions to the Receivables system and external Vendors for processing. This represents in excess of 156 million customer contacts (e.g., phone calls, e-mails, correspondence, etc.) annually. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
13883 | Pinnacle Account Servicing | In Production | PinnacleAS | FORD CREDIT | NJOSHI21 | HBRUMLEV | VCECCARE | ROBRIEN3 | Silver | S-Ox In Scope | 233 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | There are six separate applications that make up the Pinnacle Account Servicing Suite, they are Customer Service (CS), Correspondence Letter Library (COR), Administration (Admin), Payments, Disbursements,and Table Maintenance Application (TMA). These are used in all Ford Financial locations in North America and satellite locations. It interfaces with LA Receivables, Debt Manager, Account Manager, Workflow and IVR to provide the user with customer account information (e.g., account balance and customer contact history, etc.). It provides for documenting of customer interactions and submitting transactions to the Receivables system and external Vendors for processing. This represents in excess of 156 million customer contacts (e.g., phone calls, e-mails, correspondence, etc.) annually. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
16170 | Pinnacle - Smart VINCENT Middleware | In Production | PINN_SV_MW | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | Non S-Ox | 223 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Retrieves rate information from SMART VINCENT for low APR programs for the Pinnacle Discounting application. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
16170 | Pinnacle - Smart VINCENT Middleware | In Production | PINN_SV_MW | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | Non S-Ox | 223 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Retrieves rate information from SMART VINCENT for low APR programs for the Pinnacle Discounting application. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
19197 | Pinnacle - Portfolio Toolbox | In Production | PTB | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Bronze | Non S-Ox | 222 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | This application is displayed alongside Credit Analysis and it displays dealer statistics retrieved from DB2 & EDW. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
19197 | Pinnacle - Portfolio Toolbox | In Production | PTB | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Bronze | Non S-Ox | 222 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | This application is displayed alongside Credit Analysis and it displays dealer statistics retrieved from DB2 & EDW. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
13377 | Pinnacle - Office Foreign Asset Control Website | In Production | OFAC | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | Non S-Ox | 232 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | OFAC compliance and website. This ITMS entry covers EU, and Mexico OFAC deployments. It also contains Scoring Analysis and ECOA-ANF. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
15440 | Pinnacle - Loan Origination Batch | In Production | DISC NBB | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | This is an umbrella ITMS for Pinnacle LO batch processing for ITMS# 15540. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
22706 | Pinnacle - Global Utilities | In Production | PinnUtil | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 333 | No | Yes | In-House | JCHEN11 | CXUE7 | Ford Credit Services | Ford Credit (FMCC) | Global instance for the following Loan Originations applications: 1) Offering/Purchasing Summary 2) Offering/MCN Maintenance 3) Offering log 4) Discounting Settlement Summary |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
23029 | Pinnacle - Global Tools Audit | In Production | PinnAudit | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Bronze | Non S-Ox | 222 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Global instance for the following Loan Originations applications: Reconciliation Report. |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
11759 | WORKS - Online Reporting and Knowledge System | In Production | WORKS | M&S TECH | FHIRSH | NGIRISH | LSCHLEBA | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House |  |  | Marketing & Sales | Marketing, Sales and Service | WORKS is the Business Objects tool used by GTS to receive and transmit batch files for vehicle and order status purposes. It is the adhoc reporting tool used by the business team. | 3 |  | YES | 3 | NKANDULA | PLM | VM | Q4 2026 | Partial Migration to GCP | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23029 | Pinnacle - Global Tools Audit | In Production | PinnAudit | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Bronze | Non S-Ox | 222 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Global instance for the following Loan Originations applications: Reconciliation Report. |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
23428 | Pinnacle - Global Portfolio Toolbox | In Production | GLOPTB | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 333 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | This application is displayed alongside Credit Analysis and it displays dealer statistics retrieved from DB2 & EDW. |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
22823 | Pinnacle - Global Loan Origination | In Production | PinGLO | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | Pinnacle Global Loan Origination contains functionality that is used for Credit Analysis and Discounting. Initially this application will only be used in China. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
22823 | Pinnacle - Global Loan Origination | In Production | PinGLO | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | Pinnacle Global Loan Origination contains functionality that is used for Credit Analysis and Discounting. Initially this application will only be used in China. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | SQL
21194 | Work Contract System | In Production | WCS | OCETO | TSWEEN16 | KKOEHLER | WALBERS | MBALAN2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DDESAI | KKOEHLER | Human Resources | Staffs IT | Current View of the Situation: According to the works constitution act the workers council is entitled to be informed and to review any work order in due time before implementation of the work order. Details are outlined in the works agreement (Betriebsvereinbarung) signed on 13-Sep-1991. In this context about 50,000 PNs per year need to be classified, reviewed, analysed and archived. Currently no working IT system is available to support this process. Better View of the Situation: Enable Ford HR and Betriebsrat to process all PNs, by providing a supporting IT system. | 4 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2025-06-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22823 | Pinnacle - Global Loan Origination | In Production | PinGLO | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | Pinnacle Global Loan Origination contains functionality that is used for Credit Analysis and Discounting. Initially this application will only be used in China. |  |  | YES | 4 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
372 | Physical VIN Generator - Gen Extract | In Production | EuMP-PVG | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | PVG - This application provides the tools to enable the definition of the VIN that is Physically stamped on the vehicle when it is built. This VIN, in Europe, is different to the Logical VIN for specific markets. It also provides an order bank containing EOC order images and associated VIN-Plate and Physical VIN data for all orders scheduled until point of assembly offline and/or gate release. This data is passed to the plant PVS system. The Order bank is transmitted to every Plant in each Region that uses the European OTD functionality. As on 2014 this includes all Plants within the FOE, FIL and FOA Regions |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q4 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9044 | PfeP: Plan for Every Part - Pro | In Production | EuMP-PFEP | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 211 | No | Yes | In-House | GHERMAN | GHERMAN | Manufacturing Staffs | Industrial System IT | Plan-for-Every-Part from Supplier via dock/market place to vehicle line |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | Q4 2027 | On-Prem | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Oracle
9044 | PfeP: Plan for Every Part - Pro | In Production | EuMP-PFEP | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 211 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Plan-for-Every-Part from Supplier via dock/market place to vehicle line |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
870 | WIPS Ad Hoc Reporting | In Production | Ad Hoc | I-ERP | SARAUJO3 | CBISWADI | JBAJI | CWADE | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Read-only application supporting downstream applications and adhoc users; provides production-level Purchasing data sourced from WIPS and GSDB. Data contained on the WIPS AdHoc tables are pulled from the WIPS and GSDB databases on a daily basis, excluding inactive and removed parts. Reports can be run against AdHoc using customized queries via MS-Access software. (All canned reports and queries were decommissioned with the front-end as of September 2016.) | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
19 | Personnel Reporting Information System (PRISM) | In Production | PRISM | OCETO | TSWEEN16 | SCHILAKA | WPETER58 | MBALAN2 | Silver | Non S-Ox | 311 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | Data warehouse for older benefit applications and hourly data. / Old Acronym : PRISM 2004 Financials also includes Focus support for Vehicle Programs ($93k). 2005 Financials increased by $170k to fund a BA in support of UAW related systems. 2/13/06 - also contains Wage&Manpower and Wage Determination which formerly were seperate ITMS entries that have since been deleted as they are covered within the PRISM scope and ACR. | 53 |  | YES | 2 | TSWEEN16 | PLM | WebFocus - MF | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
19 | Personnel Reporting Information System (PRISM) | In Production | PRISM | OCETO | TSWEEN16 | SCHILAKA | WPETER58 | MBALAN2 | Silver | Non S-Ox | 311 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | Data warehouse for older benefit applications and hourly data. / Old Acronym : PRISM 2004 Financials also includes Focus support for Vehicle Programs ($93k). 2005 Financials increased by $170k to fund a BA in support of UAW related systems. 2/13/06 - also contains Wage&Manpower and Wage Determination which formerly were seperate ITMS entries that have since been deleted as they are covered within the PRISM scope and ACR. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
24562 | Personal Lifetime Communication | In Production | PLC | FORD CREDIT | NJOSHI21 | SFRAGAL1 | KUHL1 | ASAXENA8 | Bronze | Non S-Ox | 311 | No | Yes | In-House | NJOSHI21 | ABARNA10 | Ford Credit Services | 311 | Web facing screen presenting Personal Lifetime Communication to user where applicable |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | TBD | Version Upgrade | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
24562 | Personal Lifetime Communication | In Production | PLC | FORD CREDIT | NJOSHI21 | SFRAGAL1 | KUHL1 | ASAXENA8 | Bronze | Non S-Ox | 311 | No | Yes | In-House | NJOSHI21 | ABARNA10 | Ford Credit Services | Ford Credit (FMCC) | Web facing screen presenting Personal Lifetime Communication to user where applicable |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
24562 | Personal Lifetime Communication | In Production | PLC | FORD CREDIT | NJOSHI21 | SFRAGAL1 | KUHL1 | ASAXENA8 | Bronze | Non S-Ox | 311 | No | Yes | In-House | NJOSHI21 | ABARNA10 | Ford Credit Services | Ford Credit (FMCC) | Web facing screen presenting Personal Lifetime Communication to user where applicable |  |  | YES | 4 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
25079 | Webex Portfolio | In Production | Webex | EPEO | SRUNSON | PWILL357 | RSCHUL18 | MLESNAU1 | Platinum | Non S-Ox | 313 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | PWILL357 | Enterprise Technology | EPEO | This is a Cisco collaboration suite enabling teams to collaborate by use of persistent messaging, video conferencing meetings w/screen share, interactive whiteboard, document sharing and integrated UCM calling. | 17 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
24159 | Warehouse Inventory Next Generation System | In Production | WINGS | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Ford Customer Service | - | Warehouse Management System (WMS) for South America, in replace of Perfit (North Group) and POPIMS (South Group/Brazil). Perform PS&L inventory management for the Region as a transitional solution for any global WMS initiative. | 8 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2025-04-30 |  | In-Progress |  | 2025-05-16 |  | Planned |  | No |  | 25% | 25% | [5 empty] | GCP Migration | [5 empty] | No | VM
21175 | Performance Management Tools | In Production | PerfMgnt | EPEO | MCRNKOVI | SSOLTANI | CCRAIG39 | CCRAIG39 | Copper | Non S-Ox | 111 | No | Yes | In-House | MCRNKOVI | SSOLTANI | Enterprise Technology | EPEO | Performance Management Tools is a set of custom tools used by ITO Network Operations to integrate and manage network performance assets. In-house developed WeatherMap and IP SLA Manager Apps part of this Application ID. |  |  | YES | 2 | SWALIMBE | PLM | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
18055 | VIP - Ford Dealers Parts Sales and Inventory | In Production | VIP | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | VIP is a common Regional web-based system which the purpose is: -Dealer inventory management Inventory analysis Suggested parts order (auto and manual) Parts locator and inventory balance Standard reports -Dealer Sales and Purchase Analysis Dealer Sales analysis Customer segmentation Dealer Purchase analysis Ad-hoc reporting | 6 |  | YES | 4 | RKENNEL | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12833 | CMMS Obsolescence | In Production | CMMS OBSO | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | S-Ox In Scope | 131 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Application allows claims from DDL suppliers and mechanical canvassing plant obsolete parts. For qualified obsolete parts disposition directions will be provided by obsolete ananlysts and settlements will be issued to suppliers. Accounting information is created and sent to affected accounting systems. Rejections are sent to suppliers for incomplete/erroneous claims. |  |  | YES | 3 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-10-01 | 2024-10-26 | 2024-10-26 | Complete | Blue | 2025-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
52580 | Venezuela EDI (Goanywhere/EDISEC2) | In Production | VenEdi | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Bronze | Non S-Ox | 321 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Gentran/EDISEC2 software support the electronic data file interchange between banks and other institutions for supplier payments, payroll and receive company bank financial statement. This package was purchased in Venezuela through ENIAC supplier, a representative of Sterling Commerce, who is the company that developed the standard UN / EDIFACT, for worldwide use. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | EDC CaaS and New EDC Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
23692 | Perceived Quality Audit System | In Production | PQAS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Silver | Non S-Ox | 221 | No | Yes | In-House | JKOONS | TBROWN99 | Advanced PD and Tech | Industrial System IT | Global corporate IT enabled technology to support Vehicle Craftsmanship & Perceived Quality Audit process and provide business capabilities for end to end process integration and decisions support |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
11483 | PeopleSoft (ASR) GL | In Production | ASR GL | I-ERP | SFRANCI8 | DSHAH1 | AWALIA1 | HPADMANA | Gold | S-Ox In Scope | 232 | No | Yes | COTS | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | PeopleSoft (ASR) GL - General Ledger application. Global strategic general ledger solution. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q4 2026 | On-Prem | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
11483 | PeopleSoft (ASR) GL | In Production | ASR GL | I-ERP | SFRANCI8 | DSHAH1 | AWALIA1 | HPADMANA | Gold | S-Ox In Scope | 232 | No | Yes | COTS | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | PeopleSoft (ASR) GL - General Ledger application. Global strategic general ledger solution. | 27 |  | YES | 4 | TSWEEN16 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11483 | PeopleSoft (ASR) GL | In Production | ASR GL | I-ERP | SFRANCI8 | DSHAH1 | AWALIA1 | HPADMANA | Gold | S-Ox In Scope | 232 | No | Yes | COTS | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | PeopleSoft (ASR) GL - General Ledger application. Global strategic general ledger solution. |  |  | YES | 4 | TSWEEN16 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
16014 | Vehicle Sales Management System | In Production | VSMS | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | VSMS: Vehicle Sales Management System. Scope: Venezuela and Colombia. Main system functionalities: - Vehicle pricing (retail/fleet) - Vehicle invoicing for new and used vehicles - Vehicle distribution process for Dealers - Control of: vehicle inventory, License plates, Gas Kits (GNV) - Vehicles registration control (INTTT) - Back office for Plan Ford program. | 12 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11482 | PeopleSoft (ASR) AR / BI | In Production | ASR AR | I-ERP | SFRANCI8 | SDHANAL3 | PSATHIS3 | CWADE | Gold | S-Ox In Scope | 332 | No | Yes | COTS | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | PeopleSoft Accounts Receivables module is responsible for the entry of items (outstanding invoices), handling customer payments, dealer statements, managing customer invoices, and creating customer correspondence such as customer statements. PeopleSoft Billing information is used to create invoice, receive billing data from other upstream applications, print invoices and create accounting entries for PeopleSoft General Ledger and Accounts Receivables. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
11482 | PeopleSoft (ASR) AR / BI | In Production | ASR AR | I-ERP | SFRANCI8 | SDHANAL3 | PSATHIS3 | CWADE | Gold | S-Ox In Scope | 332 | No | Yes | COTS | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | PeopleSoft Accounts Receivables module is responsible for the entry of items (outstanding invoices), handling customer payments, dealer statements, managing customer invoices, and creating customer correspondence such as customer statements. PeopleSoft Billing information is used to create invoice, receive billing data from other upstream applications, print invoices and create accounting entries for PeopleSoft General Ledger and Accounts Receivables. |  |  | YES | 3 | TSWEEN16 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
21815 | Vehicle Sales Indicators Report South America | In Production | VESIR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | BI application to attend FSAO sales areas. It gets informations of multiple sources to compile the data in reports to Ford Sales, Sales office and dealers. | 8 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
54004 | PeopleFlow | Planned | PFW | OCETO | DBRIGHEN | BFIGUEI3 | ACOSTA95 | MBRITO9 | Silver | Non S-Ox | 211 | No | Yes | - | AMACHAD4 | BFIGUEI3 | Advanced PD and Tech | 211 | SUPPORT FOR SOUTH AMERICA ENTERPRISE CONNECTIVITY TEAM TO MANAGE PRODUCTS AND TEAM ALLOCATION/EDUCATION, SUCH AS: ONBOARDING PROCESS, BUDDY ASSIGNMENT; GUILDS SUBJECTS & SCHEDULE; HEADS AND SOURCES. REPLACING MANUAL PROCESS HANDLED VIA SHAREPOINT FUNCTIONALITIES |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
9835 | PENTA - Pan European National Type Approval | In Production | PENTA | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 212 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | 212 | PENTA is mainly a batch application for pre-registration of vehicles (i.e. providing governments/government agencies whatever is needed to be able to register the vehicle in the given market). Where governments provide registration details (mainly first registration date) PENTA is able to captures these and pass them on to downstream applications like MPS, VISTA. PENTA also has an internal facing web application, used by internal users to monitor/intervene in the results of the batch processes. It supports 16 EU markets. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | Q2 2026 | Version Upgrade | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
9835 | PENTA - Pan European National Type Approval | In Production | PENTA | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 212 | No | Yes | - | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | PENTA is mainly a batch application for pre-registration of vehicles (i.e. providing governments/government agencies whatever is needed to be able to register the vehicle in the given market). Where governments provide registration details (mainly first registration date) PENTA is able to captures these and pass them on to downstream applications like MPS, VISTA. PENTA also has an internal facing web application, used by internal users to monitor/intervene in the results of the batch processes. It supports 16 EU markets. |  |  | YES | 3 | NKANDULA | PLM | Oracle | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
12976 | Variable Data Label System | In Production | VDLS | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Silver | Non S-Ox | 223 | No | Yes | In-House |  |  | PD Operations and Quality | Industrial System IT | This application provides a mechanized system to capture certification and tire data from upstream engineering processes and generate data for VIN specific labels such as safety certification, tread act, tire pressure, etc. In addition, it provides data verification and auditing, provide timing and milestone tracking and notification and reporting capabilities. | 4 |  | YES | 5 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50959 | PEGA MP&L RPA | In Production | PEGARPAMPL | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | SSENTH15 | Silver | Non S-Ox | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | - | PEGA MP&L RPA IT Team for development |  |  | YES | 1 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
11467 | PEDRO: Period Entry and Duty Relief Online | In Production | EuAS-PEDRO | ISIT | VVIJAY55 | RADAM10 | VHESS5 | SSENTH15 | Silver | Non S-Ox | 221 | No | Yes | In-House | JPITTERL | CBOHN | Manufacturing Staffs | Industrial System IT | PEDRO-EC (movements within the EU) complies with the legal requirement to provide statistical data to the Customs Authorities covering all goods acquired from and dispatched to other European Union member states, and to calculate the payment of Acquisition Tax on all goods acquired from other EU member states. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q3 2027 | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
179 | PEARS: Parts Entry and Recall System | In Production | PEARS | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SSAIRAM | SDHANAS2 | Gold | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | PPRASAN2 | PD Operations and Quality | FCSD Tech | The PEARS system recalls parts replaced during a warranty or recall repair when the claim has been paid. / Old Acronym : PEARS | 1 |  | YES | 3 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
179 | PEARS: Parts Entry and Recall System | In Production | PEARS | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SSAIRAM | SDHANAS2 | Gold | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | PPRASAN2 | PD Operations and Quality | FCSD Tech | The PEARS system recalls parts replaced during a warranty or recall repair when the claim has been paid. / Old Acronym : PEARS |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
179 | PEARS: Parts Entry and Recall System | In Production | PEARS | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SSAIRAM | SDHANAS2 | Gold | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | PPRASAN2 | PD Operations and Quality | FCSD Tech | The PEARS system recalls parts replaced during a warranty or recall repair when the claim has been paid. / Old Acronym : PEARS |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
11320 | PDSS: Parts Decision Support System | In Production | PDSS:11320 | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | Provides data stores on Teradata of MMP production data, and information ftp from Europe for ad hoc reporting purposes. Customers as well as the PS&L ad hoc group use these tables for reporting and analytical purposes. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q2 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11320 | PDSS: Parts Decision Support System | In Production | PDSS:11320 | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | Provides data stores on Teradata of MMP production data, and information ftp from Europe for ad hoc reporting purposes. Customers as well as the PS&L ad hoc group use these tables for reporting and analytical purposes. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
13912 | PDB | In Production | EuAS-PDB | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | The Payment Database (PDB) allows on-line enquiry access to payment details for the following type of transaction: * Receipts for suppliers using Evaluated Receipt Settlement (ERS). * Self-Billing Invoices (SBIs) for suppliers using Evaluated Receipt Settlement (ERS). * Invoices for suppliers not being processed using Evaluated Receipt Settlement (ERS). * Remittance advices. Supplier details can also be accessed through PDB. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
12833 | CMMS Obsolescence | In Production | CMMS OBSO | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | S-Ox In Scope | 131 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Application allows claims from DDL suppliers and mechanical canvassing plant obsolete parts. For qualified obsolete parts disposition directions will be provided by obsolete ananlysts and settlements will be issued to suppliers. Accounting information is created and sent to affected accounting systems. Rejections are sent to suppliers for incomplete/erroneous claims. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-10-01 | 2024-10-26 | 2024-10-26 | Complete | Blue | 2025-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
12836 | CMMS Security Authorization Service | In Production | CMMS SAS | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | Non S-Ox | 113 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | The Security Authorization Service (SAS) provides a self-contained package that is designed to authorize the web security needs of all Material Planning and Logistics applications. Act as common reusable security framework which applications use as a plug and play module to secure their applications. Functionality of this application is to set up security policies, make authorization decisions based on security policies, authorization decisions of used applications. |  |  | YES | 3 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-06-28 | 2024-09-30 | 2024-09-30 | Complete | Blue | 2025-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
12836 | CMMS Security Authorization Service | In Production | CMMS SAS | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | Non S-Ox | 113 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | The Security Authorization Service (SAS) provides a self-contained package that is designed to authorize the web security needs of all Material Planning and Logistics applications. Act as common reusable security framework which applications use as a plug and play module to secure their applications. Functionality of this application is to set up security policies, make authorization decisions based on security policies, authorization decisions of used applications. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-06-28 | 2024-09-30 | 2024-09-30 | Complete | Blue | 2025-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
19014 | Transport Management System | In Production | TMS | ISIT | JPITTERL | CBOHN | MBONAKDA | SSENTH15 | Silver | Non S-Ox | 212 | Yes | No | In-House | CBOHN | IREINHO3 | Manufacturing Staffs | Industrial System IT | Application to executional plan a logistical transportation network. Main function is to provide trip sheet and pick-up information based on DCI information. Application is operated by the European LLP who's main responsibility is to plan the logistics of the inbound material into all European manufacturing plants. | 15 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50250 | PCN FMSP TOOL | In Production | FMSP TOOL | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Copper | Non S-Ox | 211 | Yes | No | In-House | DBRIGHEN | RCORDEI1 | Supply Chain | - | This is a tool for automating the PCN generation, improving in non-production purchasing and finance. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
57176 | ThreatConnect IDO (Intel Driven Ops) Dedicated Clo | Planned | TCC | EPEO | NOKEEFE | MCRNKOVI | BBOGEDIN | WJUSTICE | Silver | S-Ox Classification Pending | 222 | No | Yes | COTS | UARJUNAN | NOKEEFE | Enterprise Technology | EPEO | ThreatConnect aggregates intelligence from multiple sources both structured and unstructured. | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
12962 | PCAM: Project Control / Asset Management | In Production | PCAM | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | HPADMANA | Silver | S-Ox In Scope | 222 | No | Yes | COTS | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | PeopleSoft Project Control and Asset Management application. Intial scope is to replace the legacy PCPAS application within North America. Longer term is PCAM will be rolled out globally as the strategic solution. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
12962 | PCAM: Project Control / Asset Management | In Production | PCAM | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | HPADMANA | Silver | S-Ox In Scope | 222 | No | Yes | COTS | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | PeopleSoft Project Control and Asset Management application. Intial scope is to replace the legacy PCPAS application within North America. Longer term is PCAM will be rolled out globally as the strategic solution. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Oracle
11317 | PC: Material Mgmt - Part Control I/II | In Production | PC: M11317 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | PC I: Material Mgmt Process - Parts Control. Secondary Outage Impacts: Customer Complaint, Impact to Financial Results | 1 |  | YES | 4 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11317 | PC: Material Mgmt - Part Control I/II | In Production | PC: M11317 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | PC I: Material Mgmt Process - Parts Control. Secondary Outage Impacts: Customer Complaint, Impact to Financial Results |  |  | YES | 4 | RKENNEL | PLM | Mainframe | Q3 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11317 | PC: Material Mgmt - Part Control I/II | In Production | PC: M11317 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | PC I: Material Mgmt Process - Parts Control. Secondary Outage Impacts: Customer Complaint, Impact to Financial Results |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
11317 | PC: Material Mgmt - Part Control I/II | In Production | PC: M11317 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | PC I: Material Mgmt Process - Parts Control. Secondary Outage Impacts: Customer Complaint, Impact to Financial Results |  |  | YES | 4 | RKENNEL | PLM | WAS | Q3 2027 | Rewrite | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
51412 | PBOC V2 Credit Inquiry System | In Production | PBOCV2 | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | Non S-Ox | 332 | No | Yes | Managed by 3rd Party Purchased Service | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | PBOC V2 Credit Inquiry System for FAFC and Risk team to query credit report |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
12095 | Paystub Online | In Production | payonline | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | Displays employee pay stubs online. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
12095 | Paystub Online | In Production | payonline | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DDESAI | DDESAI | Finance | Staffs IT | Displays employee pay stubs online. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 | 2025-01-25 | Complete | Blue | 2025-09-13 |  | Planned |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | GCP Migration is completed for Database. DB VMs decommissioning planned by Q2 2025 due to HRIMS dependency | No | Oracle
51503 | Supplier Communications | In Production | SuppComm | EPEO | MCRNKOVI | BBOGEDIN | JMEZQUIT | JMEZQUIT | Bronze | Non S-Ox | 111 | No | Yes | In-House | MCRNKOVI | MCRNKOVI | Enterprise Technology | EPEO | The application displays database content in HTML format. There are forms that can be filled out by suppliers. There is content from GSEC teams throughout the world. There are PDFs and Word Documents available for download. | 4 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
12095 | Paystub Online | In Production | payonline | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | Displays employee pay stubs online. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
50509 | Paystub Mexico | In Production | PayMexico | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Copper | Non S-Ox | 331 | No | Yes | In-House | DDESAI | PTOCCO | Human Resources | Staffs IT | Displays Employee Paystub online |  | WAS | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
50341 | Paystub Canada | In Production | Paycanada | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | Displays Employee Paystub online |  | Java Struts | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is decommissioned already | No | Java < v21
50341 | Paystub Canada | In Production | Paycanada | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DDESAI | DDESAI | Finance | Staffs IT | Displays Employee Paystub online |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is decommissioned already. VMs are decommissioned | No | Oracle
13662 | Payroll-UK | In Production | EuAS_PayUK | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 321 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | All Payroll processing and employee payments are now performed for Ford of Britain Payroll by the Outsourced supplier (CGI). The UK Legacy Payroll Environment hosted on the Warley Mainframe still provides POCUS2 menu screens for navigation around the environment, an encryption and pass-through function for HMRC tax transmissions (en-route to CGI), a historic archive and EOS timekeeping and payroll reporting function. The mainframe codes supporting UK Legacy Payroll are WA.MP / WA.SP and WA.PF. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
506 | Payroll-ES | In Production | FOS-Payrol | ISIT | JPITTERL | STHOM124 | RDOMIN13 | MBALAN2 | Gold | S-Ox In Scope | 331 | No | Yes | In-House | JPITTERL | STHOM124 | Finance | Industrial System IT | Payroll ES/FOS-Payroll: The Payroll ES system generates the monthly payslip to ESP employees and files to be send to Social Security. It receives information from NETS (New European Timekeeping System) in order to know the month employee situation and pay accordingly. Additionally, generates the company accounting for PeopleSoft General Ledger. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q2 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | [9 empty] | Saran |  |  |  |  | No | Mainframe
12 | Payroll - US (HRIMS) | In Production | HRIMS | OCETO | TSWEEN16 | PTOCCO | LSUYAK | MBALAN2 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | Payroll application for US hourly and salary employees | 6 |  | YES | 2 | TSWEEN16 | PLM | WebFocus - MF | Q2 2025 | Modernize | Modernize | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | 50% | 50% | 50% | 50% | 50% | 50% | 50% |  | SaaS | [5 empty] | No | DA
12 | Payroll - US (HRIMS) | In Production | HRIMS | OCETO | TSWEEN16 | PTOCCO | LSUYAK | MBALAN2 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | Payroll application for US hourly and salary employees |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
51017 | Payments Unique Modular Application | In Production | PUMA | FORD CREDIT | JBENITO | SHODGSO9 | ADELUIS | AGALLAG9 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JBENITO | SHODGSO9 | Ford Credit Services | 311 | Application that provides functionality to perform & receive payments |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
51017 | Payments Unique Modular Application | In Production | PUMA | FORD CREDIT | JBENITO | SHODGSO9 | ADELUIS | AGALLAG9 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JBENITO | SHODGSO9 | Ford Credit Services | Ford Credit (FMCC) | Application that provides functionality to perform & receive payments |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
21632 | SteelHead | In Production | SteelHead | FORD PRO & FCSD TECH | OTHERS | LCAMAJ | MMELVIL2 | ABOBBALA | Copper | Non S-Ox | 311 | Yes | No | In-House | KDORONY | LCAMAJ | Ford Customer Service | - | Steelhead is a project management application for SEO Upstream Program Managers to track new vehicle program launch milestones and deliverables across the company. | 9 |  | YES | 2 | RKENNEL | PLM | VM | Q4 2026 | Partial Migration to GCP | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52956 | Payment Enablement Systems | In Production | PES | FORD CREDIT | IPANKAJ | VNAVEEN1 | VRUKMANG | ROBRIEN3 | Silver | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | VRUKMANG | Ford Credit Services | Ford Credit (FMCC) | Suite of services to enable payment across Ford & Ford Credit. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
11665 | Stamping Tooling Analysis and Mfg Plan Sys | In Production | Stamps | ISIT | SKING68 | JRICH264 | RCHANDA | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | RTHIRUV1 | Manufacturing Engineering | Industrial System IT | Tracks status of diesets for SBU from PDN to Prod plant shipping | 3 |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52956 | Payment Enablement Systems | In Production | PES | FORD CREDIT | IPANKAJ | VNAVEEN1 | VRUKMANG | ROBRIEN3 | Silver | Non S-Ox | 322 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Suite of services to enable payment across Ford & Ford Credit. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
23735 | Paycult CARUS Datacenter | In Production | EuHR-PayDC | OCETO | TSWEEN16 | KADOMKAI | MMUPPITA | ESTILESK | Copper | Non S-Ox | 111 | No | Yes | COTS | DDESAI | KADOMKAI | Ford Land | Staffs IT | Pay card management tool and sales data consolidation and reporting for loader and vending units. The pay cards are used in German sites at canteens, shops, and vending machines. This is a COTS application called CARUS datacentre and a CARUS card reader, both supplied by Paycult GmbH & Co KG Hamburg Germany. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q3 2025 | On-Prem | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
9088 | SMARTS/MOCA - Sales Mgmnt Analysis & Rptg Tool | In Production | SMARTS | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Data warehouse & toolset for the analysis / reporting of sales & stock information for Ford brand across the European markets. Data held within SMARTS is derived from the GENERIC EXTRACT which is updated every night. Data is held according to European business rules. Includes EMSS-MOCA (Market Offering Complexity Analysis) module which provides reports on top-selling entity/option mixes across Europe. Previous ITMS entry for MOCA (13328) now deleted and input merged with this (9088) | 3 |  | YES | 5 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50102 | PAX-IT | In Production | PAX-IT | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | PAX-IT Is an Image Management Software used for measuring, verifying and storing images of Welds. Joined parts cut and viewed under a microscope in a lab for evaluation. PRAX-IT works with a PRAXCAM camera mounted on a microscope. The images are managed by the software and are also used for reporting documents. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
22999 | SHAREPOINT CUSTOMIZATIONS | Active | SPCust | EPEO | SRUNSON | PWILL357 | MKEYSAE2 | MJANECZK | Silver | Non S-Ox | - | No | Yes | - | SRUNSON | PWILL357 | Enterprise Technology | - | Customizations to support the shared Enterprise SharePoint environment. This includes classification and labeling, site lifecycle management, security, and other miscellaneous customizations. | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
16427 | Password Expiration Notification | In Production | PEN | EPEO | SKULKA52 | SKRISH30 | MMUTHUK1 | GSIENKIE | Copper | Non S-Ox | 111 | Yes | No | In-House | CMIRABIT | CMIRABIT | Enterprise Technology | - | The Password Expiration Notification System will provide email notifications to individual and application owners when their Oracle passwords are due to expire within a 15-30 day window. |  |  | YES | 2 | SWALIMBE | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
9912 | Service Vehicle Info System (SERVIS2) | In Production | SERVIS2 | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SDEENAD1 | SDHANAS2 | Silver | S-Ox Out of Scope | 222 | No | Yes | In-House | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | SERVIS2 is the regional Warranty application for Asia Pacific. It replaced a warranty process that was largely manual and paper based. It provides the dealers with greater access to relevant vehicle data to enable them to drive customer satisfaction. The timely submission of data reduces the cycle time for feedback to quality teams via the interface to the global Analytical Warranty System (AWS). SERVIS2 is hosted in Dearborn. | 4 |  | YES | 5 | RKENNEL | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
12599 | Parts Order Processing | In Production | POPS | M&S TECH | RAHMED33 | GDIAZ1 | ASYRAGAK | IKALUGIN | Gold | Non S-Ox | 222 | No | Yes | In-House | KBERCH | GDIAZ1 | Ford Customer Service | Marketing, Sales and Service | Systems functions related to the processing of Parts order by each PDC so they are in an efficient picking sequence. |  |  | YES | 1 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
17146 | Parts Management System (PANDA) | In Production | PANDA | FORD PRO & FCSD TECH | DNANDAN | MAMUDHA | PVIVEKAN | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DNANDAN | Enterprise Technology | FCSD Tech | PANDA is the integrated parts management system used by Asia Pacific and Africa. For the warehouse, it manages all aspects of material control (receiving, storage, order processing, claims, intra-company shipments, packaging, junking and cyclic inventory). For Supply, it performs forecasting, procurement and expediting. For Marketing & Sales, it measures Work in Progress, Activity and dealer performance. For Finance, it supports Standard Costing, Accounting, Pricing and Billing through to Statements and Receivables. |  |  | YES | 4 | RKENNEL | PLM | Oracle | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
17146 | Parts Management System (PANDA) | In Production | PANDA | FORD PRO & FCSD TECH | DNANDAN | MAMUDHA | PVIVEKAN | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | MAMUDHA | Enterprise Technology | FCSD Tech | PANDA is the integrated parts management system used by Asia Pacific and Africa. For the warehouse, it manages all aspects of material control (receiving, storage, order processing, claims, intra-company shipments, packaging, junking and cyclic inventory). For Supply, it performs forecasting, procurement and expediting. For Marketing & Sales, it measures Work in Progress, Activity and dealer performance. For Finance, it supports Standard Costing, Accounting, Pricing and Billing through to Statements and Receivables. |  |  | YES | 4 | RKENNEL | PLM | SQL | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
9092 | SEER - Sales Eurovis Extract Reporter | In Production | SEER | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Analysis tool used by the following Central Business Groups: Ford of Europe (FoE), Middle East and Africa (MEA), The Americas, European Direct Markets (EDM) and Asia Pacific Africa (AP) to analyse sales & stock information at market level and below. Data held within SEER is derived from the GENERIC EXTRACT which is updated every night. It contains sales data for each market, from the point of order receipt to retail sale + history. This data can be used to find specific vehicles, spot delays, monitor dealer performance or perform sales analyses. As a result this tool is used for sales reporting & operational purposes. | 2 |  | YES | 3 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
17146 | Parts Management System (PANDA) | In Production | PANDA | FORD PRO & FCSD TECH | DNANDAN | MAMUDHA | PVIVEKAN | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | MAMUDHA | Enterprise Technology | FCSD Tech | PANDA is the integrated parts management system used by Asia Pacific and Africa. For the warehouse, it manages all aspects of material control (receiving, storage, order processing, claims, intra-company shipments, packaging, junking and cyclic inventory). For Supply, it performs forecasting, procurement and expediting. For Marketing & Sales, it measures Work in Progress, Activity and dealer performance. For Finance, it supports Standard Costing, Accounting, Pricing and Billing through to Statements and Receivables. |  |  | YES | 4 | RKENNEL | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
12597 | Parts Inventory Control | In Production | PMON | M&S TECH | RAHMED33 | GDIAZ1 | ASYRAGAK | IKALUGIN | Gold | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Ford Customer Service | Marketing, Sales and Service | Systems functions related to the management of the PDC inventory including Cycle Counting. |  |  | YES | 1 | NKANDULA | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9047 | Parts Income & Financial Analysis | In Production | PIFA | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | KVIJAY34 | PMURUG20 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | Parts Income & Financial Analysis (formerly IBIS) is a financial cost analysis data warehouse that stores the FCSD income statement for after market part sales from Ford to its distributors. It applies cost to all sales. The system is used by Ford of North America,Ford of Europe, Ford of Asia Pacific, and Ford of Middle East and Africa. |  |  | YES | 4 | RKENNEL | PLM | Mainframe | TBD | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9047 | Parts Income & Financial Analysis | In Production | PIFA | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | KVIJAY34 | PMURUG20 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | Parts Income & Financial Analysis (formerly IBIS) is a financial cost analysis data warehouse that stores the FCSD income statement for after market part sales from Ford to its distributors. It applies cost to all sales. The system is used by Ford of North America,Ford of Europe, Ford of Asia Pacific, and Ford of Middle East and Africa. |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
9047 | Parts Income & Financial Analysis | In Production | PIFA | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | KVIJAY34 | PMURUG20 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | RKENNEL | RKENNEL | Ford Customer Service | FCSD Tech | Parts Income & Financial Analysis (formerly IBIS) is a financial cost analysis data warehouse that stores the FCSD income statement for after market part sales from Ford to its distributors. It applies cost to all sales. The system is used by Ford of North America,Ford of Europe, Ford of Asia Pacific, and Ford of Middle East and Africa. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-29 | 2025-01-31 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | Oracle is decomissioned. | No | Oracle
9047 | Parts Income & Financial Analysis | In Production | PIFA | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | KVIJAY34 | PMURUG20 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | Parts Income & Financial Analysis (formerly IBIS) is a financial cost analysis data warehouse that stores the FCSD income statement for after market part sales from Ford to its distributors. It applies cost to all sales. The system is used by Ford of North America,Ford of Europe, Ford of Asia Pacific, and Ford of Middle East and Africa. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-29 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | Upgrade is completed . | No | Java < v21
19897 | Parts Data Warehouse | In Production | PDW | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | KVIJAY34 | PMURUG20 | Silver | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | Parts Data Warehouse (formerly GPARTS EDW) is a data warehouse application that receives data from 15+ interfaces (both Internal and External) and transfer all the attributes to the FORD Pricing system to set pricing for all the fter-market parts and accessories parts. The system is used by Ford of North America,Ford of Europe, Ford of Asia Pacific, and Ford of Middle East and Africa. | 1149 |  | YES | 3 | RKENNEL | PLM | Datastage | Q3 2025 | Modernize | Modernize | 2025-09-15 | 2025-09-30 |  | In-Progress | Green | 2025-12-29 |  | Planned |  | No | 25% | 25% | 25% |  |  |  | 25% | [6 empty] | This application is planned for Data stage to dataflow migration (GCP). They are in initial Phase; Project creation is completed for Dev and Prod. QA is yet to be enabled. 3 Region(AP, EU, NA). EU is planned for April 30th. | No | DA
19897 | Parts Data Warehouse | In Production | PDW | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | KVIJAY34 | PMURUG20 | Silver | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | Parts Data Warehouse (formerly GPARTS EDW) is a data warehouse application that receives data from 15+ interfaces (both Internal and External) and transfer all the attributes to the FORD Pricing system to set pricing for all the fter-market parts and accessories parts. The system is used by Ford of North America,Ford of Europe, Ford of Asia Pacific, and Ford of Middle East and Africa. |  |  | YES | 3 | RKENNEL | PLM | Mainframe | TBD | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
19897 | Parts Data Warehouse | In Production | PDW | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | KVIJAY34 | PMURUG20 | Silver | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | Parts Data Warehouse (formerly GPARTS EDW) is a data warehouse application that receives data from 15+ interfaces (both Internal and External) and transfer all the attributes to the FORD Pricing system to set pricing for all the fter-market parts and accessories parts. The system is used by Ford of North America,Ford of Europe, Ford of Asia Pacific, and Ford of Middle East and Africa. |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12013 | Parts Claims System | In Production | PCS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | The Parts Claims System allows dealers to submit claims to PS&L for parts that are received in a damaged condition or when the wrong part or part quantity has been shipped from the depot. |  |  | YES | 1 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
17966 | Parts & Accessories Datawarehouse (PAR) | In Production | PAR | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Customer Service | - | Database with P&A information that is used by P&A staff to get information abd compose some business report. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | Oracle Database is decommissioned | No | Oracle
25089 | SecOps User WebTools | In Production | SecOpTools | EPEO | NOKEEFE | MSNYDER5 | ZZHAN106 | GSIENKIE | Silver | Non S-Ox | 211 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Security Operations Tools website for Customer self-service solutions | 12 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
50896 | Partner Identity Management - SPS & MCS | In Production | PartnerIAM | EPEO | NOKEEFE | MSNYDER5 | SRAJEN26 | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Partner Identity Management is responsible for Managing B2B (Dealers, Suppliers & Other) Accounts lifecycle events. Dealer user personal accounts for their dealerships with Delegated Administration Model. Other external users such as Ford PRO, Marketingcomm,B2BSP and Tier2/3 supplier accounts. Supplier FSN accounts and their access to FORD FSP registered Applications. |  |  | YES | 5 | SWALIMBE | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50896 | Partner Identity Management - SPS & MCS | In Production | PartnerIAM | EPEO | NOKEEFE | MSNYDER5 | SRAJEN26 | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | In-House | NOKEEFE | NOKEEFE | Enterprise Technology | EPEO | Partner Identity Management is responsible for Managing B2B (Dealers, Suppliers & Other) Accounts lifecycle events. Dealer user personal accounts for their dealerships with Delegated Administration Model. Other external users such as Ford PRO, Marketingcomm,B2BSP and Tier2/3 supplier accounts. Supplier FSN accounts and their access to FORD FSP registered Applications. |  |  | YES | 5 | SWALIMBE | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
50896 | Partner Identity Management - SPS & MCS | In Production | PartnerIAM | EPEO | NOKEEFE | MSNYDER5 | SRAJEN26 | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Partner Identity Management is responsible for Managing B2B (Dealers, Suppliers & Other) Accounts lifecycle events. Dealer user personal accounts for their dealerships with Delegated Administration Model. Other external users such as Ford PRO, Marketingcomm,B2BSP and Tier2/3 supplier accounts. Supplier FSN accounts and their access to FORD FSP registered Applications. |  |  | YES | 5 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
24771 | SAS Real Time Decision Manager China | In Production | SASRDMCHNA | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Gold | Non S-Ox | 333 | No | Yes | COTS | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | SAS vendor client/server software that provides centralized control of development/delivery of tailored collections and originations strategies and scorecards (risk engine) across all portfolios and migrates them through all environments. This software also provides a repository for scorecards, strategies and metadata. | 1 |  | YES | 1 | SRAISIN1 | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
50896 | Partner Identity Management - SPS & MCS | In Production | PartnerIAM | EPEO | NOKEEFE | MSNYDER5 | SRAJEN26 | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Partner Identity Management is responsible for Managing B2B (Dealers, Suppliers & Other) Accounts lifecycle events. Dealer user personal accounts for their dealerships with Delegated Administration Model. Other external users such as Ford PRO, Marketingcomm,B2BSP and Tier2/3 supplier accounts. Supplier FSN accounts and their access to FORD FSP registered Applications. |  |  | YES | 5 | SWALIMBE | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
15340 | Part Tracking Management System | In Production | PTMS | ISIT | OTHERS | LJACOBI | SLEVAN | LPATIL | Silver | Non S-Ox | 211 | Yes | No | In-House | DLEHMKUH | LJACOBI | PD Operations and Quality | - | Part Tracking Management System is a workplanning tool to track vehicle program part information. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51971 | SA Payroll Solution (SAP EC & ECP) -Arg/Bra | In Production | SAP EC/ECP | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Gold | S-Ox Out of Scope | 311 | No | Yes | COTS | DBRIGHEN | RCORDEI1 | Finance | - | SAP solution which calculates the payroll for hourly and salaried employees of Brazil and Argentina. System already integrated with corporate applications - PeopleSoft HRMS and GL. The application is composed by two modules: EC (Employee Central) and ECP (Employee Central Payroll) which is part of SAP Success Factors suite. | 6 |  | YES | 1 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13060 | Work Order Request Manager | In Production | WORQ-RM | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | New Model Programs | Industrial System IT | WORQ (Work Order ReQuest) provides the ability to create, submit, and track Engineering Work Order ReQuests (WORQ). This app. supports Powertrain Engineering with electronic work order request forms for the tasks they need performed by the Prototype Build and Manufacturing sites. It also provides Prototype and Manufacturing Engineering with the information needed for managing work performed at a prototype facility. WORQ is used to track all types of work order requests including converter lab, metallurgical investigation, machine shop, tool design, internal work (people and their time), and part changes ... WORQ was originally created in 1995 and was ported to the WEB in 2002. Primary Users: Prototype Product and Manufacturing Engineering and Prototype Build Sites globally. NOTE: This application is replacing the VB3 version, WORQ 3.0, ITMS #775. Production support is billed is part of the WORQ suite currently billed under the prior WORQ application, itms #775. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | Java < v21
54893 | SA Mulesoft | In Production | MULE | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Bronze | Non S-Ox | 311 | No | Yes | COTS | DBRIGHEN | NMORALE7 | Marketing & Sales | - | IT manage process to support the partners to integrate platforms to facilitate, orchestrate and scale integrations between Salesforce, Dealers ERP and Ford legacy systems and support further integrations which not necessarily involve Salesforce. MuleSoft works like a middleware between platforms (integrated to Salesforce or not), connecting any technical language and architecture. | 3 |  | YES | 1 | TSWEEN16 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
53810 | Part Pedigree Tool | In Production | PPT | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | PD Operations and Quality | Industrial System IT | The Part Pedigree Tool is a common global tool for Test Engineers to view the as-built BOM for Prototype vehicles and any Part changes made to them after their initial build |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
18766 | Part Library II - PLII | In Production | PL-II | ISIT | MNOWICK1 | LSRINIVA | GPIOT1 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | Part Library II is intended to be the next generation of the Part Library application that's currently in production. This application is part of the Global Commodity Management initiative. It will serve as a catalog of technical attribute information for all commodities/parts. |  |  | YES | 3 | BWUNNAVA | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
18766 | Part Library II - PLII | In Production | PL-II | ISIT | MNOWICK1 | LSRINIVA | GPIOT1 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | Part Library II is intended to be the next generation of the Part Library application that's currently in production. This application is part of the Global Commodity Management initiative. It will serve as a catalog of technical attribute information for all commodities/parts. |  |  | YES | 3 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
52801 | SA Invoicing | In Production | SAI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | South America Invoicing application | 17 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
54257 | Part Count Input System | In Development | PCIS | ISIT | KCHRIST2 | HDIXON9 | MSILLMO1 | RPRASA22 | Bronze | Non S-Ox | 111 | Yes | No | In-House | KCHRIST2 | HDIXON9 | Enterprise Technology | - | Tracks manually entry of part inventory not otherwise captured by other systems |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
9976 | RTOM : Real Time Order Management System | In Production | RTOM | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | RTOM is a web/mainframe system that allocates vehicle and commodity production volumes from the market level to dealer level and produces Vehicle and Commodity Wholesale Guides for North American Dealers. | 12 |  | YES | 5 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23133 | Part Churn Reporting | In Production | Churn Rpt | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Silver | Non S-Ox | 211 | Yes | No | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | - | Calculates and reports on BOM Part Churn after FDJ. Reports are by program and PMT. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
21558 | RSW - Resource Staffing & Workload Hyperion | In Production | RSWHYP | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | SBONNICI | SBONNICI | PD Operations and Quality | Industrial System IT | RSW [Resource, Staffing and Workload] Hyperion is an internally hosted web application that supports common business practices / collaboration as a single source of information ensuring the right resources, at the right time (increasing resource utilization), integration of estimation models into a resource management solution and proactively detect, avoid cost overruns, and budget reconciliation to manage workload and program resources globally. | 42 |  | YES | 5 | BWUNNAVA | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
50621 | PARMS China | In Production | PARMSChina | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | 332 | PARMS is an application to maintain rates and marketing plans for Ford Credit China retail products during Offer submission and discounting. |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | Q1 2026 | Version Upgrade | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
57190 | RS&W PLANISWARE / OPERATING PLAN | In Production | RSWPLW | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Silver | Non S-Ox | 332 | No | Yes | COTS | SBONNICI | SBONNICI | PD Operations and Quality | - | RS&W Planisware / Operating Plan [Resource, Staffing and Workload] is an internally hosted web application that supports common business practices / collaboration as a single source of information ensuring the right resources, at the right time (increasing resource utilization), integration of estimation models into a resource management solution and proactively detect, avoid cost overruns, and budget reconciliation to manage workload and program resources globally. | 22 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
23676 | Paperless Illustrations Tablet Application | In Production | PITA | ISIT | OTHERS | NVIJAYA1 | SRAJMOHA | GRAO3 | Silver | Non S-Ox | 211 | Yes | No | COTS | RHAZEL | NVIJAYA1 | PD Operations and Quality | Industrial System IT | PITA (Paperless Illustrations Tablet Application) is an Windows Tablet/PC application developed to replace the hard copies of Illustration manuals with search, view, markup, and create collection features on PDF eBooks. |  |  | YES | 1 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23728 | PAM Attribute Calculator | In Production | PAM-AC | ISIT | MNOWICK1 | LSRINIVA | DESPINOS | JLUCAS1 | Silver | Non S-Ox | 233 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | 233 | Product Attribute Management (PAM) Attribute Calculator. This application provides for calculations on a highly available basis based on PAM data. Related to / interfaces with 23716 Product Attribute Management (PAM) |  | Springboot | YES | 2 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
18861 | Reval | In Production | Reval | I-ERP | SFRANCI8 | DSAKAMUR | KMOHAN15 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | Managed by 3rd Party Purchased Service | SFRANCI8 | DSAKAMUR | Finance | Integrated Enterprise Resource Planning (I-ERP) | Externally hosted application (Application Service Provider model) to be used for effectiveness testing and hedge accounting for FAS 133. Application contains debt, derivative, foreign exchange and commodity data from Wall Street Suite. | 8 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
21382 | Paint End-of-line Dirt Detection System | In Production | PEDDS | ISIT | SKING68 | JLYNN1 | GKESAVAR | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | This system stores the images from the vision systems and analyzes those images for paint problem determination |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q2 2025 | Version Upgrade | Modernize | 2024-07-31 | 2024-07-31 | 2024-07-31 | Complete | Blue | 2024-11-22 | 2024-11-19 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Priya | 2025-03-04 |  |  | App is on Java 17 & Planning for V21 upgrade in Q2 2025 | No | Java < v21
21382 | Paint End-of-line Dirt Detection System | In Production | PEDDS | ISIT | SKING68 | JLYNN1 | GKESAVAR | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | This system stores the images from the vision systems and analyzes those images for paint problem determination |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Version Upgrade | Modernize | 2024-07-31 | 2024-07-31 | 2024-07-31 | Complete | Blue | 2024-11-22 | 2024-11-19 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Priya | 2025-03-04 |  |  | App modernized to Angular & Springboot | No | Java < v21
13060 | Work Order Request Manager | In Production | WORQ-RM | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House |  |  | New Model Programs | Industrial System IT | WORQ (Work Order ReQuest) provides the ability to create, submit, and track Engineering Work Order ReQuests (WORQ). This app. supports Powertrain Engineering with electronic work order request forms for the tasks they need performed by the Prototype Build and Manufacturing sites. It also provides Prototype and Manufacturing Engineering with the information needed for managing work performed at a prototype facility. WORQ is used to track all types of work order requests including converter lab, metallurgical investigation, machine shop, tool design, internal work (people and their time), and part changes ... WORQ was originally created in 1995 and was ported to the WEB in 2002. Primary Users: Prototype Product and Manufacturing Engineering and Prototype Build Sites globally. NOTE: This application is replacing the VB3 version, WORQ 3.0, ITMS #775. Production support is billed is part of the WORQ suite currently billed under the prior WORQ application, itms #775. | 3 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-20 | 2024-12-20 |  | In-Progress | Green | 2025-06-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | No | VM
21859 | QRadar (SIEM) | In Production | QRadar | EPEO | NOKEEFE | NOKEEFE | VVENKA40 | WJUSTICE | Bronze | Non S-Ox | 232 | No | Yes | COTS | UARJUNAN | NOKEEFE | Enterprise Technology | EPEO | IBM Security QRadar Security Intelligence and Event Management (SIEM) system consolidates log source event data from thousands of devices to prioritize security incidents and vulnerabilities. | 5 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
11772 | Paint Emissions Reporting System | In Production | PERS | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Bronze | Non S-Ox | 111 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | 111 | Formerly Volatile Organic Compounds |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
11772 | Paint Emissions Reporting System | In Production | PERS | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Bronze | Non S-Ox | 111 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Formerly Volatile Organic Compounds |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
24095 | QPR (Quality System and Supplier Documents) | In Production | QPR | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Bronze | Non S-Ox | 111 | Yes | No | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Application used by suppliers and purchasing STA team to view user guides and reference material | 3 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20977 | PADB2 | In Production | PADB2 | ISIT | MNOWICK1 | LSRINIVA | VATMAKUR | LPATIL | Silver | Non S-Ox | 111 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | - | The Part Address Database holds mappings of parts to part functions and CPSC II codes, maintaining the CPSC II information standard. |  |  | YES | 2 | BWUNNAVA | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
17413 | QAD MFG/PRO | In Production | QAD | I-ERP | SFRANCI8 | RJAYAKU2 | RSRIRA18 | LWU14 | Bronze | S-Ox Out of Scope | 331 | No | Yes | COTS | SFRANCI8 | RJAYAKU2 | Finance | - | QAD MFG/PRO is an ERP application hosted in Dearborn. The following modules of QAD are extensively used in APA markets: A/P, GL, FAPC, Non-product purchasing/inventory. (Note: The JLR instances of QAD were separated in Oct 2009 via SWIFT) | 8 |  | YES | 1 | TSWEEN16 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
14893 | PackMan | In Production | PACKMAN | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Packaging data collection and maintenance system used within Vehicle and Powertrain Operation plants within Europe. |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
14893 | PackMan | In Production | PACKMAN | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | GHERMAN | Manufacturing Staffs | Industrial System IT | Packaging data collection and maintenance system used within Vehicle and Powertrain Operation plants within Europe. |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2027 | On-Prem | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Oracle
14893 | PackMan | In Production | PACKMAN | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Packaging data collection and maintenance system used within Vehicle and Powertrain Operation plants within Europe. |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
50781 | PTNVH Process Tools | In Production | PTNVH-TRS | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | In House process software to manage business process and run estimation tools. | 8 |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20032 | OWS Warranty Claim Processing | In Production | OWS Claims | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | PSATHEE2 | RC41 | Silver | S-Ox In Scope | 232 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | Global claims processing and adjudication. Includes accounting modules and interfaces to the Business Rules Engine. |  |  | YES | 5 | RKENNEL | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
20032 | OWS Warranty Claim Processing | In Production | OWS Claims | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | PSATHEE2 | RC41 | Silver | S-Ox In Scope | 232 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | Global claims processing and adjudication. Includes accounting modules and interfaces to the Business Rules Engine. |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  | 2025-12-30 |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
20032 | OWS Warranty Claim Processing | In Production | OWS Claims | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | PSATHEE2 | RC41 | Silver | S-Ox In Scope | 232 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | Global claims processing and adjudication. Includes accounting modules and interfaces to the Business Rules Engine. |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
54670 | Proving Grounds Weather Application - Vista Data V | In Production | PGWA | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Bronze | Non S-Ox | 11 | No | Yes | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | Web based application that Acquires, Monitors, analyzes, visualizes, and manages weather instrumentation data. | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
20032 | OWS Warranty Claim Processing | In Production | OWS Claims | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | PSATHEE2 | RC41 | Silver | S-Ox In Scope | 232 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | Global claims processing and adjudication. Includes accounting modules and interfaces to the Business Rules Engine. |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  | 2025-12-30 |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
19656 | OWS Service Event Data Collector | In Production | OWS SEDC | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | VRAMAC10 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | One Warranty System application to collect data throughout service event, focusing on Repair Order, Diagnostic Session data and Sync Health Reports. Will be used by Find A Vehicle Functionality. PDR - Pre Defined Repair is created in WC box and it is used in GACES. PDR Master screen in WC is used to create PDR in GACES after validating entries through web services. We have Create, Edit, Delete & Search PDR functionalities. |  |  | YES | 3 | RKENNEL | PLM | Java Struts | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
19656 | OWS Service Event Data Collector | In Production | OWS SEDC | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | VRAMAC10 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | One Warranty System application to collect data throughout service event, focusing on Repair Order, Diagnostic Session data and Sync Health Reports. Will be used by Find A Vehicle Functionality. PDR - Pre Defined Repair is created in WC box and it is used in GACES. PDR Master screen in WC is used to create PDR in GACES after validating entries through web services. We have Create, Edit, Delete & Search PDR functionalities. |  |  | YES | 3 | RKENNEL | PLM | SQL | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
57031 | ProofPoint TRAP | Planned | TRAP | EPEO | SRUNSON | ASTONE31 | MMAHAJAN | JHARR604 | Platinum | Non S-Ox | 332 | No | Yes | COTS | SRUNSON | ASTONE31 | Enterprise Technology | EPEO | Proofpoint Threat Response Auto-Pull (TRAP) enables messaging and security administrators to analyze emails and move malicious or unwanted emails to quarantine, after delivery. It follows forwarded mail and distribution lists and creates an auditable activity trail. | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
12342 | OVS - OPTIMISED VEHICLE SCHEDULING | In Production | OVS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Selects vehicles for scheduling to the manufacturing plants. OVS is a system that schedules on what particular day a vehicle is to be built. |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12342 | OVS - OPTIMISED VEHICLE SCHEDULING | In Production | OVS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Selects vehicles for scheduling to the manufacturing plants. OVS is a system that schedules on what particular day a vehicle is to be built. |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
13063 | Professional Technician System | In Production | PTS | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | QBROWN4 | BGHANTA | Gold | Non S-Ox | 222 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | PTS is the technical portal for internal FORD users and dealership employees globally. Includes SPECS, Service Advisor Portal and Newfordtech. | 41 |  | YES | 2 | RKENNEL | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12342 | OVS - OPTIMISED VEHICLE SCHEDULING | In Production | OVS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Selects vehicles for scheduling to the manufacturing plants. OVS is a system that schedules on what particular day a vehicle is to be built. |  |  | YES | 4 | NKANDULA | PLM | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
11483 | PeopleSoft (ASR) GL | In Production | ASR GL | I-ERP | SFRANCI8 | DSHAH1 | AWALIA1 | HPADMANA | Gold | S-Ox In Scope | 232 | No | Yes | COTS | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | PeopleSoft (ASR) GL - General Ledger application. Global strategic general ledger solution. | 2 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
11995 | Others | Not In EAMS |  | OTHERS | OTHERS | [5 empty] | - | No | Yes | - | OTHERS | OTHERS | - |  |  |  |  | YES | 1 | OTHERS | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | DA
50755 | OTA Based Instructions | In Production | OBI | EVDD | JWASNIC1 | FGRABOWS | TPUSHMA1 | LBURGTOR | Gold | Non S-Ox | 222 | No | Yes | - | #N/A | #N/A | Advanced PD and Tech | 222 | OBI IS A FRONT-END INTERFACE TO OTA (OVER THE AIR UPDATES SPACE) FROM EXTERNAL APPLICATIONS FOR ANY INFORMATION OR UPDATES RELATED TO A SINGLE VEHICLE. OBI ALSO ACTS AS A ROUTING SYSTEM FOR APPLICATIONS WITHIN OTA SPACE, AS IT FACILITATES MESSAGES BETWEEN OTA APPLICATIONS LIKE FORCE, VADR, FENIX ETC. DEALER SYSTEMS AND CONSUMER WEBSITE ALSO USES OBI TO REQUEST AND RECEIVE OTA MANIFEST TO DELIVER TO VEHICLE VIA USB. OBI IS ALSO THE SYSTEM THAT DELIVERS VEHICLE BASED DIRECT CONFIGURATION UPDATES TO TMC. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
12015 | Order Qualification System | In Production | OQS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | OQS is the system used by PS&L to define marketing programs for service/aftermarket parts, and to assign order discounts to those marketing programs. |  |  | YES | 1 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
9923 | Order Processing | In Production | OPS | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Batch system that accepts vehicle orders via Direct Order Entry (DOE) and Remote Job Entry (RJE); edits and submits/rejects vehicle orders and prepares vehicle order files for downstream systems and creates report based on vehicle order status. / Old Acronym : OPS SLA 1, CIA 2,3,3 |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q3 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9923 | Order Processing | In Production | OPS | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Batch system that accepts vehicle orders via Direct Order Entry (DOE) and Remote Job Entry (RJE); edits and submits/rejects vehicle orders and prepares vehicle order files for downstream systems and creates report based on vehicle order status. / Old Acronym : OPS SLA 1, CIA 2,3,3 |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
16531 | Order Mgmt Services / Single Order Bank | In Production | OMS/SOB | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Order Management Services will receive and control product and non-product related order changes to the Order Fulfillment Single Order bank. The Single Order Bank is the single master repository of orders associated with vehicles built and/or sold in North America. Order Management Services facilitates transactions to/from the Single Order Bank and provides order controls to ensure that revenue, finished goods inventory, work-in-process inventory and material utilization are properly reflected within the associated systems and financial records. |  |  | YES | 4 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
16531 | Order Mgmt Services / Single Order Bank | In Production | OMS/SOB | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Order Management Services will receive and control product and non-product related order changes to the Order Fulfillment Single Order bank. The Single Order Bank is the single master repository of orders associated with vehicles built and/or sold in North America. Order Management Services facilitates transactions to/from the Single Order Bank and provides order controls to ensure that revenue, finished goods inventory, work-in-process inventory and material utilization are properly reflected within the associated systems and financial records. |  |  | YES | 4 | NKANDULA | PLM | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
16531 | Order Mgmt Services / Single Order Bank | In Production | OMS/SOB | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Order Management Services will receive and control product and non-product related order changes to the Order Fulfillment Single Order bank. The Single Order Bank is the single master repository of orders associated with vehicles built and/or sold in North America. Order Management Services facilitates transactions to/from the Single Order Bank and provides order controls to ensure that revenue, finished goods inventory, work-in-process inventory and material utilization are properly reflected within the associated systems and financial records. |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
16531 | Order Mgmt Services / Single Order Bank | In Production | OMS/SOB | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Order Management Services will receive and control product and non-product related order changes to the Order Fulfillment Single Order bank. The Single Order Bank is the single master repository of orders associated with vehicles built and/or sold in North America. Order Management Services facilitates transactions to/from the Single Order Bank and provides order controls to ensure that revenue, finished goods inventory, work-in-process inventory and material utilization are properly reflected within the associated systems and financial records. |  |  | YES | 4 | NKANDULA | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
208 | Order History | In Production | OHist | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 111 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Batch and online processes to provide view of a historical log of transactions processed against orders on the USOB. SLA1 CIA 1,1,1 |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
208 | Order History | In Production | OHist | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 111 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Batch and online processes to provide view of a historical log of transactions processed against orders on the USOB. SLA1 CIA 1,1,1 |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
11561 | Order Fulfillment Data Warehouse | In Production | OFM/DW | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | The Order Fulfillment Metrics Data Warehouse provides standard reports, metrics, and analysis capability across the Order Fulfillment Enterprise Process (MS&S, MP&L, and Manufacturing) for North America and Europe and primarily includes data pertaining to vehicle order and part forecasting, scheduling, manufacturing, transportation, and delivery along with accruals and reconciliations to support the controllers office. | 177 |  | YES | 4 | BWUNNAVA | PLM | BO | Q1 2026 | Migrate to QlikSense | Modernize | 2026-03-31 | 2026-03-31 |  | In-Progress | Green | 2026-06-29 |  | Planned |  | No | [8 empty] | QlikSense | [5 empty] | No | DA
11561 | Order Fulfillment Data Warehouse | In Production | OFM/DW | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | The Order Fulfillment Metrics Data Warehouse provides standard reports, metrics, and analysis capability across the Order Fulfillment Enterprise Process (MS&S, MP&L, and Manufacturing) for North America and Europe and primarily includes data pertaining to vehicle order and part forecasting, scheduling, manufacturing, transportation, and delivery along with accruals and reconciliations to support the controllers office. |  |  | YES | 4 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11561 | Order Fulfillment Data Warehouse | In Production | OFM/DW | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SROYCHOU | SROYCHOU | Manufacturing Staffs | Industrial System IT | The Order Fulfillment Metrics Data Warehouse provides standard reports, metrics, and analysis capability across the Order Fulfillment Enterprise Process (MS&S, MP&L, and Manufacturing) for North America and Europe and primarily includes data pertaining to vehicle order and part forecasting, scheduling, manufacturing, transportation, and delivery along with accruals and reconciliations to support the controllers office. |  |  | YES | 4 | BWUNNAVA | PLM | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
53648 | OneSource Tax One | In Production | Taxone | OCETO | DBRIGHEN | RCORDEI1 | EDUARTE1 | NMORALE7 | Silver | S-Ox In Scope | 331 | No | Yes | COTS | DBRIGHEN | RCORDEI1 | Finance | - | OneSource Tax One - Thomson Reuters fiscal solution (SaaS) composed by: Tax One, Transfer Pricing Brasil, Tax Calendar,EFD-REINF | 4 |  | YES | 1 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
52427 | Order Exchange Services | In Production | OES | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | PSATISH2 | Bronze | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | A Collection of Order Exchange Services supporting the Ford Volkswagen Alliance. |  |  | YES | 3 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | Need to remove the EBS lineitem | No | DA
52427 | Order Exchange Services | In Production | OES | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | PSATISH2 | Bronze | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | A Collection of Order Exchange Services supporting the Ford Volkswagen Alliance. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-10-29 | Complete | Blue | 2024-12-15 | 2024-10-29 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | SQL
19522 | Onesource Suite | In Production | Onesource | I-ERP | SFRANCI8 | JCHATZKA | JBEISER1 | LWU14 | Copper | S-Ox In Scope | 331 | Yes | No | Managed by 3rd Party Purchased Service | RCAHALA1 | JCHATZKA | Finance | - | OneSource Tax is a platform that runs multiple modules. Currently Ford Motor Company licenses the Global Tax Provision, Workflow and Global Pricing Compliance modules. The global tax provision is the first chronological step of the corporate tax year. The tax provison module has all the necessary functionality to calculate the provision and provide all supporting reports. The workflow module provides workflow, dashboard, fileroom and dataflow capabilities to the other OneSource modules. The Operational Transfer Pricing module is used to segment Ford legal entities for transfer pricing purposes. | 1 |  | YES | 1 | TSWEEN16 | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
52427 | Order Exchange Services | In Production | OES | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | PSATISH2 | Bronze | Non S-Ox | 222 | No | Yes | In-House |  |  | Marketing & Sales | Marketing, Sales and Service | A Collection of Order Exchange Services supporting the Ford Volkswagen Alliance. |  | Springboot | YES | 4 | NKANDULA | PLM | Java < v21 | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
338 | Order Control | In Production | OC | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Gold | S-Ox In Scope | 133 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | Part of VSC. The application maintains the production order bank of vehicles for North America.It records the vehicle status as it moves within the assembly plant. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q3 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
338 | Order Control | In Production | OC | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Gold | S-Ox In Scope | 133 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | Part of VSC. The application maintains the production order bank of vehicles for North America.It records the vehicle status as it moves within the assembly plant. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
23097 | Order and Pricing Guides | In Production | OrdPrcGuid | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | Marketing, Sales and Service | Order and Pricing Guides is an online source for comprehensive information for FoC Dealers on Ford's new lineup of cars and trucks. Each vehicle's complete order and pricing guide pages are available on-line for quick reference. |  |  | YES | 4 | NKANDULA | PLM | Java Struts |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | It was a WAS/JSF application should we count under Java struts | No | Java < v21
23097 | Order and Pricing Guides | In Production | OrdPrcGuid | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | Marketing, Sales and Service | Order and Pricing Guides is an online source for comprehensive information for FoC Dealers on Ford's new lineup of cars and trucks. Each vehicle's complete order and pricing guide pages are available on-line for quick reference. |  |  | YES | 4 | NKANDULA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-11-10 | Complete | Blue | 2024-12-15 | 2024-11-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | New Platform altogether |  |  |  |  | Moved to FirestoreDB | No | SQL
14804 | Odyssey | In Production | Odyssey | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | TARUNKU4 | JSING217 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Odyssey is a management system for the development of all complex multilingual technical information for dealers and owners. It is comprised of XML data management workflow, graphical management and linguistic capabilities. It is used by Ford, Jaguar, Landover as a key system and by Mazda and Volvo for some features. | 26 |  | YES | 3 | RKENNEL | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23097 | Order and Pricing Guides | In Production | OrdPrcGuid | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | Marketing, Sales and Service | Order and Pricing Guides is an online source for comprehensive information for FoC Dealers on Ford's new lineup of cars and trucks. Each vehicle's complete order and pricing guide pages are available on-line for quick reference. |  |  | YES | 4 | NKANDULA | PLM | WAS |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
22574 | NMP Global Prototype System | In Production | NMPGPS | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | New Model Programs | Industrial System IT | Replacement for Scheduler, Process Locator, Pick Readiness, Stop Build and NMP Web legacy applications. | 5 |  | YES | 4 | BWUNNAVA | PLM | VM | Q4 2026 | Partial Migration to GCP | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19420 | Oracle IMS Gateway | Active | OIG | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Copper | Non S-Ox | - | No | - | - | AFRADKIN | AFRADKIN | Information Technology | Marketing, Sales and Service | The Oracle IMS Gateway is an infrastructure application developed by the ITI Ford Middleware Development Team that allows access to Fords IMS Mainframe systems from an Oracle DB environment. This infrastructure application provides the ability for any authorized Ford Oracle application to access IMS transactions. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
23894 | MICROSOFT EXCHANGE 2016 | Active | E2016 | EPEO | SRUNSON | ASTONE31 | MMAHAJAN | MMAHAJAN | Platinum | Non S-Ox | - | No | Yes | - | SRUNSON | ASTONE31 | Enterprise Technology | - | Microsoft Exchange 2016 is the update to Ford's global email infrastructure | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
19241 | Oracle Enterprise Manager | Active | OEManager | EPEO | SKULKA52 | NSHAH43 | HLIN13 | NVAIDYAN | Gold | Non S-Ox | - | No | - | - | CMIRABIT | CMIRABIT | Information Technology | ITO | Oracle Enterprise Manager Agents physical implementation information and monitoring |  |  | YES | 3 | SWALIMBE | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
19241 | Oracle Enterprise Manager | Active | OEManager | EPEO | SKULKA52 | NSHAH43 | HLIN13 | NVAIDYAN | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 3 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
11151 | Mass Analysis System | In Production | MAS | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 222 | No | Yes | In-House | DKAVITHA | UVIJAYAL | PD Operations and Quality | Industrial System IT | The Mass Analysis System MAS is designed to aid the Weight Engineering Department in documenting and communicating vehicle program weight data and recommendations to the program teams and regulatory agencies globally. In addition the MAS system will be used to consolidate the weight information to a single source which will allow more efficient and consistent resolution of weight issues tracking and reporting.It provides the following features Common system for mass analysis replacing varied systems tools. Common reporting formats that create an efficient customer interface. Flexibility to build mass models from End Item CPSC or Curb level weights. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19419 | ORACLE DRDA DOWNLOAD | In Production | DRDA DL | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | - | No | - | - | TVASU | NSENTHI1 | Information Technology | Marketing, Sales and Service | Oracle DRDA Download is an application that is used to replicate DB2 data into Oracle. It uses Oracles DRDA gateway to connect to DB2 from Oracle DB environment. Customers of this application use it to configure and monitor download jobs to selectively download DB2 data into their own Oracle database. |  |  | YES | 3 | TSWEEN16 | PLM | Java Struts | Q3 2025 | Rewrite | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
19419 | ORACLE DRDA DOWNLOAD | Active | DRDA DL | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | - | No | - | - | AFRADKIN | AFRADKIN | Information Technology | Marketing, Sales and Service | Oracle DRDA Download is an application that is used to replicate DB2 data into Oracle. It uses Oracles DRDA gateway to connect to DB2 from Oracle DB environment. Customers of this application use it to configure and monitor download jobs to selectively download DB2 data into their own Oracle database. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Oracle
12120 | Lean Manufacturing Assistant | In Production | LMA | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Staffs | Industrial System IT | The Lean Manufacturing Assistant is a real-time part flow visualization tool that enables line operators and plant personnel to increase manufacturing productivity | 2 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
19242 | Oracle | Active | Oracle | EPEO | SKULKA52 | NSHAH43 | NVAIDYAN | NVAIDYAN | Copper | Non S-Ox | - | No | - | - | CMIRABIT | CMIRABIT | Information Technology | ITO | Oracle Database physical implementation information and monitoring |  |  | YES | 2 | SWALIMBE | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
15687 | Knowledge Based Systems on Prem | In Production | KBS onPrem | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | TSAILESH | Silver | Non S-Ox | 333 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | The Knowledge Based System (KBS) is comprised of two applications, the Offering Analysis Knowledge Base System (OAKBS) and sKBS the Scoring Knowledge Base System. OAKBS use decision-reasoning software to determine strength and weakness characteristics for offerings submitted to Ford Financial. The information supplied by OAKBS is displayed in the Analysis section of Pinnacle Credit Analysis and is used by credit analysts when manually decisioning credit applications. Also oaKBS is used to decision Offerings including PreApproval or PreQualification applications submitted to Ford Financial via the internet or Creditweb. sKBS provides a set of predictive characteristics that are input into scorecards used in determining a customer's credit worthiness. | 15 |  | YES | 1 | SRAISIN1 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
51842 | Optimal Staffing Assignment | In Production | OSA | ISIT | SKING68 | DCLEME13 | MIVES6 | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Manufacturing Plants | 111 | ABILITY TO MANAGE OPERATORS FOR WORKFORCE OPTIMIZATION. VIEWING HISTORICAL PERFORMANCE TO VERSATILITY MATRIX IN OPTIMIZING ALLOCATION. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
19270 | OPST - OPEC & Stillage | In Production | OPST | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | - | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | The OPST application is based on two legacy applications which have now been combined: 1) OPEC: Administration & Control of Prototype Engines. 2) STILLAGE : Manage Engine Stillage Stores. Track Engine location changes. Monitor Engine Archiving. NB: Application production support is provided by ADS PD Practice but historically was developed within PD and resulted from an audit requirement to track prototype engines. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
19270 | OPST - OPEC & Stillage | In Production | OPST | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | - | JKOONS | JKOONS | PD Operations and Quality | Industrial System IT | The OPST application is based on two legacy applications which have now been combined: 1) OPEC: Administration & Control of Prototype Engines. 2) STILLAGE : Manage Engine Stillage Stores. Track Engine location changes. Monitor Engine Archiving. NB: Application production support is provided by ADS PD Practice but historically was developed within PD and resulted from an audit requirement to track prototype engines. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Oracle
19270 | OPST - OPEC & Stillage | In Production | OPST | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | - | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | The OPST application is based on two legacy applications which have now been combined: 1) OPEC: Administration & Control of Prototype Engines. 2) STILLAGE : Manage Engine Stillage Stores. Track Engine location changes. Monitor Engine Archiving. NB: Application production support is provided by ADS PD Practice but historically was developed within PD and resulted from an audit requirement to track prototype engines. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
12757 | Operations Management Systems | In Production | OMS | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Silver | Non S-Ox | 211 | No | Yes | In-House | KPINNU | KHILLERT | Ford Customer Service | Marketing, Sales and Service | Dealer database for COMBAT support. Contains DSP indicator, COMBAT File directory and dealership computer telephone number. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12757 | Operations Management Systems | In Production | OMS | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Silver | Non S-Ox | 211 | No | Yes | In-House | KPINNU | KHILLERT | Ford Customer Service | Marketing, Sales and Service | Dealer database for COMBAT support. Contains DSP indicator, COMBAT File directory and dealership computer telephone number. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q2 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Mainframe
22734 | OnTrack MIS | In Production | OnTrack | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Silver | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Engineering | Industrial System IT | The OnTrack MIS is the next generation of Production monitoring and downtime tracking for all Ford Stamping Plants. The application is COTS and includes interfaces to several other applications (Marquee Manager, First Page, MFM, PCON, JEDI and CMMS). In addtion to prduction monitoring, On Track MIS provides live inventory updates, schedule execution, direct labor metrics, and Die-change planning and execution, Scrap/Reject entry, tracking and reporting. Primary focus is on the part being produced. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
50206 | INFORMATICA SHARED CIM (CLOUD INTEGRATION MIDDLEWA | Active | CIM-Share | EPEO | SKULKA52 | MWILLI20 | MMAES | RMODI2 | Bronze | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | ITO | This entry is for the Informatica Shared IICS environments (aka CIM). Customers of this service are required to raise their own EAMS entries, complete GRC App Assessments, etc. as required. This Middleware Service provided by Informatica allows B2B and B2C access, data management and integration for delivery of trusted critical data, at any speed, batch or streaming, reliably and at scale, to fuel advanced analytics and critical operations. This is a PLACEHOLDER EAMS entry, per the 'IT Application Portfolio Management' guidelines. | 24 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
24411 | Onsite (Reserve/Navigate/Stop Leaks) | In Production | FSMA | OCETO | TSWEEN16 | KADOMKAI | PPOBURSK | ESTILESK | Copper | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Enterprise Technology | Staffs IT | An application to provide end users the ability and ease to smoothly carryon the activities that will increase workplace productivity, efficiency, collaboration, and will transform the way we work by being able to find or spot needed spaces, tools, or people. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-11-30 | Complete | Blue | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | Database migration completed | No | SQL
24538 | INFORMATICA DEDICATED CIM (CLOUD INTEGRATION MIDDL | Active | CIM-Dedic. | EPEO | SKULKA52 | MWILLI20 | MMAES | RMODI2 | Bronze | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | ITO | This entry is for the Informatica Dedicated IICS environments (aka CIM). Customers of this service are required to raise their own EAMS entries, complete GRC App Assessments, etc. as required. This Middleware Service provided by Informatica allows B2B and B2C access, data management and integration for delivery of trusted critical data, at any speed, batch or streaming, reliably and at scale, to fuel advanced analytics and critical operations. This is a PLACEHOLDER EAMS entry, per the 'IT Application Portfolio Management' guidelines. | 30 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
24411 | Onsite (Reserve/Navigate/Stop Leaks) | In Production | FSMA | OCETO | TSWEEN16 | KADOMKAI | PPOBURSK | ESTILESK | Copper | Non S-Ox | 211 | No | Yes | In-House |  |  | Enterprise Technology | Staffs IT | An application to provide end users the ability and ease to smoothly carryon the activities that will increase workplace productivity, efficiency, collaboration, and will transform the way we work by being able to find or spot needed spaces, tools, or people. |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
54153 | On-Prem ESXi Hosting | Active | OPESXiH | EPEO | LFULCHER | KMAHAJAN | GBRADFO3 | GBRADFO3 | Bronze | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53023 | Habitat Config Options To CDJ | In Production | HCO2CDJ | EPEO | LFULCHER | KMAHAJAN | OSHVARTS | CDOSHI | Copper | S-Ox Out of Scope | - | No | Yes | In-House | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | Configure and sends Habitat scripts | 5 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
22901 | ONP - Vehicle Energy Compliance Model | In Production | ONP-VECM | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 321 | No | Yes | In-House | JKOONS | NLAKSHMA | PD Operations and Quality | Industrial System IT | The application will support the source input data processing for the New Compliance Model calculator on Ne National Program. ONP program will enable business process improvements in products/programs cycle planning and compliance reporting process through a comprehensive integrated global IT strategy enabling business teams in developing product scenarios to optimize compliance strategy by managing vehicle and fleet level fuel economy and emissions targets. Provide technological solutions for business capabilities to optimize product mix with technology offerings for future profits and credits as well as meet the stringent regulatory compliance targets |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50278 | HABITAT | Active | Habitat | EPEO | LFULCHER | KMAHAJAN | TKLEMER | TKLEMER | Silver | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | Enterprise Technology | ITO | Habitat is a simple, flexible way to build, deploy, and manage cloud native applications | 19 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
22901 | ONP - Vehicle Energy Compliance Model | In Production | ONP-VECM | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 321 | No | Yes | In-House | JKOONS | NLAKSHMA | PD Operations and Quality | Industrial System IT | The application will support the source input data processing for the New Compliance Model calculator on Ne National Program. ONP program will enable business process improvements in products/programs cycle planning and compliance reporting process through a comprehensive integrated global IT strategy enabling business teams in developing product scenarios to optimize compliance strategy by managing vehicle and fleet level fuel economy and emissions targets. Provide technological solutions for business capabilities to optimize product mix with technology offerings for future profits and credits as well as meet the stringent regulatory compliance targets |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
20655 | Online Supplier Rating Control | In Production | OSRC | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Quality | Industrial System IT | The OSRC application is used to register and follow up IMRR, PSW and incoming parts; as well as it allows the user to evaluate the supplier rating. This application was originally designed for the Valencia Engine Plant and REDESIGNED to be used by all PTO plants within Europe. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | Q1 2025 | Will be Decommissioned | Decommission | 2025-01-09 | 2025-01-09 | 2025-01-09 | Complete | Blue | 2025-01-09 | 2025-01-09 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Ramesh | 2025-03-04 |  |  | App is Decommissioned | No | Java < v21
20655 | Online Supplier Rating Control | In Production | OSRC | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Quality | Industrial System IT | The OSRC application is used to register and follow up IMRR, PSW and incoming parts; as well as it allows the user to evaluate the supplier rating. This application was originally designed for the Valencia Engine Plant and REDESIGNED to be used by all PTO plants within Europe. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-01-09 | 2025-01-09 | 2025-01-09 | Complete | Blue | 2025-01-09 | 2025-01-09 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Ramesh | 2025-03-04 |  |  | App is Decommissioned | No | Java < v21
20655 | Online Supplier Rating Control | In Production | OSRC | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Quality | Industrial System IT | The OSRC application is used to register and follow up IMRR, PSW and incoming parts; as well as it allows the user to evaluate the supplier rating. This application was originally designed for the Valencia Engine Plant and REDESIGNED to be used by all PTO plants within Europe. |  |  | YES | 4 | BWUNNAVA | PLM | SQL | Q1 2025 | Will be Decommissioned | Decommission | 2025-01-09 | 2025-01-09 | 2025-01-09 | Complete | Blue | 2025-01-09 | 2025-01-09 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Ramesh | 2025-03-04 |  |  | App is Decommissioned | No | SQL
21935 | GOTD - Scheduling Analysis & Control | In Production | GOTD - SAC | M&S TECH | FHIRSH | SBINO | WPIERSON | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | Managed by 3rd Party Purchased Service | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | This COTS top hat function will support proactive constraint identification, allowing for better allocation strategies and global capacity optimization to support 100% first time through order scheduling, and accurate supplier demand signals. | 7 |  | YES | 4 | NKANDULA | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
900 | On-Line Stock Control and Re-ordering (OSCAR) | In Production | EuPS-OSCAR | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | S-Ox Out of Scope | 231 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Manufacturing Staffs | - | On-Line Stock Control and Re-ordering for non-Production material. Nov 2011, a web front application was launched to automate the 1295, 1296, 1621 form approval processes. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
900 | On-Line Stock Control and Re-ordering (OSCAR) | In Production | EuPS-OSCAR | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | S-Ox Out of Scope | 231 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Manufacturing Staffs | - | On-Line Stock Control and Re-ordering for non-Production material. Nov 2011, a web front application was launched to automate the 1295, 1296, 1621 form approval processes. |  |  | YES | 3 | TSWEEN16 | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
900 | On-Line Stock Control and Re-ordering (OSCAR) | In Production | EuPS-OSCAR | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | S-Ox Out of Scope | 231 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Manufacturing Staffs | - | On-Line Stock Control and Re-ordering for non-Production material. Nov 2011, a web front application was launched to automate the 1295, 1296, 1621 form approval processes. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
20875 | Online Service Booking (App) | In Production | OSB | M&S TECH | RAHMED33 | PGOWERS | PGOWERS | JPOTTE60 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKLEINSM | BMUNIE | Ford Customer Service | Marketing, Sales and Service | Online Service Booking is the Global OWN solution for customers to book vehicle service and repair appointments. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
20875 | Online Service Booking (App) | In Production | OSB | M&S TECH | RAHMED33 | PGOWERS | PGOWERS | JPOTTE60 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKLEINSM | BMUNIE | Ford Customer Service | Marketing, Sales and Service | Online Service Booking is the Global OWN solution for customers to book vehicle service and repair appointments. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
20571 | Global Treasury Home Page | In Production | GTHmePge | I-ERP | SFRANCI8 | DSAKAMUR | KMOHAN15 | LWU14 | Copper | Non S-Ox | 11 | No | Yes | In-House | SFRANCI8 | DSAKAMUR | Finance | Integrated Enterprise Resource Planning (I-ERP) | Static Web page that allows users the ability to navigate to other Tresury web sites: FCE Bank Rates (ITMS#18112) Global Banking/Banksheets (ITMS#13354) FCE Funds Forecasting (ITMS#13355) Wall Street Classic Reports Wall Street Suite Reports Treasury Corporate Insurance Risk Treasury Citrix Treasury Sharepoint | 7 |  | YES | 1 | TSWEEN16 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
20875 | Online Service Booking (App) | In Production | OSB | M&S TECH | RAHMED33 | PGOWERS | PGOWERS | JPOTTE60 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKLEINSM | BMUNIE | Ford Customer Service | Marketing, Sales and Service | Online Service Booking is the Global OWN solution for customers to book vehicle service and repair appointments. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
13360 | Online Credit Application | In Production | OCA | FORD CREDIT | NJOSHI21 | ASAPEHIA | RMANDE | ASAXENA8 | Silver | Non S-Ox | 321 | No | Yes | In-House | NJOSHI21 | ASAPEHIA | Enterprise Technology | Ford Credit (FMCC) | Ford Credit online credit application that supports customers and dealers to finance vehicle purchases. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
13360 | Online Credit Application | In Production | OCA | FORD CREDIT | NJOSHI21 | ASAPEHIA | RMANDE | ASAXENA8 | Silver | Non S-Ox | 321 | No | Yes | In-House | NJOSHI21 | NJOSHI21 | Ford Credit Services | Ford Credit (FMCC) | Ford Credit online credit application that supports customers and dealers to finance vehicle purchases. |  |  | YES | 4 | SRAISIN1 | PLM | Oracle | Q1 2025 | Modernize to Cloud Databases | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | Oracle
23042 | Global Technical Assistance Center | In Production | GTAC | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 212 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | The Technical Assistance Centre application empowers dealer technicians to collaborate with Service Engineers for expert assistance in resolving Technical service or repair issues of a vehicle that the technician cannot resolve on his/her own. The seamless integration of GTAC interactions into the GCQIS application enables Product Concern Engineers to identify key areas of focus regarding vehicle repair and quality concerns through advanced data analysis. The three types of requests supported in Global tech assistance are TSR - Technical support request PA - Prior Approval and TIS - Technical Information support | 5 |  | YES | 3 | RKENNEL | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13360 | Online Credit Application | In Production | OCA | FORD CREDIT | NJOSHI21 | ASAPEHIA | RMANDE | ASAXENA8 | Silver | Non S-Ox | 321 | No | Yes | In-House | NJOSHI21 | ASAPEHIA | Enterprise Technology | Ford Credit (FMCC) | Ford Credit online credit application that supports customers and dealers to finance vehicle purchases. |  |  | YES | 4 | SRAISIN1 | PLM | WAS | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | Java < v21
22828 | OnGuard-The Ford Global Card Access System | In Production | OnGuard | OCETO | TSWEEN16 | BBEEKEL | JWALK257 | ESTILESK | Silver | Non S-Ox | 211 | Yes | No | COTS | MFLEURY | BBEEKEL | Policy | Staffs IT | The Corporate standard application used globally to manage access control (formerly Picture Perfect). This COTS application is provided by Lenel. OnGuard is used in conjunction with NetBadge, #19066, the application that manages access control badges. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
11426 | GLOBAL STUDY PROCESS ALLOCATION SYSTEM | In Production | GSPAS | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Silver | Non S-Ox | 322 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Global Study Process Allocation System (GSPAS)GSPAS - The Global Study Process Allocation System is the global repository of engineering data and standardized processes for assembling all Ford vehicles, including the related parts, tools, and standard labor times using AI and MODAPTS. GSPAS is comprised of several integrated modules - GSPAS Core (Process, Authorization, Study), Allocations Planning Tool (APT), Time Study (TS), Operator Work Pattern (OWP), and e-QPS; and is used in the daily activites of over 7000 Manufacturing Engineers, Industrial Engineers, and Plant Workgroup Teams through NA, SA, EU, and FAP. | 5 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21474 | Ongoing Revenue Budget | In Production | ORB | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Copper | Non S-Ox | 311 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | 311 | The Ongoing Revenue Budget (ORB) tool is used for tracking and managing the users (regional legal entities) of all IT managed applications and the costs of the products and services associated with those applications. The sole purpose of the ORB tool is to assist in developing the global billing file for IT Billing. The tool captures broad data changes for a full 5-year cycle (business planning) and more detailed data for the current cycle (budget setting). The tool also includes a change request process for use outside the natural 5-year busines planning process and budget setting process. |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
24071 | OneSumX FS | In Production | OneSumX FS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | OneSumX FS IFRS9 is a financial application provided by Wolters Kluwer that uses contract data to calculate Expected Credit Loss amounts over contract lifetime. IFRS9/CECL is an accounting standard that addresses the treatment of Expected Credit Losses (ECL). These ECL amounts are then aggregated by the particular market and posted to the General Ledger. This information will be publicly available as part of the balance sheet for Ford Credit, thus making it a SOX application. 10 markets are currently in scope - FCE, US, Canada, Mexico and China. The contract scope is for the retail markets. The ECL for wholesale contracts is out of scope and will be calculated manually. OneSumX will start to generate EAD/ECL calculations from take on date (TOD). The contractual outstanding principal that FORD CREDIT is required to deliver should be the principal outstanding amount at TOD. FORD CREDIT is also required to deliver the contractual accrued interest from the contractual last repayment date to TOD. |  |  | YES | 3 | SRAISIN1 | PLM | Datastage | Q3 2026 |  | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  |  |  | Planned | [17 empty] | DA
24071 | OneSumX FS | In Production | OneSumX FS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | OneSumX FS IFRS9 is a financial application provided by Wolters Kluwer that uses contract data to calculate Expected Credit Loss amounts over contract lifetime. IFRS9/CECL is an accounting standard that addresses the treatment of Expected Credit Losses (ECL). These ECL amounts are then aggregated by the particular market and posted to the General Ledger. This information will be publicly available as part of the balance sheet for Ford Credit, thus making it a SOX application. 10 markets are currently in scope - FCE, US, Canada, Mexico and China. The contract scope is for the retail markets. The ECL for wholesale contracts is out of scope and will be calculated manually. OneSumX will start to generate EAD/ECL calculations from take on date (TOD). The contractual outstanding principal that FORD CREDIT is required to deliver should be the principal outstanding amount at TOD. FORD CREDIT is also required to deliver the contractual accrued interest from the contractual last repayment date to TOD. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q3 2027 | Modernize to Cloud Databases | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [10 empty] | BigQuerry | [6 empty] | SQL
23044 | Global Service Parts Packaging System | In Production | PS&L GSPPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | This application manages FCSD packaging specification data at a global level and assures that packaging specifications are common, where appropriate, among the regions/markets. | 7 |  | YES | 5 | RKENNEL | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50563 | Onesumx for Risk Management | In Production | RiskPro | FORD CREDIT | RMINHAS3 | PSRIKIR1 | RMRINAL2 | NKALE | Gold | Non S-Ox | 332 | No | Yes | COTS | RMINHAS3 | RMINHAS3 |  | Ford Credit (FMCC) | WK Regulatory & Liquidity Reporting System |  |  | YES | 2 | SRAISIN1 | PLM | Oracle | Q3 2027 | On-Prem | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Oracle
52876 | GLOBAL HEALTH MONITOR | In Production | GHM | ISIT | SKING68 | KRAMESH | MKRAWCZA | RPRASA22 | Copper | Non S-Ox | 211 | No | Yes | In-House |  |  | Manufacturing Staffs | - | Application designed to monitor the health of FIS application servers at Ford manufacturing plants | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
23919 | Global Enterprise Asset Repository | In Production | GEAR | M&S TECH | RKLEINSM | BMUNIE | MSRINI25 | MPINRED1 | Silver | Non S-Ox | 322 | No | Yes | COTS | RKLEINSM | BMUNIE | Marketing & Sales | Marketing, Sales and Service | To expand Digital Asset Management to all Regions/Markets in response to global vehicle product launches. Specifically to: (1) Centralize a single source of truth for all digital assets for global reuse, (2) Provide end-users, globally, the ability to effectively locate and link to digital assets using best-in-class search functionality, metadata, business rules, naming conventions, data structure and user roles (3) Provide the means to limit views of asset content, by way of filtering (4) Implement business reports to track and measure asset download history and serving as input to continually refine asset development and usage procedures | 49 |  | YES | 2 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
22883 | GITHUB.FORD.COM | Active | Github | EA | RRISS | SHE1 | PSHAH | SGURU8 | Silver | Non S-Ox | - | No | Yes | - | pshah | malamgir | Enterprise Technology | - | GitHub Enterprise is a tool used to manage software code package configurations. | 1 |  | YES | 1 | GBRAIL | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
9056 | GIROBS: GLOBAL INV REVIEW OBSOLESCENCE SYS | In Production | GIROBS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Bronze | Non S-Ox | 121 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | GIROBS is a web-based application that is a long term forecasting system for parts which have gone out of production. Forecast is based on demand in the year the part went out of production. The GIROBS application does the majority of the data manipulation on the mainframe. Any modifications that occur on the web are applied on the mainframe on a nightly basis in batch. The tables for GIROBS are DRDA downloaded to Oracle after batch processing on a nightly basis. The application functionality includes: simulation, graphing and maintenance. The target audience for the GIROBS application is the Forecast Analyst & Management. Business Criticality: Med-L Additional Outage Impact includes: Impact to Financial Results. | 8 |  | YES | 5 | RKENNEL | PLM | VM | Q4 2026 | EDC CaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
11503 | OHSIM | In Production | OHSIM | OCETO | TSWEEN16 | SCHILAKA | WPETER58 | MBALAN2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DDESAI | DDESAI | Human Resources | Staffs IT | Occupational Health and Safety Information Management: Plant based application which tracks safety incidents (IIM), Electronic Medical Records (EMR), Medical Scheduling (MSM) and data analysis (DAM).GERT and Safety Pyramid modules are also integrated into OHSIM. OHSIM is an integrated web-based information management system. It is comprised of related tools designed to optimize resources for the protection and promotion of employee health and safety through the effective management of risks. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q1 2026 | On-Prem | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Oracle
121 | GEOS: Global Export Ordering System | In Production | GEOS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | The primary functionality introduced by GEOS is the ability to take stocking and emergency orders for service parts from Ford affiliates and WDMO dealers as well as providing visibility to the Global Liaison Center (GLC) employees. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. | 9 |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52694 | OGC Legal Case Search System | In Production | CaseSearch | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | Non S-Ox | 321 | No | Yes | In-House | DDESAI | KADOMKAI | Policy | 321 | OGC request this search tool to pull data from call center, which shows the efforts both Company and customer took to resolve the issue prior to litigation. The searches also seek to identify how many other customers are having the same issue and can impact the value of the case and any potential punitive damages. OGC has a legal obligation to comply with requests for information about other customers who may have also complained about a particular product or component. OGC must also be able to pull records relating to customer who have filed suit or made claims against the Company. The search tool allows user to search by model year, model, symptom codes, case categories, VIN number, engine code, keyword in the comments, etc. Note: This new search tool will replace the existing one which used FMC360 as data source (FMC360 was decommissioned in 2019) |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | no upgrade of Java Spring Boot app to Java 21 required for OGC Search Tool | No | Java < v21
52694 | OGC Legal Case Search System | In Production | CaseSearch | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | Non S-Ox | 321 | No | Yes | In-House | DDESAI | KADOMKAI | Policy | Staffs IT | OGC request this search tool to pull data from call center, which shows the efforts both Company and customer took to resolve the issue prior to litigation. The searches also seek to identify how many other customers are having the same issue and can impact the value of the case and any potential punitive damages. OGC has a legal obligation to comply with requests for information about other customers who may have also complained about a particular product or component. OGC must also be able to pull records relating to customer who have filed suit or made claims against the Company. The search tool allows user to search by model year, model, symptom codes, case categories, VIN number, engine code, keyword in the comments, etc. Note: This new search tool will replace the existing one which used FMC360 as data source (FMC360 was decommissioned in 2019) |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 | 2025-01-25 | Complete | Blue | 2025-09-13 | 2025-02-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | GCP Migration is completed for Database | No | SQL
21540 | GDT Syntax Checker | In Production | GDTSC | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | GDT syntax checking tool to verify the Geometry Tolerance syntax for each dimentions to meet the GDT standards | 2 |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2026 | Partial Migration to GCP | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22262 | OGC Due Diligence | In Production | OGC DD | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | Managed by 3rd Party Purchased Service | DDESAI | KADOMKAI | Policy | Staffs IT | The Third Party Due Diligence Tool provides an automated tool to assess the relative risk of bribery and corruption posed by any given third party to whom Ford has a relationship and document Ford's due diligence review |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
11293 | GBO: Global Buy Optimization | In Production | GBO: 11293 | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | The GBO Web application will assure the consistent application of buy models that will optimize total inventory carrying and material costs. GBO will also provide support for the maintenance of the buy models. Estimates indicate that this project will deliver 50% of the cost savings identified in the global purchasing system project at 25% of the cost. GBO will also provide worldwide access to the buy models and efficient user interface. GBO provides access for the user to use the Economic Buy Quantity and Balance Out Buy modules by both Europe and the U.S. GBO is sponsored by the Purchasing and Material Flow organizations. Additional Outage Impacts include: Impact to Productivity and Customer Complaint. | 5 |  | YES | 3 | RKENNEL | PLM | VM | Q4 2026 | EDC CaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
52873 | OGC Consumer Warranty Workflow Automation System | In Production | OGCONWARA | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Policy | - | Consumer Warranty Automation System (CWAT) is designed to allow trial teams, discovery teams, and the OGC to collaborate together, track assigned tasks, upcoming deadlines, case progress, settlement negotiations and will eventually capture other case data as this platform evolves. |  |  | YES | 1 | TSWEEN16 | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Request REQ0147950 created to assign servers under App 52873 to App # 12314. | No | SQL
52463 | Funding Services | In Production | GSFS | FORD CREDIT | DTAURO | SKHAN29 | APAUL31 | VPOTTIBO | Silver | Non S-Ox | 233 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Ford Credit common service application provides reusable API functions for file conversion and file transfer. | 6 |  | YES | 3 | SRAISIN1 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
14804 | Odyssey | In Production | Odyssey | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | TARUNKU4 | JSING217 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Odyssey is a management system for the development of all complex multilingual technical information for dealers and owners. It is comprised of XML data management workflow, graphical management and linguistic capabilities. It is used by Ford, Jaguar, Landover as a key system and by Mazda and Volvo for some features. |  |  | YES | 3 | RKENNEL | PLM | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
14804 | Odyssey | In Production | Odyssey | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | TARUNKU4 | JSING217 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | RKENNEL | Ford Customer Service | FCSD Tech | Odyssey is a management system for the development of all complex multilingual technical information for dealers and owners. It is comprised of XML data management workflow, graphical management and linguistic capabilities. It is used by Ford, Jaguar, Landover as a key system and by Mazda and Volvo for some features. |  |  | YES | 3 | RKENNEL | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
18051 | FTM - File Transfer Management | In Production | FTM | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Enterprise Technology | - | The FTM (File Transfer Management) system allows file transfers from server to server through different platforms using a WEB interface. The technology requires System Analyst, Supervisor and ITI analysts. The process begins with the System Development staff supplying all information required in the FTM web page. The next step involves the supervisors responsible for transferring approvals and the last step involves Support Analysts that are responsible to validate all parameters and identify the gaps based on infrastructure information. The FTM has a database to retrieve the parameters (sFTP information). The servers and scripts do the transfers automatically based on the parameters informed by System Analysts and validated by ITI Analysts. The scripts and servers require ITI support to analyze if the servers runs the sFTP script and the analysts will also be responsible to check the servers and update the sFTP script. This technology supports Brazil, Venezuela, Argentina and Mexico ADS teams. | 9 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22738 | OCR (Payables) | In Production | OCR | I-ERP | SFRANCI8 | RJAYAKU2 | RSRIRA18 | LWU14 | Silver | Non S-Ox | 311 | No | Yes | COTS | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | OCR Application as part of GAPS Suite |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
19254 | FSAO Full Economics (EE) | In Production | AREE | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Manages price increase requests issued by part suppliers and preparing the negotiation strategy based on the analysis of the cost structure of the parts the economic indexes evolution in the market and the impact of the price increases for the Company. Also provide cost forecasting functionality and the impact analysis due to price increase requests. | 6 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50916 | OCPP Server | In Production | OCPP | EVDD | JWOOD38 | RDEBSHAL | JCHANDR4 | MNAVANE6 | Silver | Non S-Ox | 121 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 121 | OCPP SERVER IS CHARGEPOINT MANAGEMENT SYSTEM THAT SERVERS AS CENTRAL SERVER FOR CONNECTED WALLBOXES(EVSE). |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
13821 | Occupational Health Manager | In Production | OHM | OCETO | TSWEEN16 | SCHILAKA | WPETER58 | MBALAN2 | Copper | Non S-Ox | 311 | No | Yes | COTS | DDESAI | SCHILAKA | Human Resources | Staffs IT | This application software supports audiometric testing, evaluation, calculations, and reporting for all Ford sites in Canada, US and Mexico, with interfaces to legacy applications(internal and external). 2/3/05- changed app name from HEARTRAC2 to OHM and placed IN PRODUCTION (vs IN DEVELOPMENT). |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q1 2026 | On-Prem | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | SQL
21592 | FRame Eng Design Order Manufacturing System | In Production | FREDOM | ISIT | SKING68 | JRICH264 | RCHANDA | AELANGO | Silver | Non S-Ox | 211 | No | Yes | In-House | SKING68 | RTHIRUV1 | Advanced PD and Tech | Industrial System IT | Frame Hole Management System | 4 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20679 | OCCUPATIONAL HEALTH BY POSITION | In Production | EOH | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Human Resources | - | The Brazilian government requires employers to keep track of employee occupational health by work position. Functionality is above and beyond to that provided by OHSIM. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
20679 | OCCUPATIONAL HEALTH BY POSITION | In Production | EOH | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Human Resources | - | The Brazilian government requires employers to keep track of employee occupational health by work position. Functionality is above and beyond to that provided by OHSIM. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
12367 | Ford of Mexico Payroll | In Production | FoM e-Pay | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Bronze | Non S-Ox | 331 | No | Yes | COTS | KBERCH | GDIAZ1 | Finance | - | Ford of Mexico PeopleSoft Payroll & International Payroll.The application supports all FoM and Ford Credit Mexico Salary and Hourly personnel. For foreign personnel. | 15 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2026 | Partial Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
20679 | OCCUPATIONAL HEALTH BY POSITION | In Production | EOH | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Human Resources | - | The Brazilian government requires employers to keep track of employee occupational health by work position. Functionality is above and beyond to that provided by OHSIM. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
51464 | OBD Status Database | In Production | OBD-Sta-DB | ISIT | JKOONS | MNOVAK1 | HLIN11 | JLUCAS1 | Copper | Non S-Ox | 111 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | This application hosts the database that interfaces with OBD DVM application and the business managed OBD Status Dashboard application |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
19946 | Ford of Mexico Electronic Invoicing | In Production | MX09FMEI | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | KBERCH | GDIAZ1 | Finance | - | This application will generate and control the Electronic Invoice Application. Implement an electronic solution that process the data invoicing, adding the authorization digital signoff to each fiscal document and maintain the fiscal documentation at least five years. The application should automatically register the emission date. The system must guarantee the integrity of the information and avoid duplicated data. | 18 |  | YES | 2 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
23973 | OBD and DVM Database | In Production | OBD-DVM-DB | ISIT | JKOONS | MNOVAK1 | HLIN11 | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | 211 | This application allows PCCN global calibration teams to work with a common standard format for calibration requirements and improve management and distribution of latest calibration guides and DV test procedures. It enables users to generate DVM test procedures manually on demand and auto generated vehicle test configuration files that can achieve fully automated DBD testing using OCTAV on HIL. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23973 | OBD and DVM Database | In Production | OBD-DVM-DB | ISIT | JKOONS | MNOVAK1 | HLIN11 | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | This application allows PCCN global calibration teams to work with a common standard format for calibration requirements and improve management and distribution of latest calibration guides and DV test procedures. It enables users to generate DVM test procedures manually on demand and auto generated vehicle test configuration files that can achieve fully automated DBD testing using OCTAV on HIL. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
12314 | Ford Matter Management System | In Production | FMMS | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | S-Ox In Scope | 331 | No | Yes | COTS | DDESAI | KADOMKAI | Policy | Staffs IT | FMMS (new Matters Management system) to replace LMMS. It is a COTS package by Mitratech inc, with a layer of customization to meet business requirements globally also it includes legal e-Billing (Collaborati). | 10 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
56710 | Ford Lincoln Protect Portal | In Production | FLPP | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | JBROADW4 | RKADAM1 | Silver | S-Ox In Scope | 231 | No | Yes | In-House |  |  | Ford Customer Service | - | Dealer portal enabling dealers to register, maintain ESB contracts. Generates contracts PDF forms. | 6 |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
54326 | NVH Workshop Request Center | In Development | MEC-WRC | ISIT | OTHERS | JNAJORK | MKOENIG2 | JLUCAS1 | Bronze | Non S-Ox | - | Yes | No | In-House | KESTIEV1 | JNAJORK | PD Operations and Quality | Industrial System IT | Managing requests and equipment for NVH measurements |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
13895 | Ford Java Frameworks | In Development | FJFTest | EA | RRISS | THALL6 | KPRAVE27 | SGURU8 | Copper | Non S-Ox | - | No | Yes | In-House | RRISS | THALL6 | Enterprise Technology | - | Application used to test the suite of Ford Java Frameworks(FJF) prior to release of framework modifications to J2EE applications within Ford, and contain FJF libraries and associated static content. | 1 |  | YES | 3 | GBRAIL | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
53671 | Nuance Security Suite | In Production | VoiceID | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Silver | Non S-Ox | 321 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | - | Voice Identification tool that uses Phone number, Background Noise, SIP Header, connected infrastructure and voice audio to provide probabilities that identify a caller for authentication. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
51291 | Ford IDP (ADFS Extension) | In Production | FordIdP | EPEO | NOKEEFE | MSNYDER5 | ZZHAN106 | GSIENKIE | Silver | Non S-Ox | 211 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Ford Identity Provider ( a new module of ADFS) provides ADFS login user to authenticate against for Ford FDS. The application will use SAML protocols to communicate with ADFS. The system will support Employee, Retiree, Supplier, Dealer and 2nd Tier Supplier to login from Internet or Intranet. FordIdP will also support SecurID Login. The Architecture Design: 1. Host the Ford Identity in the PCF Foundry. 2. In the initial phase, only deploy the application in EDC1 and scale horizontally. 3. After EDC2 available, we configure the application as active-active between EDC1 and EDC2. 4. Use node.js, MongoDB as implementation tool. | 6 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
52577 | Nuance NLU & TTS Services | In Production | NLU | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Silver | Non S-Ox | 111 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | Application consists of Nuance ASR and TTS services |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
22433 | Ford E-Store | In Production | F E-STORE | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | Marketing, Sales and Service | This website allows Ford of Canada Dealers to order merchandise for dealership staff (ie promotional material like shirts, jackets, pens, etc.) | 13 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
207 | North American Vehicle Information System | In Production | NAVIS | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Corporate respository of all north american vehicle information. SLA 1 CIA 3,3,3 |  |  | YES | 1 | NKANDULA | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
50118 | North American Sales Analysis & Reporting System | In Production | NASales | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 322 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | 322 | North American Sales Analysis & Reporting System (NASales) is a dashboard that provides key Sales & Stock information at all organization levels, right from the business units down to the dealers for the Ford & Lincoln Brands. NorthAmericanSales provides the ability to summarize the sales data for up to 10 yrs. by sales type, vehicle type, Vehicle Line & model years for a day/month/year. Stock information is reported at VIN level with their age (Number of days in lot). Ranking the dealers, reporting sales details/seasonality/period to period analysis, providing the stock details & dealer profile are the other major highlights of this application. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50118 | North American Sales Analysis & Reporting System | In Production | NASales | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 322 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | North American Sales Analysis & Reporting System (NASales) is a dashboard that provides key Sales & Stock information at all organization levels, right from the business units down to the dealers for the Ford & Lincoln Brands. NorthAmericanSales provides the ability to summarize the sales data for up to 10 yrs. by sales type, vehicle type, Vehicle Line & model years for a day/month/year. Stock information is reported at VIN level with their age (Number of days in lot). Ranking the dealers, reporting sales details/seasonality/period to period analysis, providing the stock details & dealer profile are the other major highlights of this application. |  |  | YES | 3 | NKANDULA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
21528 | Ford Cloud Identity Services | In Production | FCIS | EPEO | NOKEEFE | MSNYDER5 | RSUNDARE | GSIENKIE | Silver | Non S-Ox | 333 | No | Yes | Managed by 3rd Party Purchased Service | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Ford Cloud based identity and access management platform. | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
24334 | North America Services API | In Production | NASAPI | M&S TECH | KHEMANT | KDANDUPA | SPOTLUR6 | MPINRED1 | Gold | Non S-Ox | 322 | No | Yes | In-House | KHEMANT | KDANDUPA | Enterprise Technology | - | The North America Services API (NASAPI) powers Ford's digital consumer experiences by providing a variety of web-based services for Products and other Marketing capabilities. Each service has a RESTful Application Programming Interface (API) that can be used to access the resources that the platform offers. |  |  | YES | 3 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | Cloud SQL PostgreSQL |  |  |  |  | Team is working on API modernization | No | SQL
19089 | FOM TIMEKEEPING IN PS | In Production | FOMTIMEK | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | MBALAN2 | Bronze | Non S-Ox | 331 | No | Yes | COTS |  |  | Finance | - | Technological solution aligned to FoM Plants business practices, reducing the complexity in the current system. Provide a flexible system to support the different work patterns allowing the Supervisors a simple way to report overtime and absenteeism exceptions. Proposal is to focus on standard worked time payment for hourly personnel and just register exceptions (overtime and absenteeism). One of the main objectives is to distribute processes that are not related to timekeeping core process to the responsible areas as the calculation of worked hours and exceptions payment, distribution of overtime to calculate the payment, generate the journal entry, calculate the premiums, etc. Weekly Audit reports will be generated. Metrics will be provided to controllers, Labor Relations and Manufacturing Managers to evaluate critical issues as excess of overtime not approved, frequent omissions and information that proactively may identify potential payment issues. | 15 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2026 | Partial Migration to GCP | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24334 | North America Services API | In Production | NASAPI | M&S TECH | KHEMANT | KDANDUPA | SPOTLUR6 | MPINRED1 | Gold | Non S-Ox | 322 | No | Yes | In-House | KHEMANT | KDANDUPA | Enterprise Technology | - | The North America Services API (NASAPI) powers Ford's digital consumer experiences by providing a variety of web-based services for Products and other Marketing capabilities. Each service has a RESTful Application Programming Interface (API) that can be used to access the resources that the platform offers. |  |  | YES | 3 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Version Upgrade | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | Java 17 |  |  |  |  | Team is working on API modernization | No | Java < v21
11412 | Non-Design Price Change (NDPC II) | In Production | NDPC II | I-ERP | SARAUJO3 | KSYROCKI | LRUMPTZ | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | SARAUJO3 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Non-Design Price Change II (NDPC II)is a web based tool used to report production material cost savings |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
12368 | FoM PeopleSoft Human Resources | In Production | FoM HR App | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | MBALAN2 | Bronze | Non S-Ox | 331 | No | Yes | COTS | KBERCH | GDIAZ1 | Human Resources | - | Ford of Mexico PeopleSoft Human Resources Applications as Awards, Overtime, Vacations, Performance Review, the letters modules, self service module | 16 |  | YES | 2 | NKANDULA | PLM | VM | Q4 2026 | Partial Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
11412 | Non-Design Price Change (NDPC II) | In Production | NDPC II | I-ERP | SARAUJO3 | KSYROCKI | LRUMPTZ | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Non-Design Price Change II (NDPC II)is a web based tool used to report production material cost savings |  |  | YES | 3 | TSWEEN16 | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
50386 | FMCDealer - AEM | In Production | FMCDUS | M&S TECH | NKANDULA | JLEWIS10 | KDAILY | JHARPER2 | Platinum | Non S-Ox | 213 | No | Yes | COTS | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | FMCDealer AEM is the secured, password protected portal provided by Ford Motor Company to communicate with and provide access to business-critical applications which allow its dealerships to sell, finance, and service FMC vehicles. Brands and business units supported include: Ford and Lincoln, Ford Motor Credit/FMCC, Extended Service Coverage/ESC, MCDistributor/MCD/Motorcraft, Quick Lane/QL, Ford Authorized Distributors/FAD, Ford Customer Service Division/FCSD and Retailer Education & Training/RE&T. Market regions included: USA and Canada | 33 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Vm is decomisioned from 50386 and will be realloacted to 50385. 50385 is still analyzing the AEM Stategery. | No | VM
22574 | NMP Global Prototype System | In Production | NMPGPS | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | New Model Programs | Industrial System IT | Replacement for Scheduler, Process Locator, Pick Readiness, Stop Build and NMP Web legacy applications. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
22574 | NMP Global Prototype System | In Production | NMPGPS | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | New Model Programs | Industrial System IT | Replacement for Scheduler, Process Locator, Pick Readiness, Stop Build and NMP Web legacy applications. |  |  | YES | 4 | BWUNNAVA | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | SQL | [5 empty] | No | SQL
22574 | NMP Global Prototype System | In Production | NMPGPS | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | New Model Programs | Industrial System IT | Replacement for Scheduler, Process Locator, Pick Readiness, Stop Build and NMP Web legacy applications. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
54247 | FMCC Qlik Replicate | In Production | FCQlikRepl | FORD CREDIT | RMINHAS3 | SSINGH14 | SASIF | VBHUPATH | Bronze | Non S-Ox | 323 | No | Yes | - | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | Shared Extract-Transform-Load (ETL) infrastructure environment utilizing Qlik Replicate to support multiple discrete applications. | 4 |  | YES | 1 | SRAISIN1 | PLM | VM | Q4 2026 | Partial Migration to GCP | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
50367 | NGAVS-Schedule Management | In Production | NGAVS-SM | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Silver | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | NGAVS-SM provides the capabilities to receive daily production schedules from order management systems and allow plant scheduler to amend, hold, cancel and submit order and plant blend requests. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | Q2 2025 | Version Upgrade | Modernize | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-06-30 |  | Planned |  | No | 100% | 100% | 50% |  | 100% |  | 100% |  | Java 17 | Priya | 2025-03-06 |  |  | Migrated to EDC CaaS in Q4 2024. Upgrade to Java version 17 estimated completion by end of Q2 2025 & on track | No | Java < v21
50367 | NGAVS-Schedule Management | In Production | NGAVS-SM | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Silver | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | NGAVS-SM provides the capabilities to receive daily production schedules from order management systems and allow plant scheduler to amend, hold, cancel and submit order and plant blend requests. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [9 empty] | Priya |  |  |  |  | No | SQL
13569 | First Page | In Production | FP | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 211 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Staffs | Industrial System IT | Purchased package to manage configuration and messaging for alarming and escalation, and messaging to pagers. | 8 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
50384 | NGAVS-Schedule Execution | In Production | NGAVS-SE | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Platinum | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | 121 | NGAVS-SE provides the capabilities to execute daily order schedule, providing tracking and production status of vehicle, provide broadcast data to downstream systems, communicate order data to industrial controls/automation and provide critical reports to in-plant personnel |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q2 2025 | Version Upgrade | Modernize | 2025-03-05 | 2025-03-05 | 2025-03-05 | Complete | Blue | 2025-03-05 | 2025-03-05 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Priya | 2025-03-05 |  |  | Single site migration to EDC CaaS completed. Upgrade to Java version 17 completed | No | Java < v21
50384 | NGAVS-Schedule Execution | In Production | NGAVS-SE | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Platinum | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | NGAVS-SE provides the capabilities to execute daily order schedule, providing tracking and production status of vehicle, provide broadcast data to downstream systems, communicate order data to industrial controls/automation and provide critical reports to in-plant personnel |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  | 2027-12-15 |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | SQL | Priya | 2025-03-05 |  |  | Requires SQL AlwaysOn. Database VM will be migrated to OSV AS-IS. No changes will be made to the application. Timeline depends on OSV availability | No | SQL
24464 | FFLA Brazil - Easy Way Tributos (EWT) | In Production | EWT | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | ROBRIEN3 | Silver | Non S-Ox | 211 | No | Yes | COTS | DBRIGHEN | RCORDEI1 | Ford Credit Services | - | Easy-Tributos and Easy-SPED apps support Tax and Accounting departments of Ford Credit Brazil, respectively. Easy-tributos provides tax reports and Easy-SPED provides holding Tax (REINF) and Financial Operations of the Bank Ford with dealers reports, all of these reports feed IRS - Internal Revenue Service of Brazil. Those apps are developed and supported by a Brazilian company named Easy-Way of Brasil. | 6 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
17599 | NFe - Nota Fiscal Eletronica Brasil | In Production | NFe | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | NFe system is composed by 2 subsystems, NFe (web module), NF & LL (Mainframe module for electronic invoices) that is in charge to validate invoices. Electronic invoice process demands government permission. This permission is granted by means of a webservice communication. The government communication can result in different responses like: Authorization, in this case a Danfe (Printed assisting document for electronic invoice) is emitted and the material is released; Rejection, the invoice must be corrected and resent; or denied, so the invoice cannot be generated. Also is possible to cancel an invoice once respected legal period established by local state rule or turn it unused, in case the invoice will not be resent and its number need to be canceled. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-05-30 |  | In-Progress | Green | 2025-05-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
17599 | NFe - Nota Fiscal Eletronica Brasil | In Production | NFe | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | NFe system is composed by 2 subsystems, NFe (web module), NF & LL (Mainframe module for electronic invoices) that is in charge to validate invoices. Electronic invoice process demands government permission. This permission is granted by means of a webservice communication. The government communication can result in different responses like: Authorization, in this case a Danfe (Printed assisting document for electronic invoice) is emitted and the material is released; Rejection, the invoice must be corrected and resent; or denied, so the invoice cannot be generated. Also is possible to cancel an invoice once respected legal period established by local state rule or turn it unused, in case the invoice will not be resent and its number need to be canceled. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-05-30 |  | In-Progress | Green | 2025-05-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Oracle
13017 | FCSD Remanufacturing System | In Production | REMAN | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | KPATEL77 | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | MAMUDHA | Ford Customer Service | FCSD Tech | The REMAN application supports: 1) core recover from dealers, 2) core payment to dealers and 3) core management in the remanufacturing pipeline. It is built on SAP technology. | 2 |  | YES | 7 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q4 2026 | EDC CaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
17599 | NFe - Nota Fiscal Eletronica Brasil | In Production | NFe | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | NFe system is composed by 2 subsystems, NFe (web module), NF & LL (Mainframe module for electronic invoices) that is in charge to validate invoices. Electronic invoice process demands government permission. This permission is granted by means of a webservice communication. The government communication can result in different responses like: Authorization, in this case a Danfe (Printed assisting document for electronic invoice) is emitted and the material is released; Rejection, the invoice must be corrected and resent; or denied, so the invoice cannot be generated. Also is possible to cancel an invoice once respected legal period established by local state rule or turn it unused, in case the invoice will not be resent and its number need to be canceled. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-05-30 |  | In-Progress | Green | 2025-05-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
23762 | FCSD Parts Sales Management System | In Production | FPSMS | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Customer Service | - | Venezuela, Colombia Main system functionalities: 1. Customers Definitions. 2. Vendors Definitions. 3. Sales objectives Definitions. 4. Salesman Visit Schedules. 5. Customers Sales Statistics. 6. Prices Parts List Process. 7. Customers Parts Orders. 8. Customers Invoice Request Orders Process. 9. Parts Invoice recollection and package process. 10. Credits and Debits Notes. 11. Backorders Management. 12. Customers Claims Process. 13. Sales Information Inquiry. 14. Sales Reports. 15. Basic Sales Definitions | 8 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50071 | NextGen VHCOS | In Production | VHCOSNG | ISIT | SBONNICI | KRAMMOHA | MJESKA | JLUCAS1 | Bronze | Non S-Ox | 331 | No | Yes | COTS | SBONNICI | SBONNICI | Policy | Industrial System IT | VHCOS Next Gen - using Planisware software - enables the full integration of VH&C project management and change control processes, with PD tools like Global Integrator or FEDE. Allowing easy integration with existing vehicle program milestones. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23763 | FCSD Parts Purchasing Management System | In Production | FPPMS | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Gold | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Customer Service | - | Scope: Venezuela, Colombia Main system functionalities: - Procurement process for local and imported parts | 8 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50071 | NextGen VHCOS | In Production | VHCOSNG | ISIT | SBONNICI | KRAMMOHA | MJESKA | JLUCAS1 | Bronze | Non S-Ox | 331 | No | Yes | COTS | SBONNICI | SBONNICI | Policy | Industrial System IT | VHCOS Next Gen - using Planisware software - enables the full integration of VH&C project management and change control processes, with PD tools like Global Integrator or FEDE. Allowing easy integration with existing vehicle program milestones. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
16105 | FCLA Mexico - ICMS | In Production | MIC | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | RMANGAL | Bronze | Non S-Ox | 321 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | The ICMS (Integral Cash Management System) is application that manages the payments which Mexico Bank files are loaded by Mex Treasury Team. Mex BOSS Team runs the process consolidating the banks files and separating wholesale payment and retail payment. The Wholesale and Retail payments file are transferred to WFOCUS App and BLESS App based on Business option on ICMS screen according to the operation. It also manages the approvals of wholesale exchange operations, wholesale month end files loading applied Mex BOSS team showed in the Dealer Extranet and allow Mex Treasury team controls operation files. ICMS App has connection with Webfocus tool using restful connection to execute their reports and also allows the other Mexico Local Applications using the same connection to execute the reports.ICMS is facilitator between FoM Apps and WFOCUS App, transferring to WFOCUS APP, the Ford/Lincoln invoice information posted by FoM in the FC shared drive server. | 12 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2026 | EDC CaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
53398 | Next-gen Global Packaging Portal | In Production | NGGPP | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 211 | No | Yes | In-House | GHERMAN | ADURSO | Enterprise Technology | 211 | NGGPP is Next-gen Global Packaging Portal |  | Springboot | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13586 | VIPER:European Vehicle Inventory Prod Eng Rep | In Production | EuMP-VIPER | ISIT | JPITTERL | CBOHN | MBONAKDA | SSENTH15 | Bronze | Non S-Ox | 211 | No | Yes | In-House | CBOHN | IREINHO3 | Manufacturing Plants | Industrial System IT | This application records the progress of UK Ford owned vehicles, including demonstrators, management roll cars, pool cars and press cars throughout their Ford ownership. It is used by the Dagenham Car Conditioning Centre (Ford Autotech) to record the progress of Company and Contract Direct Sales Vehicles through the garage and provide management-reporting facilities. It is also installed at several satellite locations in the UK to record Company vehicles moving into active service and being returned for disposal. | 3 |  | YES | 4 | BWUNNAVA | PLM | VM | Q4 2024 | Partial Migration to GCP | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [13 empty] | TBD, due to Business priorities | No | VM
53398 | Next-gen Global Packaging Portal | In Production | NGGPP | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 211 | No | Yes | In-House | GHERMAN | GHERMAN | Enterprise Technology | Industrial System IT | NGGPP is Next-gen Global Packaging Portal |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2027 | On-Prem | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Oracle
15989 | FC GLOBAL WHOLESALE | In Production | BLESSEWHOL | FORD CREDIT | MLOPEZ31 | OLOPEZ7 | PGUILLEN | AGALLAG9 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | MLOPEZ31 | OLOPEZ7 | Ford Credit Services | Ford Credit (FMCC) | Dealer and back-office application to operate the wholesale finance portfolio for FCE / IMG / China. It includes the former entry 15416 FCE BLESS Wholesale. | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q4 2026 | EDC CaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
15406 | NextGen DM | In Production | NextGen | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | NextGen DM is the new recovery management system that manages the charged-off accounts through the recovery process. This system interfaces with vendors and internal systems to process financial transactions for charged-off accounts. RMS2 is implemented in FICO Debt Manager solution. | 533 |  | YES | 5 | SRAISIN1 | PLM | Datastage | Q3 2026 |  | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  |  |  | Planned | [17 empty] | DA
15406 | NextGen DM | In Production | NextGen | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | NextGen DM is the new recovery management system that manages the charged-off accounts through the recovery process. This system interfaces with vendors and internal systems to process financial transactions for charged-off accounts. RMS2 is implemented in FICO Debt Manager solution. |  |  | YES | 5 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
15406 | NextGen DM | In Production | NextGen | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | NextGen DM is the new recovery management system that manages the charged-off accounts through the recovery process. This system interfaces with vendors and internal systems to process financial transactions for charged-off accounts. RMS2 is implemented in FICO Debt Manager solution. |  |  | YES | 5 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50973 | FAFC Anti Money and Fraud services | In Production | FAFCAMLAF | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | Non S-Ox | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | FAFC Anti Money Laundering service helps to screen new and existing customers in Ford Credit Originations and Account servicing processes. New and existing customers will be screened against Sanction, PEP and high country risk lists. Data from Accuity Vendor will be pulled using SFTP and loaded into DB. FAFC Anti-Fraud service helps to validate customers submitted by dealer against BaiHang Interface during Ford Credit Originations processes. This service consumes a BaiHang service to retrieve the special attention lists of a customer which will be stored in GLO. | 1 |  | YES | 3 | SRAISIN1 | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
15406 | NextGen DM | In Production | NextGen | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | NextGen DM is the new recovery management system that manages the charged-off accounts through the recovery process. This system interfaces with vendors and internal systems to process financial transactions for charged-off accounts. RMS2 is implemented in FICO Debt Manager solution. |  |  | YES | 5 | SRAISIN1 | PLM | WAS | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
20972 | NextGen Data ModelingTool | In Production | NG-DMT | OCETO | TVASU | MWAWZYSK | SFAN21 | KTRACY8 | Bronze | Non S-Ox | 111 | No | Yes | COTS | NSENTHI1 | MWAWZYSK | Enterprise Technology | Technology & Enterprise Services (TES) | A Data Modeling tool is used to develop and document data models for IT applications. Logical and physical data model designs are created and updated by data architects. Business Analysts, Developers and Database Administrators also use the data modeling tool to update data model metadata information. The information entered into the tool should be able to create graphical drawings (ER diagrams, Server Model diagrams, etc.) and DDL script files. The tool will be maintained by Enterprise Architecture. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q2 2027 | On-Prem | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | SQL
12876 | Factory Information System | In Production | FIS | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 211 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Staffs | Industrial System IT | FIS is the next generation of equipment monitoring for Ford plants. The application is primarily based on a commercial package (Activplant) and includes interfaces to several other applications (Marquee Manager, First Page, Enterprise Gateway) for managing PCB's, paging, TEM, PCON, and CSI. The primary functions of FIS is to reduce the launch curve for new model programs and break production bottlenecks in on-going production operations. | 44 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
18483 | NextGen Automated Vehicle Scheduling | In Production | NGAVS | ISIT | AMEHER1 | ADURSO | JLAKATO7 | RPRASA22 | Silver | Non S-Ox | 121 | No | Yes | COTS | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Next Generation Automated Vehicle Scheduling (NGAVS) is a global application that coordinates execution of the vehicle production schedule provided from corporate order management systems for body, paint and the final assembly of the vehicle to ensure that vehicles are built according to schedule. NGAVS provides real-time vehicle build information to operators, suppliers and automation within all areas of the plant. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | TBD | Rewrite | Decommission |  |  |  | Not Started | Green | 0 |  | Planned |  | No | [14 empty] | No | Java < v21
18483 | NextGen Automated Vehicle Scheduling | In Production | NGAVS | ISIT | AMEHER1 | ADURSO | JLAKATO7 | RPRASA22 | Silver | Non S-Ox | 121 | No | Yes | COTS | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Next Generation Automated Vehicle Scheduling (NGAVS) is a global application that coordinates execution of the vehicle production schedule provided from corporate order management systems for body, paint and the final assembly of the vehicle to ensure that vehicles are built according to schedule. NGAVS provides real-time vehicle build information to operators, suppliers and automation within all areas of the plant. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Decommission |  |  |  | Not Started | Green | 0 |  | Planned |  | No | [14 empty] | No | Java < v21
18483 | NextGen Automated Vehicle Scheduling | In Production | NGAVS | ISIT | AMEHER1 | ADURSO | JLAKATO7 | RPRASA22 | Silver | Non S-Ox | 121 | No | Yes | COTS | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Next Generation Automated Vehicle Scheduling (NGAVS) is a global application that coordinates execution of the vehicle production schedule provided from corporate order management systems for body, paint and the final assembly of the vehicle to ensure that vehicles are built according to schedule. NGAVS provides real-time vehicle build information to operators, suppliers and automation within all areas of the plant. |  |  | YES | 4 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
20981 | ESB Contract Assistance | In Production | DCW-ESBCA | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | JBROADW4 | RKADAM1 | Silver | Non S-Ox | 221 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | This application enables the dealers to submit the contract maintenance requests to Ford Extended Service Business (ESB). It also provides the business process automation (workflow) to streamline the ESB contract management. The application name for the external dealers is called ESB Contract Assistance | 8 |  | YES | 2 | RKENNEL | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
13867 | Next Gen User Access Mgmt System New | In Production | NGUAMS-NEW | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | In-House | JKOONS | JKOONS | Advanced PD and Tech | Industrial System IT | This tool creates Users Ids in TeamCenterEngineering (TCe)and assigns car programs, groups, and/or roles to those users. All requests and granted access is tracked in a database for audit purposes. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
23244 | ENTERPRISE VIDEO & WEBCASTING | Active | EVW | EPEO | SRUNSON | PWILL357 | SKENNE67 | WDRAKE10 | Silver | Non S-Ox | - | No | Yes | - | SRUNSON | PWILL357 | Enterprise Technology | - | This project will provide an all new video platform and interface to Ford, upgrading our current standards to cross platform HD video for both VOD and live streaming events Global Town Hall, The Right Wa. It will provide an all new YouTube like, end user video portal that will have webcasting features and enable users to easily upload and share videos across the enterprise in a secure manner. | 6 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
19966 | Next Gen eFPA | In Production | eFPA | ISIT | OTHERS | AHOROVIT | CGOLDMA4 | TBIRMIN1 | Copper | Non S-Ox | 111 | Yes | No | In-House | AHOROVIT | CGOLDMA4 | Manufacturing Engineering | - | NextGen eFPA contains modules ( Clay Studio feasability,Stamping New model tooling, Stamping operations, Body in White), Reject Log and Metal finish tracking, LastHit/TCO, and Rack repair tracking. Migration to New Data Center planned for Wave 19 |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50048 | Enterprise Key Management | Planned | EKM | EPEO | NOKEEFE | VNACHIMU | BSARAV20 | GSIENKIE | Silver | Non S-Ox | - | No | Yes | COTS | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | (Never launched to Prod, Infrastructure decomissioned, records being updated) Providing a complete Enterprise Key Management (EKM) solution or service to Ford, will support strategic initiatives (like Next-Gen Data Center), improve security controls, reduce maintenance complexity and cost, and strategically position the company to support current and future business needs (like Connected Vehicle, Mobility, Ford Credit, and Cloud). | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
24397 | New Vehicle Orientation Application | In Production | NVO | M&S TECH | RKLEINSM | BMUNIE | DCHITRA1 | JPOTTE60 | Gold | Non S-Ox | 222 | No | Yes | In-House | RKLEINSM | BMUNIE | Enterprise Technology | - | Provide a simple to use, device agnostic, interactive resource center that provides customer focused vehicle feature education and engages the customer throughout the delivery/orientation and initial ownership experience. Provide Delivery guides & feature education resources conveniently avail from FMCDealer, Fordowner, Lincolnowner and also accessible online, throught the Dealer Showcase App (iPad) tablets and smart phones. The Delivery guides will be available to dealership employees, corp users and customers. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-24 | Complete | Blue | 2025-06-13 | 2025-01-24 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | SQL
23712 | Enterprise GRC - RSA Archer | In Production | GRC | I-ERP | SFRANCI8 | SFRANCI8 | AKANSKI | LWU14 | Copper | Non S-Ox | 321 | No | Yes | COTS | TSWEEN16 | SFRANCI8 | Finance | Enterprise Connectivity - PDO | Internal Control implementation of RSA Archer for Enterprise GRC purposes | 15 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
24397 | New Vehicle Orientation Application | In Production | NVO | M&S TECH | RKLEINSM | BMUNIE | DCHITRA1 | JPOTTE60 | Gold | Non S-Ox | 222 | No | Yes | In-House | RKLEINSM | BMUNIE | Enterprise Technology | - | Provide a simple to use, device agnostic, interactive resource center that provides customer focused vehicle feature education and engages the customer throughout the delivery/orientation and initial ownership experience. Provide Delivery guides & feature education resources conveniently avail from FMCDealer, Fordowner, Lincolnowner and also accessible online, throught the Dealer Showcase App (iPad) tablets and smart phones. The Delivery guides will be available to dealership employees, corp users and customers. |  |  | YES | 3 | NKANDULA | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-24 | Complete | Blue | 2025-06-13 | 2025-01-24 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
50549 | New Parts Setup | In Production | NPS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | TOBERHOF | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | 211 | New Parts Setup will support parts data collection prior to job 1#. |  | Springboot | YES | 3 | RKENNEL | PLM | Java < v21 | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-31 | 2025-03-10 | Complete | Blue | 2025-06-29 | 2025-03-10 | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Decom Only .Followed up with PDO. 10 VMs are pending. | No | Java < v21
50549 | New Parts Setup | In Production | NPS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | TOBERHOF | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | - | New Parts Setup will support parts data collection prior to job 1#. |  |  | YES | 3 | RKENNEL | PLM | SQL | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Decom Only .Followed up with PDO. 10 VMs are pending. | No | SQL
23081 | ENTERPRISE ARCHITECTURE MANAGEMENT SYSTEM | In Production | EAMS | OCETO | TVASU | MWAWZYSK | PGUNNA | KTRACY8 | Silver | Non S-Ox | 211 | No | Yes | COTS | NSENTHI1 | MWAWZYSK | Enterprise Technology | Technology & Enterprise Services (TES) | The Enterprise Architecture Management System, originally known as 'EATOOL', is a tool suite designated as the official System of Record (SoR) for all enterprise architecture modeling artifacts providing foundational information and support for enterprise blueprints and all other IT business processes. This information includes the application and technology portfolios supporting the technology management (TM), application portfolio management (APM) processes as well as architecture assurance (AAA) and business architecture (BA) activities. EAMS is supported by the Mega Hopex COTS product and a Ford custom developed web interface | 13 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
19820 | NEW MIDAS: Marketing Incentive Dealer Audit System | In Production | MIDAS Rewr | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Finance | Staffs IT | This re-write of the original MIDAS application (ITMS 11278) was completely re-written by ADS. This application uses many feeds to bring the high risk dealers and VINS to the fore-front. This application recovers funds that are inappropriately paid on invalid incentive claims. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
19820 | NEW MIDAS: Marketing Incentive Dealer Audit System | In Production | MIDAS Rewr | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Finance | Staffs IT | This re-write of the original MIDAS application (ITMS 11278) was completely re-written by ADS. This application uses many feeds to bring the high risk dealers and VINS to the fore-front. This application recovers funds that are inappropriately paid on invalid incentive claims. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q4 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
50490 | New Global Integrator | In Production | GI/TI | ISIT | SBONNICI | KRAMMOHA | MJESKA | JLUCAS1 | Silver | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | SBONNICI | SBONNICI | PD Operations and Quality | Industrial System IT | New Global Integrator is a common global tool that encompasses and replaces the functionality of two existing applications: GI (Global Integrator) and TI (Technology Integrator). GI perspective: The New Integrator will be used by Vehicle Programs, Powertrain and Functions to track and maintain deliverables status, in support of the GPDS (Global Product Development System) process. TI perspective: The New Integrator will be used by Research & Advanced Engineering teams to track and maintain deliverable status, in support of four processes: (1) Discovery QOS (Quality Operating System), (2) Product GTDS (Global Technology Development System) QOS, (3) Process GTDS QOS, and (4) Corporate Support. In both GI and TI, teams update timing, assessments and attach supporting documents/evidence to relevant deliverables. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
12986 | Employee Profile Maintenance | In Production | EPM | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 122 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | A security system that contains roles and positions for local and regional Marketing and Sales employees. The system is used for base security by DBP/eCommitment and IRT/PDT/Commitment Outlook and RTOM. | 4 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50490 | New Global Integrator | In Production | GI/TI | ISIT | SBONNICI | KRAMMOHA | MJESKA | JLUCAS1 | Silver | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | SBONNICI | SBONNICI | PD Operations and Quality | Industrial System IT | New Global Integrator is a common global tool that encompasses and replaces the functionality of two existing applications: GI (Global Integrator) and TI (Technology Integrator). GI perspective: The New Integrator will be used by Vehicle Programs, Powertrain and Functions to track and maintain deliverables status, in support of the GPDS (Global Product Development System) process. TI perspective: The New Integrator will be used by Research & Advanced Engineering teams to track and maintain deliverable status, in support of four processes: (1) Discovery QOS (Quality Operating System), (2) Product GTDS (Global Technology Development System) QOS, (3) Process GTDS QOS, and (4) Corporate Support. In both GI and TI, teams update timing, assessments and attach supporting documents/evidence to relevant deliverables. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
50109 | Email Relay | In Production | EmailRelay | EPEO | SRUNSON | ASTONE31 | MMAHAJAN | MMAHAJAN | Gold | Non S-Ox | 333 | No | Yes | COTS | SRUNSON | ASTONE31 | Enterprise Technology | EPEO | Ford Mirapoint SMTP Relay/Gateway Infrastructure is the core component for Ford email system. It provides the message routing, anti-spoofing, IP validation, email address validation, domain validation, AV scan, email filtering/message control, SMTP relay and message buffering services for Ford Motor Company email environment. All Ford external inbound/outbound emails are processed by Mirapoint Infrastructure. Emails between Ford and Ford business partners are also encrypted and scanned by anti-virus software running on Mirapoint appliances. The email sender domain, recipient domain, sender address and recipient address(es) are validated by Mirapoint system to stop SMTP spoofing. Mirapoint system also provides global SMTP relay services for Ford application servers. The application server IP, hostname, and sender address is validated by Mirapoint system | 4 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
13357 | Network Business Tools | In Production | NBT | EPEO | MCRNKOVI | SPANDRAN | NVIDICAN | NVIDICAN | Copper | Non S-Ox | 222 | No | Yes | In-House | MCRNKOVI | MCRNKOVI | Enterprise Technology | EPEO | Network Business Tools (NBT) is comprised of many different applications using a common platform and code base. Currently, the application list includes SAM, VAL, GSEC DB, FSS, SMTP Registration, ECS Review, CMS, and smaller utilities. There are many urls associated with this application. nbt.netops.ford.com, nbt.ford.com, fssford.com, sam.ford.com, val.ford.com, ecsreview.ford.com, gsecdb.ford.com, network.ford.com |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
20372 | Electronic Interchange (EI) | In Production | AREI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | The goal of this system is to fulfill with government regulations with respect to interchange electronics files between Ford and AFIP.This system takes information from Ford Pacheco Invoicing Systems gives them the appropiate format and sends the information to AFIP WEB services. Afterwards it receives the answer from AFIP. | 2 |  | YES | 5 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13628 | NETS | In Production | EuAS-NETS | OCETO | TSWEEN16 | KKOEHLER | MRAUTERK | LWU14 | Gold | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KKOEHLER | Finance | Staffs IT | NETS - New European Timekeeping System. The NETS System registers working hours, absence time and schedule absence time. This information feeds the Payroll and IPIS systems. The system is still in use for Spain only. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
18635 | NetOps Tools | In Production | NETOPSTOOL | EPEO | MCRNKOVI | SPANDRAN | NVIDICAN | NVIDICAN | Platinum | Non S-Ox | 221 | No | Yes | In-House | MCRNKOVI | MCRNKOVI | Enterprise Technology | - | Automation and Tooling to support ITI Operations - Network Operations and Network Management Systems (NMS). As of 5/19/2015, merging this ITMS Application with ITMS App 19547 and decomming that app to consolidate portfolio. |  |  | YES | 3 | SWALIMBE | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
11353 | eCommitment | In Production | ECOMMIT | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Ecommitment is a laptop based application that provides zone managers an input mechanism for vehicle wholesale numbers. The tool is used to submit wholesale commitment to dealers. The applications also provides North American Zone Managers with a means for analysis and tracking of data during monthly wholesale. The ecommit web reports are also part of the application. These reports provide web-based reports to the Zone Managers as to the current state of the wholesale period. | 9 |  | YES | 4 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
18635 | NetOps Tools | In Production | NETOPSTOOL | EPEO | MCRNKOVI | SPANDRAN | NVIDICAN | NVIDICAN | Platinum | Non S-Ox | 221 | No | Yes | In-House | MCRNKOVI | MCRNKOVI | Enterprise Technology | - | Automation and Tooling to support ITI Operations - Network Operations and Network Management Systems (NMS). As of 5/19/2015, merging this ITMS Application with ITMS App 19547 and decomming that app to consolidate portfolio. |  |  | YES | 3 | SWALIMBE | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
21337 | NetOps Support Database | In Production | NETSUPDB | EPEO | MCRNKOVI | BKARMAKA | JSATHEES | VCHEDARA | Copper | Non S-Ox | 222 | No | Yes | In-House | MCRNKOVI | BKARMAKA | Enterprise Technology | EPEO | Network Operations Network Database is the authoritative source for global network device information and support data. |  |  | YES | 2 | SWALIMBE | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
14773 | eAssets | In Production | eAssets | EPEO | SRUNSON | PSIMONTE | JDEBIAS1 | GSIENKIE | Bronze | Non S-Ox | 211 | Yes | No | In-House | SRUNSON | PSIMONTE | Enterprise Technology | - | This application is the authoritative asset management tool/database for PC as well as Distributed Servers. | 3 |  | YES | 3 | SWALIMBE | PLM | VM | Q4 2026 | Partial Migration to GCP | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
17715 | Dealers File Exchange Management (e-Datadif) | In Production | DTF | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | Data exchange Information(Dealers and Ford), download commom files and request from Ford to resend files to dealers regarding business information. This application informs details of file exchanged via EMVIA. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
19066 | NetBadge | In Production | NetBadge | OCETO | TSWEEN16 | BBEEKEL | JWALK257 | ESTILESK | Silver | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | MFLEURY | BBEEKEL | Policy | Staffs IT | NetBadge is a front end to the Ford access control system providing for the request and control of access control badges. NetBadge is used in conjunction with OnGuard, #22828, the application that manages access control. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
52022 | Dealer Accounting Management System | In Production | DAMS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Make available to dealers information regarding their Account within Ford. The dealers can also ask for transfer between units of their group(filiais). | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
15659 | NetAgent NA Database | In Production | NetAgentDB | FORD CREDIT | IPANKAJ | DSINACOL | SVYSYARA | RPARAME4 | Bronze | Non S-Ox | 311 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | This application nGenera Netagent has been in use until June 2023. It is a 2-way Secure email SaaS product from vendor Moxie (now under NICE CXone) for use by FC Agents in NA, Canada and Argentina. This functionality has been integrated within MSDynamics using a Microsoft solution. In order retain email communication data as per GIS requirements (C+6), this application has been renamed to Netagent NA Database and the historical data is stored on SQL database ITO080643. Database has to be decommissioned during 2030 AFR unless there is a change in retention period or to retain for any suspension orders. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53039 | Data Transfer as a Service | In Production | DTaaS | EPEO | LFULCHER | KMAHAJAN | TKLEMER | CCARR53 | Bronze | Non S-Ox | - | No | Yes | In-House | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | SFTP to S3 on VM | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
23752 | NetAgent FCE | In Production | NetAgent | FORD CREDIT | IPANKAJ | DSINACOL | SVYSYARA | RPARAME4 | Bronze | Non S-Ox | 311 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | This NetAgent application (earlier owned by Moxie) is a Vendor SaaS product from NICE CXone for 2-way Secured email communication mainly with Ford Credit Customers and supports Europe markets. Data stored by this application may contain SPII. A new product/solution may replace this in near future as part of Contact Center of the Future (CCOF) program. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | SQL
600 | Daily Production Reporting | In Production | DPR | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | DPR provides management with manufacturing and assembly plant production data from the previous day (close of business). It is a global application used by ford plants globally, both assembly and powertrain. | 3 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53937 | Nectar 2.0 | In Production | Nectar DPA | FORD PRO & FCSD TECH | HSHEKER | RRAJKIR2 | RSUBRA17 | SDHANAS2 | Silver | Non S-Ox | 311 | No | Yes | In-House | #N/A | #N/A | Ford Customer Service | 311 | ITS A DPA APPLICATION PLANNED TO REDUCE VOR TIME |  | Springboot | YES | 1 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Java 21 | [5 empty] | No | Java < v21
19934 | CORL replacement | In Production | CORL REPL | ISIT | JKOONS | MNOVAK1 | JSURESHR | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | COTS | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | This project will provide a vendor-supplied, web-based data archive, retrieval, reporting, and plotting system that will provide the following benefits for Road Load Durability Engineering: -improve search capability -enhance search results reports -improve customer satisfaction -reduce IT support burden | 6 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
23315 | NAC-Pivotal Cloud Foundry | Active | PCF | EPEO | SJOHN172 | MHANTON | MAHMED7 | AGERTZ | Copper | Non S-Ox | - | No | - | - | SJOHN172 | MHANTON | #N/A | #N/A | Pivotal Cloud Foundry is an open platform as a service, providing a choice of clouds, developer frameworks, and application services. Cloud Foundry makes it faster and easier to build, test, deploy, and scale applications. |  | Springboot | YES | 3 | SWALIMBE | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
23315 | NAC-Pivotal Cloud Foundry | Active | PCF | EPEO | SJOHN172 | MHANTON | MAHMED7 | AGERTZ | Copper | Non S-Ox | - | No | Yes | - | SJOHN172 | MHANTON | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 3 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
22821 | Chef | Active | Chef | EPEO | LFULCHER | KMAHAJAN | TKLEMER | TKLEMER | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | Enterprise Technology | ITO | Chef Enterprise is an IT automation framework that helps make rapid, repeatable changes to help manage various stages of the IT infrastructure lifecycle, including the provisioning, patching, configuration, and management of operating system and application components across enterprise data centers. | 50 |  | YES | 3 | SWALIMBE | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
23793 | NAC-Global Server Operations Utilities | Active | GSOU | EPEO | LFULCHER | KMAHAJAN | AKHALI11 | SPOYNTE4 | Silver | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | ENTERPRISE TECHNOLOGY | - | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50695 | CERTMAN (SSL) | In Production | SSL | EPEO | NOKEEFE | VNACHIMU | BSARAV20 | ADOREZA | Silver | Non S-Ox | 111 | No | Yes | In-House |  |  | Enterprise Technology | EPEO | Certman (SSL) is a homegrown application which allows users to request publicly trusted TLS/SSL certificates (thru Web and API) to protect Ford websites/applications. | 4 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
18122 | NAC-DBA | Active | DBA | EPEO | SKULKA52 | CGIACOBB | AMULLIN3 | JHARPER2 | Copper | Non S-Ox | - | No | Yes | - |  |  | ENTERPRISE TECHNOLOGY | EPEO | ITO - LSI- MAINFRAME DBA |  | MF - WAS Liberty | YES | 1 | SWALIMBE | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
20918 | NAC- Porting Center ADS APA | Active | PC-ADSAPA | OCETO | TVASU | SANANTH | VPARVADH | HMUTHUK1 | Copper | Non S-Ox | - | No | Yes | - | TVASU | SANANTH | #N/A | - | #N/A |  |  | YES | 1 | TSWEEN16 | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
21655 | Ceridian Salaried/Temporary Payroll | In Production | CeridianSP | I-ERP | SFRANCI8 | FFIORINO | KDELACY | CDEMERIN | Copper | Non S-Ox | 322 | Yes | No | Open Source | DDUDLEY3 | FFIORINO | Finance | - | Ford of Canada's Salaried and Temporary employee payroll system is outsourced to Ceridian. | 2 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
17716 | CCD - User Profile Management South America | In Production | CCD | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | CCD System is a Ford and dealership user profile management for B2B (Dealer) applications. Also there is a module to view old brazilian dealer communications. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
53011 | NA Light Duty Near Term Compliance Command Center | In Production | NTC | GDIA | AFRADKIN | JLIDDLE1 | JBELZYT1 | GCARLSO2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | AFRADKIN | JLIDDLE1 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | A DB + Dashboard application that helps EPLM Sustainability Planning team to display Near Term Compliance data for emission and environmental regulations. |  |  | NO | 2 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
24816 | Canadian Dealer Facilities Website | In Production | CFW | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | Marketing, Sales and Service | Web application to manage Canadian dealer facilities information. | 4 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50716 | NA GUX eCommerce shop and buy | In Production | NAGUX | M&S TECH | RKLEINSM | RKLEINSM | ASYED3 | VMARAMR1 | Platinum | Non S-Ox | 233 | No | Yes | Managed by 3rd Party Purchased Service | #N/A | #N/A | Enterprise Technology | 233 | NA GUX ECOMMERCE EXPERIENCE |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-09-22 | Complete | Blue | 2024-12-15 | 2024-09-22 | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
21526 | MyFordVehicles | In Production | MFV | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | Web application used for ordering management lease vehicles. Replacement for existing Quicklease system (ITMS: 70) | 116 |  | YES | 7 | NKANDULA | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
21526 | MyFordVehicles | In Production | MFV | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | Web application used for ordering management lease vehicles. Replacement for existing Quicklease system (ITMS: 70) |  |  | YES | 7 | NKANDULA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-06 | Complete | Blue | 2024-12-15 | 2025-02-28 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | [5 empty] | No | Java < v21
21526 | MyFordVehicles | In Production | MFV | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | Web application used for ordering management lease vehicles. Replacement for existing Quicklease system (ITMS: 70) |  |  | YES | 7 | NKANDULA | PLM | Mainframe | Q4 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
21526 | MyFordVehicles | In Production | MFV | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | Web application used for ordering management lease vehicles. Replacement for existing Quicklease system (ITMS: 70) |  |  | YES | 7 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
21526 | MyFordVehicles | In Production | MFV | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | Web application used for ordering management lease vehicles. Replacement for existing Quicklease system (ITMS: 70) |  |  | YES | 7 | NKANDULA | PLM | SQL | Q4 2027 | Modernize to Cloud Databases | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | SQL
23359 | AVL Creta | In Production | AVL-C | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Copper | Non S-Ox | - | Yes | No | COTS | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | AVL Creta is software supplied by AVL that manages the development lifecycle of engine calibrations and facilitates the managed sharing of engine calibrations across different vehicle programs and software calibrators. Initially being used as a pilot on V408 in Europe with a view to evaluating as the global strategic solution. | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21526 | MyFordVehicles | In Production | MFV | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | Web application used for ordering management lease vehicles. Replacement for existing Quicklease system (ITMS: 70) |  |  | YES | 7 | NKANDULA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-06 | Complete | Blue | 2024-12-15 | 2025-02-28 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | [5 empty] | No | Java < v21
24086 | My Next Vehicle | In Production | MNV | FORD CREDIT | IPANKAJ | VSUNDA21 | GSRINI34 | ROBRIEN3 | Bronze | Non S-Ox | 111 | No | Yes | In-House | IPANKAJ | VSUNDA21 | Ford Credit Services | 111 | Web Application used to increase Retail/Lease Sales by offering Account Manager users options for future Retail/Lease purchases based on account specific data. |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | Q2 2025 | Version Upgrade | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | Java < v21
24086 | My Next Vehicle | In Production | MNV | FORD CREDIT | IPANKAJ | VSUNDA21 | GSRINI34 | ROBRIEN3 | Bronze | Non S-Ox | 111 | No | Yes | In-House | IPANKAJ | VSUNDA21 | Ford Credit Services | Ford Credit (FMCC) | Web Application used to increase Retail/Lease Sales by offering Account Manager users options for future Retail/Lease purchases based on account specific data. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
24086 | My Next Vehicle | In Production | MNV | FORD CREDIT | IPANKAJ | VSUNDA21 | GSRINI34 | ROBRIEN3 | Bronze | Non S-Ox | 111 | No | Yes | In-House | IPANKAJ | VSUNDA21 | Ford Credit Services | Ford Credit (FMCC) | Web Application used to increase Retail/Lease Sales by offering Account Manager users options for future Retail/Lease purchases based on account specific data. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
24084 | Assigned Sales Vehicle Administration | In Production | ASVA | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Marketing & Sales | Marketing, Sales and Service | The Assigned Sales Vehicle application allows Ford of Canada to manage the request and approval and removal processes involved in the assigned sales vehicle process. Employees can request assigned sales vehicles and the appropriate managers can approve or decline their requests. Additionally, the application can also manage an audit process where employees in possession of assigned sales vehicles must attest to their continued need for them. Finally, the application also allows administrators to manage, access and monitor the processes provided by the application as well as to generate reports | 12 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53278 | Multi-cloud Consumption Dashboard | In Production | MCCD | EPEO | SJOHN172 | SJOHN172 | GGARIMEL | GGARIMEL | Copper | S-Ox Out of Scope | 122 | No | Yes | COTS | SJOHN172 | SJOHN172 | Enterprise Technology | EPEO | External Cloud consumption tracking tool. SaaS Product that supports Cloud Billing |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
24041 | Ariba Indirect | In Production | Aurora | I-ERP | SARAUJO3 | VANURAD2 | PCHITIYA | SNAG1 | Silver | S-Ox In Scope | 231 | No | Yes | Managed by 3rd Party Purchased Service | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Aurora- A Global cloud-based tool (Ariba/SAP) that manages requisitioning, sourcing, purchasing, and receiving of non-production materials. | 10 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53653 | Multi-channel Messaging | In Production | MCM | EVDD | DHE14 | QJI4 | TGUO9 | WJIN12 | Silver | Non S-Ox | 321 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 321 | MULTI-CHANNEL MESSAGING IS A PRODUCT FOR SENDING MESSAGES TO MULTIPLE CHANNELS, E.G. IN-APP/PUSH MESSAGE TO MOBILE APP, SMS TO MOBILE PHONE, MESSAGES TO IVI(IN-VEHICLE INFOTAINMENT) ,ALSO HANDLE MESSAGE LOGIC TO MEET CHINESE LOCAL MARKET REQUIREMENT LOGIC |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
24799 | Ariba Direct Sourcing | In Production | ADS | I-ERP | SARAUJO3 | KSYROCKI | PBUKKAPA | SNAG1 | Copper | Non S-Ox | 221 | No | Yes | Managed by 3rd Party Purchased Service |  |  | Supply Chain | - | SAP Ariba cloud-based SaaS solution for next generation supplier sourcing and contracting to support the Direct Sourcing process. Improvements in Direct Sourcing processes will position Ford to take advantage of best in class offering: 1. Align with mature industry offerings that provide solutions at market speed 2. Enable Ford to explore suppliers beyond the traditional automotive supply chain. | 8 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
14569 | MSDS External Public Website | In Production | MSDS | I-ERP | OTHERS | TWESP | RSCHMI16 | MMEHTA5 | Copper | Non S-Ox | 11 | Yes | No | Managed by 3rd Party Purchased Service | TWILKS2 | TWESP | Ford Customer Service | - | MSDS External Web-site provides information on chemical aftermarket products with Ford/Motorcraft brand. The site contains legally required documentation like Material Safety Data Sheets and Ingredients Data Sheets, as well as a chemical catalog with detailed product/part information. In total 30 global countries with 23 languages are covered. The site is not access controlled and therefore disposable to the world wide web community. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
17928 | Arg. VAT Recovery (VR) | In Production | ARVR | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Finance | - | The application does the assignment of the fiscal credit to be recovered that is related to the vehicles, parts and accessories that are exported during a month. This assignment is based in the fiscal credit that the company pays in their purchases. | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51089 | MS&S - RPA | In Production | MSSRPA | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | RSUBRA17 | SDHANAS2 | Copper | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | RKENNEL | Ford Customer Service | 221 | MS&S RPA Projects based on Pega & Chatbot |  | Springboot | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
51089 | MS&S - RPA | In Production | MSSRPA | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | RSUBRA17 | SDHANAS2 | Copper | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | RKENNEL | Ford Customer Service | Marketing, Sales and Service | MS&S RPA Projects based on Pega & Chatbot |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | [8 empty] | BigQuerry |  |  |  |  | DB Modernization as per PDO- Q2 2026 | No | SQL
17828 | Arg. Transport Documentation (MK) | In Production | ARMK | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Plants | - | Manages Bailment process to control parts delivered to Suppliers and their return with new features. Supports all legal requirements of Argentina Customs regime in factories. | 4 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
98 | MRS: Management Reporting System | In Production | MRS98 | M&S TECH | KPINNU | KHILLERT | GAJAY | JHARPER2 | Silver | Non S-Ox | 221 | No | Yes | In-House | KPINNU | KHILLERT | Ford Customer Service | Marketing, Sales and Service | Data warehouse which contains all of the information necessary to meet the business analysis and reporting needs of FCSD's North American business activities. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q4 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
98 | MRS: Management Reporting System | In Production | MRS98 | M&S TECH | KPINNU | KHILLERT | GAJAY | JHARPER2 | Silver | Non S-Ox | 221 | No | Yes | In-House | KPINNU | KHILLERT | Ford Customer Service | Marketing, Sales and Service | Data warehouse which contains all of the information necessary to meet the business analysis and reporting needs of FCSD's North American business activities. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
22572 | MPS1 Archive | In Production | MPSArchive | M&S TECH | VMUTHUPA | RANANDAL | JRAMU1 | JHARPER2 | Copper | Non S-Ox | 211 | No | Yes | - | VMUTHUPA | RANANDAL | Marketing & Sales | - | SQL Database to store archived data from MPS1 in accordance to GIS policies, as part of the applications decommisioning. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
16025 | Arg. Traffic & Customs (T&C) | In Production | ARTC | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | - | Manages Ford Argentina Import & Export Operations. Sends information to Custom Brokers with the material to be imported/exported and receives the information from the custom office with the imports and exports declared. | 6 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20167 | MPS - Web Jet Admin | In Production | MPS - WJA | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Copper | Non S-Ox | 11 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | PSIMONTE | Enterprise Technology | EPEO | HP Web Jet Admin is freely distributed software that provides the ability to install, configure, manage and troubleshoot TCP/IP printers. The software monitors network printers and detects error states. [TM to follow up & identify what action software takes when error state [event] occurs.] |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
17850 | Arg. Parts Document Recording (PDR) | In Production | ARPD | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Finance | - | This system allocates the purchasing documents (suppliers invoices and Import dispatches) to the produced vehicles. Allows to Financial inventory control and production FIFO by documents. This is the baseline to take advantage of the RAF import regime and the VAT Recovery process. | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
17831 | Arg. End-User File Upload Control (Consola) | In Production | ARCO | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Enterprise Technology | - | This system was developed to process all manual file input to accomplish all acr interfaces requirements. Users can send files (in pre defined formats) to a system, and CO makes the transference after a manager approval. | 7 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
17873 | ARG. EDI-FIS DEALER (FD) | In Production | ARFD | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Information sent to Dealers, Suppliers, Carriers, Browkers & Partners. Files generated by Mainframe and Others Ford Systems. Information received from Dealers Suppliers Carriers Browkers & Partners Files generated IN House PC to be processed in Mainframe systems in Ford. | 8 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2025-03-30 |  | Not Started |  | 2025-06-28 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
24133 | MPS - Jet Advantage Security Manager (printer secu | In Production | MPS -JA SM | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Bronze | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | PSIMONTE | Enterprise Technology | EPEO | JA SM is an application from HP to provide real time security for printers installed under the MPS (Managed Print Services) program. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
17860 | Arg. Dealer Retail Data Collection (DR) | In Production | ARDR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Copper | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | This system contains information about: - Vehicle orders submitted - Tracking of vehicles: . From Assembly to Delivery to Dealer . Transportation to Dealer Arrivals/Delivery to Customers at Dealer Location - Wholesale Invoicing - Ford Credit financing status - Retail Invoicing - Vehicle patents at R.N.P.A. | 12 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
22096 | MPS - HP Digital Sending Server | In Production | MPS HP DSS | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Copper | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | PSIMONTE | Enterprise Technology | EPEO | Digital Sending Software is the server side software which controls the Scan to Email and Scan to Folder functions on the HP Managed Print Services multifunction devices. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
17834 | Arg. Custom In House Regime (RAF) | In Production | ARFA | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House |  |  | Manufacturing Staffs | - | Manages Custom in House Imports & Exports. This Regime suspends duties and import fees payment for import parts used in production until the invoicing date. | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
18586 | Arg. Catalog Administration System (CAS) | In Production | ARAC | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Copper | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | Industrial System IT | This application is used to define and generate the different catalogs of the produced models. | 4 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
17838 | Arg. Application Access Profile Sytem (MS) | In Production | ARMS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Copper | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Enterprise Technology | - | Local Profile administration security system developed to manage access of users to each application and job in Ford Argentina. | 4 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
23297 | MPS - HP AC (Secure Pull Print) | Planned | MPS SPP | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Silver | Non S-Ox | 22 | No | Yes | - | SRUNSON | PSIMONTE | Enterprise Technology | - | Secure Pull Print - HP software managed by the Global Managed Print Service team. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
23673 | Appspace | Active | ADSS | EPEO | SRUNSON | PWILL357 | SKENNE67 | HLEVINE | Bronze | Non S-Ox | - | No | Yes | - | SRUNSON | PWILL357 | Enterprise Technology | - | ADSS provides a solution to manage, create, and deliver multimedia content (video, graphics) playback to digital signs (Digital Media Players (DMP) and monitor), as well as centrally manage DMPs at sites throughout Ford Motor Company. | 5 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
55007 | MPL-8502-BROADCAST | Planned | MPL-8502BC | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | SSENTH15 | Copper | Non S-Ox | - | No | Yes | - | SROYCHOU | BGANESH | Manufacturing Staffs | - | DPA solution : 8502 - Solve Code Update for Broadcast Commodities |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
13562 | Anthropomorphic Dummy Lab (ATD) | In Production | ATD | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | Verify suitability of Dummies for NHTSA test purposes, and to track parts for asset management and auditing. | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2026 | EDC New Hypervisor | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
55007 | MPL-8502-BROADCAST | Planned | MPL-8502BC | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | SSENTH15 | Copper | Non S-Ox | - | No | Yes | - | SROYCHOU | BGANESH | Manufacturing Staffs | - | DPA solution : 8502 - Solve Code Update for Broadcast Commodities |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
54900 | MPL GSCI EU Reports | In Production | MPL_EUGSCI | ISIT | OTHERS | JSCHULE6 | MMORTSIE | MMORTSIE | Bronze | Non S-Ox | 111 | Yes | No | In-House | AKURIAN | JSCHULE6 | Manufacturing Staffs | - | The application is used to support MPL in their daily work. We create a lot of reports, metrics and calculations, mostly based on CMMS, to support departments within MP&L. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
16136 | Andina Dealer Website Portal | In Production | CONFORD | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | Conford: CONcesionarios FORD. Andina Dealer Website Portal. Scope: Venezuela, Colombia, Ecuador Main system functionalities: - Submit FCSD part orders - Register retail vehicle sales - Warranty claims management - Payments control (FCSD Parts/Vehicles) - Inquiry financial statements - Issuance of Warranty certificate | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52758 | MP&L SCM DPA | In Production | MPLSCMDPA | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | SSENTH15 | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | - | Digital Process Automation for SCM for MPL business team |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | SQL
11346 | Allocation Optimization | In Production | ALLOPT | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Allocation Optimization takes the monthly Sales planning total vehicle and commodity allocations (for Markets, Reserve Accounts, Regions, and Dealers) and breaks those allocations into buildable weeks within the scheduling month based upon reasonable customer preference patterns. That weekly data is then electronically sent to the OSR, RTOM, COS and SRO systems so those processes use the same allocation data. | 4 |  | YES | 2 | NKANDULA | PLM | VM | Q4 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24478 | MP Fire | In Production | EuHR-MPF | OCETO | TSWEEN16 | KADOMKAI | MMUPPITA | ESTILESK | Copper | Non S-Ox | 211 | No | Yes | COTS | DDESAI | KADOMKAI | Ford Land | Staffs IT | Application supports Cologne fire brigade business: (1) Equipment Maintenance, (2) Issue Report, (3) Run Report. The application uses a purchased package MP Feuer (https://mp-feuer.de/) which runs on Citrix. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q3 2025 | On-Prem | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
15663 | Adaptive Control Systems | In Production | ACS | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | JMANI | Bronze | Non S-Ox | 311 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | - | Implements collections strategies and probability of default models. EU ACS business owner: Steve Earle | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q4 2026 | Partial Migration to GCP | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
20865 | Active Directory Federation Services | In Production | ADFS | EPEO | NOKEEFE | MSNYDER5 | ZZHAN106 | GSIENKIE | Gold | Non S-Ox | 211 | No | Yes | COTS | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | The Active Directory Federation Service ADFS provides a Ford Motor Company centralized Multiple Domain Single-Sign-On solution for web based applications. ADFS uses the Security Assertion Markup Language SAML and the WS-Federation framework to securely and directly communicate information about application users between Ford Motor Company and trusted partners. ADFS acts as either an identity provider or a service provider depending on the needs of the partner application. The Identity Provider role is used to gather required user attributes - generate a Federated Response-Assertion Document, sign the document, encrypt the document, and redirect the browser with the Federated Response-Assertion Document to the federated partners server acting in the Service Provider Role. The Service Provider is used to decrypt the Federated Response-Assertion Document provided by the federated partners server acting in the Identity Provider Role, verify the signature of the Document, and pass the validated user | 68 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | VM
21413 | Monthly Discount Rates | In Production | MDR | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Bronze | Non S-Ox | 121 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | - | This purpose of this application is to load monthly Discounting Rates prepared in the Thomson Reuters ATS application, store them in the MDR database and make them available to Ford finance and accounting Groups via a user interface and web services. |  |  | YES | 2 | TSWEEN16 | PLM | Java Struts | TBD | Rewrite | Modernize |  | 2024-11-24 |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
21413 | Monthly Discount Rates | In Production | MDR | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Bronze | Non S-Ox | 121 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | - | This purpose of this application is to load monthly Discounting Rates prepared in the Thomson Reuters ATS application, store them in the MDR database and make them available to Ford finance and accounting Groups via a user interface and web services. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  | 2024-04-24 |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
19524 | @Ford Online | In Production | @Ford | OCETO | TSWEEN16 | KADOMKAI | GWHOLIHA | MBALAN2 | Gold | Non S-Ox | 112 | No | Yes | COTS | DDESAI | DDESAI | Communications | Staffs IT | Single communication website for salaried and hourly employees, retirees, and agency personnel. | 39 |  | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2026 | Complete Migration to SaaS | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | VM
6358 | MONEX | In Production | MONEX | I-ERP | SFRANCI8 | DSHAH1 | NVARANAS | LWU14 | Gold | S-Ox In Scope | 31 | No | Yes | In-House | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | MONEX: Contains currency exchange rates used by various Ford Accounting applicaitons. The data is maintained by FoM Accounting personnel. ACR 2004-488 |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q4 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
12019 | MOES | In Production | MOES | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | Motorcraft (part) order entry system, used to maintain POPS Customer Master File. |  |  | YES | 1 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
9850 | Work Hours Maintenance System (eWHMS) | In Production | EWHMS | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House |  |  | PD Operations and Quality | Industrial System IT | Work Hours Management System - was created to electronically capture and report hours and head count information from hours charged against work orders at build sites and against GPIDs or Categories by the PD engineering community | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | Partial Migration to GCP | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2025-12-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | GCP Migration |  |  |  |  | [esankara 01/21] : Migrating to GCP Postgres by Q3 2025. | No | VM
51799 | MobileEye Road book Download | In Production | MRBD | EVDD | JWASNIC1 | ACHRIS39 | SHOWE | RKRISH61 | Copper | Non S-Ox | 122 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 122 | API USED TO PROVIDE MOBILEYE ROADBOOK MAP TILES AND BLUE CRUISE MAPS TO OUR FNV2 VEHICLES IN SUPPORT OF BLUE CRUISE FUNCTIONALITY. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
125 | MMP: Materials Management Process | In Production | MMP | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | Material Management System for FCSD PS&L organization. It is predecessor to uSAP. Gets data backfeed in to MMP and used as Data hub for Inventory, demand, planning info to Legacy downstream applications. Additional Outage Impacts include: Customer Complaint and Impact to Financial Results |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q2 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
125 | MMP: Materials Management Process | In Production | MMP | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | Material Management System for FCSD PS&L organization. It is predecessor to uSAP. Gets data backfeed in to MMP and used as Data hub for Inventory, demand, planning info to Legacy downstream applications. Additional Outage Impacts include: Customer Complaint and Impact to Financial Results |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
51944 | MKT Advocacy tool | In Production | Advocacy | M&S TECH | VMUTHUPA | DSHANKA1 | RPURUSH3 | MPREETH6 | Bronze | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | VMUTHUPA | DSHANKA1 | Marketing & Sales | 211 | Advocacy program is the tool allowing Ford owner to recommend Ranger through theirs own peer to peer social media contact. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | EAMS status - Decommissioned | No | Java < v21
24209 | Warehouse Inventory Next Generation sys- Account | In Production | WINGSA | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Copper | S-Ox Out of Scope | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Regional FCSD Accounting system in SA | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-04-30 |  | In-Progress |  | 2025-05-16 |  | Planned |  | No |  | 25% | 25% | [5 empty] | GCP Migration | [5 empty] | No | VM
51944 | MKT Advocacy tool | In Production | Advocacy | M&S TECH | VMUTHUPA | DSHANKA1 | RPURUSH3 | MPREETH6 | Bronze | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | VMUTHUPA | DSHANKA1 | Marketing & Sales | - | Advocacy program is the tool allowing Ford owner to recommend Ranger through theirs own peer to peer social media contact. |  |  | YES | 3 | NKANDULA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status - Decommissioned | No | SQL
382 | MITCOS: Material In Transit Control System | In Production | EuMP-MITCO | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | MITCOS, MATERIAL IN TRANSIT CONTROL ONLINE SYSTEM, deals with the transit of Material from mostly European & APA Suppliers via Carriers to Plants. The Supplier ships Parts to the Plants to build cars. These Parts are bundled together in boxes or on pallets and are documented in an ASN - Advanced Shipping Note, which is ideally be generated based on Releases/DCIs. ASN information most importantly details Part numbers, Quantities, a unique ASN number, the originating Supplier code, the Carrier code(s) and the final destination plant. FCSD suppliers also send their ASNs through MITCOS which will be processed and send to FCSD and BTR SAP application. Also MITCOS will receive ASNs from CMMS3 which are routed to customers through GEDI application. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11481 | Misc. Interco. Settlements of Non-prod Mat. (MICS) | In Production | MICS | I-ERP | SFRANCI8 | AKANSKI | TPRASAD1 | LWU14 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | MICS (Miscellaneous Intercompany Settlements of Non-prod Materials) / Old Acronym : NA |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
15745 | MIS Reporting | In Production | MIS | FORD CREDIT | IPANKAJ | VGA | BSENTHI1 | VBHUPATH | Bronze | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | VGA | Ford Credit Services | Ford Credit (FMCC) | MIS Reporting provides a centralized integrated management reporting function for Ford Credit. It allows for reduced data storage and processing needs through the elimination of redundant and obsolete reports, and resources spent on data reconciliation between reports. With CIG as the business customer, MIS Reporting utilizes a centralized process and leverages the Ford Credit Enterprise Data Warehouse (EDW). WebFOCUS is the core technology for all new reports with a few reports still on Business Objects. | 1194 |  | YES | 3 | SRAISIN1 | PLM | WebFocus | Q4 2024 | Migrate to Webfocus 9 | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-30 | 2024-12-30 | Complete | [15 empty] | Do not recognize this as a WebFOCUS app, not in my tracker. (KW 3-14-25) |  | DA
15745 | MIS Reporting | In Production | MIS | FORD CREDIT | IPANKAJ | VGA | BSENTHI1 | VBHUPATH | Bronze | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | VGA | Ford Credit Services | Ford Credit (FMCC) | MIS Reporting provides a centralized integrated management reporting function for Ford Credit. It allows for reduced data storage and processing needs through the elimination of redundant and obsolete reports, and resources spent on data reconciliation between reports. With CIG as the business customer, MIS Reporting utilizes a centralized process and leverages the Ford Credit Enterprise Data Warehouse (EDW). WebFOCUS is the core technology for all new reports with a few reports still on Business Objects. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
23997 | VMCWEB | In Production | VMCWEB | ISIT | JPITTERL | CBOHN | MBONAKDA | DNEWTON | Copper | Non S-Ox | 211 | No | Yes | In-House | CBOHN | IREINHO3 | Manufacturing Plants | Industrial System IT | A self developed Java application to support Business operations @ VMC in Cologne. The first release of VMCWEB contains pool car administration, issueing and billing. Enhancing VMCWEB will lead to a strategic step by step Migration of the legacy Software RAMCAM (ITMS 13877) | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
23090 | VIRTUAL DESKTOPS AS A SERVICE (VDIAAS) | Active | VDIaaS | EPEO | LFULCHER | LFULCHER | EREYNOL3 | GSIENKIE | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | Enterprise Technology | - | Strategic Virtual Desktop Infrastructure (VDI) is a cost effective, robust, secure, scalable and supportable solution that provides access by both internal (on Ford premises) and external (suppliers, joint ventures) users to applications and shared tools/services/resources hosted in Ford EDC. Ford has decided to implement production pilot with Cisco, followed by production roll-out. | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
50255 | Vehicle Key Management System | In Production | KEMAS | ISIT | JPITTERL | CBOHN | MBONAKDA | JLUCAS1 | Copper | Non S-Ox | 211 | No | Yes | COTS | CBOHN | IREINHO3 | PD Operations and Quality | Industrial System IT | The Application allows users to schedule the pickup and delivery of Keys automatically for Prototypes and Fleet Vehicles in Merkenich. | 7 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
23127 | uDeploy | Active | uDeploy | EPEO | LFULCHER | EREYNOL3 | JKADAKIA | SHAMID1 | Gold | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | Enterprise Technology | ITO | An IT automation framework that helps make rapid, repeatable changes to help manage various stages of the IT application lifecycle including: Automated, consistent deployments and rollbacks of applications Orchestration of changes across servers, tiers and components Configuration and security differences across environments Clear visibility: what is deployed where and who changed what Integrated with middleware, provisioning and service virtualization | 36 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
51722 | Mfg Digital Twin | In Production | MFGDigTwin | ISIT | SKING68 | JLYNN1 | KKISIEL | AELANGO | Copper | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | 211 | Digital Twin for Manufacturing Process |  | Springboot | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
18306 | TIVOLI ENTERPRISE PORTAL | Active | TEP | EPEO | SKULKA52 | CGIACOBB | DMUCKLIN | DMUCKLIN | Copper | Non S-Ox | - | No | Yes | - | CMIRABIT | CGIACOBB | Enterprise Technology | - | Visualization of the status of the Tivoli Monitoring (ITM) results. | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
56321 | Mfg Cost Optimization Suite | In Production | MAOS | GDIA | KLIDDLE | MNOEL2 | TMASLYK1 | GGREEN5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KLIDDLE | MNOEL2 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | This is a suite of Manufacturing Products that execute models used to optimize production and/or help Ford Manufacturing make optimization planning decisions. |  |  | NO | 2 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
54671 | Thousand Eyes | In Development | TE | EPEO | MCRNKOVI | SSOLTANI | CCRAIG39 | CCRAIG39 | Copper | Non S-Ox | 211 | No | Yes | COTS | MCRNKOVI | SSOLTANI | Enterprise Technology | EPEO | A tool used for Webex client diagnostics | 6 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
50273 | MFG Application Enablement Platform | In Production | MFG AEP | ISIT | SKING68 | CSHORTZ | MDENDRIN | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | COTS | SKING68 | CSHORTZ | Manufacturing Engineering | 211 | The AEP is a platform for ingesting data from manufacturing plant floor devices and integrating data from multiple applications, seamlessly integrating into an analytics solution. |  | Springboot | YES | 2 | BWUNNAVA | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
50057 | Technopedia | In Production | TECHNOPD | OCETO | TVASU | MWAWZYSK | SFAN21 | KTRACY8 | Silver | Non S-Ox | 211 | No | Yes | COTS | NSENTHI1 | MWAWZYSK | Enterprise Technology | Technology & Enterprise Services (TES) | Technopedia is a standardized library of IT technologies. It integrates with various systems in the ERP suite and aligns the catalogs and offerings to standard taxonomy. | 17 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
13620 | Environmental Label | In Production | EVL | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Silver | Non S-Ox | 21 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Marketing & Sales | Industrial System IT | Prints environmental information labels specific to individual vehicles and markets. These labels are required by law on vehicles put on public display in a few EU countries. |  |  | YES | 2 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13620 | Environmental Label | In Production | EVL | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Silver | Non S-Ox | 21 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Marketing & Sales | Industrial System IT | Prints environmental information labels specific to individual vehicles and markets. These labels are required by law on vehicles put on public display in a few EU countries. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | SQL
19238 | METRICS MANAGEMENT SYSTEM | In Production | MMS | ISIT | JKOONS | DMEENAK2 | TLEE7 | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | DMEENAK2 | Enterprise Technology | Industrial System IT | The Metrics Management System (MMS) will enable us to effectively measure and manage these critical and expensive software resources. MMS Reporting Repository enables the company to manage costs as well as assets by monitoring the software usage patterns of engineers by centrally compiling and analyzing relevant usage data. Through analysis of this data, we will be able to identify and correct areas of non-compliance, gaps in inventory versus usage - where cost savings are possible, and opportunities for enterprise license changes that would benefit the company in both the short and the long term. Of similar criticality is the need to identify where a shift in application licenses is needed. For example, some features may be under purchased (Under Purchased) today resulting in unproductive license denials, while other features have been overbought and are therefore not used effectively. |  |  | YES | 4 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [13 empty] | 01/22: Reached out to tlee7 via webex and he responded me in mail saying "MS SQL Server DB and MS Report Server (SSRS) will be migrated to EDC New Hypervisor (on-prem). Date=Q2 2026 (Tentatively) , Application Admin portal was moved to GCP Cloud run in 2024. This is the only part of the app that required migration to GCP. | No | SQL
21813 | StruxureWare for Data Centers | In Production | Struxure | EPEO | SKULKA52 | SYUKI2 | MDIERING | GSIENKIE | Copper | Non S-Ox | 111 | No | Yes | COTS | CMIRABIT | SYUKI2 | Enterprise Technology | EPEO | Data Center Infrastruxure Management software provided by Schneider for monitoring and management of Data Center Infrastructure. Comprises of Data Center Expert and Data Center Operation. | 7 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
13001 | Metal Spec Database | In Production | MSDB | ISIT | SKING68 | JRICH264 | RCHANDA | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | JLYNN1 | RTHIRUV1 | Manufacturing Engineering | Industrial System IT | Metal Spec. Database MSDB is based on the EU2066/EU55 process and describes the blanking stamping process including the specification of material properties and ordered coils. Data owner: European Stamping Plants Data User: Purchases M&PL Stamping Group Staff PD Laboratory | 112 |  | YES | 3 | BWUNNAVA | PLM | WebFocus | Q3 2025 | Migrate to Webfocus 9 | Modernize | 2025-09-30 | 2025-09-30 |  | In-Progress | Green | 2025-12-29 |  | Planned |  | No | [14 empty] | No | DA
13001 | Metal Spec Database | In Production | MSDB | ISIT | SKING68 | JRICH264 | RCHANDA | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | Metal Spec. Database MSDB is based on the EU2066/EU55 process and describes the blanking stamping process including the specification of material properties and ordered coils. Data owner: European Stamping Plants Data User: Purchases M&PL Stamping Group Staff PD Laboratory |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
13001 | Metal Spec Database | In Production | MSDB | ISIT | SKING68 | JRICH264 | RCHANDA | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | RTHIRUV1 | Manufacturing Engineering | Industrial System IT | Metal Spec. Database MSDB is based on the EU2066/EU55 process and describes the blanking stamping process including the specification of material properties and ordered coils. Data owner: European Stamping Plants Data User: Purchases M&PL Stamping Group Staff PD Laboratory |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
11306 | Medium Truck: Medium Truck VBOM | In Production | Mediu11306 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Gold | Non S-Ox | 111 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Medium Truck: Medium Truck VBPM |  |  | YES | 1 | RKENNEL | PLM | Mainframe | Q4 2026 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
206 | Mech Spec System | In Production | MechSpec | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 112 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | The Mech Spec System is a batch mainframe application which edits order amendments on the VSO, Cancellation, Spec Change and Re-Bill transactions for North American Marketing & Sales and then forwards the transactions to the appopriate systems for further processing. SLA 1, CIA 1,1,2 |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q3 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
206 | Mech Spec System | In Production | MechSpec | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 112 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | The Mech Spec System is a batch mainframe application which edits order amendments on the VSO, Cancellation, Spec Change and Re-Bill transactions for North American Marketing & Sales and then forwards the transactions to the appopriate systems for further processing. SLA 1, CIA 1,1,2 |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
6335 | MEARS - Appropriation Request System | In Production | EuAS-MEARS | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | LWU14 | Gold | Non S-Ox | 122 | No | Yes | In-House | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Standard global tool for assessing project related cost and benefits. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q4 2026 | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
24297 | MEA ZA SVD Archiving SQL Reporting Services | In Production | MEA ZA SVD | EPEO | ARAJKUMA | SSURES35 | EVANVUU1 | SKANIMO2 | Copper | Non S-Ox | 211 | No | Yes | Managed by 3rd Party Purchased Service | ARAJKUMA | SSURES35 | Marketing & Sales | EPEO | Archiving and reporting solution to support the decommissioning of the South Africa legacy Sales & Vehicle Distribution mainframe solution. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
16088 | Stock Administration Web Site | In Production | SAWS | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Bronze | S-Ox Out of Scope | 331 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | The Incentive Compensation Office (ICO) utilizes SAWS to maintain the history of annual grants and special grants. The application is also used to administer new grants. Participant information and Grants information is transmitted to Morgan Stanley (MS) who administers the exercise, by participants, of the options granted, and who ultimately becomes the master source for all stock award information. | 6 |  | YES | 5 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
15438 | MD&R/PARMS | In Production | PARMS | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | 333 | This Application ID applies to both the Plan and Rate Management System PARMS and Mechanized Discounting and Rate MD&R applications. . MD&R performs Loan Originations contract validations and contract data management . PARMS is a user interface for the development and launching of finance plans, and, rate structures for retail, lease and TRAC products. The Business Application Data Owners are: PARMS: kdudley1 MD&R: mmanion; lmervyn |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
15438 | MD&R/PARMS | In Production | PARMS | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | This Application ID applies to both the Plan and Rate Management System PARMS and Mechanized Discounting and Rate MD&R applications. . MD&R performs Loan Originations contract validations and contract data management . PARMS is a user interface for the development and launching of finance plans, and, rate structures for retail, lease and TRAC products. The Business Application Data Owners are: PARMS: kdudley1 MD&R: mmanion; lmervyn | 2 |  | YES | 4 | SRAISIN1 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned | [17 empty] | DA
15438 | MD&R/PARMS | In Production | PARMS | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | This Application ID applies to both the Plan and Rate Management System PARMS and Mechanized Discounting and Rate MD&R applications. . MD&R performs Loan Originations contract validations and contract data management . PARMS is a user interface for the development and launching of finance plans, and, rate structures for retail, lease and TRAC products. The Business Application Data Owners are: PARMS: kdudley1 MD&R: mmanion; lmervyn |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20867 | Splunk | In Production | Splunk | EPEO | RHAMMO57 | MBRUM | KTELLER1 | GSIENKIE | Copper | Non S-Ox | 221 | No | Yes | Managed by 3rd Party Purchased Service | RHAMMO57 | SHAYDEN5 | Enterprise Technology | EPEO | Splunk is used to index and search logs and machine data from various sources in a single interface as a part of MaaS (Monitoring as a Service) | 53 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
54319 | MCS - Task Builder | Planned | MCS-TB | ISIT | OTHERS | AHOROVIT | GKIENER | RPRASA22 | Bronze | Non S-Ox | 111 | No | Yes | In-House | AVARADH4 | AHOROVIT | Manufacturing Engineering | - | A component of the Manufacturing Master Control System that creates a set of executable tasks to be performed at a workstation based on a Process Configuration from the Process Configuration Tool. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
11565 | MCR: Material Cost Reporting | In Production | MCR | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | NBAECKER | DWIERZBI | Finance | FCSD Tech | MCR provides FCSD Purchasing and Finance with the ability to plan, forecast and track material cost. Specifically, the MCR project will provide the capability to plan forward year settlements - an aligned but slightly modified 100 day study similar to Production Purchasing. The planning process will also lead to deployment actions and plans for meeting business plan and budget objectives for material costs. The MCR system will also provide capability to forecast and track supplier year-over-year performance percentages by average period and by point-in-time to point-in-time. MCR is related to the Ford Customer Service and Production Purchasing alignment project and will support the supplier improvement metric (SIM) process by providing a consistent cost metric with production purchasing that is common between Europe and the U.S. Additional Outage Impact includes: Impact to Financial Results |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q4 2025 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
11565 | MCR: Material Cost Reporting | In Production | MCR | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | NBAECKER | DWIERZBI | Finance | FCSD Tech | MCR provides FCSD Purchasing and Finance with the ability to plan, forecast and track material cost. Specifically, the MCR project will provide the capability to plan forward year settlements - an aligned but slightly modified 100 day study similar to Production Purchasing. The planning process will also lead to deployment actions and plans for meeting business plan and budget objectives for material costs. The MCR system will also provide capability to forecast and track supplier year-over-year performance percentages by average period and by point-in-time to point-in-time. MCR is related to the Ford Customer Service and Production Purchasing alignment project and will support the supplier improvement metric (SIM) process by providing a consistent cost metric with production purchasing that is common between Europe and the U.S. Additional Outage Impact includes: Impact to Financial Results |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
20420 | MAXIMO FOR MAINTENANCE | In Production | MFM | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Silver | S-Ox In Scope | 222 | No | Yes | COTS | SKING68 | SKING68 | Manufacturing Staffs | Industrial System IT | Enables plant and equipment maintenance at our manufacturing facilities. Replacement for TEM 4. Based on Maximo 7.6.X |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
22434 | Spin 2 Win - Parts | In Production | S2W PARTS | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | Marketing, Sales and Service | The purpose of the Spin 2 Win - Parts website is to set up and administer campaigns that give eligible Ford of Canada Dealership participants a chance to win prizes for meeting sales objectives. | 13 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20420 | MAXIMO FOR MAINTENANCE | In Production | MFM | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Silver | S-Ox In Scope | 222 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Staffs | Industrial System IT | Enables plant and equipment maintenance at our manufacturing facilities. Replacement for TEM 4. Based on Maximo 7.6.X |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23824 | MaterialCenter | In Production | MatCen | ISIT | JPITTERL | CBOHN | HBOYSEN | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | JPITTERL | CBOHN | Advanced PD and Tech | Industrial System IT | MSC's MaterialCenter is a Material Lifecycle Management System for materials data & process management. MaterialCenter supports CAE and Material Engineering work streams. | 15 |  | YES | 3 | BWUNNAVA | PLM | BO | Q4 2024 | Already Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-31 | 2024-12-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | QlikSense | [5 empty] | No | DA
23824 | MaterialCenter | In Production | MatCen | ISIT | JPITTERL | CBOHN | HBOYSEN | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | JPITTERL | CBOHN | Advanced PD and Tech | Industrial System IT | MSC's MaterialCenter is a Material Lifecycle Management System for materials data & process management. MaterialCenter supports CAE and Material Engineering work streams. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51541 | South America OTD | In Production | SOTD | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Collect orders to South America | 5 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19048 | Material Release Analysis | In Production | MRA | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Bronze | Non S-Ox | 111 | No | Yes | In-House | JEISIMIN | SJINGILI | Manufacturing Staffs | Marketing, Sales and Service | This application will allow the business the analyze a supplier release considering all inputs through release. |  | WAS | YES | 1 | NKANDULA | PLM | WAS | Q2 2027 | Will be Decommissioned | Decommission | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
17711 | Material Release | In Production | MR | M&S TECH | FHIRSH | - | DRAMESH5 | PSATISH2 | Gold | Non S-Ox | 133 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | Minimize total supply chain inventory and ensure that sufficient material volumes are available to support production, thereby reducing Premium freight; Piece prices; Inbound Transportation costs; Obsolescence costs. Objective is to provide suppliers with accurate, stable and level releases. |  |  | YES | 1 | NKANDULA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
50573 | Material Forecasting | In Production | MF | M&S TECH | FHIRSH | SBINO | SBINO | PSATISH2 | Silver | Non S-Ox | 231 | No | Yes | - | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | MF is an application generates 53 weeks of constrainted feature forecast and sends the fully expanded orders to cmms. It takes inputs from various applications like PDO, SPCPS, SAC, OAR, OPA, CFF to arrive at the forecast. This application contains a COTS product called Kinaxis. MF product is a package of Order Forecasting (OF) , Controllable Feature Forecast (CFF) and Global Operating plan ( OPA). |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
50573 | Material Forecasting | In Production | MF | M&S TECH | FHIRSH | SBINO | SBINO | PSATISH2 | Silver | Non S-Ox | 231 | No | Yes | - | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | MF is an application generates 53 weeks of constrainted feature forecast and sends the fully expanded orders to cmms. It takes inputs from various applications like PDO, SPCPS, SAC, OAR, OPA, CFF to arrive at the forecast. This application contains a COTS product called Kinaxis. MF product is a package of Order Forecasting (OF) , Controllable Feature Forecast (CFF) and Global Operating plan ( OPA). |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
51540 | South America Direct Sales | In Production | SADS | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Manage Direct Sales for South America. | 8 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50573 | Material Forecasting | In Production | MF | M&S TECH | FHIRSH | SBINO | SBINO | PSATISH2 | Silver | Non S-Ox | 231 | No | Yes | - | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | MF is an application generates 53 weeks of constrainted feature forecast and sends the fully expanded orders to cmms. It takes inputs from various applications like PDO, SPCPS, SAC, OAR, OPA, CFF to arrive at the forecast. This application contains a COTS product called Kinaxis. MF product is a package of Order Forecasting (OF) , Controllable Feature Forecast (CFF) and Global Operating plan ( OPA). |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
11116 | Master Part Number Registry | In Production | MPNR | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Silver | Non S-Ox | 212 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | MPNR is an application to application integration solution that opens up existing MPNR functionality to other applications in a platform independent way. MPNR (Master Part Number Registry) provides a central part number repository that is needed to keep track of all part numbers (base and full) that are assigned at Ford Motor Company. MPNR will be used to request valid part numbers that will be validated and registered. Primary Users: Engineering, Design, PPM, and Service. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
11116 | Master Part Number Registry | In Production | MPNR | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Silver | Non S-Ox | 212 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | MPNR is an application to application integration solution that opens up existing MPNR functionality to other applications in a platform independent way. MPNR (Master Part Number Registry) provides a central part number repository that is needed to keep track of all part numbers (base and full) that are assigned at Ford Motor Company. MPNR will be used to request valid part numbers that will be validated and registered. Primary Users: Engineering, Design, PPM, and Service. |  |  | YES | 3 | BWUNNAVA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11116 | Master Part Number Registry | In Production | MPNR | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Silver | Non S-Ox | 212 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | MPNR is an application to application integration solution that opens up existing MPNR functionality to other applications in a platform independent way. MPNR (Master Part Number Registry) provides a central part number repository that is needed to keep track of all part numbers (base and full) that are assigned at Ford Motor Company. MPNR will be used to request valid part numbers that will be validated and registered. Primary Users: Engineering, Design, PPM, and Service. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
53915 | Master Data Management Tool - DHL | In Production | MDM | ISIT | VVIJAY55 | RADAM10 | OORLOVA | SSENTH15 | Silver | Non S-Ox | 222 | Yes | No | In-House | JPITTERL | CBOHN | Manufacturing Staffs | - | Application to executional plan a logistical outbound transportation network. Application is operated by the European LLP (DHL Supply Chain) who's main responsibility is to plan the logistics of the outbound (FVL) vehicles for Ford of Europe. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
53268 | SERVICE XP PLATFORM | In Production | SXP | M&S TECH | KPINNU | KMURALIK | SGUMUDA1 | PANTONI6 | Gold | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | KPINNU | KMURALIK | Customer Experience | Marketing, Sales and Service | The Ford Service Experience Platform (ServiceXP) provides the foundation for customer and dealer experiences (CX/DX) supporting our Service Customer Journey end-to-end. ServiceXP is based on Pega and will provide CX/DX related products and services such as Reservations, Global Uptime, Mobile Service. | 78 |  | YES | 3 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
18469 | Mass Autosave | In Production | MDT | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | SKING68 | Manufacturing Engineering | - | The AutoSave programmable device support software is a change management and storage system for the plants automation device programs. It features full documentation support, program history, access control, and full integration with programming application software packages for Schneider PL7/Unity, Indramat MTC200 and other controllers presently running in the plants. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
18469 | Mass Autosave | In Production | MDT | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Engineering | - | The AutoSave programmable device support software is a change management and storage system for the plants automation device programs. It features full documentation support, program history, access control, and full integration with programming application software packages for Schneider PL7/Unity, Indramat MTC200 and other controllers presently running in the plants. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
14840 | Secured Password Management | In Production | PwdMgmt | EPEO | NOKEEFE | MSNYDER5 | DDALKOVS | GSIENKIE | Silver | Non S-Ox | 222 | Yes | No | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Ford's complex, heterogeneous computing environment needs a simple way to manage multiple passwords. The P-Synch software simplifies multi-system password management by providing users, generic ID owners, and help desk operators with a web interface for managing their Active Directory password. Additionally, the P-Synch software provides a transparent password synchronization across different systems. Those systems are Active Directory (ICR #: 2005-1744), RACF (ICR #: 2003-1926_ and IBM Lighthouse (ICR #: 2013-1). P-Synch will enable Ford to strengthen and manage password authentication and reduce administration and help desk costs by: 1. Allowing all user passwords on registered Target Applications (i.e., Active Directory, RACF Mainframe Systems, IBM Lighthouse, etc...) to be changed to a single value simultaneously. 2. Enforcing a centralized password policy and history. 3. Allowing users to reset their own passwords via various self-service options (e.g., Q&A, Alternate Email, etc...) reducing | 12 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
11151 | Mass Analysis System | In Production | MAS | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 222 | No | Yes | In-House | DKAVITHA | DKAVITHA | PD Operations and Quality | Industrial System IT | The Mass Analysis System MAS is designed to aid the Weight Engineering Department in documenting and communicating vehicle program weight data and recommendations to the program teams and regulatory agencies globally. In addition the MAS system will be used to consolidate the weight information to a single source which will allow more efficient and consistent resolution of weight issues tracking and reporting.It provides the following features Common system for mass analysis replacing varied systems tools. Common reporting formats that create an efficient customer interface. Flexibility to build mass models from End Item CPSC or Curb level weights. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
51292 | SDE Utilities | In Production | SDE | EA | RRISS | SHE1 | LKESHRI | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | In-House | RRISS | SHE1 | Enterprise Technology | Technology & Enterprise Services (TES) | Utility Infrastructure to support SDE applications | 1 |  | YES | 2 | GBRAIL | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
11151 | Mass Analysis System | In Production | MAS | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 222 | No | Yes | In-House |  |  | PD Operations and Quality | Industrial System IT | The Mass Analysis System MAS is designed to aid the Weight Engineering Department in documenting and communicating vehicle program weight data and recommendations to the program teams and regulatory agencies globally. In addition the MAS system will be used to consolidate the weight information to a single source which will allow more efficient and consistent resolution of weight issues tracking and reporting.It provides the following features Common system for mass analysis replacing varied systems tools. Common reporting formats that create an efficient customer interface. Flexibility to build mass models from End Item CPSC or Curb level weights. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
21238 | Marketing Return on Investment Datawarehouse | In Production | MROI DW | GDIA | AFRADKIN | PBOSCO3 | KNAWAZ | MPATEL20 | Bronze | Non S-Ox | 221 | No | Yes | In-House | AFRADKIN | PBOSCO3 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | The Ford MROI Data Warehouse will capture all required data and automatically feed to the Market Share Partners Optimizer system. Support a world class MROI process to effectively optimize marketing and sales resources to areas of highest strategic importance across product portfolio, customer base, geographies, media mix, etc by establishing a fact based decision making process grounded in econometric/scenario planning models to predict and improve Fixed Marketing performance outcomes. | 141 |  | NO | 2 | FRANBELL | PLM | Datastage |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
21238 | Marketing Return on Investment Datawarehouse | In Production | MROI DW | GDIA | AFRADKIN | PBOSCO3 | KNAWAZ | MPATEL20 | Bronze | Non S-Ox | 221 | No | Yes | In-House | AFRADKIN | PBOSCO3 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | The Ford MROI Data Warehouse will capture all required data and automatically feed to the Market Share Partners Optimizer system. Support a world class MROI process to effectively optimize marketing and sales resources to areas of highest strategic importance across product portfolio, customer base, geographies, media mix, etc by establishing a fact based decision making process grounded in econometric/scenario planning models to predict and improve Fixed Marketing performance outcomes. |  |  | NO | 2 | FRANBELL | PLM | Mainframe |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
16800 | Marketing Program System 2 | In Production | MPS2 | M&S TECH | VMUTHUPA | RANANDAL | JRAMU1 | MPREETH6 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | MPS2 (formerly known as NGMPS) is a strategic replacement for MPS. This application will handle all VIN-based marketing payments (both VM and revenue) for European markets, with potential to expand to AP&A markets in the near future. MPS2 uses an off-the-shelf rule engine to allow business users to create the programs, and contains a batch engine which determines what payments need to be made under each program, and handles payments approval and administration. |  |  | YES | 6 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
16800 | Marketing Program System 2 | In Production | MPS2 | M&S TECH | VMUTHUPA | RANANDAL | JRAMU1 | MPREETH6 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | MPS2 (formerly known as NGMPS) is a strategic replacement for MPS. This application will handle all VIN-based marketing payments (both VM and revenue) for European markets, with potential to expand to AP&A markets in the near future. MPS2 uses an off-the-shelf rule engine to allow business users to create the programs, and contains a batch engine which determines what payments need to be made under each program, and handles payments approval and administration. | 499 |  | YES | 6 | NKANDULA | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
16800 | Marketing Program System 2 | In Production | MPS2 | M&S TECH | VMUTHUPA | RANANDAL | JRAMU1 | MPREETH6 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | MPS2 (formerly known as NGMPS) is a strategic replacement for MPS. This application will handle all VIN-based marketing payments (both VM and revenue) for European markets, with potential to expand to AP&A markets in the near future. MPS2 uses an off-the-shelf rule engine to allow business users to create the programs, and contains a batch engine which determines what payments need to be made under each program, and handles payments approval and administration. |  |  | YES | 6 | NKANDULA | PLM | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
16800 | Marketing Program System 2 | In Production | MPS2 | M&S TECH | VMUTHUPA | RANANDAL | JRAMU1 | MPREETH6 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | VMUTHUPA | VMUTHUPA | Marketing & Sales | Marketing, Sales and Service | MPS2 (formerly known as NGMPS) is a strategic replacement for MPS. This application will handle all VIN-based marketing payments (both VM and revenue) for European markets, with potential to expand to AP&A markets in the near future. MPS2 uses an off-the-shelf rule engine to allow business users to create the programs, and contains a batch engine which determines what payments need to be made under each program, and handles payments approval and administration. |  |  | YES | 6 | NKANDULA | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Oracle
51273 | SCAC Strategic Data Environment | In Production | SCAC SDE | GDIA | CBUCKL19 | KJINNA | RKODEESW | NDEVI3 | Silver | Non S-Ox | 311 | No | Yes | In-House |  |  | Enterprise Technology | Global Data Insight and Analytics (GDIA) | SCAC SDE system contains holistic customer centric data to support Campaigning, Decisioning, Reporting, Modeling, and Analytics functions for global Ford/ FMCC/ other Ford centric organizations | 6 |  | YES | 2 | FRANBELL | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-10-01 | 2025-10-01 |  | In-Progress | Green | 2025-11-15 |  | Planned |  | No | [14 empty] | No | VM
16800 | Marketing Program System 2 | In Production | MPS2 | M&S TECH | VMUTHUPA | RANANDAL | JRAMU1 | MPREETH6 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | MPS2 (formerly known as NGMPS) is a strategic replacement for MPS. This application will handle all VIN-based marketing payments (both VM and revenue) for European markets, with potential to expand to AP&A markets in the near future. MPS2 uses an off-the-shelf rule engine to allow business users to create the programs, and contains a batch engine which determines what payments need to be made under each program, and handles payments approval and administration. |  |  | YES | 6 | NKANDULA | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
16795 | Marketing Features Availability List | In Production | MFAL | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | JLUCAS1 | Bronze | Non S-Ox | 231 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | - | Repository of Product Definition Features. Includes the pre-processing for MSL. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11131 | Market Offering Complexity Analysis (MOCA) | In Production | MOCA | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Copper | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | MOCA - Market Offering Complexity Analysis is a Web-based application that allows Brand Teams to analyze historical vehicle order information and supports their efforts to develop more customer-focused vehicles. MOCA provides four core reports: Canned reports, Ad Hoc Queries, Models and Scenarios Reporting and Market Offering Health Reports (Mohr). | 8 |  | YES | 4 | NKANDULA | PLM | BO | Q4 2024 | Already Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-31 | 2024-12-31 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
11131 | Market Offering Complexity Analysis (MOCA) | In Production | MOCA | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Copper | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | MOCA - Market Offering Complexity Analysis is a Web-based application that allows Brand Teams to analyze historical vehicle order information and supports their efforts to develop more customer-focused vehicles. MOCA provides four core reports: Canned reports, Ad Hoc Queries, Models and Scenarios Reporting and Market Offering Health Reports (Mohr). |  |  | YES | 4 | NKANDULA | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status - App is Decommissioned . PDO team confirmed on the status | No | Oracle
11131 | Market Offering Complexity Analysis (MOCA) | In Production | MOCA | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Copper | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | MOCA - Market Offering Complexity Analysis is a Web-based application that allows Brand Teams to analyze historical vehicle order information and supports their efforts to develop more customer-focused vehicles. MOCA provides four core reports: Canned reports, Ad Hoc Queries, Models and Scenarios Reporting and Market Offering Health Reports (Mohr). |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q1 2025 | Will be Decommissioned | Decommission |  |  |  | Complete |  |  |  | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | EAMS status - App is Decommissioned . PDO team confirmed on the status | No | Mainframe
23863 | Retirement Data Archive (Open Text) | In Production | RDA | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Copper | Non S-Ox | 311 | Yes | No | Managed by 3rd Party Purchased Service | DDESAI | NMUTHUK2 | Human Resources | - | Data Archive Application. Internally hosted vendor application to store historical retirement records | 6 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
50371 | MAPS Manual Adjustment / Adhoc System | In Production | MAPS - MAA | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The primary use of this SQL Server and its data is to facilitate end-user, ad-hoc queries of account-level MAPS data. The data are used to provide more granular (tactical) breakdowns of the MAPS operational reports on a case-by-case, ad-hoc basis. Also, the data are used to identify deficiencies in the source systems' feeds to MAPS and prototype workarounds and ultimate resolutions to the deficiencies. Was AMPO 2648 MAPS EUC with a launch date of 5/31/2006. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53807 | Retail Network Information Bridge | Planned | RNIB | M&S TECH | NKANDULA | JLEWIS10 | TMCKEE2 | JHARPER2 | - | Non S-Ox | - | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | Data processing asset used to bridge information between the retail network transactional systems and the Dealer Franchising Portal (DFP) | 4 |  | YES | 3 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19338 | MAPS Budget | In Production | MAPSBudget | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The MAPS Budget reports provide a budget and actual for key measures relating to the business of Ford Credit. There are 18 reports for MAPS Budget. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
9079 | Retail Identification Program/Sign Ordering System | In Production | RIP/SOS | M&S TECH | NKANDULA | JLEWIS10 | KMICHALE | JHARPER2 | Silver | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Retail Identification Program Sign Ordering System (RIP/SOS) is the control system for all company approved exterior signs at franchised Ford and Lincoln dealerships within U.S. under the Retail identification Program. The group responsible for administering this program is the Retail Identification Activity (RIA). The RIA consists of one Ford Manager and his staff located in Dearborn with additional non-Ford Order Administrators located at the Sign Vendors. The Ford RIA is responsible for maintaining the SOS database of orderable sign models and associated pricing. The Vendors will be responsible for Order management and fulfilment. The Web platform allows for the partnering of Ford with the Sign Vendors to improve the process of timely completion Dealer Sign Orders. | 13 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13671 | Lommel Calibration Database/System | In Production | LCD/LCS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Copper | Non S-Ox | 111 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Calibration lab system for Lommel Proving Ground. The application consists of 2 parts: LCD (Oracle Forms 10G) for calibration preparation and reporting and LCS (Labview 5.1) for the actual sensor calibration. | 4 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2024 | Partial Migration to GCP | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | 25% | [7 empty] | GCP Migration | Ramesh | 2025-03-06 |  |  |  | No | VM
50552 | Relativity | In Production | Relativity | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | Non S-Ox | 321 | No | Yes | COTS | DDESAI | KADOMKAI | Policy | Staffs IT | Relativity contains the latest in advanced searching, analytics, machine learning and visualizations built into the application and is utilized by the majority of law firms and eDiscovery vendors used by OGC Litigation team. | 43 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
14484 | Design Verification Plan and Report | In Production | e-DVP&R | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | e-DVP&R is a powerful engineering tool which allows engineers to maintain engine and component DVP&Rs online. All DVP&Rs are maintained in one centralized database thus enabling communication efficiences. Management concurrence is contained within the e-DVP&R application.The Engine Program Engineer/Development Engineers initiate the process that assigns responsibilities. Component Engineers then enter the Engine & Vehicle Test sample sizes. The Engine Program Engineer then enters a proposed test sample based on the engine and test facilities budget. A reconciled sample size is entered which creates both the engine and all identified component DVP&Rs. The DVP&R is a standardized planning and tracking document that, when completed, validates the design. | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | VM
50986 | Manufacturing Vehicle Distribution - Corrective Action Management | In Production | MVD-CAM | ISIT | VVIJAY55 | RADAM10 | VDODDAMR | SSENTH15 | Silver | Non S-Ox | 122 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | The purpose of Manufacturing Vehicle Distribution - Corrective Action Management is to assist with the handling of exceptions when a VIN is off-plan between vehicle production and delivery to the final destination. This can include facilitating Spot Buys, Diversions, Manual Invoice submission and approvals, and telematics alerts based on various business thresholds and KPI criteria. |  |  | YES | 3 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
14607 | DVA Website | In Production | DVA | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Copper | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Web application used to support Ford Motor Companys Quality Initiatives by providing access to data used for analyzing and driving dimensionally optimized designs and processes DVA Website contains. --> DVA Studies for all vehicle programs; Competitive vehicle dimension data; Capability concurrence process sheet. Used to calculate ability to achieve fit and finish relative to completive vehicle set |  |  | YES | 1 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [9 empty] | Ramesh |  |  |  |  | No | SQL
53621 | REC AND NTC Test Vehicle Gate Control System | In Production | TVGCS | ISIT | SBONNICI | KRAMMOHA | ZWAN3 | HYANG80 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SBONNICI | KRAMMOHA | PD Operations and Quality | - | Smart gate control system for testing vehicle in REC/NTC | 1 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
14809 | Vehicle Special Ordering - MPL | In Production | eVSO | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 131 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Unique functionality within CMMS to manage VSO bill of material and order processing. eVSO is the system of record for vehicle special order parts and options only. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-06-23 | 2024-11-30 | 2024-11-30 | Complete | Blue | 2025-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
19977 | Manufacturing Order and Vehicle Information System | In Production | Movis | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Delivers VIN17/Part Number Bill of Materials (received from CMMS3) to consuming applications that reside within the Assembly Plant. MOVIS is expanding responsibilites to include providing WERS/MFAL codes received from GOTD/GOB based upon VIN17 (functionality referred to as Vehicle Features). |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | SQL | Priya | 2025-03-05 |  |  | Requires SQL 2019 AlwaysOn. Database VM will be migrated to OSV AS-IS. No changes will be made to the application. Timeline depends on OSV availability. | No | SQL
14648 | PTO Manufacturing Engineering Home Page | In Production | MEWEB | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Bronze | Non S-Ox | 111 | Yes | No | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | The Main PTO Manufacturing Engineering (ME) Web page. This Web site encompasses all the non-dynamic web sites within the global ME organization. | 11 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
19977 | Manufacturing Order and Vehicle Information System | In Production | Movis | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House |  |  | Manufacturing Staffs | Industrial System IT | Delivers VIN17/Part Number Bill of Materials (received from CMMS3) to consuming applications that reside within the Assembly Plant. MOVIS is expanding responsibilites to include providing WERS/MFAL codes received from GOTD/GOB based upon VIN17 (functionality referred to as Vehicle Features). |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-05 | 2025-03-05 | 2025-03-05 | Complete | Blue | 2025-03-05 | 2025-03-05 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Priya | 2025-03-05 |  |  | MOVIS GEN3 CaaS in EDC Java Version is curently 17. Migration Completed | No | Java < v21
50178 | PROXY INFRASTRUCTURE | Active | Proxy | EPEO | MCRNKOVI | BKARMAKA | HPATEL48 | HPATEL48 | Gold | Non S-Ox | - | No | Yes | - | MCRNKOVI | MCRNKOVI | Enterprise Technology | - | Proxy solution used Globally | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
14809 | Vehicle Special Ordering - MPL | In Production | eVSO | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 131 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Unique functionality within CMMS to manage VSO bill of material and order processing. eVSO is the system of record for vehicle special order parts and options only. |  |  | YES | 3 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-06-23 | 2024-11-30 | 2024-11-30 | Complete | Blue | 2025-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
51144 | Proxy Autoconfig | In Production | PrxyAutoC | EPEO | SKULKA52 | MCRNKOVI | BKARMAKA | IMACLEOD | Gold | Non S-Ox | 11 | No | Yes | In-House | CMIRABIT | CMIRABIT | Enterprise Technology | EPEO | The Proxy Autoconfig allows end user compute devices as well as EDC hosted servers to automatically resolve the closest proxy server to themselves. | 3 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
52066 | Manufacturing Gamification | In Production | MG | ISIT | OTHERS | CGOLDMA4 | LGARDN50 | AELANGO | Copper | Non S-Ox | 211 | Yes | No | In-House | AHOROVIT | CGOLDMA4 | Manufacturing Engineering | - | Application created to provide operators with real-time quality feedback, creating intrinsic motivation to improve and exceed in their work. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Priya |  |  |  |  | No | SQL
18786 | Project Directory Management and Server Access Too | In Production | ProjDirSAT | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | In-House | SKING68 | KRAMESH | Enterprise Technology | Industrial System IT | This web base application allows users to request access to project folder or request new project folders. Application allows the approvers for that folder to approve or deny request. Approved requests are reviewed by IT and access is granted using Active Directory (AD)groups | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
18584 | Manufacturing eXecution Advanced Planning and Sche | In Production | MX_APS | ISIT | SKING68 | JLYNN1 | GKESAVAR | AELANGO | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Provides up-front capacity planning and sourcing for new model programs for press subassemblies, racks, direct and indirect labour. This application is now global since 18 August 2015. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
13566 | Privilege Club - UK | In Production | EuHRPrivUK | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 321 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | Online application for employee discounted vehicle sales | 3 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
12158 | Manufacturing Capacity Planning Volume System | In Production | MCPV | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | The Manufacturing Capacity Planning Volume (MCPV) System generates forecasted capacity planning volumes (CPVs) for the N.A., European, and Asian Powertrain plants, and the N.A. Power Products plant. CPVs are sent to Purchasing and are used to tool up suppliers. MCPV is also the central repository for supplier capacity information (entered by Suppliers). MCPV provides the ability to process capacities studies, Broadcast and What If, and mechanically communicate study requirements to suppliers. MCPV is the pilot application for stronger authentication requiring a SecurID token for access to the application. MCPV supports the following business activities: PP&S, PPM, Purchasing and Suppliers. |  |  | YES | 2 | NKANDULA | PLM | Java Struts | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
12158 | Manufacturing Capacity Planning Volume System | In Production | MCPV | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | The Manufacturing Capacity Planning Volume (MCPV) System generates forecasted capacity planning volumes (CPVs) for the N.A., European, and Asian Powertrain plants, and the N.A. Power Products plant. CPVs are sent to Purchasing and are used to tool up suppliers. MCPV is also the central repository for supplier capacity information (entered by Suppliers). MCPV provides the ability to process capacities studies, Broadcast and What If, and mechanically communicate study requirements to suppliers. MCPV is the pilot application for stronger authentication requiring a SecurID token for access to the application. MCPV supports the following business activities: PP&S, PPM, Purchasing and Suppliers. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
15866 | Management, Analysis and Planning-MAPS UI | In Production | MAPS UI | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | MAPS Presentation uses Microsoft Analysis Services, an OLAP application, to build data cubes from MAPS Teradata once a month. The end user can access Microsoft Analysis Microsoft Reporting Services reports. There are many standard reports which reports on performance of field organizations and their dealer base. The Microsoft Analysis Services tool is flexible in that the user can see the data broke down in numerous views and well as allowing limited ad-hoc capabilities. |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q1 2027 | Rewrite | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | Java < v21
15860 | Management, Analysis and Planning-MAPS MF | In Production | MAPS - MF | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | MAPS MF is a cobol mainframe system (facility A) which takes in 20+ data feeds from receivable systems and Op Cost. The system runs at month-end. It processes the data and buckets it according to a g-number definition (EG; Average net receivables = g2004)which represents either a dollar value or a tranaction count. The data is passed to a Teradata repository. The data in the Teradata repository is pulled by the MAPS Presentation System which provides OLAP reports (another system). |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
15860 | Management, Analysis and Planning-MAPS MF | In Production | MAPS - MF | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | MAPS MF is a cobol mainframe system (facility A) which takes in 20+ data feeds from receivable systems and Op Cost. The system runs at month-end. It processes the data and buckets it according to a g-number definition (EG; Average net receivables = g2004)which represents either a dollar value or a tranaction count. The data is passed to a Teradata repository. The data in the Teradata repository is pulled by the MAPS Presentation System which provides OLAP reports (another system). |  |  | YES | 3 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50291 | PowerCurve Originations | In Production | PCO | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Bronze | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Consumer Credit Scoring Application | 3 |  | YES | 2 | SRAISIN1 | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
23711 | POLICY PORTAL - DOCUMENTUM D2 | In Production | PolicyMgmt | I-ERP | SFRANCI8 | SFRANCI8 | AKANSKI | LWU14 | Copper | Non S-Ox | 222 | No | Yes | COTS | TSWEEN16 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Policy Portal - Documentum D2 tool for Corporate Policy Management | 13 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2025 | Partial Migration to GCP | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50250 | PCN FMSP TOOL | In Production | FMSP TOOL | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Copper | Non S-Ox | 211 | Yes | No | In-House | DBRIGHEN | RCORDEI1 | Supply Chain | - | This is a tool for automating the PCN generation, improving in non-production purchasing and finance. | 2 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
12026 | Mainframe Charges Facility E | Active | FACe | OCETO | DBRIGHEN | VSILVEST | VSILVEST | NMORALE7 | Silver | Non S-Ox | - | No | Yes | - |  |  |  | Not in EAMS |  |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
21888 | Mainframe Billing & Reporting | Active | CDBR | EPEO | SKULKA52 | CGIACOBB | VMANDELL | VMANDELL | Copper | Non S-Ox | - | No | Yes | - |  |  | ENTERPRISE TECHNOLOGY | EPEO | MEMO BILLING FOR THE MAINFRAME. |  | MF - WAS Liberty | YES | 1 | SWALIMBE | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
16797 | Magnum Credit Bureau Interface | In Production | CBI | FORD CREDIT | RMINHAS3 | PBALUSU | JMADDEN5 | JMANI | Silver | Non S-Ox | 333 | No | Yes | COTS | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | Vendor (Magnum) software package to use loan application data and retrieve customer credit bureau data to create critera code values to be used in the scoring process. PC component creates rule set to determine the criteria code values. Rule set is compiled and moved to the mainframe to run as a black box within the Pinnacle application. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
23820 | MagicDraw Teamwork Server | In Production | MDRAWTWORK | ISIT | MNOWICK1 | PBORGAO1 | JYANDOO1 | GRAO3 | Copper | Non S-Ox | 311 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | 311 | Teamwork Cloud is a collaboration server that houses SysML models created using the MagicDraw client (COTS products). MD is used to engineer features and define architecture for platform systems at multiple, traceable abstraction levels through models. System design tasks in MD/TWC include definition of use cases, detailed system requirements, interface definition that turns into FIDL and APIs, FMEA and Functional safety. System design then feeds software development |  | Springboot | YES | 2 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
51017 | Payments Unique Modular Application | In Production | PUMA | FORD CREDIT | JBENITO | SHODGSO9 | ADELUIS | AGALLAG9 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JBENITO | SHODGSO9 | Ford Credit Services | Ford Credit (FMCC) | Application that provides functionality to perform & receive payments | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
51038 | M/ECAD | In Production | M/ECAD | ISIT | MNOWICK1 | PBORGAO1 | IAKLEH | GRAO3 | Bronze | Non S-Ox | - | Yes | No | In-House | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | - | M/ECAD is a comprehensive project that is focused on looking for the most optimal way to address the current and future business changes for the EDS Core department; this solution was designed to support the most recent engineering platforms CAD The Master and the upcoming FSS. Project: M/ECAD includes a series of functional components such as 3D PMI, DTSync, MCI 2.0, FFA2, EDS Checklist, WGO and a series of ECAD Inputs. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
20032 | OWS Warranty Claim Processing | In Production | OWS Claims | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | PSATHEE2 | RC41 | Silver | S-Ox In Scope | 232 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | Global claims processing and adjudication. Includes accounting modules and interfaces to the Business Rules Engine. | 95 |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
17826 | M&S Executive Dashboard | In Production | EDB | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The M&S Executive Dashboard is a reporting tool and data refresh process for a well-defined set of business drivers and measures. | 177 |  | YES | 7 | NKANDULA | PLM | BO | Q4 2024 | Already Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-31 | 2024-12-31 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
17826 | M&S Executive Dashboard | In Production | EDB | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The M&S Executive Dashboard is a reporting tool and data refresh process for a well-defined set of business drivers and measures. | 50 |  | YES | 7 | NKANDULA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
17826 | M&S Executive Dashboard | In Production | EDB | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The M&S Executive Dashboard is a reporting tool and data refresh process for a well-defined set of business drivers and measures. |  |  | YES | 7 | NKANDULA | PLM | Java Struts | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
17826 | M&S Executive Dashboard | In Production | EDB | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The M&S Executive Dashboard is a reporting tool and data refresh process for a well-defined set of business drivers and measures. |  |  | YES | 7 | NKANDULA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
17826 | M&S Executive Dashboard | In Production | EDB | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | The M&S Executive Dashboard is a reporting tool and data refresh process for a well-defined set of business drivers and measures. |  |  | YES | 7 | NKANDULA | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
19656 | OWS Service Event Data Collector | In Production | OWS SEDC | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | VRAMAC10 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | One Warranty System application to collect data throughout service event, focusing on Repair Order, Diagnostic Session data and Sync Health Reports. Will be used by Find A Vehicle Functionality. PDR - Pre Defined Repair is created in WC box and it is used in GACES. PDR Master screen in WC is used to create PDR in GACES after validating entries through web services. We have Create, Edit, Delete & Search PDR functionalities. | 5 |  | YES | 3 | RKENNEL | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
17826 | M&S Executive Dashboard | In Production | EDB | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The M&S Executive Dashboard is a reporting tool and data refresh process for a well-defined set of business drivers and measures. |  |  | YES | 7 | NKANDULA | PLM | WAS | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Need to check the Quater | No | Java < v21
19241 | Oracle Enterprise Manager | Active | OEManager | EPEO | SKULKA52 | NSHAH43 | HLIN13 | NVAIDYAN | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | Enterprise Technology | ITO | Oracle Enterprise Manager Agents physical implementation information and monitoring | 14 |  | YES | 3 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
19242 | Oracle | Active | Oracle | EPEO | SKULKA52 | NSHAH43 | NVAIDYAN | NVAIDYAN | Copper | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | Enterprise Technology | ITO | Oracle Database physical implementation information and monitoring | 30 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
20875 | Online Service Booking (App) | In Production | OSB | M&S TECH | RAHMED33 | PGOWERS | PGOWERS | JPOTTE60 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKLEINSM | BMUNIE | Ford Customer Service | Marketing, Sales and Service | Online Service Booking is the Global OWN solution for customers to book vehicle service and repair appointments. | 4 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23265 | LPG Electronic Workflow | In Production | eDocs | ISIT | OTHERS | GTACKOEN | FBOMANS | JLUCAS1 | Silver | Non S-Ox | 111 | Yes | No | In-House | GVANNOYE | GTACKOEN | PD Operations and Quality | Industrial System IT | Web- and SQL server infrastructure to host a Web based workflow system to process PD forms. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
22262 | OGC Due Diligence | In Production | OGC DD | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | Managed by 3rd Party Purchased Service | DDESAI | KADOMKAI | Policy | Staffs IT | The Third Party Due Diligence Tool provides an automated tool to assess the relative risk of bribery and corruption posed by any given third party to whom Ford has a relationship and document Ford's due diligence review | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23142 | LPG BUSINESS ADMINISTRATION WEB | In Production | LPGBAW | ISIT | OTHERS | GTACKOEN | FBOMANS | JLUCAS1 | Silver | Non S-Ox | 211 | Yes | No | In-House | GVANNOYE | GTACKOEN | PD Operations and Quality | Industrial System IT | To improve the efficiency of the business administration and the transparency of the LPG operation, all data should only be entered once into a central database using standardized forms and reports. . Through a global portal, specific users will be allowed to retrieve specific data in line with the company guidelines. The system should include the possibility to collect the same data from agency and hired persons that are under Ford supervision. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
20679 | OCCUPATIONAL HEALTH BY POSITION | In Production | EOH | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Human Resources | - | The Brazilian government requires employers to keep track of employee occupational health by work position. Functionality is above and beyond to that provided by OHSIM. | 6 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
23142 | LPG BUSINESS ADMINISTRATION WEB | In Production | LPGBAW | ISIT | OTHERS | GTACKOEN | FBOMANS | JLUCAS1 | Silver | Non S-Ox | 211 | Yes | No | In-House | GVANNOYE | GTACKOEN | PD Operations and Quality | Industrial System IT | To improve the efficiency of the business administration and the transparency of the LPG operation, all data should only be entered once into a central database using standardized forms and reports. . Through a global portal, specific users will be allowed to retrieve specific data in line with the company guidelines. The system should include the possibility to collect the same data from agency and hired persons that are under Ford supervision. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
50745 | Loyalty Products & Services | In Production | LPS | M&S TECH | MRICHA62 | MRICHA62 | VSARIPA1 | SNETHAJI | Gold | Non S-Ox | 211 | Yes | No | In-House | NKANDULA | MRICHA62 | Customer Experience | Marketing, Sales and Service | Loyalty Products and Services is the global strategic platform providing Loyalty capabilities at Ford. It provides a set of orchestration, experience APIs, and an abstraction layer to the Comarch Loyalty Management vendor platform. |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
13683 | Lommel Visitor Book | In Production | EuPV-LVB | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Electronic visitor records for Lommel Proving Ground. |  |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 25% | [7 empty] | Cloud SQL PostgreSQL | Ramesh | 2025-03-06 |  |  |  | No | Oracle
13683 | Lommel Visitor Book | In Production | EuPV-LVB | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Electronic visitor records for Lommel Proving Ground. |  |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 25% | [7 empty] | Cloud Run | Ramesh | 2025-03-06 |  |  |  | No | Java < v21
13671 | Lommel Calibration Database/System | In Production | LCD/LCS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Copper | Non S-Ox | 111 | No | Yes | In-House | JKOONS | JKOONS | PD Operations and Quality | Industrial System IT | Calibration lab system for Lommel Proving Ground. The application consists of 2 parts: LCD (Oracle Forms 10G) for calibration preparation and reporting and LCS (Labview 5.1) for the actual sensor calibration. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 25% | [7 empty] | Cloud SQL PostgreSQL | Ramesh | 2025-03-06 |  |  |  | No | Oracle
13671 | Lommel Calibration Database/System | In Production | LCD/LCS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Copper | Non S-Ox | 111 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Calibration lab system for Lommel Proving Ground. The application consists of 2 parts: LCD (Oracle Forms 10G) for calibration preparation and reporting and LCS (Labview 5.1) for the actual sensor calibration. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 25% | [7 empty] | Cloud Run | Ramesh | 2025-03-06 |  |  |  | No | Java < v21
51464 | OBD Status Database | In Production | OBD-Sta-DB | ISIT | JKOONS | MNOVAK1 | HLIN11 | JLUCAS1 | Copper | Non S-Ox | 111 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | This application hosts the database that interfaces with OBD DVM application and the business managed OBD Status Dashboard application | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | Partial Migration to GCP | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50145 | Loan Origination Services | In Production | LOS | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | Non S-Ox | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | 333 | This application hosts all the micro services related to Pinnacle Loan Origination. Services are either called from Pinnacle Loan Origination or they expose data from Pinnacle Loan Origination tables. |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | Q3 2027 | Version Upgrade | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
50145 | Loan Origination Services | In Production | LOS | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | Non S-Ox | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | This application hosts all the micro services related to Pinnacle Loan Origination. Services are either called from Pinnacle Loan Origination or they expose data from Pinnacle Loan Origination tables. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50145 | Loan Origination Services | In Production | LOS | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | Non S-Ox | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | This application hosts all the micro services related to Pinnacle Loan Origination. Services are either called from Pinnacle Loan Origination or they expose data from Pinnacle Loan Origination tables. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | Cloud SQL PostgreSQL | [6 empty] | SQL
50367 | NGAVS-Schedule Management | In Production | NGAVS-SM | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Silver | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | NGAVS-SM provides the capabilities to receive daily production schedules from order management systems and allow plant scheduler to amend, hold, cancel and submit order and plant blend requests. | 7 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [9 empty] | Priya |  |  |  |  | No | VM
53398 | Next-gen Global Packaging Portal | In Production | NGGPP | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 211 | No | Yes | In-House | GHERMAN | ADURSO | Enterprise Technology | Industrial System IT | NGGPP is Next-gen Global Packaging Portal | 4 |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2025 | Partial Migration to GCP | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22565 | LoadRunner Global | Active | LR | EA | RRISS | THALL6 | JSAJID | PSHAH | - | Non S-Ox | - | No | Yes | - |  |  | Enterprise Technology | - |  |  | Springboot | YES | 2 | GBRAIL | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
21875 | Network Visibilty | In Production | NetVis | EPEO | MCRNKOVI | BKARMAKA | HPATEL48 | HPATEL48 | Copper | Non S-Ox | 222 | No | Yes | COTS | MCRNKOVI | MCRNKOVI | Enterprise Technology | EPEO | Network Visibilty is a robust network analysis and packet inspection tool for network personnel. It gives high visibility into traffic types, trends, and application performance management. It offers an enhanced expert analysis and troubleshooting tools to operational staff and runs on many platforms including: - Gigastor: Long term disk-based capture appliance - Probe: 1G/10G speed capture appliance with large buffer memory - Local machines: Servers and laptops running windows operating system (7+, 2k8+) may also act like probes | 4 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
24438 | Litigation HotDocs | In Production | HotDocs | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Policy | Staffs IT | HotDocs App is an automated document production system implemented for OGC (Office of General Counsel). The system will automate the production of legal documents using a template with a common language, and data from various enterprise systems based on user inquiries. The solution is based on a COTS product, HotDocs, and involve developing templates, interface development to multiple systems to integrate data within the templates. HotDocs App is a web-based COTS application based on .NET technologies and hosted in Ford Data Center. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
13357 | Network Business Tools | In Production | NBT | EPEO | MCRNKOVI | SPANDRAN | NVIDICAN | NVIDICAN | Copper | Non S-Ox | 222 | No | Yes | In-House | MCRNKOVI | MCRNKOVI | Enterprise Technology | EPEO | Network Business Tools (NBT) is comprised of many different applications using a common platform and code base. Currently, the application list includes SAM, VAL, GSEC DB, FSS, SMTP Registration, ECS Review, CMS, and smaller utilities. There are many urls associated with this application. nbt.netops.ford.com, nbt.ford.com, fssford.com, sam.ford.com, val.ford.com, ecsreview.ford.com, gsecdb.ford.com, network.ford.com | 10 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
53246 | Lincoln Loyalty APP | In Production | Lin_L_APP | I-ERP | HHUANGJI | JZHOU42 | YYU34 | YXU116 | Bronze | Non S-Ox | 212 | No | Yes | Open Source | #N/A | #N/A | Marketing & Sales | 212 | THIS IS THE SYSTEM TO PROVIDE THE MEMBERSHIP CREDITS FOR CHINA CUSTOMER. |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
51240 | Lincoln China Mall | In Production | LCNML | I-ERP | HHUANGJI | JZHOU42 | CGU7 | HYANG80 | Gold | Non S-Ox | 212 | No | Yes | In-House | #N/A | #N/A | Marketing & Sales | 212 | LINCOLN CHINA MALL APPLICATION IS TO PROVIDES LIST OF WEBSERVICES AND DATA THAT ENABLES FUNCTIONALITY FOR LINCOLN CUSTOMER FACING DIGITAL CHANNELS IN CHINA |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13729 | LIMS: Laboratory Information Management System | In Production | EuVP_LIMS | ISIT | JKOONS | CBOHN | MZIRWES1 | JLUCAS1 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | JKOONS | PD Operations and Quality | Industrial System IT | This LIMS is a full-featured Client Server Laboratory Information Management System that is integrated into Windows environment for the European Materials Laboratory developed by LABWARE Association. The system manages all projects e.g. workload test protocol and results cost controlling reporting. The system is concepted to be variable to the various business requirements. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
21337 | NetOps Support Database | In Production | NETSUPDB | EPEO | MCRNKOVI | BKARMAKA | JSATHEES | VCHEDARA | Copper | Non S-Ox | 222 | No | Yes | In-House |  |  | Enterprise Technology | EPEO | Network Operations Network Database is the authoritative source for global network device information and support data. | 4 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
11975 | LIMA - Logistics Integration Management App | In Production | EuMP-LIMA | ISIT | JPITTERL | CBOHN | MBONAKDA | SSENTH15 | Bronze | Non S-Ox | 211 | No | Yes | In-House | CBOHN | IREINHO3 | Manufacturing Plants | 211 | This application comprises the following functionality to support the Transport Operations Business in Britain: (1) Truck Fleet, (2) Central Repair Garage, (3) European Premium Freight, (4) SWAP Body Pitch, and (5) ex- Works. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q2 2025 | Rewrite | Modernize |  | 2025-11-15 |  | In-Progress | Green | 2025-11-15 |  | Planned |  | No | [8 empty] | Java 17 | Priya | 2025-04-03 |  |  | App rewrite & DB migration in GCP is targeted for Q2 2025. Java 11 to Java 21 upgrade planned for Q4 2025 | No | Java < v21
21162 | NAC- BARTENDER | In Production | BARTENDER | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | Managed by 3rd Party Purchased Service |  |  | PD Operations and Quality | Industrial System IT | BarTender is software for designing and printing labels, barcodes and RFID tags. This is a tool to be used with the APTL ACS RFID application. Refer to APTL RFID Server Renewal 19638 | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
18043 | LGT - MP&L Datawarehous (MP) | In Production | LGT | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Manufacturing Staffs | - | Database with logistics information (MP and G3 Systems) that is used by MP&L staff to get information and compose some business reports. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | Database servers & EAMS Status decommissioned | No | Oracle
21526 | MyFordVehicles | In Production | MFV | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | Web application used for ordering management lease vehicles. Replacement for existing Quicklease system (ITMS: 70) | 4 |  | YES | 7 | NKANDULA | PLM | VM | Q4 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
15391 | Web Based Catalyst Packaging Information System | In Production | WCPI | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 221 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | The Web-based Catalyst Packaging System (WCPI) is utilized in the creation, transmittal and storage of Catalyst Packaging Information in support of the analysis and forecasting of the catalyst commodity. It is a web-based functional tool that was created to facilitate the design and procurement of PROTOTYPE catalyst systems. | 4 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2024 | EDC CaaS | Modernize | 2024-08-16 | 2024-08-16 | 2024-08-16 | Complete | Blue | 2024-09-30 | 2024-09-25 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0 | EDC CaaS | Priya | 2025-03-06 |  |  | VMs removed | No | VM
15470 | Lending Automotive-LA Applications (FCNA and FAFC) | In Production | LA | FORD CREDIT | IPANKAJ | RRAJESH8 | TNARAYA2 | NVARADA2 | Silver | S-Ox In Scope | 332 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Externally hosted - FCNA and FAFC Lending Automotive (LA) system is designed to track all retail installment loans and customer leases from booking to conclusion, including payments, disbursements, account closing, late charges and fees. | 1 |  | YES | 4 | SRAISIN1 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned | [17 empty] | DA
15470 | Lending Automotive-LA Applications (FCNA and FAFC) | In Production | LA | FORD CREDIT | IPANKAJ | RRAJESH8 | TNARAYA2 | NVARADA2 | Silver | S-Ox In Scope | 332 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Externally hosted - FCNA and FAFC Lending Automotive (LA) system is designed to track all retail installment loans and customer leases from booking to conclusion, including payments, disbursements, account closing, late charges and fees. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
15470 | Lending Automotive-LA Applications (FCNA and FAFC) | In Production | LA | FORD CREDIT | IPANKAJ | RRAJESH8 | TNARAYA2 | NVARADA2 | Silver | S-Ox In Scope | 332 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Externally hosted - FCNA and FAFC Lending Automotive (LA) system is designed to track all retail installment loans and customer leases from booking to conclusion, including payments, disbursements, account closing, late charges and fees. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
22572 | MPS1 Archive | In Production | MPSArchive | M&S TECH | VMUTHUPA | RANANDAL | JRAMU1 | JHARPER2 | Copper | Non S-Ox | 211 | No | Yes | - | VMUTHUPA | RANANDAL | Marketing & Sales | - | SQL Database to store archived data from MPS1 in accordance to GIS policies, as part of the applications decommisioning. | 1 |  | YES | 2 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53585 | Leidos-AMS | In Production | Leidos-AMS | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Silver | Non S-Ox | 322 | Yes | No | COTS | JKOONS | TBROWN99 | New Model Programs | Industrial System IT | COTS software to be used to operate wireless Ingersoll-Rand torque wrenches at NMPDC. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
52758 | MP&L SCM DPA | In Production | MPLSCMDPA | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | SSENTH15 | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | - | Digital Process Automation for SCM for MPL business team | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
12120 | Lean Manufacturing Assistant | In Production | LMA | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | SKING68 | Manufacturing Staffs | Industrial System IT | The Lean Manufacturing Assistant is a real-time part flow visualization tool that enables line operators and plant personnel to increase manufacturing productivity |  |  | NO | 3 | BWUNNAVA | PLM | Oracle |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
23134 | Motorcraft.com - 2015 | In Production | motorcraft | M&S TECH | RKLEINSM | BMUNIE | MSRINI25 | JPOTTE60 | Copper | Non S-Ox | 111 | No | Yes | - | RKLEINSM | BMUNIE | Ford Customer Service | Marketing, Sales and Service | Motorcraft dot com is a public facing website created to provide Motorcraft part information to our consumers B2C and business customers B2B. In addition, we provide a seller locator that includes both our dealer network and ford authorized distributors FAD contact information. The site is developed using Responsive and Adaptive Design RAD to support multiple devices desktop, tablet, mobile. This is a joint venture of the U.S., Canada, and EMS markets Central America, Caribbean, Puerto Rico, Middle East, Sub Sahara and Africa, APEM and South Korea that supports 6 languages (English, Arabic, French, Spanish, Korean and Portuguese). | 13 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
12120 | Lean Manufacturing Assistant | In Production | LMA | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | SKING68 | Manufacturing Staffs | Industrial System IT | The Lean Manufacturing Assistant is a real-time part flow visualization tool that enables line operators and plant personnel to increase manufacturing productivity |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2026 | On-Prem | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
53915 | Master Data Management Tool - DHL | In Production | MDM | ISIT | VVIJAY55 | RADAM10 | OORLOVA | SSENTH15 | Silver | Non S-Ox | 222 | Yes | No | In-House |  |  | Manufacturing Staffs | - | Application to executional plan a logistical outbound transportation network. Application is operated by the European LLP (DHL Supply Chain) who's main responsibility is to plan the logistics of the outbound (FVL) vehicles for Ford of Europe. | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
25080 | Lead Access Platform (LEAP) | In Production | LEAP | FORD PRO & FCSD TECH | TJUNIPER | GRIST | SRAVI6 | AJOGIYAT | Silver | Non S-Ox | 321 | No | Yes | COTS |  |  | Marketing & Sales | Marketing, Sales and Service | Track Leads from point of initiation to fulfilment including activities by dealers agnostic of DMS |  | Springboot | YES | 2 | RKENNEL | PLM | Java < v21 | Q2 2026 | Version Upgrade | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
12350 | LDS EU (Lead Delivery System) | In Production | LDS | FORD PRO & FCSD TECH | TJUNIPER | GRIST | SRAVI6 | AJOGIYAT | Silver | Non S-Ox | 321 | No | Yes | In-House | TJUNIPER | GRIST | Marketing & Sales | Marketing, Sales and Service | LDS is a web service based application designed to deliver EU prospects (leads) to Dealer DMS systems. It enables DMS systems to send updates (feedback the progress they have made on following up those leads) to the leads as well. |  |  | YES | 3 | RKENNEL | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
12350 | LDS EU (Lead Delivery System) | In Production | LDS | FORD PRO & FCSD TECH | TJUNIPER | GRIST | SRAVI6 | AJOGIYAT | Silver | Non S-Ox | 321 | No | Yes | In-House | TJUNIPER | GRIST | Marketing & Sales | Marketing, Sales and Service | LDS is a web service based application designed to deliver EU prospects (leads) to Dealer DMS systems. It enables DMS systems to send updates (feedback the progress they have made on following up those leads) to the leads as well. |  |  | YES | 3 | RKENNEL | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | 0% | 100% | N/A | 75% | 0% |  | N/A |  | Cloud SQL SQLServer | [5 empty] | No | SQL
16800 | Marketing Program System 2 | In Production | MPS2 | M&S TECH | VMUTHUPA | RANANDAL | JRAMU1 | MPREETH6 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | MPS2 (formerly known as NGMPS) is a strategic replacement for MPS. This application will handle all VIN-based marketing payments (both VM and revenue) for European markets, with potential to expand to AP&A markets in the near future. MPS2 uses an off-the-shelf rule engine to allow business users to create the programs, and contains a batch engine which determines what payments need to be made under each program, and handles payments approval and administration. | 21 |  | YES | 6 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53694 | Launch Digital Score Card | In Development | LDSC | ISIT | OTHERS | - | LRUIZMAT | DNEWTON | Silver | Non S-Ox | 211 | Yes | No | In-House | RGARCI45 | SMORADO | Manufacturing Plants | - | it's an integrated App that collect data from internal and external sources and makes different displays of them. |  |  | YES | 1 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51092 | Manufacturing Vehicle Distribution - Dashboards and Analytics | In Production | MVD - DNA | ISIT | VVIJAY55 | RADAM10 | VDODDAMR | SSENTH15 | Silver | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Finished Vehicle logistics operations dashboards | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22978 | Landed Cost Solution - AP | In Production | L-CAS | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Copper | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | AP-Regional-Landed Cost & Cubing Solution. Automated system to calculate Landed Cost: for a production part, it is the sum of its actual cost, transportation charges and any customs duties that could have been paid for it, the total amount Ford has spent for that part to be available at the plant from source. |  | WAS | YES | 2 | BWUNNAVA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
22978 | Landed Cost Solution - AP | In Production | L-CAS | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Copper | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | AP-Regional-Landed Cost & Cubing Solution. Automated system to calculate Landed Cost: for a production part, it is the sum of its actual cost, transportation charges and any customs duties that could have been paid for it, the total amount Ford has spent for that part to be available at the plant from source. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize | 2024-06-19 | 2024-06-19 | 2024-05-29 | Complete | Blue | 2024-06-28 | 2024-06-29 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL SQLServer | Priya | 2025-03-15 |  |  | App & DB migrated in 2024. | No | SQL
19977 | Manufacturing Order and Vehicle Information System | In Production | Movis | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Delivers VIN17/Part Number Bill of Materials (received from CMMS3) to consuming applications that reside within the Assembly Plant. MOVIS is expanding responsibilites to include providing WERS/MFAL codes received from GOTD/GOB based upon VIN17 (functionality referred to as Vehicle Features). | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | EDC CaaS | Priya | 2025-03-05 |  |  | Migration to EDC CaaS for a single site (DCP) Completed. | No | VM
24438 | Litigation HotDocs | In Production | HotDocs | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Policy | Staffs IT | HotDocs App is an automated document production system implemented for OGC (Office of General Counsel). The system will automate the production of legal documents using a template with a common language, and data from various enterprise systems based on user inquiries. The solution is based on a COTS product, HotDocs, and involve developing templates, interface development to multiple systems to integrate data within the templates. HotDocs App is a web-based COTS application based on .NET technologies and hosted in Ford Data Center. | 6 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53585 | Leidos-AMS | In Production | Leidos-AMS | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Silver | Non S-Ox | 322 | Yes | No | COTS | JKOONS | TBROWN99 | New Model Programs | Industrial System IT | COTS software to be used to operate wireless Ingersoll-Rand torque wrenches at NMPDC. | 6 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
51282 | Key Cabinet | In Production | Traka | EPEO | SKULKA52 | SYUKI2 | MDIERING | ESTILESK | Copper | Non S-Ox | 111 | No | Yes | COTS | CMIRABIT | SYUKI2 | Enterprise Technology | EPEO | Manage access to keys at EDC1/EDC2/BLDG6 with Traka Key Management System S series cabinet with attached HMI screen, using Traka Web interface to administer access policies. | 4 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
17770 | CMMS Open-To-Go Reporting | In Production | CMMS OTG | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 333 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Open To Go (OTG) is a global reporting application for vehicle and manufacturing parts progress that allows Launch Team and Preproduction Analyst to quickly gather metrics on part availability issues so that they can prove-out launch readiness. The OTG reports are the mechanism by which all parts new to a vehicle line/engine/transmission and required for launch are tracked. It indicates the part status relative to Production Part Approval Process (PPAP), sample promise date, part identification, supplier name/GSDB code, engineering release level, part approval status, etc. The report is used to determine launch readiness, provide an early indication of the health of a program and to create status projections into the future. The application is used as the primary tool for a series of on-going OTG meetings held with launch management. |  |  | YES | 3 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-03-25 | 2024-03-25 | 2024-03-25 | Complete | Blue | 2024-11-08 | 2024-11-04 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Priya | 2025-03-06 |  |  |  | No | Java < v21
50696 | Knock Down LOT Set Order Management System | In Production | KDLOTSOM | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Knock Down LOT Set Order Management System (KDLOTSOM) manages KD Lot-Set Kit orders for both confirmed and forecast period. KD Kits can be ordered in user defined quantities (Lots) to support KD Kit assembly at a non-CMMS enabled 3rd party destination (Partner). This application enables KD Lot-Set program planning, KD Lot-Set order management and KD Lot-Set order tracking. It interacts with PDO upstream system to get the buildability at WERS level and CMMS downstream by providing KD order details at WERS level to drive supplier material release. Other Key functionalities: 1. Orders are driven based on SPCPS Sales allocations & CMMS OP Plan. 2. Triggers Dealer order creation in GOALS 3. Facilitates Physical VIN generation using PVG & communicates to Partner, MVP, NGAVS, GEVIS. 4. Communicates order details to NGAVS to drive PFS related functionalities at partner end. 5. Receives Vehicle Assembly Order Status from Partner systems & communicates to GEVIS. 6. Order Status Tracking from Forecast to Wholesale. |  |  | YES | 4 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
14920 | Integrity Compliance Education Training | In Production | Integrity | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Silver | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | DDESAI | KADOMKAI | Policy | Staffs IT | This application provides web-based Compliance Education training and certification. It is hosted externally by application service provider (asp) SAI. | 2 |  | YES | 1 | TSWEEN16 | PLM | VM | Q4 2025 | Partial Migration to GCP | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50696 | Knock Down LOT Set Order Management System | In Production | KDLOTSOM | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | 221 | Knock Down LOT Set Order Management System (KDLOTSOM) manages KD Lot-Set Kit orders for both confirmed and forecast period. KD Kits can be ordered in user defined quantities (Lots) to support KD Kit assembly at a non-CMMS enabled 3rd party destination (Partner). This application enables KD Lot-Set program planning, KD Lot-Set order management and KD Lot-Set order tracking. It interacts with PDO upstream system to get the buildability at WERS level and CMMS downstream by providing KD order details at WERS level to drive supplier material release. Other Key functionalities: 1. Orders are driven based on SPCPS Sales allocations & CMMS OP Plan. 2. Triggers Dealer order creation in GOALS 3. Facilitates Physical VIN generation using PVG & communicates to Partner, MVP, NGAVS, GEVIS. 4. Communicates order details to NGAVS to drive PFS related functionalities at partner end. 5. Receives Vehicle Assembly Order Status from Partner systems & communicates to GEVIS. 6. Order Status Tracking from Forecast to Wholesale. |  |  | YES | 4 | BWUNNAVA | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
51282 | Key Cabinet | In Production | Traka | EPEO | SKULKA52 | SYUKI2 | MDIERING | ESTILESK | Copper | Non S-Ox | 111 | No | Yes | COTS | CMIRABIT | SYUKI2 | Enterprise Technology | EPEO | Manage access to keys at EDC1/EDC2/BLDG6 with Traka Key Management System S series cabinet with attached HMI screen, using Traka Web interface to administer access policies. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
52238 | Integrated Launch Management Platform | In Production | ILMGPDSNMP | ISIT | JDEGUZMA | RMEHTA3 | RNARAY23 | ISIDDIQ6 | Silver | Non S-Ox | 332 | No | Yes | COTS | JDEGUZMA | RMEHTA3 | Advanced PD and Tech | Industrial System IT | Integrated Launch Management Platform - GPDS-NMP program Launch Fitness Dashboard | 4 |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13742 | Incentive Single Input System Support | In Production | ISIS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Web based tool to compliment & improve the time required to enter the program rules in to SMART VINCENT. The complimentary application to render the dealer summary grids and supply incentives to downstream systems is covered by ITMS applications #20184 - DRIVE and #20703 VIDS. | 6 |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24806 | KBS Mainframe NA | In Production | KBS MF NA | FORD CREDIT | RMINHAS3 | PBALUSU | JMADDEN5 | JMANI | Silver | Non S-Ox | 333 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | NA Mainframe jobs used to send data from Risk Scoring Online into KBS Server. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
12855 | Just-in-time Execution and Delivery Initiative | In Production | JEDI | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Silver | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | The JEDI application is a decision support tool used by Stamping plants to efficiently schedule the parts being produced at the plant. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | SQL | Priya | 2025-03-05 |  |  | Solution will continue to use SQL until absorbed into another application. Database VM will be migrated to OSV AS-IS. No changes will be made to the application. Timeline depends on OSV availability | No | SQL
24042 | ICI Campaign Manager | In Production | ICI CM | M&S TECH | NKANDULA | TBRYANS1 | PRAO2 | RFERMAN1 | Gold | Non S-Ox | 211 | No | Yes | COTS | SBAILE17 | TBRYANS1 | Communications | Marketing, Sales and Service | Adobe Campaign Tool solution to support the execution of marketing campaigns. | 43 |  | YES | 2 | NKANDULA | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
18 | Job Security Program | In Production | JSP | OCETO | TSWEEN16 | SCHILAKA | WPETER58 | MBALAN2 | Silver | Non S-Ox | 311 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | UAW Jobs Security program that tracks employment levels. Renamed from Guaranteed Employment Number (GEN). | 22 |  | YES | 2 | TSWEEN16 | PLM | WebFocus | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
18 | Job Security Program | In Production | JSP | OCETO | TSWEEN16 | SCHILAKA | WPETER58 | MBALAN2 | Silver | Non S-Ox | 311 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | UAW Jobs Security program that tracks employment levels. Renamed from Guaranteed Employment Number (GEN). | 22 |  | YES | 2 | TSWEEN16 | PLM | WebFocus - MF | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
23489 | JIRA | In Production | JIRA | EVDD | AGARBY | NWEBST14 | NWHITEH8 | SGURU8 | Bronze | Non S-Ox | 321 | Yes | No | Managed by 3rd Party Purchased Service | AGARBY | NWEBST14 | Advanced PD and Tech | - | JIRA is a defect tracking tool used as part of an agile s/w development environment within the R&A EESE organization. |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
20750 | Hyperion-Financial Management | In Production | HFM | I-ERP | SFRANCI8 | DSHAH1 | NVARANAS | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | COTS | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Hyperion Financial Management system for consolidate reporting of North America, Ford Credit, and Ford Credit Europe. | 41 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
56066 | JFrog Enterprise Plus | In Production | JFA | EA | RRISS | SHE1 | PSHAH | SGURU8 | Gold | Non S-Ox | 233 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | - | A software suite and repository through which Ford (1) manages and releases Model e control software binaries, application packages and installers, container images, libraries, and configuration files, and (2) reviews build process analytics and insights. |  |  | YES | 2 | GBRAIL | PLM | SQL | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | SQL
52782 | HR Integrated Archival & Advanced Analytics Platfo | In Production | IAAAP | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Silver | Non S-Ox | 322 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | Ford Human Resources has migrated its several core HR systems to Oracle HCM Cloud platform and some of the existing applications are getting decommissioned. This proposed application shall establish the platform for aggregated archival platform covering 6 sun-setting applications, enabling accessibility with custom reports/queries to people leaders. HR integrated analytics & visualization platform establishment over data marts of set of in-scope applications. This application serves as a centralized platform to retrieve archived data & performing advanced analytics and visualization by HR Global Business teams. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
56485 | HCL NIO | Planned | HCL NIO | EPEO | SKULKA52 | SYUKI2 | MDIERING | GSIENKIE | Copper | Non S-Ox | - | No | Yes | COTS | CMIRABIT | SYUKI2 | Enterprise Technology | - | HCL NetZero Intelligent Operations Solution | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
51794 | Jacobs Test SLATE | In Production | TestSLATE | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | Test SLATE is Jacobs' comprehensive, easy-to-use test control and measurement process management application, ideal for testing virtually any product under a variety of environmental and product conditions. W |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-03-31 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Priya | 2025-03-03 |  |  | Decommission complete, Validation in progress | No | SQL
24316 | HashiCorp Secrets Management System | Active | VAULT | EPEO | NOKEEFE | VNACHIMU | KCARDWEL | KCARDWEL | Silver | Non S-Ox | 0 | No | Yes | - |  |  | Enterprise Technology | EPEO | Secures, stores, and tightly controls access to tokens, passwords, certificates, API keys, and other secrets in NG datacenters and Cloud environments. | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
50835 | IVI-C Watchdog | In Production | IVIC-WD | EVDD | JREYN149 | NFAGEN | MGORDO64 | ECHURCHM | Bronze | Non S-Ox | 111 | Yes | No | - | JREYN149 | NFAGEN | Advanced PD and Tech | - | Metrics, Software Release Reports and Quality Scorecard along with other web based tools used by IVI-C to manage software development |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
840 | GPIRS - Global Prototype Inv Req & Sched Sys | In Production | GPIRS | ISIT | JKOONS | TBROWN99 | JBROSKI | JLUCAS1 | Silver | Non S-Ox | 212 | No | Yes | In-House | JKOONS | TBROWN99 | Manufacturing Staffs | - | GPIRS (Global Prototype Inventory Requisition and Scheduling System)GPIRS is an application that supports the prototype vehicle development process globally, and Powertrain development process for Europe. Supports prototype vehicle business processes including; Scheduling, Bill of Material, Part Ordering, Part Warehousing. and Shipping. | 4 |  | YES | 4 | BWUNNAVA | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
11760 | GOaLS - Global Ordering and Logistics System | In Production | GOaLS | M&S TECH | FHIRSH | NGIRISH | NMATTA2 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | GOaLS is the system used by Export & Growth dealers, APA dealers and affiliates to order multiple sourced vehicles, review status, order guides and report sales. CIA 2,2,2 | 3 |  | YES | 7 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50063 | IT4IT Development Tools | Active | FCIT4IT | FORD CREDIT | JBRADB21 | JBRADB21 | DSINACOL | RMANGAL | Bronze | Non S-Ox | - | No | - | - | SRAISIN1 | JBRADB21 | Ford Credit Services | - | Suite of Ford Credit application development tools supporting application and product teams. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50063 | IT4IT Development Tools | Active | FCIT4IT | FORD CREDIT | JBRADB21 | JBRADB21 | DSINACOL | RMANGAL | Bronze | Non S-Ox | - | No | Yes | - | SRAISIN1 | JBRADB21 | #N/A | - | #N/A |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
21472 | IT Spending Agreement | In Production | ITSA | OCETO | TVASU | SANANTH | PMCAULIF | WJUSTICE | Copper | Non S-Ox | 211 | No | Yes | In-House | TVASU | SANANTH | Enterprise Technology | Technology & Enterprise Services (TES) | The IT Spending Agreement workflow application is used by teams that need to establish financial commitments and support billing of IT services. The ITSA tool is used to obtain electronic approvals for the commitments. | 6 |  | YES | 3 | TSWEEN16 | PLM | WebFocus | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | [8 empty] | QlikSense | [5 empty] | No | DA
21472 | IT Spending Agreement | In Production | ITSA | OCETO | TVASU | SANANTH | PMCAULIF | WJUSTICE | Copper | Non S-Ox | 211 | No | Yes | In-House | TVASU | SANANTH | Enterprise Technology | Technology & Enterprise Services (TES) | The IT Spending Agreement workflow application is used by teams that need to establish financial commitments and support billing of IT services. The ITSA tool is used to obtain electronic approvals for the commitments. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q3 2027 | Modernize to Cloud Databases | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | SQL
12103 | Global Warranty Measurement System | In Production | GWMS | FORD PRO & FCSD TECH | KELY8 | MMORSE3 | JSOPFE | ADEVEND1 | Copper | Non S-Ox | 211 | Yes | No | In-House | KELY8 | MMORSE3 | Ford Customer Service | - | This application provides dealers with access to their warranty trends reporting information. This allows dealers to better manage their warranty performance. Dealer can select a report called 126EZ and GWMSEZ to view their data and allow them to view trends in their warranty data over a period of time. Customer is managing the web site provider (IBI) | 8 |  | YES | 2 | RKENNEL | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | 25% | 25% | [6 empty] | GCP Migration | [5 empty] | No | VM
24566 | IT Data Hub | In Production | ITDH | OCETO | TVASU | KBALAS13 | JEKAMBA3 | WJUSTICE | Copper | Non S-Ox | 311 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | 311 | A single data repository for various IT4IT applications used to create dashboards, downstreams feeds and APIs to support data driven decision making for business of IT |  | Springboot | YES | 3 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
24566 | IT Data Hub | In Production | ITDH | OCETO | TVASU | KBALAS13 | JEKAMBA3 | WJUSTICE | Copper | Non S-Ox | 311 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | A single data repository for various IT4IT applications used to create dashboards, downstreams feeds and APIs to support data driven decision making for business of IT |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | BigQuerry |  |  |  |  | GCP Migration is completed for Database | No | SQL
24402 | Global Quick Lane Website | In Production | GQLWeb | M&S TECH | RKLEINSM | BMUNIE | DCHITRA1 | JPOTTE60 | Gold | Non S-Ox | 222 | No | Yes | In-House | RKLEINSM | BMUNIE | Marketing & Sales | FCSD Tech | Provides a consumer web presence that will help visitors easily find a Quick Lane store in their area, using multiple devices such as desktops, laptops, touch laptops, tablet devise, and mobile smart phones. This will provide relevant content and feature offers to assist in driving business to Quick Lane stores. The consumer web site will work to separate the Quick Lane stores from localized mom and pop shops competition and national competition to strengthen the Quick Lane brand. This will replace ACR 2013-679 that will be Decommissioned. | 39 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
51784 | Issuetrak - APTL | In Production | IAPTL | ISIT | KCHRIST2 | KCHRIST2 | JCICOTTE | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | Issuetrak COTS solution for test issue managment |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
18516 | Global Personal Identifier/GPID | In Production | GPID | EPEO | NOKEEFE | MSNYDER5 | DDALKOVS | GSIENKIE | Silver | Non S-Ox | 122 | Yes | No | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | A process (developed by BP)with an underlying web based infrastructure used to identify people uniquely, acurately and practically within Ford Motor Company without the use of personal (risky) information | 11 |  | YES | 3 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
22077 | iqs Gauge Calibration Management | In Production | iqs GCM | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | SKING68 | DCLEME13 | Quality | Industrial System IT | iqs-GCM (Gauge Calibration Management), is the Globally approved software module that is used to schedule and manage gauge certifications. The iqs-GCM solution provides quality management personnel with valid, actionable process data, and reporting. Without reliable device management protocols, manufacturers may increase the risk of unknowingly producing nonconforming items, which can delay time-to-market objectives. In the worst-case scenario, invalid process data resulting from inaccurate equipment gages can lead to defective products reaching the open market. A commercial description can be found at: http://www.iqs.de/en-Inspection-equipment-Management.html |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
24393 | Global Owner | In Production | OWNER | M&S TECH | RKLEINSM | BMUNIE | JWANG28 | JPOTTE60 | Silver | Non S-Ox | 222 | No | Yes | In-House |  |  | Enterprise Technology | Marketing, Sales and Service | B2C Global Owner products and platform serving customers on web channel. | 5 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
22004 | iProof | In Production | IIT | I-ERP | SFRANCI8 | RJAYAKU2 | RSRIRA18 | LWU14 | Silver | S-Ox In Scope | 331 | No | Yes | COTS | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Workflow solution to validate scanned supplier paper invoices and monitor invoice payment process status |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
23340 | Global MFG Online Database (GMOD) | In Production | VOME_PROG | ISIT | OTHERS | BBELL2 | RNICKLA2 | AELANGO | Copper | Non S-Ox | 311 | Yes | No | COTS | ASTEVE43 | JSMIT754 | Manufacturing Engineering | - | Central database and related reporting engine for global Vehicle Operations Manufacturing Engineering vehicle program launch activities | 6 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
20509 | Investor Reporting and Accounting | In Production | GSIRA | FORD CREDIT | DTAURO | SKHAN29 | HMANDA | VPOTTIBO | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Investor reporting and accounting (IRA) is an application to manage retail, lease, and wholesale securitization deals, produce investor reporting and accounting, and manage Cash Wires of the deals. It is an application developed in-house and supported by Ford Credit IT. | 403 |  | YES | 3 | SRAISIN1 | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned | [10 empty] | Webfocus 9 | [6 empty] | DA
20509 | Investor Reporting and Accounting | In Production | GSIRA | FORD CREDIT | DTAURO | SKHAN29 | HMANDA | VPOTTIBO | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Investor reporting and accounting (IRA) is an application to manage retail, lease, and wholesale securitization deals, produce investor reporting and accounting, and manage Cash Wires of the deals. It is an application developed in-house and supported by Ford Credit IT. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50437 | GLOBAL IMAGE VIEWER - DOCUMENT MANAGEMENT SERVICES | In Production | GIV-DMS | FORD CREDIT | DTAURO | JJACK348 | NBHALWAN | ROBRIEN3 | Silver | Non S-Ox | 332 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | DMS consists of Micro services to retrieve or upload customer related documents. Global Image Viewer(GIV) is part of DMS. GIV allows Ford Credit employees to view or manage customer documents. | 5 |  | YES | 4 | SRAISIN1 | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
20509 | Investor Reporting and Accounting | In Production | GSIRA | FORD CREDIT | DTAURO | SKHAN29 | HMANDA | VPOTTIBO | Silver | S-Ox In Scope | 232 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Investor reporting and accounting (IRA) is an application to manage retail, lease, and wholesale securitization deals, produce investor reporting and accounting, and manage Cash Wires of the deals. It is an application developed in-house and supported by Ford Credit IT. |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | Q3 2027 | Version Upgrade | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
13786 | In-Use Verification Program | In Production | IUVP | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 111 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | New EPA regulation for In-Use vehicle testing, requires additional vehicle data and automated data transfer from test facilities to central datbase. Mandatory to ensure Corp compliance with EPA. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 25% | [7 empty] | Cloud Run | Priya | 2025-03-06 |  |  |  | No | Java < v21
13786 | In-Use Verification Program | In Production | IUVP | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 111 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | New EPA regulation for In-Use vehicle testing, requires additional vehicle data and automated data transfer from test facilities to central datbase. Mandatory to ensure Corp compliance with EPA. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 25% | [7 empty] | Cloud Run | Priya | 2025-03-06 |  |  |  | No | Java < v21
13786 | In-Use Verification Program | In Production | IUVP | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 111 | No | Yes | In-House | DKAVITHA | DKAVITHA | Policy | Industrial System IT | New EPA regulation for In-Use vehicle testing, requires additional vehicle data and automated data transfer from test facilities to central datbase. Mandatory to ensure Corp compliance with EPA. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 25% | [7 empty] | Cloud SQL PostgreSQL | Priya | 2025-03-06 |  |  |  | No | Oracle
50713 | Intune | In Production | Intune | EPEO | SRUNSON | ASTONE31 | MEDWA173 | AWROBEL2 | Gold | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | ASTONE31 | Enterprise Technology | EPEO | Microsoft Intune is an application used to manage mobile devices as well as deploy mobile apps to managed and unmanaged devices. Intune is part of Microsoft Azure, which is a public cloud-computing platform, developed, maintained, hosted, and managed by Microsoft Corporation. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
21223 | Global Illustrated Launch Timing | In Production | GILT | ISIT | OTHERS | CRISTIC | CSELF | ISIDDIQ6 | Silver | Non S-Ox | 322 | Yes | No | In-House | JLANE15 | CRISTIC | New Model Programs | - | Manage Timing, Status, Metrics and critical issues for vehicle/powertrain launches globally. In addition, manages the launch 'Read-Across' to inform in-flight launch teams of potential issues with critical timing. | 5 |  | YES | 4 | BWUNNAVA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20062 | Global Brand Protection System | In Production | GBPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Copper | Non S-Ox | 111 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | This application will track brand protection exemption requests and approvals. | 4 |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21596 | Interim Volume Mix and Rates | In Production | IVMR | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 311 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | This is an interim contirbution margin and Volume Mix Rate application. | 90 |  | YES | 3 | TSWEEN16 | PLM | Datastage | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | DA
21596 | Interim Volume Mix and Rates | In Production | IVMR | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 311 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | This is an interim contirbution margin and Volume Mix Rate application. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
53867 | Gigamon Fabric Manager | Planned | GFM | EPEO | MCRNKOVI | BKARMAKA | HPATEL48 | HDIRANI | Copper | Non S-Ox | - | Yes | No | COTS | MCRNKOVI | MCRNKOVI | Enterprise Technology | EPEO | Centralized management for Gigamon devices | 3 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
11480 | Inter-Company Settlements (ICS) | In Production | ICS | I-ERP | SFRANCI8 | AKANSKI | TPRASAD1 | LWU14 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Inter-Company Settlements processes global production shipment information between manufacturing plants and prepares postings to the general ledger and accounts receivable systems. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
51806 | Interactive Platform for Data Analytics | In Development | IPDA | ISIT | JKOONS | MNOVAK1 | HBOYSEN | GRAO3 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JPITTERL | CBOHN | Advanced PD and Tech | Industrial System IT | A platform to merge Ford internal CAE and physical crash test data in a single database. The database also includes external, publicly available test crash data (i.e. NHTSA, IIHS). The system applies data analytics methods on the different data sources to identify success factors. An interactive frontend platform allows data analysis and supports virtual/physical data correlation. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
9827 | GDS: Global Distribution System | In Production | GDS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | GDS accepts aftermarket service parts orders for NA sourced vehicles from FORD dealerships located outside North America, Ford Affilate locations (eg. FORD of Venezuela, FORD of Australia, etc.) and from association partners MAZDA and NISSAN. Additional Outage Impacts include: Customer Complaint and Impact to Productivity. | 7 |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53129 | Intel EndPoint Management Assistant | Planned | EMA | EPEO | SRUNSON | ASTONE31 | JJAFANO | JJAFANO | Gold | Non S-Ox | - | Yes | No | - | SRUNSON | ASTONE31 | Enterprise Technology | - | Application and server needed to manage remote control of Ford owned PC's and Laptops |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
12967 | GDS Online | In Production | GDSONL | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House |  |  | Ford Customer Service | FCSD Tech | Provides online access for GDS business partners. GDS accepts aftermarket service parts orders for NA sourced vehicles from FORD dealerships located outside North America, Ford Affilate locations (eg. FORD of Venezuela, FORD of Australia, etc.) and from association partners MAZDA and NISSAN. Additional Outage Impacts include: Customer Complaint and Impact to Productivity. | 4 |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23288 | GDIA - Alteryx | Active | Alteryx | EPEO | SKULKA52 | MWILLI20 | TCULLER | GARUNAC1 | Silver | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Alteryx Analytics provides analysts with an intuitive workflow for data blending and advanced analytics, including data extractions, cleansing to blending, and data enrichment. It allows users to create a workflow by dragging in various data sources, and then packages the design into re-usable workflows which can be shared on the Alteryx Gallery and can be used to generate reports, pivot tables, and other visual representations. Alteryx is a data wrangling tool. Data wrangling is loosely the process of manually converting or mapping data from one raw form into another format that allows for more convenient consumption of the data. Alteryx can either receive data from a secondary data gathering tool or connect directly to external and internal data sources to acquire the raw data. Alteryx consists of both a client side and server side. The client can be run as a standalone environment. | 66 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
22779 | Gas Metrology System | In Production | GMS | ISIT | KCHRIST2 | KCHRIST2 | JCICOTTE | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | APTL's Gas Standards Lab (GSL)supplies emission gas standards traceable to NIST for use throughout the facility. Compressed gas cylinders are purchased from outside sources at specified nominal concentrations and are tested to establish their exact concentrations. This gas cylinder naming procedure is accomplished by comparing the unknown gas concentration to working standards for the purpose of establishing the exact concentrations. The existing system includes analyzers, Oracle database and Forms front end. It is obsolete and is being updated to make improved use of the newer mexa that has been put into the mix. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | Partial Migration to GCP | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20419 | INTEGRATED SOURCING MANUFACTURING & DESIGN | In Production | ISMD | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Production Implementation of Big Bang Project from Research & Advanced Engineering. Define, develop, and implement upfront design tools that integrate product attribute, sourcing, and manufacturing considerations to achieve weight & cost savings. Modules Include: GMUD, MATREC, TECHSELECT, DAWN & CET-FTI Batch Process Integrator |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
20419 | INTEGRATED SOURCING MANUFACTURING & DESIGN | In Production | ISMD | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Production Implementation of Big Bang Project from Research & Advanced Engineering. Define, develop, and implement upfront design tools that integrate product attribute, sourcing, and manufacturing considerations to achieve weight & cost savings. Modules Include: GMUD, MATREC, TECHSELECT, DAWN & CET-FTI Batch Process Integrator |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
16746 | Fuel House Fuel Monitoring System | In Production | FHFMS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | The Fuel House Fuel Monitoring system tracks fuel levels for inventory management and tank leakage analysis which is an EPA requirement. It also tracks the types of fuels used by each test cell to facilitate EPA mandated fuel consumption reporting, relative to Building emissions. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20419 | INTEGRATED SOURCING MANUFACTURING & DESIGN | In Production | ISMD | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Production Implementation of Big Bang Project from Research & Advanced Engineering. Define, develop, and implement upfront design tools that integrate product attribute, sourcing, and manufacturing considerations to achieve weight & cost savings. Modules Include: GMUD, MATREC, TECHSELECT, DAWN & CET-FTI Batch Process Integrator |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
22721 | Integrated Management & Profit Reporting System | In Production | IMPRS | I-ERP | SFRANCI8 | AKANSKI | CDERUITE | LWU14 | Silver | S-Ox In Scope | 331 | No | Yes | COTS | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | This is a corporate system which consolidates and produces internal as well as external-facing views of corporate financials. Specifically, it address the business plan (5 year plan), next year calendarized budget, and present year actuals, forecast, and variance analysis. | 521 |  | YES | 3 | TSWEEN16 | PLM | Datastage | Q3 2026 | Migrate to CP4D | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | DA
22721 | Integrated Management & Profit Reporting System | In Production | IMPRS | I-ERP | SFRANCI8 | AKANSKI | CDERUITE | LWU14 | Silver | S-Ox In Scope | 331 | No | Yes | COTS | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | This is a corporate system which consolidates and produces internal as well as external-facing views of corporate financials. Specifically, it address the business plan (5 year plan), next year calendarized budget, and present year actuals, forecast, and variance analysis. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q1 2027 | On-Prem | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [14 empty] | No | SQL
19268 | Ford SIV (WebImmat) | In Production | Ford SIV | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 312 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Registration system for Ford of France enabling the registration of new and used vehicles and the French plate conversion to SIV plates. | 5 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22721 | Integrated Management & Profit Reporting System | In Production | IMPRS | I-ERP | SFRANCI8 | AKANSKI | CDERUITE | LWU14 | Silver | S-Ox In Scope | 331 | No | Yes | COTS |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | This is a corporate system which consolidates and produces internal as well as external-facing views of corporate financials. Specifically, it address the business plan (5 year plan), next year calendarized budget, and present year actuals, forecast, and variance analysis. |  | Springboot | YES | 4 | TSWEEN16 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
52238 | Integrated Launch Management Platform | In Production | ILMGPDSNMP | ISIT | JDEGUZMA | RMEHTA3 | RNARAY23 | ISIDDIQ6 | Silver | Non S-Ox | 332 | No | Yes | COTS | JDEGUZMA | RMEHTA3 | Advanced PD and Tech | Industrial System IT | Integrated Launch Management Platform - GPDS-NMP program Launch Fitness Dashboard |  |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
50195 | FORD PRO: DEALER KEY CODE | In Production | DKC | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Bronze | Non S-Ox | 221 | No | Yes | In-House | RSING163 | RKENNEL | Marketing & Sales | Ford Pro | This online system allows dealers to obtain key code for vehicles that they have in stock or have sold. | 10 |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q4 2025 | Partial Migration to GCP | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | 25% | [7 empty] | GCP Migration |  |  |  |  | They are already in GCP CaaS | No | VM
52780 | Integrated Fleet Management | Planned | - | FORD PRO & FCSD TECH | RKENNEL | TUNDER17 | SINJETI | RANKAM1 | - | Non S-Ox | 211 | No | - | - | #N/A | #N/A | Integrated Services | 211 | IFM PORTFOLIO |  | Springboot | YES | 1 | RKENNEL | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission | 2025-01-31 | 2024-12-20 | 2024-12-20 | Complete |  | 2025-12-30 | 2025-01-31 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | No VMs found. EAMS is already marked Decomissioned. | No | Java < v21
23481 | Integral Translation System(ITS) | In Production | ITS | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Application to support Interaction & Ergonomics department for the translation specification management |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
18492 | Ford Oracle Security Administration | In Production | FOSA II | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Bronze | Non S-Ox | 331 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Tool to handle User Administration and password maintenance for Oracle databases | 3 |  | YES | 3 | SWALIMBE | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
23481 | Integral Translation System(ITS) | In Production | ITS | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | Application to support Interaction & Ergonomics department for the translation specification management |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
52817 | InnovMetric Dataloop in PD | In Production | IDiPD | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Bronze | Non S-Ox | 311 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | InnovMetric DataLoop is a scalable data management solution that allows you to optimally handle the vast amount of data produced by your 3D measurement activities by storing your inspection projects, their revisions, and 3D measurement data in a centralized database |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2027 | On-Prem | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | SQL
50687 | Ford Credit Receivable Account Information Service | In Production | FCRAIS | FORD CREDIT | NJOSHI21 | HBRUMLEV | XZHOU110 | ROBRIEN3 | Gold | Non S-Ox | 232 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | Suite of micro services that access Ford Credit receivable account data | 4 |  | YES | 4 | SRAISIN1 | PLM | VM | Q4 2025 | Partial Migration to GCP | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
18424 | Initial Stock Order | In Production | ISO | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | ISO provides data to Ford in support of Dealer Initial Stock Orders. | 2 |  | YES | 2 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
18424 | Initial Stock Order | In Production | ISO | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | ISO provides data to Ford in support of Dealer Initial Stock Orders. |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
19664 | Information Server | Active | ETL-InfSvr | EPEO | SKULKA52 | MWILLI20 | MSIVAANA | RMODI2 | Silver | S-Ox In Scope | - | No | - | - | CMIRABIT | CMIRABIT | Information Technology | ITO | Shared Extract-Transform-Load (ETL) infrastructure environment based on IBM's Information Server suite (aka DataStage/QualityStage) to support multiple discrete applications. This is a PLACEHOLDER EAMS entry, per the 'IT Application Portfolio Management' guidelines. Customers of this service are required to raise their own EAMS entries, complete GRC App Assessments, etc. as required. This is not an 'Application'. This EAMS record is required to manage server ownership, and other contact information needed by Server Hosting. |  |  | YES | 2 | SWALIMBE | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
24857 | Ford Credit Customer Information Services | In Production | FCCIS | FORD CREDIT | NJOSHI21 | HBRUMLEV | VCECCARE | ROBRIEN3 | Gold | Non S-Ox | 232 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | Suite of micro services that manages Ford Credit customer data including Customer Communication Permissions, Customer Activity Service, and Customer Information Management Customer Communication Permissions CRUD for Ford Credit customer's permissions (e.g. Opt In / Opt Out) by communication channel (e.g. email, text, etc). Customer Activity Service CR for customer account activities (feeds Pinnacle contacts) Customer Information Management Service retrieves receivable customer data | 7 |  | YES | 3 | SRAISIN1 | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
15921 | Information Resource Center-IRC | In Production | IRC | FORD CREDIT | RMINHAS3 | SSINGH14 | SASIF | VBHUPATH | Copper | Non S-Ox | 211 | No | Yes | In-House | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit Information Resource Center is a FOCUS repository intended for end-user ad-hoc reporting of mainframe application files. Initial intention was for the LA data. | 2 |  | YES | 2 | SRAISIN1 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned | [17 empty] | DA
15921 | Information Resource Center-IRC | In Production | IRC | FORD CREDIT | RMINHAS3 | SSINGH14 | SASIF | VBHUPATH | Copper | Non S-Ox | 211 | No | Yes | In-House | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit Information Resource Center is a FOCUS repository intended for end-user ad-hoc reporting of mainframe application files. Initial intention was for the LA data. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
16478 | Ford Component Sales - Baan IVC4 ERP Application | In Production | FCS BAAN | FORD PRO & FCSD TECH | RKENNEL | RANGEL | RANGEL | MMEHTA5 | Bronze | S-Ox In Scope | 231 | Yes | No | COTS | TCANNIS | CBILLS1 | Ford Customer Service | - | Ford Component Sales is a wholy owned subsidiary of Ford Motor Co. and organizationally reports to the FCSD NA Operations activity. It provides specialized aftermarket products to other aftermarket suppliers. BAAN is a third party ERP package that is used by Ford Component Sales to run most of their business operations, except for HR functions. It handles the item/part master, customer orders, procurement from suppliers (including some EDI), and financials (billing and payables). It is supported by FCS' internal IT staff, managed by Renee Angel. Their HQ is at FPN in Dearborn, MI. Hosted internally: hpn-1.fcssales.ford.com | 3 |  | YES | 1 | RKENNEL | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
53147 | Informatica PCDQ - Shared | Active | Infa-PCDQ | EPEO | SKULKA52 | MWILLI20 | MMAES | RPOLLO13 | Gold | S-Ox In Scope | - | No | - | - | CMIRABIT | CMIRABIT | Information Technology | Ford Credit (FMCC) | This is a PLACEHOLDER EAMS entry, per the 'IT Application Portfolio Management' guidelines. Customers of this service are required to raise their own EAMS entries, complete GRC App Assessments, etc. as required. ITO Shared environment featuring Informatica's Power Center and Data Quality product suites. |  |  | YES | 2 | SWALIMBE | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
51581 | Ford Application for eLectronic CONtracting | In Production | FALCON | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Silver | Non S-Ox | 211 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Middleware application that provides electronic signature services | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
51212 | Informatica MDM FMCC | In Production | FMCC MDM | FORD CREDIT | IPANKAJ | PSRIKIR1 | RMRINAL2 | NKALE | Gold | Non S-Ox | 322 | No | Yes | - | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | The application uses customer, dealer and organisational data from the FMCC / FCE GDW which is automatically matched and combined using industry standard tools supplied by Informatica to create a set of Counterparties. Information about the Counterparties is uploaded back into the GDW, where it is then used for regulatory reporting. |  |  | YES | 1 | SRAISIN1 | PLM | Oracle | Q3 2027 | On-Prem | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Oracle
51300 | INFORMATICA MDM | Active | Infa-MDM | EPEO | SKULKA52 | MWILLI20 | MMAES | RPOLLO13 | Gold | S-Ox In Scope | - | No | - | - | CMIRABIT | CMIRABIT | Information Technology | ITO | This is a PLACEHOLDER EAMS entry, per the 'IT Application Portfolio Management' guidelines. Customers of this service are required to raise their own EAMS entries, complete GRC App Assessments, etc. as required. ITO Shared environment featuring Informatica's MDM product suite. |  |  | YES | 4 | SWALIMBE | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
51300 | INFORMATICA MDM | Active | Infa-MDM | EPEO | SKULKA52 | MWILLI20 | MMAES | RPOLLO13 | Gold | S-Ox In Scope | - | No | Yes | - | CMIRABIT | MWILLI20 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 4 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
12372 | FoM Payments to Suppliers | In Production | FoM PtS | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | - | This system receives information from CCAPS system. With this information, checks are generated and printed. Text files are generated in order to send them to the bank. Receives CCAPS files to separate it in three different ways of payment like: EFT DAP Printed Checks | 11 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51300 | INFORMATICA MDM | Active | Infa-MDM | EPEO | SKULKA52 | MWILLI20 | MMAES | RPOLLO13 | Gold | S-Ox In Scope | - | No | Yes | - | CMIRABIT | MWILLI20 | #N/A | ITO | #N/A |  |  | YES | 4 | SWALIMBE | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50039 | Informatica for GCCT | Active | GCCTInfo | M&S TECH | RAHMED33 | DPOOVATH | DJAIN6 | MSCHOLT3 | Gold | Non S-Ox | - | No | Yes | - | APALAZZO | jbenedic | CUSTOMER EXPERIENCE | Marketing, Sales and Service |  |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
12364 | FoM Mexican Vehicle Information System | In Production | MEVIS | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | - | Mexican Vehicles Information System. This application contains vehicle tracking and invoicing data. The application receives vehicle data from NAVIS and Invoicing data from the US Vehicle Invoicing Application and produces the local dealer invoices. | 8 |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12369 | FoM Dealer Current Accounts | In Production | FoM DCC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This application generates dealer statements based on accounting transactions received from Vehicles and Parts & Accesories Invoicing, Debits and Credits Memos by Incentives, Warranties, miscellaneous Invoices, P&A Material returns (PA20), P&A Material not received (PA293), bank deposits and Ford Credit payments, also receive information from Corporate Systems in a file to extract and add manual transactions and miscellaneous invoices generated during the month for each dealer, which should be matched with the transactions and balances of General Ledger records. This System is a batch Application. | 4 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53724 | iNexus | In Production | iNexus | I-ERP | SARAUJO3 | VANURAD2 | PCHITIYA | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Change Management Tracking system to integrate Ariba and S4 |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 75% | 50% | 50% | 100% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-06 |  |  |  | No | SQL
19741 | FoM Company Cars | In Production | MX09FNCC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | - | Application to support the Company Vehicles as Pools, Vehicles assigned to Manage Level Personnel, Demo units and Enginering vehicles. This application is used to manage Company Vehicle inventory, LL6+ vehicle selection, Finance conciliation process vs. physical invetory and the tracking of these vehicles since the order proces until the delivery. | 4 |  | YES | 5 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | 100% | 50% | 50% | [5 empty] | GCP Migration | [5 empty] | No | VM
53724 | iNexus | In Production | iNexus | I-ERP | SARAUJO3 | VANURAD2 | PCHITIYA | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Change Management Tracking system to integrate Ariba and S4 |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
13141 | Industrial Materials-GIMME | In Production | IMR-GIMME | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 221 | No | Yes | In-House | SKING68 | KRAMESH | Manufacturing Staffs | - | GIMME Industrial Materials Reporting on mainframe for NA. | 24 |  | YES | 1 | BWUNNAVA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
598 | Industrial Materials Reporting - GPAE | In Production | IMR-GPAE | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 221 | No | Yes | In-House | SKING68 | SKING68 | Manufacturing Staffs | - | Inventory Management (Reporting)--Provides analytical environment for the integration of world wide manuf. plants and their suppliers access to information required by plant self-directed work teams in support of FPS-Ford Production Systems. Commodity Mgmt Suppliers(CMS) will have access to processes which they are responsible for. It is a web based tool that provides metrics to gauge success of engineering efforts, and operational reports which are used by the plants and suppliers to help manage inventory. |  |  | YES | 1 | BWUNNAVA | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
23242 | India Tax Register Solution | In Production | ITRS | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Silver | S-Ox Out of Scope | 221 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | ITRS system has an invoicing solution which would be used to generate and print miscellaneous and service invoices for various shipment types. ITRS will provide an option to maintain price for Service Billings, Other Parts. The ITRS system will have the master data for the TAX rates based on the HSN/SAC. On successful generation of invoice, ITRS will post the invoice details to PSGL/ AR system It would also act as Sales and Purchase register for India Market and would be used as base to file the GST tax returns |  |  | YES | 3 | TSWEEN16 | PLM | Java Struts | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
23242 | India Tax Register Solution | In Production | ITRS | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Silver | S-Ox Out of Scope | 221 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | ITRS system has an invoicing solution which would be used to generate and print miscellaneous and service invoices for various shipment types. ITRS will provide an option to maintain price for Service Billings, Other Parts. The ITRS system will have the master data for the TAX rates based on the HSN/SAC. On successful generation of invoice, ITRS will post the invoice details to PSGL/ AR system It would also act as Sales and Purchase register for India Market and would be used as base to file the GST tax returns |  |  | YES | 3 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
14924 | FoM 3040s System | In Production | MX 3040s | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Copper | Non S-Ox | 112 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This System is used to automate 3040s process which moves vehicles from different accounts within ford such as: marketing, preproduction, public affairs, etc. | 4 |  | YES | 2 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24505 | Independent Over The Air | In Production | IOTA | EVDD | JWASNIC1 | CRAJA1 | PDHANAPA | CSUBHA1 | Silver | Non S-Ox | 122 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 122 | INDEPENDENT OVER-THE-AIR CATERS TO PROVISIONING OF THE FIRMWARE / SOFTWARE UPGRADES TO ELECTRONIC CONTROL UNITS (ECU) BY LEVERAGING USB, WI-FI, AND CELLULAR CONNECTIVITY CHANNELS USING CLOUD INFRASTRUCTURE, DATA AND PLATFORM SERVICES |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
13742 | Incentive Single Input System Support | In Production | ISIS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Web based tool to compliment & improve the time required to enter the program rules in to SMART VINCENT. The complimentary application to render the dealer summary grids and supply incentives to downstream systems is covered by ITMS applications #20184 - DRIVE and #20703 VIDS. |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13742 | Incentive Single Input System Support | In Production | ISIS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Web based tool to compliment & improve the time required to enter the program rules in to SMART VINCENT. The complimentary application to render the dealer summary grids and supply incentives to downstream systems is covered by ITMS applications #20184 - DRIVE and #20703 VIDS. |  |  | YES | 5 | NKANDULA | PLM | Mainframe | Q4 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
13742 | Incentive Single Input System Support | In Production | ISIS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Web based tool to compliment & improve the time required to enter the program rules in to SMART VINCENT. The complimentary application to render the dealer summary grids and supply incentives to downstream systems is covered by ITMS applications #20184 - DRIVE and #20703 VIDS. |  |  | YES | 5 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
51704 | FLUID FILL GATEWAY | In Production | FLUIDGW | ISIT | JPITTERL | CBOHN | OGRIES | AELANGO | Silver | Non S-Ox | 113 | No | Yes | COTS |  |  | Manufacturing Plants | Industrial System IT | Because of network security policies, no direct communication from eCATS portable tester (W-LAN) to Fluid Fill machine (plant network, MPN) allowed. As soon as the ECATS tester passes the Beacons for the fluid fill zones, the eCATS tester will start an Ethernet (TCP-IP) communication (telegram) to a transparent gateway server and gateway server will forward telegram to the fluid fill central PC. Based on the telegram data the eCATS tester will send corresponding CAN data to the ABS module through the OBD connector to control the ABS module during the ABS filling process. | 1 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
13742 | Incentive Single Input System Support | In Production | ISIS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | MPREETH6 | Gold | S-Ox In Scope | 333 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Web based tool to compliment & improve the time required to enter the program rules in to SMART VINCENT. The complimentary application to render the dealer summary grids and supply incentives to downstream systems is covered by ITMS applications #20184 - DRIVE and #20703 VIDS. |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13181 | IN VEHICLE SOFTWARE SYSTEM | In Production | IVS | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 221 | No | Yes | COTS | MNOWICK1 | MNOWICK1 | Advanced PD and Tech | Industrial System IT | In Vehicle Software System combined is a high level customization for implementation of IVS TeamCenter Enterprise Application. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
13181 | IN VEHICLE SOFTWARE SYSTEM | In Production | IVS | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | 221 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | In Vehicle Software System combined is a high level customization for implementation of IVS TeamCenter Enterprise Application. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
18610 | FLEXnet Manager | In Production | FNM | EPEO | SKULKA52 | CPENNEY | DECKART1 | DECKART1 | Copper | Non S-Ox | 211 | No | Yes | COTS | CMIRABIT | CPENNEY | Enterprise Technology | EPEO | FLEXnet License Manager is the industry standard tool used by Ford's Central License System (CLS). This project will upgrade FLEXnet to improve consumption management and reporting capabilities, including support for IBM's LUM (Catia license manager). | 2 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
56158 | IN VEHICLE SOFTWARE NEXT GEN | In Development | IVSNG | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | - | No | Yes | - | MNOWICK1 | MNOWICK1 |  | - | In Vehicle Software System combined is a high level customization for implementation of IVS TeamCenter Application. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
15875 | FIS FORD CUSTOM REPORTS | In Production | FISFCR | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 211 | No | Yes | In-House |  |  | Manufacturing Staffs | Industrial System IT | FIS reports created for Ford VO and PTO operations. | 9 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
56158 | IN VEHICLE SOFTWARE NEXT GEN | In Development | IVSNG | ISIT | MNOWICK1 | PBORGAO1 | VJAKKA | GRAO3 | Silver | Non S-Ox | - | No | Yes | - | MNOWICK1 | PBORGAO1 | Enterprise Technology | - | In Vehicle Software System combined is a high level customization for implementation of IVS TeamCenter Application. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
20753 | FCSD Dashboard | In Production | FCSD DshBd | M&S TECH | KPINNU | KHILLERT | GAJAY | JHARPER2 | Copper | Non S-Ox | 111 | Yes | No | In-House | KPINNU | KHILLERT | Marketing & Sales | - | This application covers the presentation layer for the Global UDB Dashboard Reporting. The reporting layer is being built by Information Builders using Web Focus and is being supported by IB. Hosting is internal at the Ford data center. | 4 |  | YES | 3 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19418 | IMS INTEGRATION APP | In Production | IMS-IA | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | 222 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | IMS Integration App provides web interface to access Ford IMS regions through XML, via https post method. Windows or Non-Windows platform based applications use this interface to connect with IMS region to access their IMS Transaction Program. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
19418 | IMS INTEGRATION APP | In Production | IMS-IA | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | 222 | No | Yes | In-House | TVASU | TVASU | Enterprise Technology | Technology & Enterprise Services (TES) | IMS Integration App provides web interface to access Ford IMS regions through XML, via https post method. Windows or Non-Windows platform based applications use this interface to connect with IMS region to access their IMS Transaction Program. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
22233 | FCO Tooling Leasing System | In Production | FCOTLS | I-ERP | SFRANCI8 | SDHANAL3 | PSATHIS3 | LWU14 | Silver | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | A new application to handle FCO Tooling Leasing business process, it is to develop by FCO Tooling Project (ITMS 21607) | 4 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19418 | IMS INTEGRATION APP | In Production | IMS-IA | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | 222 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | IMS Integration App provides web interface to access Ford IMS regions through XML, via https post method. Windows or Non-Windows platform based applications use this interface to connect with IMS region to access their IMS Transaction Program. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
20370 | IMS - Global | Active | IMS | EPEO | SKULKA52 | CGIACOBB | JKOOPMA3 | JKOOPMA3 | Copper | S-Ox In Scope | - | No | Yes | - |  |  | ENTERPRISE TECHNOLOGY | EPEO | IMS GLOBAL SERVICES AND SUPPORT |  | MF - WAS Liberty | YES | 1 | SWALIMBE | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
56364 | IMG Parts and Logistics Systems | In Production | IPLS | FORD PRO & FCSD TECH | DNANDAN | MAMUDHA | MAMUDHA | MMEHTA5 | Gold | S-Ox Out of Scope | 233 | No | Yes | COTS | RSING163 | DNANDAN | Enterprise Technology | 233 | IPLS is the Integrated Parts management system used for aftermarket service parts management across IMG markets. |  | Springboot | YES | 2 | RKENNEL | PLM | Java < v21 | Q3 2026 | Version Upgrade | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
53113 | FCNA Dealer Advisor Application | In Production | DA | FORD CREDIT | NJOSHI21 | GSHAH3 | SMANE4 | NVARADA2 | Silver | Non S-Ox | 211 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit Dealer Advisor (DA) is a responsive web-based tool that will allow Dealers to self-serve their latest Ford Credit performance data and valuable insights through an interactive dashboard. | 6 |  | YES | 2 | SRAISIN1 | PLM | VM | Q4 2025 | Partial Migration to GCP | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
53679 | IMG OSB -MSV/PUD Mobile App | In Production | IMG OSB | OCETO | DBRIGHEN | NMORALE7 | PDELMOND | NMORALE7 | Gold | Non S-Ox | 311 | No | Yes | Managed by 3rd Party Purchased Service | #N/A | #N/A | Ford Customer Service | 311 | MSV/PUD NATIVE APP WILL BE BUILT FOR FORD MOBILE SERVICE VAN TECHNICIANS AND PICKUP-DROP DRIVERS |  | Springboot | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
253 | IMCS : Inbound Material Carrier System | In Production | EuMP-IMCS | ISIT | JPITTERL | CBOHN | MBONAKDA | SSENTH15 | Bronze | S-Ox In Scope | 231 | No | Yes | In-House | CBOHN | CBOHN | Manufacturing Staffs | Industrial System IT | IMCS is the strategic European Ford System for carrier billing (400 Mill. $ p.A. ) tracking for all inbound material in UK and support generation of load lists (Waybill), freight invoicing, statistics and reporting. Main users of the system are Ford's external logistics partners, Ford Global Logistics and MP&L. SBI inclusion into this European application allows carrier invoices to be fed electronically into the Ford Accounts Payables system. |  |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [13 empty] | Most of the application modules depend on Oracle PL/ SQL procedures. | No | Oracle
17770 | CMMS Open-To-Go Reporting | In Production | CMMS OTG | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 333 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Open To Go (OTG) is a global reporting application for vehicle and manufacturing parts progress that allows Launch Team and Preproduction Analyst to quickly gather metrics on part availability issues so that they can prove-out launch readiness. The OTG reports are the mechanism by which all parts new to a vehicle line/engine/transmission and required for launch are tracked. It indicates the part status relative to Production Part Approval Process (PPAP), sample promise date, part identification, supplier name/GSDB code, engineering release level, part approval status, etc. The report is used to determine launch readiness, provide an early indication of the health of a program and to create status projections into the future. The application is used as the primary tool for a series of on-going OTG meetings held with launch management. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-03-25 | 2024-03-25 | 2024-03-25 | Complete | Green | 2024-11-08 | 2024-11-04 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Priya | 2025-03-06 |  |  |  | No | Java < v21
13396 | Imagine - NBSC LTS | In Production | NBSC LTS | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Bronze | Non S-Ox | 311 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Internet website that allows Ford Financial outside attorney/agency firms to access Ford Financial images such as customer contract. Also allows Ford Financial Bankruptcy attorneys to accept, respond to and bill for bankruptcy case assignments (this NBSC Legal Tracking System (LTS) functionality was added in 2/15/2005) |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
13396 | Imagine - NBSC LTS | In Production | NBSC LTS | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Bronze | Non S-Ox | 311 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Internet website that allows Ford Financial outside attorney/agency firms to access Ford Financial images such as customer contract. Also allows Ford Financial Bankruptcy attorneys to accept, respond to and bill for bankruptcy case assignments (this NBSC Legal Tracking System (LTS) functionality was added in 2/15/2005) |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
23564 | ILCOS | In Production | EuHR-ILCOS | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | - | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | ILCOS is an online company car ordering system for German management lease cars. |  |  | YES | 2 | NKANDULA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | Java < v21
23564 | ILCOS | In Production | EuHR-ILCOS | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | - | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | ILCOS is an online company car ordering system for German management lease cars. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q4 2027 | Modernize to Cloud Databases | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | SQL
54069 | IIoT Quality & Traceability | In Development | IQT | ISIT | SKING68 | KBARTHO1 | BELDRED1 | RPRASA22 | Bronze | Non S-Ox | 121 | No | Yes | - | SKING68 | KBARTHO1 | Manufacturing Engineering | 121 | FORD'S NEW STRATEGY FOR BIRTH HISTORY, TRACEABILITY, DEFECT & REPAIR TRACKING FOR BOTH POWER TRAIN AND ASSEMBLY PLANTS. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
52996 | IIoT Monitoring | In Production | IOTM | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Manufacturing Staffs | 211 | IIOT MONITORING IS FACTORY OF TOMORROW EQUIPMENT MONITORING APPLICATION FOR USE AT FORD PLANTS. THE APPLICATION IS PRIMARILY BASED ON IN HOUSE DEVELOPED SOFTWARE AND INCLUDES INTERFACES TO THE APPLICATIONS MARQUEE MANAGER AND FIRST PAGE FOR MANAGING PCB'S AND PAGING. THE PRIMARY FUNCTIONS OF IIOT MONITORING IS TO REDUCE THE LAUNCH CURVE FOR NEW MODEL PROGRAMS AND BREAK PRODUCTION BOTTLENECKS IN ON-GOING PRODUCTION OPERATIONS. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
51749 | I-ERP Vendor Master | In Production | IERPSRM | I-ERP | SARAUJO3 | JBRITT31 | TSHYAM | SNAG1 | Copper | S-Ox Out of Scope | 332 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | 332 | used to manage supplier information |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-31 | 2025-02-15 | Complete | Blue | 2025-04-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | 2 Interfaces migrated to GCP | No | Java < v21
20978 | FCE Scriptura | In Production | FCE Script | FORD CREDIT | JBENITO | MLOPEZ31 | MSIMON12 | AGALLAG9 | Silver | Non S-Ox | 321 | No | Yes | COTS | JBENITO | MLOPEZ31 | Ford Credit Services | Ford Credit (FMCC) | This component is the printing solution for the BLESS Suite applications (BLESS CAPS, BLESS Receivables, BLESS Wholesale & BLESS WTF) | 7 |  | YES | 2 | SRAISIN1 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
50921 | I-ERP Platform | Active | IERP | I-ERP | SVISWANA | SVISWANA | MMOORE41 | MMOORE41 | Gold | S-Ox In Scope | - | No | - | - | TSWEEN16 | SVISWANA | #N/A | #N/A | This is the IERP SAP application infrastructure and license management project |  | Springboot | YES | 3 | TSWEEN16 | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50921 | I-ERP Platform | Active | IERP | I-ERP | SVISWANA | SVISWANA | MMOORE41 | MMOORE41 | Gold | S-Ox In Scope | - | No | Yes | - | TSWEEN16 | SVISWANA | ENTERPRISE TECHNOLOGY | - | #N/A |  |  | YES | 3 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | AlloyDB | [5 empty] | No | SQL
19273 | FCE SCHUFA Batch Credit Bureau Interface | In Production | schufacbi | FORD CREDIT | JBENITO | JCOCKWIL | JGOLDST4 | AGALLAG9 | Bronze | Non S-Ox | 311 | No | Yes | Managed by 3rd Party Purchased Service | JBENITO | JCOCKWIL | Ford Credit Services | Ford Credit (FMCC) | Provides a gateway to the German credit bureau for transmitting files of customer details from LA, PhinAMV and two external Lawyers | 3 |  | YES | 1 | SRAISIN1 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
52469 | I-ERP Material Master | In Production | IERPMAT | I-ERP | SVISWANA | SVISWANA | DMCAULI3 | MJOHN873 | Gold | S-Ox In Scope | 322 | No | Yes | COTS | TSWEEN16 | SVISWANA | Enterprise Technology | 322 | I-ERP Material Master |  | Springboot | YES | 3 | TSWEEN16 | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
52469 | I-ERP Material Master | In Production | IERPMAT | I-ERP | SVISWANA | SVISWANA | DMCAULI3 | MJOHN873 | Gold | S-Ox In Scope | 322 | No | Yes | COTS | TSWEEN16 | SVISWANA | Enterprise Technology | Integrated Enterprise Resource Planning (I-ERP) | I-ERP Material Master |  |  | YES | 3 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
15824 | FCE SalesPartner | In Production | sp | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Credit Application Entry application. Used by dealers. Currently SalesPartner application is only active for UK market | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
51747 | I-ERP Direct Material Source to Contract | In Production | IERPSC | I-ERP | SARAUJO3 | CBISWADI | TSUNDARA | SNAG1 | Gold | S-Ox Out of Scope | 221 | No | Yes | Managed by 3rd Party Purchased Service | SARAUJO3 | CBISWADI | Supply Chain | 221 | used for requesting supplier quoting events program approval |  | Springboot | YES | 3 | TSWEEN16 | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-01-15 | 2025-01-15 | Complete | Blue | 2025-01-15 | 2025-01-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Praveen | 2025-03-05 |  |  |  | No | Java < v21
51747 | I-ERP Direct Material Source to Contract | In Production | IERPSC | I-ERP | SARAUJO3 | CBISWADI | TSUNDARA | SNAG1 | Gold | S-Ox Out of Scope | 221 | No | Yes | Managed by 3rd Party Purchased Service | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | used for requesting supplier quoting events program approval |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 75% | 100% | 75% | 75% | 50% | 50% | 100% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-06 |  |  |  | No | SQL
15414 | FCE Bless Rec | In Production | BLESSREC | FORD CREDIT | MLOPEZ31 | MVILLASE | SCASCO1 | AGALLAG9 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | MLOPEZ31 | MVILLASE | Ford Credit Services | Ford Credit (FMCC) | FCE BLESS Rec is a receivable system which permit finance (retail & leasing) vehicles to Ford Credit for private customers and companies. | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
53542 | FC Enablement Systems | In Production | FCES | FORD CREDIT | IPANKAJ | VNAVEEN1 | VRUKMANG | ROBRIEN3 | Silver | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | VNAVEEN1 | Ford Credit Services | Ford Credit (FMCC) | Suite of APIs developed to support Ford Credit Enabling API product. | 7 |  | YES | 2 | SRAISIN1 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
18215 | IDS Feedback | In Production | IDSFDBCK | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Feedback server - capture/storage and reporting on diagnostic field data collected from in-dealership IDS units. | 806 |  | YES | 5 | RKENNEL | PLM | WebFocus | Q1 2025 | Migrate to QlikSense | Modernize | 2025-03-31 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-29 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | QlikSense | [5 empty] | No | DA
18215 | IDS Feedback | In Production | IDSFDBCK | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Feedback server - capture/storage and reporting on diagnostic field data collected from in-dealership IDS units. |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
18215 | IDS Feedback | In Production | IDSFDBCK | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | RKENNEL | Ford Customer Service | FCSD Tech | Feedback server - capture/storage and reporting on diagnostic field data collected from in-dealership IDS units. |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
55057 | Experian Data Arc 360 | In Production | DA360 | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | TSAILESH | Bronze | Non S-Ox | 311 | No | Yes | COTS | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | Software to monitor and assess the accuracy and integrity of credit reporting data | 3 |  | YES | 1 | SRAISIN1 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
18215 | IDS Feedback | In Production | IDSFDBCK | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Feedback server - capture/storage and reporting on diagnostic field data collected from in-dealership IDS units. |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
170 | ICPC: Inter / Intra Company Procurement cost | In Production | ICPC | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Finance | 211 | ICPC: UPDATES FCSD COST FILES USING ACTUAL SETTLEMENT AMOUNTS FROM ICS AND CCAPS |  | Springboot | YES | 2 | RKENNEL | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
170 | ICPC: Inter / Intra Company Procurement cost | In Production | ICPC | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Finance | FCSD Tech | ICPC: Updates FCSD cost files using actual settlement amounts from ICS and CCAPS |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
9093 | EXECNET - Executive Intranet Sales Reporting Tool | In Production | ExecNet | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | EXECNET is a web-based application which is updated daily with Sales and Stock information for Ford models for all European markets, to Market and sub-model level. | 3 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
24073 | ICI Decisioning | In Production | ICI DSP | M&S TECH | NKANDULA | TBRYANS1 | MMEADOR | RFERMAN1 | Copper | Non S-Ox | 311 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Enterprise Technology | Marketing, Sales and Service | Sense and respond machine learning and BRMS application. |  |  | YES | 2 | NKANDULA | PLM | WAS | Q4 2024 | 0 | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | The planned launch date was mentioned as 15th Dec 2024 but based on below understanding both WAS and VM will be same date. "Confirmed with PDO. Decom date is Q2 2025. Websphere does not run any home grown applications. Websphere runs COTS product called pega decisioning. We are moving pega decisoning to Salesforce. So no specific migration required for websphere. Most PCF services under 24073 has been migrated to GCP cloud run" | No | Java < v21
24042 | ICI Campaign Manager | In Production | ICI CM | M&S TECH | NKANDULA | TBRYANS1 | PRAO2 | RFERMAN1 | Gold | Non S-Ox | 211 | No | Yes | COTS | SBAILE17 | TBRYANS1 | Communications | Marketing, Sales and Service | Adobe Campaign Tool solution to support the execution of marketing campaigns. |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
21809 | e-Social Employees Records Management | In Production | SCL | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Human Resources | - | Application to support e-Social, a brazilian government program which is part of a broader initiative called SPED. Application goals are to consolidate, manage and send electronic information to the government related to Personal and Payroll related Data of every Ford employee, in accordance with the e-Social regulations. | 4 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
24042 | ICI Campaign Manager | In Production | ICI CM | M&S TECH | NKANDULA | TBRYANS1 | PRAO2 | RFERMAN1 | Gold | Non S-Ox | 211 | No | Yes | COTS |  |  | Communications | Marketing, Sales and Service | Adobe Campaign Tool solution to support the execution of marketing campaigns. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
15723 | ICE | In Production | ICE | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | Non S-Ox | 222 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | ICE (Internal Communications Exchange) is the primary business logic engine for dealer and consumer originated business. ICE is assuming the business logic responsibilities from XNet. It will be a service that processes XML transactions for applications/systems that utilize the CreditNet Platform and other Ford Financial services. ICE can process both synchronous and asynchronous transactions, support XML Schema formats, SOAP protocols as well as both Document and RPC formats. For all transactions processed, ICE will record metric information required to verify performance characteristics set forth by Dealer Web Services and RouteOne business teams. In addition to metrics, ICE will also record all billing characteristics to and from RouteOne for legal and auditing purposes. It is a centralized point of business logic (required checks, length checks, edits and validations) as well as the interface to the COMPASS database for dealer entered originations business. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
15723 | ICE | In Production | ICE | FORD CREDIT | JMALETZ | JJACK348 | VKHANNA1 | JMANI | Silver | Non S-Ox | 222 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | ICE (Internal Communications Exchange) is the primary business logic engine for dealer and consumer originated business. ICE is assuming the business logic responsibilities from XNet. It will be a service that processes XML transactions for applications/systems that utilize the CreditNet Platform and other Ford Financial services. ICE can process both synchronous and asynchronous transactions, support XML Schema formats, SOAP protocols as well as both Document and RPC formats. For all transactions processed, ICE will record metric information required to verify performance characteristics set forth by Dealer Web Services and RouteOne business teams. In addition to metrics, ICE will also record all billing characteristics to and from RouteOne for legal and auditing purposes. It is a centralized point of business logic (required checks, length checks, edits and validations) as well as the interface to the COMPASS database for dealer entered originations business. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
23548 | eSignature Enterprise Service (DocuSign) | In Production | eSign | OCETO | TVASU | SANANTH | VSRIRAMA | WJUSTICE | Silver | Non S-Ox | 311 | No | Yes | Managed by 3rd Party Purchased Service | TVASU | SANANTH | Enterprise Technology | Technology & Enterprise Services (TES) | eSignature Enterprise Service ((DocuSign) - It is the next generation of sending, receiving, reviewing and approving documents with a highly visual interface. The electronic signature tool allows users to complete an approval faster compared to the traditional means of hand carrying documents for approval. This is used extensively by Ford Motor, Ford Credit, Ford EU and other IMG Markets. | 4 |  | YES | 1 | TSWEEN16 | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
54648 | IBM License Management Tool | In Production | ILMT | EPEO | RHAMMO57 | JGIES | PSTRICK3 | GSIENKIE | Copper | Non S-Ox | 211 | No | Yes | COTS | RHAMMO57 | JGIES | Enterprise Technology | - | This tool allows the counting of IBM licenses utilized in our compute environment |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
12606 | eProfile | In Production | eProfile | FORD PRO & FCSD TECH | TJUNIPER | GRIST | SRAVI6 | KMADHUMI | Silver | Non S-Ox | 321 | No | Yes | In-House | TJUNIPER | GRIST | Marketing & Sales | Marketing, Sales and Service | eProfile is an application that provides a consistent way of data capture and storage across differing market web sites in accordance with data protection legislation and using a standard set of web consumer data capture templates. | 14 |  | YES | 2 | RKENNEL | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | 50% | 50% | 75% | 50% |  |  | 50% |  | GCP CaaS |  |  |  |  | DB Migration is completed. GCP CaaS in progress. .Net Aplication. | No | VM
19960 | IBM Business Process Manager (BPM) | In Production | BPM | OCETO | TVASU | SANANTH | PMCAULIF | WJUSTICE | Silver | Non S-Ox | 322 | No | Yes | - | TVASU | TVASU | Enterprise Technology | Technology & Enterprise Services (TES) | This is the entry for the BPM Core / IBM BPM application. This supports BPM common framework and utilities, along with platform services. Many applications use this as part of their overall solution and should define this as part of their architecture manifest. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q3 2027 | Modernize to Cloud Databases | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | Oracle
19960 | IBM Business Process Manager (BPM) | In Production | BPM | OCETO | TVASU | SANANTH | PMCAULIF | WJUSTICE | Silver | Non S-Ox | 322 | No | Yes | - | TVASU | SANANTH | Enterprise Technology | Technology & Enterprise Services (TES) | This is the entry for the BPM Core / IBM BPM application. This supports BPM common framework and utilities, along with platform services. Many applications use this as part of their overall solution and should define this as part of their architecture manifest. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q3 2027 | Modernize to Cloud Databases | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | SQL
19103 | ENTERPRISE DOCUMENT MANAGEMENT SYSTEM | In Production | EDMS | EPEO | SRUNSON | PWILL357 | GSARAV13 | GSIENKIE | Silver | Non S-Ox | 322 | No | Yes | COTS | SRUNSON | PWILL357 | Enterprise Technology | EPEO | EDMS for corporate records requiring long term retention and archiving | 34 |  | YES | 3 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
19960 | IBM Business Process Manager (BPM) | In Production | BPM | OCETO | TVASU | SANANTH | PMCAULIF | WJUSTICE | Silver | Non S-Ox | 322 | No | Yes | - |  |  | Enterprise Technology | Technology & Enterprise Services (TES) | This is the entry for the BPM Core / IBM BPM application. This supports BPM common framework and utilities, along with platform services. Many applications use this as part of their overall solution and should define this as part of their architecture manifest. |  | Springboot | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | Currently some of the APIs in GCP are running Java 17 and some are running Java 21 | No | Java < v21
11363 | I/A Online: IA-ONLINE | In Production | I/AONLIN | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The I/A Online application allows users to generate adhoc reports on sales, orders and stock units currently being processed through the vehicle order processing and sales systems. | 2 |  | YES | 2 | NKANDULA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11363 | I/A Online: IA-ONLINE | In Production | I/AONLIN | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The I/A Online application allows users to generate adhoc reports on sales, orders and stock units currently being processed through the vehicle order processing and sales systems. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
20750 | Hyperion-Financial Management | In Production | HFM | I-ERP | SFRANCI8 | DSHAH1 | NVARANAS | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | COTS | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Hyperion Financial Management system for consolidate reporting of North America, Ford Credit, and Ford Credit Europe. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
17375 | Engineering Job Authorization | In Production | EJA | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | MAKES A CONTROL OF THE BUDGET OF A PROJECT OF ENGINEERING THROUGH WORN-OUT HOURS FOR ACTIVITY OF THIS PROJECT ALSO MAKING VALUE OF THE HOURS PRESENTING A REAL EXPENSE TO THE FORESEEN IN THE MONTH COUNTING THE EXPENSE AND THROWING THE SAME IN THE FIXED ASSETS. | 4 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
10012 | HVBOM: Historical Vehicle Bill of Material | In Production | HVBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 122 | No | Yes | In-House | NBAECKER | NBAECKER | Ford Customer Service | FCSD Tech | The HVBOM web-based system is a tool that will be used by Ford dealership service and parts personnel to view a vehicle bill of material by VIN in order to identify correct service part numbers. Secondary outage impact is 'Impact to Productivity'. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q2 2026 | Modernize to Cloud Databases | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Oracle
10012 | HVBOM: Historical Vehicle Bill of Material | In Production | HVBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 122 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | The HVBOM web-based system is a tool that will be used by Ford dealership service and parts personnel to view a vehicle bill of material by VIN in order to identify correct service part numbers. Secondary outage impact is 'Impact to Productivity'. |  |  | YES | 4 | RKENNEL | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
10012 | HVBOM: Historical Vehicle Bill of Material | In Production | HVBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 122 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | The HVBOM web-based system is a tool that will be used by Ford dealership service and parts personnel to view a vehicle bill of material by VIN in order to identify correct service part numbers. Secondary outage impact is 'Impact to Productivity'. |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
50293 | ELD Calibration | In Production | ELD Cal | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Silver | Non S-Ox | 12 | Yes | No | COTS | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Engine Lab Calibration Tool | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23545 | HR Systems Security Access | In Production | HRSSA | OCETO | TSWEEN16 | KKOEHLER | WALBERS | MBALAN2 | Bronze | Non S-Ox | 121 | No | Yes | In-House | DDESAI | DDESAI | Human Resources | Staffs IT | HR System Security Access Tool for HCM, IAAAP, ET Suite of applications, DEU UK Pension |  |  | YES | 1 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
25082 | HR Middleware | In Production | HRMW | OCETO | TSWEEN16 | NMUTHUK2 | PVENKA12 | MBALAN2 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | 332 | HR Middleware(ITMS#25082) Informatica Cloud - is an integration platform to facilitate HR data need for all HCM ERP interfaces(Payroll and Non-Payroll, MDM and Non-HR applications). |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | Upgraded to Java 17, Java 21 upgrade will be completed in 2026 | No | Java < v21
25082 | HR Middleware | In Production | HRMW | OCETO | TSWEEN16 | NMUTHUK2 | PVENKA12 | MBALAN2 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | HR Middleware(ITMS#25082) Informatica Cloud - is an integration platform to facilitate HR data need for all HCM ERP interfaces(Payroll and Non-Payroll, MDM and Non-HR applications). |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
13554 | eBatch Communication Module (eBCM) | In Production | eBCM | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Silver | Non S-Ox | 212 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | eBCMWeb services is the file transfer interface to BCM covering entire Europe(3500) via public internet. eBCM web is the sub-function on the same platform used by approx. 100 Finland /German dealers (out of 3500 in Europe). | 4 |  | YES | 4 | NKANDULA | PLM | VM | Q4 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
24068 | HR Life@Ford | In Production | HR Portal | OCETO | TSWEEN16 | NABBAS | MKOMATH1 | MBALAN2 | Copper | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | DDESAI | NABBAS | Human Resources | Staffs IT | HR Life@Ford supports operations and changes to the technology platform used by the HR Contact Centers located in Chennai, Mexico City, Budapest and two satellite centers, one each in China and Thailand. The technology platform consists of Dynamics 365 hosted on Azure Cloud, Documentum, and Informatica Middleware, all hosted in the Europe Region. Life@Ford application supports 800+ agents in 5 global contact centers who handle 190k employee transactions, leveraging the MS Dynamics 365 suite of tools to provide sefl-service and HR case management services |  |  | YES | 1 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
52782 | HR Integrated Archival & Advanced Analytics Platfo | In Production | IAAAP | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Silver | Non S-Ox | 322 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | Ford Human Resources has migrated its several core HR systems to Oracle HCM Cloud platform and some of the existing applications are getting decommissioned. This proposed application shall establish the platform for aggregated archival platform covering 6 sun-setting applications, enabling accessibility with custom reports/queries to people leaders. HR integrated analytics & visualization platform establishment over data marts of set of in-scope applications. This application serves as a centralized platform to retrieve archived data & performing advanced analytics and visualization by HR Global Business teams. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
20461 | DNS, DHCP and IPAM (DDI) | In Production | DDI | EPEO | MCRNKOVI | SPANDRAN | MMIDDLET | MMIDDLET | Copper | Non S-Ox | 113 | No | Yes | Managed by 3rd Party Purchased Service | MCRNKOVI | MCRNKOVI | Enterprise Technology | EPEO | DNS (Domain Name System) is a standard Internet protocol that provides name-to-address resolution of servers and applications, allowing a user to connect to an easily remembered name like myapp.ford.com, rather than an esoteric IP address like 19.9.9.9. DHCP (Dynamic Host Configuration Protocol) is a standard Internet protocol that automatically configures workstation network information such as IP address, default router, DNS server, etc., eliminating the need to manually administer this information on each machine. IP Address Management (IPAM) software tracks IP Address allocation and manages distributed enterprise DNS and DHCP services. Use of an IPAM generates consistent and syntactically correct configuration files, reducing DNS and DHCP errors, and allowing delegation of day-to-day data administration to Level-1 site administrators. | 22 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
11992 | Direct Order Entry System | In Production | DOESII | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Provides dealerships with the ability to enter parts orders to FCSD. It also allows them to check on part inventories and track order status. | 4 |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | 6 VMs are pending , Followed with PDO. Internal dependecies. | No | VM
21539 | Dealer Service Agenda System | In Production | Agenda | OCETO | DBRIGHEN | NMORALE7 | PDELMOND | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | Electronic Agenda System to allow customers to schedule services at Dealers (regular warranty check point, vehicle breaks, etc) in such a way that customers will be able to get online availability to book services at the Dealership, So that a common process for booking services at dealership is achieved. | 19 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24549 | DEALER REPORTING APPLICATION | In Production | DRA | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Silver | Non S-Ox | 211 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | The Dealer Reporting App is an application to save and index document information and its templates providing document generation and information lookup functionalities. Currently is being used to generate the Daily Summary Remittance Advice and Payment Advice documents as part of the eContracting project. | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
21346 | HOST ON DEMAND | In Production | HOD | EPEO | SKULKA52 | CGIACOBB | COLIVE34 | COLIVE34 | Silver | Non S-Ox | 112 | Yes | No | COTS | CMIRABIT | CGIACOBB | Enterprise Technology | EPEO | Host On Demand (HOD) is a thin client terminal emulation solution. Thin client being a java applet rather than the traditional, fat client, operating system specific executable file,ie (Windows EXE file). HOD is a solution for communicating with servers using a terminal interface commonly called Green Screen Emulation. This method of communication is non-graphical and consists of purely standard ASCII characters. HOD sessions are pre-configured java applets that are deployed to any standard web server. The java applet is accessed through a web page link that, in turn, will run inside the client's web browser. The java applet connects to a specified host based on the pre-configuration data and produces a Green Screen session within the client's browser. |  |  | YES | 2 | SWALIMBE | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
757 | Homologation Document Distribution System | In Production | EuOGC-HDDS | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Bronze | Non S-Ox | 212 | No | Yes | COTS | DKAVITHA | DKAVITHA | Policy | Industrial System IT | Document scanning storing retrieval system for Approval Documents Web enabled document delivery. Product Name TypMaster DD Module by Supplier T-Systems. Also utilised by CGN-Technik for document storage. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | Cloud SQL PostgreSQL | Priya | 2025-03-03 |  |  | Plan is to move to On-Prem EDC CaaS with Oracle running in ExaCC as a first step. Later, move to GCP CaaS along with Postgres in Q4 2025. | No | Oracle
757 | Homologation Document Distribution System | In Production | EuOGC-HDDS | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Bronze | Non S-Ox | 212 | No | Yes | COTS | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Document scanning storing retrieval system for Approval Documents Web enabled document delivery. Product Name TypMaster DD Module by Supplier T-Systems. Also utilised by CGN-Technik for document storage. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | GCP CaaS | Priya | 2025-03-03 |  |  | COTS Package, Vendor working on the rewrite to make the package compatible for CaaS | No | Java < v21
18814 | Dealer profile and performance reporting (DlrPls) | In Production | DealerPlus | EPEO | ARAJKUMA | LEHLERS1 | JBRETT1 | LRODR205 | Bronze | Non S-Ox | - | Yes | No | Managed by 3rd Party Purchased Service | ARAJKUMA | IKOVALEV | Marketing & Sales | - | Dealer profile and performance reporting. Provide a central repository of dealer data, collected from numerous sources, in order to decrease the time for end users to access dealer profile data. Data is updated monthly by Sylke Dickes, the application administrator. One record per year per dealer is archived to enable year on year comparisons. Dealer Profile Database covering a wider range of dealer data than DID. | 4 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
17774 | Compliance with Regulatory Information Systems 2.0 | In Production | CRIS 2.0 | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 231 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | To create label information for Fuel Ecomony (includes BEV's, PHEVs); Green House Gas calculations and CAFE to meet North American government reporting requirements for EPA, Environment Canada, CARB, and other NA government agencies. | 4 |  | YES | 4 | BWUNNAVA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-11-30 | 2024-11-30 | 2024-11-25 | Complete | Blue | 2024-11-30 | 2024-11-25 | Complete |  | No | [8 empty] | Decommission | Priya | 2025-03-06 |  |  |  | No | VM
17774 | Compliance with Regulatory Information Systems 2.0 | In Production | CRIS 2.0 | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 231 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | To create label information for Fuel Ecomony (includes BEV's, PHEVs); Green House Gas calculations and CAFE to meet North American government reporting requirements for EPA, Environment Canada, CARB, and other NA government agencies. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Will be Decommissioned | Decommission | 2024-11-30 | 2024-11-30 | 2024-11-25 | Complete | Blue | 2024-11-30 | 2024-11-25 | Complete |  | No | [8 empty] | Decommission | Priya | 2025-03-06 |  |  |  | No | Java < v21
51167 | HealthNut | In Production | HealthNut | EPEO | RHAMMO57 | MBRUM | KTELLER1 | NKAUSHAL | Bronze | Non S-Ox | 112 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 112 | A LIGHTWEIGHT HEALTH ENDPOINT MONITOR THAT CAN NOTIFY YOU OF AN OUTAGE OR CHANGE IN STATUS VIA SLACK & WEBEX TEAMS MESSAGES. |  | Springboot | YES | 1 | SWALIMBE | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete | [10 empty] | Decommission | [6 empty] | Java < v21
17400 | Header & Trailer Management | In Production | CRS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Gold | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Enterprise Technology | - | Header & Trailler Module: Consists File records according to amount and index; send email to the analysts in case of process interruption. Access Revision Module: sends emails to the system, folders and procedures owners in order to request certification related the access revision under their responsibility. |  |  | YES | 1 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
24201 | Dealer Connectivity & Data Services | In Production | DCDS(GUDB) | M&S TECH | KPINNU | KHILLERT | GBONUTTI | JHARPER2 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | Previous ITMS is 107. This new ITMS entry is to reflect next generation technology upgrades. Global Unified Database is a data warehouse for customer pay and warranty repair data from Ford and Lincoln Mercury dealers. It provide one globally standardized POS database to provide POS performance metrics, global dashboards and reports, and standardized data extracts that support downstream applications and programs. | 8 |  | YES | 3 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12402 | HC: Unicare RTW - Return to Work (Ford Side) | In Production | RTW | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DDESAI | DDESAI | Human Resources | Staffs IT | Batch interface process that permits Unicare Disability to query DLORS timekeeing records to determine if employee has returned to work when receiving Disability benefits. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Oracle Database is decommissioned | No | Oracle
19598 | DCW: Dealer Contracts Worksite | In Production | DCW | M&S TECH | NKANDULA | JLEWIS10 | CVOGLER1 | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | DCW is a SharePoint online application used by U.S. Market Rep to track dealer contract progress using InfoPath forms. The site houses training and other documents required throughout the contract lifecycle. The application is a subsite to Market Rep which is the main landing page for the Market Representation group to post content related to Rep Planning. DCW relies on GOLDD views to ETL dealer data into the DCW SQL database and the Ford Business and PDO team are actively working on a replacement for this application. | 3 |  | YES | 2 | NKANDULA | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
21822 | Data Loss Prevention | In Production | DLP | EPEO | NOKEEFE | VNACHIMU | WMAGGETT | WJUSTICE | Silver | Non S-Ox | 311 | No | Yes | - | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | Symantec Tool to monitor data in an effort to prevent loss. | 73 |  | YES | 3 | SWALIMBE | PLM | VM | Q4 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | SaaS | [6 empty] | VM
24316 | HashiCorp Secrets Management System | Active | Vault | EPEO | NOKEEFE | VNACHIMU | KCARDWEL | KCARDWEL | - | Non S-Ox | - | No | Yes | - |  |  | Enterprise Technology | - |  |  | Springboot | YES | 2 | SWALIMBE | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Decommission | [6 empty] | Java < v21
18815 | Daily download from DID database into local DB | In Production | SQL DID | EPEO | ARAJKUMA | LEHLERS1 | JBRETT1 | LRODR205 | Bronze | Non S-Ox | - | Yes | No | Managed by 3rd Party Purchased Service | ARAJKUMA | IKOVALEV | Marketing & Sales | - | Daily download from DID database. The data is loaded into a local database, and used by various Business Managed Apps for Dealer Info. This application referes only to the Database portion. | 4 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
52594 | Cortona 3D Training | In Production | C3DT | ISIT | SKING68 | JLYNN1 | KKISIEL | AELANGO | Bronze | Non S-Ox | 311 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Deploy training material created by Cortona 3D application so that users on the plant floor can access it and get trained. | 4 |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | EDC Hypervisor | [5 empty] | No | VM
17774 | Compliance with Regulatory Information Systems 2.0 | In Production | CRIS 2.0 | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 231 | No | Yes | In-House | DKAVITHA | DKAVITHA | Policy | Industrial System IT | To create label information for Fuel Ecomony (includes BEV's, PHEVs); Green House Gas calculations and CAFE to meet North American government reporting requirements for EPA, Environment Canada, CARB, and other NA government agencies. |  |  | YES | 4 | BWUNNAVA | PLM | Oracle | Q4 2024 | Will be Decommissioned | Decommission | 2024-11-30 | 2024-11-30 | 2024-11-25 | Complete | Blue | 2024-11-30 | 2024-11-25 | Complete |  | No | [8 empty] | Decommission | Priya | 2025-03-06 |  |  |  | No | Oracle
19996 | CISCO SECURITY MANAGER | Active | CSM | EPEO | MCRNKOVI | BBOGEDIN | CRICHA15 | CRICHA15 | Copper | Non S-Ox | - | No | Yes | - | MCRNKOVI | MCRNKOVI | Enterprise Technology | - | Management Tool for Cisco Firewalls and VPN devices | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | EDC Hypervisor | [6 empty] | VM
50779 | H&C-Heavy Duty Verify | In Production | HD Verify | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 231 | No | Yes | In-House |  |  | Policy | Industrial System IT | As part of Homologate & Certify Product supporting the Heavy duty dyno cert process for EPA & CARB |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
17774 | Compliance with Regulatory Information Systems 2.0 | In Production | CRIS 2.0 | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 231 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | To create label information for Fuel Ecomony (includes BEV's, PHEVs); Green House Gas calculations and CAFE to meet North American government reporting requirements for EPA, Environment Canada, CARB, and other NA government agencies. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | Q4 2024 | Will be Decommissioned | Decommission | 2024-11-30 | 2024-11-30 | 2024-11-25 | Complete | Blue | 2024-11-30 | 2024-11-25 | Complete |  | No | [8 empty] | Decommission | Priya | 2025-03-06 |  |  |  | No | Java < v21
18786 | Project Directory Management and Server Access Too | In Production | ProjDirSAT | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | In-House | SKING68 | KRAMESH | Enterprise Technology | Industrial System IT | This web base application allows users to request access to project folder or request new project folders. Application allows the approvers for that folder to approve or deny request. Approved requests are reviewed by IT and access is granted using Active Directory (AD)groups |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | SQL
50664 | Cisco Hyperflex | In Production | HFLEX | EPEO | MCRNKOVI | BBOGEDIN | CRICHA15 | CRICHA15 | Gold | Non S-Ox | 112 | No | Yes | COTS | MCRNKOVI | MCRNKOVI | Enterprise Technology | EPEO | Cisco HyperFlex delivers software-defined networking and computing. | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | EDC Hypervisor | [6 empty] | VM
162 | GWTS: Global Warranty Trends System | In Production | GWTS | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | RKUMART1 | Silver | Non S-Ox | 231 | No | Yes | In-House | RSING163 | SKOVACIC | Ford Customer Service | FCSD Tech | Measures the warranty performance of the dealers within their Region/Measurement Group. The Web-based is GWMS which is a global application, managed in Dearborn and provides dealers with access to their warranty trends reporting information in 15 languages. This allows dealers to better manage their warranty performance. Dealers can use the many diagnostics tools and claims lists to identify warranty claiming deficiencies and take corrective action | 81 |  | YES | 3 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
162 | GWTS: Global Warranty Trends System | In Production | GWTS | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | RKUMART1 | Silver | Non S-Ox | 231 | No | Yes | In-House | RSING163 | SKOVACIC | Ford Customer Service | FCSD Tech | Measures the warranty performance of the dealers within their Region/Measurement Group. The Web-based is GWMS which is a global application, managed in Dearborn and provides dealers with access to their warranty trends reporting information in 15 languages. This allows dealers to better manage their warranty performance. Dealers can use the many diagnostics tools and claims lists to identify warranty claiming deficiencies and take corrective action |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q1 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | Mainframe Modernzation Update Pending | No | Mainframe
162 | GWTS: Global Warranty Trends System | In Production | GWTS | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | RKUMART1 | Silver | Non S-Ox | 231 | No | Yes | In-House | RSING163 | SKOVACIC | Ford Customer Service | FCSD Tech | Measures the warranty performance of the dealers within their Region/Measurement Group. The Web-based is GWMS which is a global application, managed in Dearborn and provides dealers with access to their warranty trends reporting information in 15 languages. This allows dealers to better manage their warranty performance. Dealers can use the many diagnostics tools and claims lists to identify warranty claiming deficiencies and take corrective action |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
54678 | GTS HUB | In Production | GTSHUB | M&S TECH | FHIRSH | NGIRISH | LSCHLEBA | CKEMPSKI | Silver | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | 211 | GTS Hub has capabilities to receive, validate and transform Order data and send it to downstream systems |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-12-15 | 2024-11-18 | 2024-11-18 | Complete | Blue | 2024-12-23 | 2024-12-23 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Decommission | [5 empty] | No | Java < v21
100 | GSLTS: Global Service Labor Time Standards | In Production | GSLTS | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RSRINI38 | Bronze | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Labor Time Schedule Database - Provides labor time information for use by dealers in the preparation of Warranty Claims and customer invoices, and for the validation of Warranty Claims by the ACES system. |  |  | YES | 4 | RKENNEL | PLM | Mainframe | Q1 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
100 | GSLTS: Global Service Labor Time Standards | In Production | GSLTS | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RSRINI38 | Bronze | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Labor Time Schedule Database - Provides labor time information for use by dealers in the preparation of Warranty Claims and customer invoices, and for the validation of Warranty Claims by the ACES system. |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
100 | GSLTS: Global Service Labor Time Standards | In Production | GSLTS | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RSRINI38 | Bronze | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | RKENNEL | Ford Customer Service | FCSD Tech | Labor Time Schedule Database - Provides labor time information for use by dealers in the preparation of Warranty Claims and customer invoices, and for the validation of Warranty Claims by the ACES system. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | [13 empty] | Q4 DB Modernization- Possibly move to 2026 as PDO | No | Oracle
23138 | China Benefit Platform | In Production | CBP | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Bronze | Non S-Ox | 311 | No | Yes | In-House |  |  | Human Resources | Staffs IT | Implement a one-stop shop portal for employee benefit self-service and HR Shared Service to process the benefit administration on numerous benefit programs. | 3 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11169 | GSEVIN: Global Secure Vehicle Info Sys | In Production | GSEVI11169 | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 222 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | GSEVIN: Global Secure Vehicle Info System that is supported along with GOASIS (Single SOW). |  |  | YES | 1 | RKENNEL | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
8951 | GSDB Online | In Production | GSDBOL | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Bronze | Non S-Ox | 232 | No | Yes | In-House | CBISWADI | CPARTHIB | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | GSDB OnLine provides suppliers who are FSP and GSDB Online registered the ability to add and change their own supplier details codes on-line and submit changes to the DMA. CIA rating is 2-1-1 ACR is 2002-641 |  | Java Struts | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
19403 | GSDB Change Request Process (GCRP) | In Production | GCRP | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Bronze | Non S-Ox | 232 | No | Yes | In-House | CBISWADI | CPARTHIB | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | GSDB CRP is a global application used to support the process of Buyers requesting changes (updates or additions) to GSDB Supplier Data. It was initially funded by EU Accounts Payable with an aim to ensure that high-quality data, especially European tax information, is input into GSDB. Process (up to 2008), Buyers were asked to complete a complex, multi-tiered form. This was often filled in incorrectly or is incomplete, which in turn can lead to significant errors, for instance in the amount of tax that Ford pays. This web-based application ensures, where possible, that the end user will only be required to input data that is relevant to their request. This will be done by intelligently reducing the number of fields shown dependent on the type of request e.g. location of requestor, Prod vs. NonProd, type of GSDB site being requested etc. The tool will seamlessly feed the requests into GSDB and will be used primarily by the Buyers (to request change) and the DMA's (to approve and implement those changes). |  | Java Struts | YES | 1 | TSWEEN16 | PLM | Java Struts | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
18786 | Project Directory Management and Server Access Too | In Production | ProjDirSAT | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | In-House |  |  | Enterprise Technology | Industrial System IT | This web base application allows users to request access to project folder or request new project folders. Application allows the approvers for that folder to approve or deny request. Approved requests are reviewed by IT and access is granted using Active Directory (AD)groups |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
839 | GSAR: Global System for Analytics & Reporting-AWS | In Production | GSAR | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | JDEGUZMA | RMEHTA3 | PD Operations and Quality | Industrial System IT | Provides a database of warranty claims and vehicle information that supports common global warranty reporting, analysis, and feedback processes for model years 1991 and forward. Customers have the flexibility to request on-line reports using a wide range of selection criteria and a variety of output formats. Primary Users: Analysts in Quality, Engineering, Finance, Vehicle Operations and Powertrain Plants. |  |  | YES | 4 | BWUNNAVA | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | Yes | [14 empty] | Yes | Mainframe
839 | GSAR: Global System for Analytics & Reporting-AWS | In Production | GSAR | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | JDEGUZMA | JDEGUZMA | PD Operations and Quality | Industrial System IT | Provides a database of warranty claims and vehicle information that supports common global warranty reporting, analysis, and feedback processes for model years 1991 and forward. Customers have the flexibility to request on-line reports using a wide range of selection criteria and a variety of output formats. Primary Users: Analysts in Quality, Engineering, Finance, Vehicle Operations and Powertrain Plants. |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | Yes | [14 empty] | Yes | Oracle
12932 | CENTRAL LICENSE SYSTEM | Active | CLS | EPEO | SKULKA52 | CPENNEY | DECKART1 | DECKART1 | Copper | Non S-Ox | - | No | Yes | - | CMIRABIT | CPENNEY | Enterprise Technology | ITO | Centrally serve licenses for 3rd party software which is shared globally by the Ford enterprise. Objective : CLS allows our business partners to significantly reduce costs by sharing licenses globally. | 23 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
15693 | GRMS Scoring Application | In Production | ORDB | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | TSAILESH | Silver | S-Ox In Scope | 332 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Enterprise Technology | Ford Credit (FMCC) | Database to support research and development of new scoring models. ORDB (operations research data base) is an analytic database used to create Loan Orgination pricing policy. Global Risk Anaylsts use this SAS database to determine optimal Probability of Payment and Risk Analysis Tiers. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50740 | Gravity Sketch | In Production | GS | ISIT | SBONNICI | KRAMMOHA | IWEITZER | IWEITZER | Bronze | Non S-Ox | 311 | Yes | No | - | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | Gravity Sketch is a VR (virtual reality) design creative tool. Feasibility and reference data (including 3D data and imagery) can be imported and 3D data can be exported for use downstream in the design process. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
12552 | Campaign Administration and Microsites | In Production | CA&Msites | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 221 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | Marketing, Sales and Service | The primary goal of the Campaign Administration Tool is to create a generic, reusable version of a contest entry form that allows the business to quickly generate and publish contests and campaigns. This application is hosted on Ford B2B server and the microsites are created on the Ford B2C servers. Campaign Administration Tool complies with Federal Canadian Anti-Spam Legislation (CASL) requirements which requires Ford of Canada to communicate electronically only with individuals, who have provided explicit permission to communicate with them. | 21 |  | YES | 2 | NKANDULA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11589 | GPW: Global Parts Warehouse | In Production | GPW | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | The GPW data warehouse is the central repository of information related to logistics functions, order performance, customer preferences, and activity costs throughout the parts supply chain. It will be used in conjunction with and as the foundation for the Network Integrator, IMAS, and Global Metrics systems. The data warehouse will drive better decision-making and therefore, more efficient business practices. Specific benefits include reduced transportations costs, lower inventory levels, and fewer lost sales due to cancelled backorders. The data warehouse will reside on the Teradata Machine and consist of MMP Purchasing, Supply Chain data, WIPS data and European data. Business Objects will be used as the OLAP tool to create customer reports. Criticality: Med-H Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. | 200 |  | YES | 4 | RKENNEL | PLM | BO | Q2 2025 | Modernize | Modernize | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | SaaS | [5 empty] | No | DA
11589 | GPW: Global Parts Warehouse | In Production | GPW | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | The GPW data warehouse is the central repository of information related to logistics functions, order performance, customer preferences, and activity costs throughout the parts supply chain. It will be used in conjunction with and as the foundation for the Network Integrator, IMAS, and Global Metrics systems. The data warehouse will drive better decision-making and therefore, more efficient business practices. Specific benefits include reduced transportations costs, lower inventory levels, and fewer lost sales due to cancelled backorders. The data warehouse will reside on the Teradata Machine and consist of MMP Purchasing, Supply Chain data, WIPS data and European data. Business Objects will be used as the OLAP tool to create customer reports. Criticality: Med-H Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. | 2 |  | YES | 4 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11589 | GPW: Global Parts Warehouse | In Production | GPW | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | The GPW data warehouse is the central repository of information related to logistics functions, order performance, customer preferences, and activity costs throughout the parts supply chain. It will be used in conjunction with and as the foundation for the Network Integrator, IMAS, and Global Metrics systems. The data warehouse will drive better decision-making and therefore, more efficient business practices. Specific benefits include reduced transportations costs, lower inventory levels, and fewer lost sales due to cancelled backorders. The data warehouse will reside on the Teradata Machine and consist of MMP Purchasing, Supply Chain data, WIPS data and European data. Business Objects will be used as the OLAP tool to create customer reports. Criticality: Med-H Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  |  | YES | 4 | RKENNEL | PLM | Mainframe | Q2 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11589 | GPW: Global Parts Warehouse | In Production | GPW | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | The GPW data warehouse is the central repository of information related to logistics functions, order performance, customer preferences, and activity costs throughout the parts supply chain. It will be used in conjunction with and as the foundation for the Network Integrator, IMAS, and Global Metrics systems. The data warehouse will drive better decision-making and therefore, more efficient business practices. Specific benefits include reduced transportations costs, lower inventory levels, and fewer lost sales due to cancelled backorders. The data warehouse will reside on the Teradata Machine and consist of MMP Purchasing, Supply Chain data, WIPS data and European data. Business Objects will be used as the OLAP tool to create customer reports. Criticality: Med-H Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
9006 | GPPS/GPH: Global Part Pricing System/Pricing Hub | In Production | GPPS | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | KVIJAY34 | PMURUG20 | Bronze | S-Ox In Scope | 232 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | GPPS/GPH (Global Pricing Hub) is a mainframe system that receives part price data from the Ford pricing system (GPARTS) and publishes to downstream Ford systems. The old Oracle pricing and web platform of GPPS is decommissioned. |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q3 2025 | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9006 | GPPS/GPH: Global Part Pricing System/Pricing Hub | In Production | GPPS | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | KVIJAY34 | PMURUG20 | Bronze | S-Ox In Scope | 232 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | GPPS/GPH (Global Pricing Hub) is a mainframe system that receives part price data from the Ford pricing system (GPARTS) and publishes to downstream Ford systems. The old Oracle pricing and web platform of GPPS is decommissioned. |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
23731 | GPL (CVision - Purchasing) | In Production | GPL | I-ERP | SARAUJO3 | SCRANFOR | GALONSO6 | SNAG1 | Bronze | Non S-Ox | 111 | Yes | No | In-House | ASMYTH3 | SCRANFOR | Supply Chain | - | EMC software that enables OCR of scanned documents and integration with EDMS. This is a Purchasing skill team solution. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
50991 | Broadcast Web Services | In Production | BCWS | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Silver | Non S-Ox | 121 | No | Yes | In-House |  |  | Manufacturing Staffs | Industrial System IT | Broadcast Web Services is a service allowing downstream subscribers internal to assembly plants to receive various types of vehicle build data | 3 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | EDC CaaS | Priya |  |  |  | Migration to EDC CaaS for a single site (DCP) Completed. | No | VM
840 | GPIRS - Global Prototype Inv Req & Sched Sys | In Production | GPIRS | ISIT | JKOONS | TBROWN99 | JBROSKI | JLUCAS1 | Silver | Non S-Ox | 212 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | - | GPIRS (Global Prototype Inventory Requisition and Scheduling System)GPIRS is an application that supports the prototype vehicle development process globally, and Powertrain development process for Europe. Supports prototype vehicle business processes including; Scheduling, Bill of Material, Part Ordering, Part Warehousing. and Shipping. |  |  | YES | 4 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
840 | GPIRS - Global Prototype Inv Req & Sched Sys | In Production | GPIRS | ISIT | JKOONS | TBROWN99 | JBROSKI | JLUCAS1 | Silver | Non S-Ox | 212 | No | Yes | In-House | JKOONS | JKOONS | Manufacturing Staffs | - | GPIRS (Global Prototype Inventory Requisition and Scheduling System)GPIRS is an application that supports the prototype vehicle development process globally, and Powertrain development process for Europe. Supports prototype vehicle business processes including; Scheduling, Bill of Material, Part Ordering, Part Warehousing. and Shipping. |  |  | YES | 4 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
840 | GPIRS - Global Prototype Inv Req & Sched Sys | In Production | GPIRS | ISIT | JKOONS | TBROWN99 | JBROSKI | JLUCAS1 | Silver | Non S-Ox | 212 | No | Yes | In-House | JKOONS | TBROWN99 | Manufacturing Staffs | - | GPIRS (Global Prototype Inventory Requisition and Scheduling System)GPIRS is an application that supports the prototype vehicle development process globally, and Powertrain development process for Europe. Supports prototype vehicle business processes including; Scheduling, Bill of Material, Part Ordering, Part Warehousing. and Shipping. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
23753 | BlueOvalNow | In Production | BON | OCETO | TSWEEN16 | KADOMKAI | GWHOLIHA | MBALAN2 | Copper | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | TSWEEN16 | DDESAI | Communications | Staffs IT | BlueOvalNow (SocialChorus) is a mobile app that connects employees to a daily digest of work news and content. | 2 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
18599 | GPD Enhanced MSL | In Production | GEMSL | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | JLUCAS1 | Silver | Non S-Ox | 221 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Manufacturing Staffs | - | Source of Product Definition data for FoE downstream business (eg. MP&L, Marketing & Sales). Scope also covers update of MFAL EU VL data from PDO feed. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
509 | GPAM/GTFM | In Production | EuMP-GPAMG | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | General Purpose Analysis Module (GPAM) is an application that processes the vehicle specification from customer areas, as well as the data from the system areas in a common format. The functions are Feasibility - to check feasibility of orders , Solve - to convert EOCs to SFIs , Physical VIN creation - Create physical Vehicle Identification Number, Patent Plate Creation - creation of patent plate GPAM is used by number applications based on their needs. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
17702 | GPA - Manufacturing FPS Action Plan Management | In Production | GPA | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Silver | Non S-Ox | 111 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Staffs | - | FPS measurable Toll. The system manages the improvement opportunities identified in the work groups (GNTs). Global system which supports Manufacturing plants in all regions : SA, NA, Europe and APA. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
56317 | AutoPay Online Plus | In Production | AOP | FORD CREDIT | JBENITO | SHODGSO9 | ADELUIS | AGALLAG9 | Silver | Non S-Ox | 333 | No | Yes | - | JBENITO | SHODGSO9 | Ford Credit Services | - | Application provides an interface to the BACS payment clearing system in the UK. It provides a service for Ford of Britain FCE systems (Lending Automotive, BLESS and Major Daily Rental Operations). | 3 |  | YES | 1 | SRAISIN1 | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
17702 | GPA - Manufacturing FPS Action Plan Management | In Production | GPA | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Silver | Non S-Ox | 111 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Staffs | - | FPS measurable Toll. The system manages the improvement opportunities identified in the work groups (GNTs). Global system which supports Manufacturing plants in all regions : SA, NA, Europe and APA. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
21819 | GOTD - Transitional Data Interface | In Production | GOTD-TDI | M&S TECH | FHIRSH | SBINO | VSRINI23 | PSATISH2 | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | Global Service Interfaces (GOTD-Service Interfaces) is a service module of Global -OTD, which abstracts all the interfaces of Global - OTD Applications with multiple Data sources (e.g. dealer, customer, sales & contracting, vehicle & commodity allocations), in order to provide information, which are gathered and collected from multiple applications from Ford Motor Company at any time across the Globe. | 166 |  | YES | 4 | NKANDULA | PLM | Datastage | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | DA
21819 | GOTD - Transitional Data Interface | In Production | GOTD-TDI | M&S TECH | FHIRSH | SBINO | VSRINI23 | PSATISH2 | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | Global Service Interfaces (GOTD-Service Interfaces) is a service module of Global -OTD, which abstracts all the interfaces of Global - OTD Applications with multiple Data sources (e.g. dealer, customer, sales & contracting, vehicle & commodity allocations), in order to provide information, which are gathered and collected from multiple applications from Ford Motor Company at any time across the Globe. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
18231 | ATNPC Website | In Production | ATNPC | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Copper | Non S-Ox | 222 | Yes | No | In-House | SKING68 | JLYNN1 | New Model Programs | Industrial System IT | Automatic Transmission New Product Center Website | 10 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
21819 | GOTD - Transitional Data Interface | In Production | GOTD-TDI | M&S TECH | FHIRSH | SBINO | VSRINI23 | PSATISH2 | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | Global Service Interfaces (GOTD-Service Interfaces) is a service module of Global -OTD, which abstracts all the interfaces of Global - OTD Applications with multiple Data sources (e.g. dealer, customer, sales & contracting, vehicle & commodity allocations), in order to provide information, which are gathered and collected from multiple applications from Ford Motor Company at any time across the Globe. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
21935 | GOTD - Scheduling Analysis & Control | In Production | GOTD - SAC | M&S TECH | FHIRSH | SBINO | WPIERSON | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | Managed by 3rd Party Purchased Service | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | This COTS top hat function will support proactive constraint identification, allowing for better allocation strategies and global capacity optimization to support 100% first time through order scheduling, and accurate supplier demand signals. |  |  | YES | 4 | NKANDULA | PLM | Java Struts | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-09-17 | Complete | Blue | 2024-12-15 | 2024-09-17 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
21935 | GOTD - Scheduling Analysis & Control | In Production | GOTD - SAC | M&S TECH | FHIRSH | SBINO | WPIERSON | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | Managed by 3rd Party Purchased Service | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | This COTS top hat function will support proactive constraint identification, allowing for better allocation strategies and global capacity optimization to support 100% first time through order scheduling, and accurate supplier demand signals. |  |  | YES | 4 | NKANDULA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
14080 | APDM - Analytical Powertrain Data Manager | In Production | APDM | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | APDM is a data management system that stores non-geometric Powertrain and PD engineering data. | 6 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21935 | GOTD - Scheduling Analysis & Control | In Production | GOTD - SAC | M&S TECH | FHIRSH | SBINO | WPIERSON | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | Managed by 3rd Party Purchased Service | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | This COTS top hat function will support proactive constraint identification, allowing for better allocation strategies and global capacity optimization to support 100% first time through order scheduling, and accurate supplier demand signals. |  |  | YES | 4 | NKANDULA | PLM | WAS | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-09-17 | Complete | Blue | 2024-12-15 | 2024-09-17 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
22036 | GOTD - Order Production Scheduling & Sequencing | In Production | GOTD -OPSS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | OPSS streamlines, simplifies and enhances the Replanning and Sequencing business processes and supporting systems within the Marketing & Sales and Material Planning & Logistics organizations. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q2 2027 | Modernize to Cloud Databases | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | SQL
21714 | AP Weights & Measures | In Production | AP W&M | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Copper | Non S-Ox | 121 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Tactical solution to manage vehicle weights and measures. | 8 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-06 | 2024-12-06 | 2024-12-06 | Complete | Blue | 2024-12-20 | 2024-12-20 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0 | GCP Migration | Priya | 2025-03-10 |  |  | App tier & DB moved to GCP in 2024. This was a complete rewrite to GCP with DB migrated to GCP PostgreSQL | No | VM
25047 | GOTD - Order Integration Services | In Production | GOTD - OIS | M&S TECH | FHIRSH | VDONTHY | JKHARE | CKEMPSKI | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | This application is to bring data into the Global Order Bank (GOB) and provide data to all consumers including GOTD. Previously known as SICON. |  |  | YES | 5 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
25047 | GOTD - Order Integration Services | In Production | GOTD - OIS | M&S TECH | FHIRSH | VDONTHY | JKHARE | CKEMPSKI | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | This application is to bring data into the Global Order Bank (GOB) and provide data to all consumers including GOTD. Previously known as SICON. |  |  | YES | 5 | NKANDULA | PLM | Java Struts | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
25047 | GOTD - Order Integration Services | In Production | GOTD - OIS | M&S TECH | FHIRSH | VDONTHY | JKHARE | CKEMPSKI | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | This application is to bring data into the Global Order Bank (GOB) and provide data to all consumers including GOTD. Previously known as SICON. |  |  | YES | 5 | NKANDULA | PLM | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | SQL | [5 empty] | No | SQL
23928 | Analytics X Planning | In Development | AXP | EPEO | SKULKA52 | MWILLI20 | SBATHISH | SBATHISH | Copper | Non S-Ox | 111 | No | Yes | In-House | CMIRABIT | MWILLI20 | Enterprise Technology | EPEO | Application to track IT data and generate utilization reports | 1 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
25047 | GOTD - Order Integration Services | In Production | GOTD - OIS | M&S TECH | FHIRSH | VDONTHY | JKHARE | CKEMPSKI | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | This application is to bring data into the Global Order Bank (GOB) and provide data to all consumers including GOTD. Previously known as SICON. |  |  | YES | 5 | NKANDULA | PLM | WAS | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
21682 | GOTD - Order Generation | In Production | GOTD -OG | M&S TECH | FHIRSH | SBINO | VSRINI23 | PSATISH2 | Silver | Non S-Ox | 232 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | OG (Order Generation) application forecasts and generate orders by utilize Sales History and fast turn data as well as a variety of established data sources to predict trends at a dealer level and target specific customer demand requirements. It provides a set of completely specified orders that are selected to turn as quickly as possible given the expected inventory mix rates. Purpose: Recommend orders to dealers to meet customer demand. Recommend Feature Allocation to Dealers. Achieving reduced days on lot through forecasting buildable and saleable orders. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
21682 | GOTD - Order Generation | In Production | GOTD -OG | M&S TECH | FHIRSH | SBINO | VSRINI23 | PSATISH2 | Silver | Non S-Ox | 232 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | OG (Order Generation) application forecasts and generate orders by utilize Sales History and fast turn data as well as a variety of established data sources to predict trends at a dealer level and target specific customer demand requirements. It provides a set of completely specified orders that are selected to turn as quickly as possible given the expected inventory mix rates. Purpose: Recommend orders to dealers to meet customer demand. Recommend Feature Allocation to Dealers. Achieving reduced days on lot through forecasting buildable and saleable orders. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 75% | 25% | [12 empty] | No | SQL
12334 | AIM on the WEB- | In Production | AIMWEB | ISIT | JKOONS | TBROWN99 | JBROSKI | ISIDDIQ6 | Silver | Non S-Ox | 312 | No | Yes | In-House | JKOONS | TBROWN99 | New Model Programs | Industrial System IT | The Automated Issues Management system is designed to provide structured management of issues, with proper enforcement of key business rules. The initial version of AIM on the Web was created to manage Vehicle Launch Team issues, which was the primary issue type managed by the Client/Server version of AIM. The primary business owner for the VLT module of AIM is A&ME/VO Global Quality New Model Programs. In 2011, AIM became the primary issues management tool for Powertrain launch programs. Integrated into AIM on the Web is the Drive Evaluation Management System (DEMS). This module is used to track Voice of the Customer fleet vehicles, drives, service actions and other data and to ensure proper capture and resolution of all engineering concerns for the drive fleets. The Durability Information System (DURIS) is used for Proving Ground test scheduling, program status, vehicle incident and concern reporting, driver assignment and test status. DURIS was added into AIMWEB in early 2013. | 17 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | VM
21682 | GOTD - Order Generation | In Production | GOTD -OG | M&S TECH | FHIRSH | SBINO | VSRINI23 | PSATISH2 | Silver | Non S-Ox | 232 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | OG (Order Generation) application forecasts and generate orders by utilize Sales History and fast turn data as well as a variety of established data sources to predict trends at a dealer level and target specific customer demand requirements. It provides a set of completely specified orders that are selected to turn as quickly as possible given the expected inventory mix rates. Purpose: Recommend orders to dealers to meet customer demand. Recommend Feature Allocation to Dealers. Achieving reduced days on lot through forecasting buildable and saleable orders. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
21334 | GOTD - Order Entry and Management | In Production | GOTD-OMCC | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | CKEMPSKI | Bronze | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Order Entry and Management provides the UI and supporting service functionality that enables dealers, internal user and consumers to create or amend orders in the Global Orderbank. Additional functionality will be provided to support reduced inventory management for the Enterprise and to enable any authorised stakeholder to search for and view an order they are interested in. Several key business functions are in scope including bulk order management, plus various administrative actions such as creating and managing template orders and work in progress. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-04-30 |  | In-Progress | Green | 2025-07-29 |  | Planned |  | No | 100% | 75% | 25% | [5 empty] | Java 21 | [5 empty] | No | Java < v21
21334 | GOTD - Order Entry and Management | In Production | GOTD-OMCC | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | CKEMPSKI | Bronze | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Order Entry and Management provides the UI and supporting service functionality that enables dealers, internal user and consumers to create or amend orders in the Global Orderbank. Additional functionality will be provided to support reduced inventory management for the Enterprise and to enable any authorised stakeholder to search for and view an order they are interested in. Several key business functions are in scope including bulk order management, plus various administrative actions such as creating and managing template orders and work in progress. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
18560 | Active Directory Certificate Services (ADCS) | In Production | CA | EPEO | NOKEEFE | VNACHIMU | BSARAV20 | GSIENKIE | Silver | Non S-Ox | 232 | No | Yes | COTS | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | Active Directory Certificate Services is the Windows OS-based software which issues digital certificates for use within the Ford computing environment. | 71 |  | YES | 2 | SWALIMBE | PLM | VM | Q4 2025 | EDC New Hypervisor | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | VM
21334 | GOTD - Order Entry and Management | In Production | GOTD-OMCC | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | CKEMPSKI | Bronze | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Order Entry and Management provides the UI and supporting service functionality that enables dealers, internal user and consumers to create or amend orders in the Global Orderbank. Additional functionality will be provided to support reduced inventory management for the Enterprise and to enable any authorised stakeholder to search for and view an order they are interested in. Several key business functions are in scope including bulk order management, plus various administrative actions such as creating and managing template orders and work in progress. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-04-30 |  | In-Progress | Green | 2025-07-29 |  | Planned |  | No | 100% | 75% | 25% | [5 empty] | Java 21 | [5 empty] | No | Java < v21
50120 | GOTD - Global Wholesale Services | In Production | GOTD-GWS | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Contains services to support Global Wholesale processes and integrate with regional tooling. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | 2024 |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | Its already completed as part of PCF migration. | No | Java < v21
50120 | GOTD - Global Wholesale Services | In Production | GOTD-GWS | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Contains services to support Global Wholesale processes and integrate with regional tooling. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-10-20 | 2024-10-20 | Complete | Blue | 2024-11-19 | 2024-11-19 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | Its already completed as part of PCF migration. | No | SQL
19035 | VEV RFID | In Production | VEV RFID | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Copper | Non S-Ox | 11 | Yes | No | In-House | GHERMAN | KCHRIST2 | Enterprise Technology | Industrial System IT | An open standards based Radio Frequency Identification (RFID) technologies that will provide time stamped, zone based, vehicle visibility and location information to the staff and operators of the Allen Park Test Lab (APTL). An RFID based vehicle tracking solution. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | SQL
50924 | GOTD - Global Order Management Services | In Production | GOMS | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Services to provide Order Management capabilities |  |  | YES | 4 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
50924 | GOTD - Global Order Management Services | In Production | GOMS | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | 222 | Services to provide Order Management capabilities |  | Springboot | YES | 4 | NKANDULA | PLM | Java < v21 | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | Java 17 |  |  |  |  | Team is working for Spring/Java Verion upgrade | No | Java < v21
50924 | GOTD - Global Order Management Services | In Production | GOMS | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Services to provide Order Management capabilities |  |  | YES | 4 | NKANDULA | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | Cloud SQL PostgreSQL |  |  |  |  | Team is working on SQL server to Postgres Upgrade | No | SQL
19035 | VEV RFID | In Production | VEV RFID | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Copper | Non S-Ox | 11 | Yes | No | In-House | GHERMAN | KCHRIST2 | Enterprise Technology | Industrial System IT | An open standards based Radio Frequency Identification (RFID) technologies that will provide time stamped, zone based, vehicle visibility and location information to the staff and operators of the Allen Park Test Lab (APTL). An RFID based vehicle tracking solution. | 10 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | VM
21336 | GOTD - Global Order Bank | In Production | GOTD - GOB | M&S TECH | FHIRSH | VDONTHY | JKHARE | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | GOTD Order Bank Management provides a central view of orders further enabling Cross-CBG OTD Build Anywhere, Sell Anywhere processes. Global Order Bank is the common repository of all new vehicle order information for all vehicles built or sold by Ford mapped to the single codification language with a common aligned representation supported by global information retention standards. |  |  | YES | 5 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
21336 | GOTD - Global Order Bank | In Production | GOTD - GOB | M&S TECH | FHIRSH | VDONTHY | JKHARE | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | GOTD Order Bank Management provides a central view of orders further enabling Cross-CBG OTD Build Anywhere, Sell Anywhere processes. Global Order Bank is the common repository of all new vehicle order information for all vehicles built or sold by Ford mapped to the single codification language with a common aligned representation supported by global information retention standards. |  |  | YES | 5 | NKANDULA | PLM | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
21336 | GOTD - Global Order Bank | In Production | GOTD - GOB | M&S TECH | FHIRSH | VDONTHY | JKHARE | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | GOTD Order Bank Management provides a central view of orders further enabling Cross-CBG OTD Build Anywhere, Sell Anywhere processes. Global Order Bank is the common repository of all new vehicle order information for all vehicles built or sold by Ford mapped to the single codification language with a common aligned representation supported by global information retention standards. |  |  | YES | 5 | NKANDULA | PLM | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
12271 | Web Service Modules | In Production | WSMOD | M&S TECH | KHEMANT | KDANDUPA | AKURAMNA | JPOTTE60 | Gold | Non S-Ox | 122 | No | Yes | In-House | KHEMANT | KDANDUPA | Enterprise Technology | - | WSMOD(Web Service Modules) is collection of web services that provides for the retrieval of vehicle related information. Services include VIN Decoding, Genuine Scheduled Maintenance. Web service modules are designed to be re-usable functions that all Ford Trustmark brands and regions use in their consumer/dealer facing web applications and mobile applications. | 4 |  | YES | 4 | NKANDULA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-02 | Complete | Blue | 2024-12-15 | 2025-01-24 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | GCP Migration |  |  |  |  | Already done, as part of PCF migration | Yes | VM
21336 | GOTD - Global Order Bank | In Production | GOTD - GOB | M&S TECH | FHIRSH | VDONTHY | JKHARE | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | GOTD Order Bank Management provides a central view of orders further enabling Cross-CBG OTD Build Anywhere, Sell Anywhere processes. Global Order Bank is the common repository of all new vehicle order information for all vehicles built or sold by Ford mapped to the single codification language with a common aligned representation supported by global information retention standards. |  |  | YES | 5 | NKANDULA | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
50418 | GOTD - Global Allocation | In Production | GAT | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | 222 | GOTD - Allocation Product, to support Dealer allocations |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | Q4 2024 | 0 | Modernize | 2024-12-15 | 2024-08-11 | 2024-08-11 | Complete | Blue | 2024-10-01 | 2024-10-01 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | Its already completed as part of PCF migration | No | Java < v21
50418 | GOTD - Global Allocation | In Production | GAT | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | GOTD - Allocation Product, to support Dealer allocations |  |  | YES | 3 | NKANDULA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-08-11 | 2024-08-11 | Complete | Blue | 2024-10-01 | 2024-10-01 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | Its already completed as part of PCF migration | No | SQL
19238 | METRICS MANAGEMENT SYSTEM | In Production | MMS | ISIT | JKOONS | DMEENAK2 | TLEE7 | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | DMEENAK2 | Enterprise Technology | Industrial System IT | The Metrics Management System (MMS) will enable us to effectively measure and manage these critical and expensive software resources. MMS Reporting Repository enables the company to manage costs as well as assets by monitoring the software usage patterns of engineers by centrally compiling and analyzing relevant usage data. Through analysis of this data, we will be able to identify and correct areas of non-compliance, gaps in inventory versus usage - where cost savings are possible, and opportunities for enterprise license changes that would benefit the company in both the short and the long term. Of similar criticality is the need to identify where a shift in application licenses is needed. For example, some features may be under purchased (Under Purchased) today resulting in unproductive license denials, while other features have been overbought and are therefore not used effectively. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | Saran | 2025-03-06 |  |  |  | No | Java < v21
50302 | GOTD - Customs | In Production | Customs | M&S TECH | FHIRSH | VDONTHY | MCRABB | PSATISH2 | Bronze | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Application to support Customs business process for imports/exports and aiding in the definition of transfer pricing. Used by GOTD and FTC & GTS |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
19238 | METRICS MANAGEMENT SYSTEM | In Production | MMS | ISIT | JKOONS | DMEENAK2 | TLEE7 | GRAO3 | Copper | Non S-Ox | 211 | No | Yes | In-House | JKOONS | DMEENAK2 | Enterprise Technology | Industrial System IT | The Metrics Management System (MMS) will enable us to effectively measure and manage these critical and expensive software resources. MMS Reporting Repository enables the company to manage costs as well as assets by monitoring the software usage patterns of engineers by centrally compiling and analyzing relevant usage data. Through analysis of this data, we will be able to identify and correct areas of non-compliance, gaps in inventory versus usage - where cost savings are possible, and opportunities for enterprise license changes that would benefit the company in both the short and the long term. Of similar criticality is the need to identify where a shift in application licenses is needed. For example, some features may be under purchased (Under Purchased) today resulting in unproductive license denials, while other features have been overbought and are therefore not used effectively. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | Saran | 2025-03-06 |  |  |  | No | Java < v21
367 | GOLFF-Generic Order Level Feature Forecasting | In Production | EuMP-GOLFF | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | GOLFF is a forecasting application used for material forecast for the next 18 months. The main purpose of GOLFF application is to send a 6 months forecast file to CMMS3. CMMS3 in turn uses it for supplier release. GOLFF reads the entity data from SPCPS and deducts the year to date actual and the segmented in-plant orders, this produces a balance-to-go volume for each Market entity. GOLFF then overlays orders from the Sales bank with Estimated Build dates/periods into the appropriate dates and then uses the remaining undated orders to fill in more gaps. The resultant balance-to-go is then forecast by GOLFF using the most recent historical data (3 months Demand Intelligence or DI) thus completing the requirements through the whole future 6 month period. The 80 column order images created in GOLFF are then exploded via GPAM Solve table to generate SFI volumes which in turn are converted into actual manufacturing parts. The parts volume data is then transmitted through CMMS3 to all Suppliers on a weekly basis. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q4 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
99 | GOASIS : Global Online Automotive Service Info Sys | In Production | GOASIS | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 222 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Provides latest vehicle and technical service information for a specific vin. Authoring application for SSM, (Special Service Information) BCM (Broadcast Messages) and TSB (Techical Service Bulletins). |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
99 | GOASIS : Global Online Automotive Service Info Sys | In Production | GOASIS | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 222 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Provides latest vehicle and technical service information for a specific vin. Authoring application for SSM, (Special Service Information) BCM (Broadcast Messages) and TSB (Techical Service Bulletins). |  |  | YES | 4 | RKENNEL | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
99 | GOASIS : Global Online Automotive Service Info Sys | In Production | GOASIS | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 222 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Provides latest vehicle and technical service information for a specific vin. Authoring application for SSM, (Special Service Information) BCM (Broadcast Messages) and TSB (Techical Service Bulletins). |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
99 | GOASIS : Global Online Automotive Service Info Sys | In Production | GOASIS | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 222 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Provides latest vehicle and technical service information for a specific vin. Authoring application for SSM, (Special Service Information) BCM (Broadcast Messages) and TSB (Techical Service Bulletins). |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | WAS |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
11760 | GOaLS - Global Ordering and Logistics System | In Production | GOaLS | M&S TECH | FHIRSH | NGIRISH | NMATTA2 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | GOaLS is the system used by Export & Growth dealers, APA dealers and affiliates to order multiple sourced vehicles, review status, order guides and report sales. CIA 2,2,2 |  |  | YES | 7 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
11760 | GOaLS - Global Ordering and Logistics System | In Production | GOaLS | M&S TECH | FHIRSH | NGIRISH | NMATTA2 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | GOaLS is the system used by Export & Growth dealers, APA dealers and affiliates to order multiple sourced vehicles, review status, order guides and report sales. CIA 2,2,2 |  |  | YES | 7 | NKANDULA | PLM | Oracle | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-23 | Complete | Blue | 2024-12-15 | 2024-12-23 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
11760 | GOaLS - Global Ordering and Logistics System | In Production | GOaLS | M&S TECH | FHIRSH | NGIRISH | NMATTA2 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | GOaLS is the system used by Export & Growth dealers, APA dealers and affiliates to order multiple sourced vehicles, review status, order guides and report sales. CIA 2,2,2 |  |  | YES | 7 | NKANDULA | PLM | Java Struts | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
11760 | GOaLS - Global Ordering and Logistics System | In Production | GOaLS | M&S TECH | FHIRSH | NGIRISH | NMATTA2 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | GOaLS is the system used by Export & Growth dealers, APA dealers and affiliates to order multiple sourced vehicles, review status, order guides and report sales. CIA 2,2,2 |  |  | YES | 7 | NKANDULA | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11760 | GOaLS - Global Ordering and Logistics System | In Production | GOaLS | M&S TECH | FHIRSH | NGIRISH | NMATTA2 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | GOaLS is the system used by Export & Growth dealers, APA dealers and affiliates to order multiple sourced vehicles, review status, order guides and report sales. CIA 2,2,2 |  |  | YES | 7 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
20210 | Customs Import Security Filing 10+2 | In Production | eISF | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Silver | Non S-Ox | 113 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Customs Import Security Filing 10+2 screens to communicate with the US government |  |  | YES | 2 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-18 | 2024-12-18 | 2024-12-18 | Complete | Blue | 2024-12-18 | 2024-12-18 | Complete |  | No | [8 empty] | Decommission | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
11760 | GOaLS - Global Ordering and Logistics System | In Production | GOaLS | M&S TECH | FHIRSH | NGIRISH | NMATTA2 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | GOaLS is the system used by Export & Growth dealers, APA dealers and affiliates to order multiple sourced vehicles, review status, order guides and report sales. CIA 2,2,2 |  |  | YES | 7 | NKANDULA | PLM | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
12103 | Global Warranty Measurement System | In Production | GWMS | FORD PRO & FCSD TECH | KELY8 | MMORSE3 | JSOPFE | ADEVEND1 | Copper | Non S-Ox | 211 | Yes | No | In-House | KELY8 | KELY8 | Ford Customer Service | - | This application provides dealers with access to their warranty trends reporting information. This allows dealers to better manage their warranty performance. Dealer can select a report called 126EZ and GWMSEZ to view their data and allow them to view trends in their warranty data over a period of time. Customer is managing the web site provider (IBI) |  |  | YES | 2 | RKENNEL | PLM | Oracle | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
20703 | Vehicle Incentive Data Service | In Production | VIDS | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Gold | Non S-Ox | 211 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | The VIDS application provides web service to downstream systems to obtain Vehicle Incentive data | 1 |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
12103 | Global Warranty Measurement System | In Production | GWMS | FORD PRO & FCSD TECH | KELY8 | MMORSE3 | JSOPFE | ADEVEND1 | Copper | Non S-Ox | 211 | Yes | No | In-House |  |  | Ford Customer Service | - | This application provides dealers with access to their warranty trends reporting information. This allows dealers to better manage their warranty performance. Dealer can select a report called 126EZ and GWMSEZ to view their data and allow them to view trends in their warranty data over a period of time. Customer is managing the web site provider (IBI) |  | Springboot | YES | 3 | RKENNEL | PLM | Java < v21 | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
20814 | Global Warranty Finance System | In Production | GWFS | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Common Global IT tool to support Warranty Reserve Process. - Supports consistent application of Warranty Rules of The Road (RoTR). - Elimination of complex manual processes on high risk reserve -- improve control environment. (Wholly Excel based today). - Provides greater granularity at market / vehicle line level to support PF3 reporting and concurrent close (US and Local GAAP). - Enhanced cost analysis reporting based on physicals. - Key enabler to reserve centralization to Europe (delivers cash tax benefit). - Increased employee satisfaction | 711 |  | YES | 5 | TSWEEN16 | PLM | WebFocus | Q2 2025 | Migrate to QlikSense | Modernize | 2025-06-30 | 2025-06-30 |  | In-Progress | Red | 2025-09-28 |  | Planned |  | Yes | 100% | 50% | 25% | 25% | 25% | 25% | 25% |  | QlikSense | [5 empty] | No | DA
20814 | Global Warranty Finance System | In Production | GWFS | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Common Global IT tool to support Warranty Reserve Process. - Supports consistent application of Warranty Rules of The Road (RoTR). - Elimination of complex manual processes on high risk reserve -- improve control environment. (Wholly Excel based today). - Provides greater granularity at market / vehicle line level to support PF3 reporting and concurrent close (US and Local GAAP). - Enhanced cost analysis reporting based on physicals. - Key enabler to reserve centralization to Europe (delivers cash tax benefit). - Increased employee satisfaction |  |  | YES | 5 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | Yes | 100% | 50% | 25% |  |  |  | 25% |  | Cloud Run | Praveen | 2025-03-06 |  |  |  | No | Java < v21
20814 | Global Warranty Finance System | In Production | GWFS | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Common Global IT tool to support Warranty Reserve Process. - Supports consistent application of Warranty Rules of The Road (RoTR). - Elimination of complex manual processes on high risk reserve -- improve control environment. (Wholly Excel based today). - Provides greater granularity at market / vehicle line level to support PF3 reporting and concurrent close (US and Local GAAP). - Enhanced cost analysis reporting based on physicals. - Key enabler to reserve centralization to Europe (delivers cash tax benefit). - Increased employee satisfaction |  |  | YES | 5 | TSWEEN16 | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Red | 2025-09-28 |  | Planned |  | Yes | 100% | 50% | 25% |  |  |  | 25% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-06 |  |  |  | No | SQL
20210 | Customs Import Security Filing 10+2 | In Production | eISF | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Silver | Non S-Ox | 113 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Customs Import Security Filing 10+2 screens to communicate with the US government |  |  | YES | 2 | BWUNNAVA | PLM | WAS | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-18 | 2024-12-18 | 2024-12-18 | Complete | Blue | 2024-12-18 | 2024-12-18 | Complete |  | No | [8 empty] | Decommission | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
20814 | Global Warranty Finance System | In Production | GWFS | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Common Global IT tool to support Warranty Reserve Process. - Supports consistent application of Warranty Rules of The Road (RoTR). - Elimination of complex manual processes on high risk reserve -- improve control environment. (Wholly Excel based today). - Provides greater granularity at market / vehicle line level to support PF3 reporting and concurrent close (US and Local GAAP). - Enhanced cost analysis reporting based on physicals. - Key enabler to reserve centralization to Europe (delivers cash tax benefit). - Increased employee satisfaction |  |  | YES | 5 | TSWEEN16 | PLM | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | Yes | 100% | 50% | 25% |  |  |  | 25% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | Java < v21
21380 | Global Volume Mix and Rate | In Production | GVMR | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Bronze | Non S-Ox | 322 | No | Yes | COTS | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | US and EU Marketing and Sales teams use a separate system and set of processes to collect, calculate and analyze actual and forecasted volumes, vehicle mix and option take rates. This process is also done manually throughout the globe in Canada, Mexico, South America and Asia Pacific. Both the US and EU systems need significant upgrades to operate properly and efficiently. There are discrepancies in the business practices which must be resolved. Manual effort takes up many resources to retrieve data for both systems. Additionally, neither of these systems supports the five year business planning forecasting window or a Fleet vs. Retail forecast split. GVMR is a standardized, lean, flexible global system to collect and report volume/mix/rate and revenue data. The system would enforce common business practices such as budget performance calculations yet allow for global differences such as vehicle definition. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
20481 | Body-Shop Information System | In Production | BIS | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Engineering | Industrial System IT | Electronic Maintenance Manuals. Replaces Paper Manuals. Contains documentation for Ford assembly and stamping plant welding assembly automation. Users are plant skilled trades personnel. Access through Ford Intranet. | 3 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12764 | Global Vehicle Programming | In Production | GVP | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Silver | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | Global Vehicle Programming - US Based - reporting of Actual and Forecast volume and mix rate data from North American operational systems (CPV2, 9270, Pseudo Order). |  |  | YES | 3 | NKANDULA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
12764 | Global Vehicle Programming | In Production | GVP | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Silver | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | Global Vehicle Programming - US Based - reporting of Actual and Forecast volume and mix rate data from North American operational systems (CPV2, 9270, Pseudo Order). |  |  | YES | 3 | NKANDULA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
20631 | PD Multi Application Access Request System | In Production | PDMAARS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | GRAO3 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JKOONS | TBROWN99 | Advanced PD and Tech | Industrial System IT | D&R engineers have to work with multiple IT systems and tools for their job.Each tool requires a separate access control request and registration process.The access request user interface is part of each tool and there is no central place to each tool for access.Ideally D&R engineers could submit a single request for access and can track the progress of their request(s).Approvers/Authorizers can manage and update status of the requests submitted to them.This central place can also be used to link to the training requirements or other pre-requisites necessary for each tool before requesting access.It is a web-based system where users can choose the applications they need access to and submit the information required by each application for granting access.The system will send email notification to approvers forwarding the information entered by the engineer.Approvals recorded in the system will be used for auditing and re-authorization. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-14 | 2024-12-14 | 2024-12-14 | Complete | Blue | 2024-12-14 | 2024-12-14 | Complete |  | No | [8 empty] | Decommission | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
24281 | Global Vehicle Management System | In Production | GVMS | EVDD | MJAMWAL | TPINTO3 | BCHITTI | CSUBHA1 | Platinum | Non S-Ox | 223 | No | Yes | In-House | MJAMWAL | MJAMWAL | Advanced PD and Tech | - | Global Vehicle Management System |  |  | YES | 4 | MJONE308 | PLM | Oracle | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
24281 | Global Vehicle Management System | In Production | GVMS | EVDD | MJAMWAL | TPINTO3 | BCHITTI | CSUBHA1 | Platinum | Non S-Ox | 223 | No | Yes | In-House | MJAMWAL | TPINTO3 | Advanced PD and Tech | - | Global Vehicle Management System |  |  | YES | 4 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
20631 | PD Multi Application Access Request System | In Production | PDMAARS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | GRAO3 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JKOONS | TBROWN99 | Advanced PD and Tech | Industrial System IT | D&R engineers have to work with multiple IT systems and tools for their job.Each tool requires a separate access control request and registration process.The access request user interface is part of each tool and there is no central place to each tool for access.Ideally D&R engineers could submit a single request for access and can track the progress of their request(s).Approvers/Authorizers can manage and update status of the requests submitted to them.This central place can also be used to link to the training requirements or other pre-requisites necessary for each tool before requesting access.It is a web-based system where users can choose the applications they need access to and submit the information required by each application for granting access.The system will send email notification to approvers forwarding the information entered by the engineer.Approvals recorded in the system will be used for auditing and re-authorization. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-14 | 2024-12-14 | 2024-12-14 | Complete | Blue | 2024-12-14 | 2024-12-14 | Complete |  | No | [8 empty] | Decommission | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
24281 | Global Vehicle Management System | In Production | GVMS | EVDD | MJAMWAL | TPINTO3 | BCHITTI | CSUBHA1 | Platinum | Non S-Ox | 223 | No | Yes | In-House | MJAMWAL | TPINTO3 | Advanced PD and Tech | - | Global Vehicle Management System |  |  | YES | 4 | MJONE308 | PLM | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
21150 | Global vehicle Distribution Solution | In Production | GVDS | ISIT | VVIJAY55 | RADAM10 | DASHOK1 | SSENTH15 | Gold | S-Ox In Scope | 232 | No | Yes | COTS | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | The Global Vehicle Distribution Solution (GVDS) application has been established in order to support the global vehicle distribution process. Main goal of the application is the implementation of logistics optimization for finished vehicles. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green | 2025-06-30 |  | Planned |  | No | 100% | 100% | 50% | 50% | 100% | 25% | 50% |  | SaaS | Saran | 2025-03-17 |  |  | App is moving to SaaS | No | SQL
20627 | Supplier APQP Assessment System | In Production | eAPQP | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 321 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Automated Supplier APQP Assessment System is a key enabler for integration of suppliers into GPDS and the company global platform strategies. Suppliers all over the world will be producing common parts for common vehicle architectures. Supplier status information must be communicated and analyzed by different parties in different regions at the same time. Progra m decisionmaking will require accurate information from suppliers in an efficient and timely manner. It also supports one of the key components of the Global Product Development System (GPDS), which is the Supplier Engagement Process. The Supplier Engagement Process defines the disciplined set of work activities from the point of sourcing to Job1. This work activity ensures ontime part readiness at the desired quality levels. | 12 |  | YES | 5 | TSWEEN16 | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-02-14 | 2024-12-20 | 2024-12-20 | Complete | Blue | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Praveen | 2025-03-04 |  |  |  | No | VM
20631 | PD Multi Application Access Request System | In Production | PDMAARS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | GRAO3 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JKOONS | TBROWN99 | Advanced PD and Tech | Industrial System IT | D&R engineers have to work with multiple IT systems and tools for their job.Each tool requires a separate access control request and registration process.The access request user interface is part of each tool and there is no central place to each tool for access.Ideally D&R engineers could submit a single request for access and can track the progress of their request(s).Approvers/Authorizers can manage and update status of the requests submitted to them.This central place can also be used to link to the training requirements or other pre-requisites necessary for each tool before requesting access.It is a web-based system where users can choose the applications they need access to and submit the information required by each application for granting access.The system will send email notification to approvers forwarding the information entered by the engineer.Approvals recorded in the system will be used for auditing and re-authorization. |  |  | YES | 4 | BWUNNAVA | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-14 | 2024-12-14 | 2024-12-14 | Complete | Blue | 2024-12-14 | 2024-12-14 | Complete |  | No | [8 empty] | Decommission | Ramesh | 2025-03-10 |  |  |  | No | SQL
22012 | Global Unified Contact Center Enterprise | Planned | GUCCE | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Silver | Non S-Ox | 223 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | - | Cisco based IP Contact Center infrastructure supporting Ford Contact Center operations across the globe. |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
22012 | Global Unified Contact Center Enterprise | Planned | GUCCE | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Silver | Non S-Ox | 223 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | - | Cisco based IP Contact Center infrastructure supporting Ford Contact Center operations across the globe. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53633 | Siveillance Viewpoint | In Development | Viewpoint | EPEO | ARAJKUMA | LEHLERS1 | JBRETT1 | ESTILESK | - | Non S-Ox | - | Yes | No | Managed by 3rd Party Purchased Service | ARAJKUMA | IKOVALEV | Ford Land | - | Physical security information management (PSIM) system hosted on-site on hardware provided by the vendor Siemens. PSIM uses technology and methods to import sensors and integrate data seamlessly. A unique, logical structure and user interface ensure optimized decision-making and incident management, increasing safety and security for a sites employees and visitors, assuring operational continuity, and ensuring compliance to organizational security policies. | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2024 | Complete Migration to SaaS | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned | [17 empty] | VM
12065 | Scopus Case Management | In Production | SCOPUS | OCETO | TSWEEN16 | NABBAS | MKOMATH1 | MBALAN2 | Bronze | Non S-Ox | 321 | No | Yes | In-House | DDESAI | NABBAS | Human Resources | - | Case Management Software System which supports the HR Benefits Office | 1 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | No VMs in latest VM Data file | No | VM
51682 | Global Translation Handler Interface | In Production | GTHI | I-ERP | SFRANCI8 | SDHANAL3 | MWARRE10 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Global Translation Handler Interface extracts the feeds with pricing information from VI&D and maps Sales codes to WERS codes with pricing data if available. Then, creates the XML message in the format required by SAP and sends data to SAP or other systems for sales order creation. This application uses SOE VOLFMS webservice to map Sales codes to WERS codes. This interface assumes VOLFMS to return WERS codes from every sales code given as INPUT - every Sales code on the Order is mapped to WERS in SOE. There is no edit in this interface process which how the data is retrieved from VI&D it will be passed on to the SAP or other systems as origin on XML message format. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 50% | 25% |  |  |  | 25% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-06 |  |  |  | No | SQL
20631 | PD Multi Application Access Request System | In Production | PDMAARS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | GRAO3 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JKOONS | TBROWN99 | Advanced PD and Tech | Industrial System IT | D&R engineers have to work with multiple IT systems and tools for their job.Each tool requires a separate access control request and registration process.The access request user interface is part of each tool and there is no central place to each tool for access.Ideally D&R engineers could submit a single request for access and can track the progress of their request(s).Approvers/Authorizers can manage and update status of the requests submitted to them.This central place can also be used to link to the training requirements or other pre-requisites necessary for each tool before requesting access.It is a web-based system where users can choose the applications they need access to and submit the information required by each application for granting access.The system will send email notification to approvers forwarding the information entered by the engineer.Approvals recorded in the system will be used for auditing and re-authorization. | 4 |  | YES | 4 | BWUNNAVA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-14 | 2024-12-14 | 2024-12-14 | Complete | Blue | 2024-12-14 | 2024-12-14 | Complete |  | No | [8 empty] | Decommission | Ramesh | 2025-03-10 |  |  |  | No | VM
51682 | Global Translation Handler Interface | In Production | GTHI | I-ERP | SFRANCI8 | SDHANAL3 | MWARRE10 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | Global Translation Handler Interface extracts the feeds with pricing information from VI&D and maps Sales codes to WERS codes with pricing data if available. Then, creates the XML message in the format required by SAP and sends data to SAP or other systems for sales order creation. This application uses SOE VOLFMS webservice to map Sales codes to WERS codes. This interface assumes VOLFMS to return WERS codes from every sales code given as INPUT - every Sales code on the Order is mapped to WERS in SOE. There is no edit in this interface process which how the data is retrieved from VI&D it will be passed on to the SAP or other systems as origin on XML message format. |  | Springboot | YES | 3 | TSWEEN16 | PLM | Java < v21 | Q2 2025 | Version Upgrade | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 50% | 50% |  |  |  | 50% |  | Java 17 | Praveen | 2025-03-06 |  |  |  | No | Java < v21
53431 | Global Trading Partner Community Management | In Production | GTPCM | OCETO | TVASU | KBALAS13 | CBHARGAV | KTRACY8 | Silver | Non S-Ox | 232 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | This website is used by Data Exchange customers to request/change connections, view status of request/transactions, maintain credential and use other information required to establish data exchange to support their business need. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
15978 | PURCHASING ANNUAL ACCESS REVIEW SYSTEM | In Production | PAARS | I-ERP | SARAUJO3 | CBISWADI | TSUNDARA | SNAG1 | Bronze | Non S-Ox | 111 | No | Yes | In-House |  |  | Supply Chain | - | Purchasing Annual Access Review System | 3 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2024 | Partial Migration to GCP | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53431 | Global Trading Partner Community Management | In Production | GTPCM | OCETO | TVASU | KBALAS13 | CBHARGAV | KTRACY8 | Silver | Non S-Ox | 232 | No | Yes | In-House |  |  | Enterprise Technology | Technology & Enterprise Services (TES) | This website is used by Data Exchange customers to request/change connections, view status of request/transactions, maintain credential and use other information required to establish data exchange to support their business need. |  | Springboot | YES | 3 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
51005 | Global Trade in Valuation | In Production | GTIV | M&S TECH | RKLEINSM | MMILBOC1 | EGRIFF38 | SRUDENK2 | Gold | Non S-Ox | 221 | No | Yes | In-House | RKLEINSM | MMILBOC1 | Enterprise Technology | Marketing, Sales and Service | Global Trade In Valuation is an online Trade-In solution for all vehicle makes and models for up to 15 model years. It is a standalone application, which is intended to exist within the eCommerce experience, but can also be integrated with other internal applications. The Trade In Valuation experience is orchestrated through a series of web service calls to both internal and external APIs. The application has been generalized as much as possible to ensure consistency across regions, but has features that are specific to each region. |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
21023 | Engineering Statement of Work | In Production | PTO ESOW | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Enterprise Technology | Industrial System IT | Engineering Statement of Work (eSOW) is web-based application used to document and define the requirements between Ford Motor Company and the Supplier in support of target setting, design, development, manufacturing, production process, communication, timing, quality, documentation and warranty. This document establishes a consensus for deliverables and formats to ensure understanding between the Supplier and Ford Motor Company. The SOW also is a guide to the division of responsibilities between Ford Motor Company and the Supplier. | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-11-15 | 2024-11-15 | 2024-11-11 | Complete | Blue | 2024-12-31 | 2024-12-18 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 4 | GCP Migration | Priya | 2025-03-13 |  |  |  | No | VM
23432 | Global Track & Trace | In Production | GT&T | ISIT | VVIJAY55 | RADAM10 | SMAHES11 | SSENTH15 | Silver | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Global Track and Trace Purpose of this application is to consume non PII vehicle plant to dealership shipment data from various applications like VMACS, GLADS, GVDS, QLS and NGAVS, standardize the data into the GTT Database and transmit the data to the vendor, Freight Verify (EAMS App# 52009), who are integrated with partners and will populate a dashboard for Ford business customers and provide the ability to run reports. |  |  | NO | 5 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts |  |  | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | Priya | 2025-03-06 |  |  | This app has no struts | No | Java < v21
23432 | Global Track & Trace | In Production | GT&T | ISIT | VVIJAY55 | RADAM10 | SMAHES11 | SSENTH15 | Silver | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Global Track and Trace Purpose of this application is to consume non PII vehicle plant to dealership shipment data from various applications like VMACS, GLADS, GVDS, QLS and NGAVS, standardize the data into the GTT Database and transmit the data to the vendor, Freight Verify (EAMS App# 52009), who are integrated with partners and will populate a dashboard for Ford business customers and provide the ability to run reports. |  |  | YES | 5 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
21253 | BOM Validation ICA | In Production | BOMval_ICA | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | Manufacturing Staffs | Industrial System IT | Excel/VBA tool originally developed by PD Business consist of an Excel/VBA file stored in SharePoint and with a SQL database on the backend. It is used by MP&L PPM and D&R Engineers to confirm the Parts listed in the GPIRS BOM are accurate for a specific Build before ordering them for that Build. The tool contains Part numbers and usages retrieved from GPIRS and provides a point-in-time copy of the GPIRS BOM for an upcoming Prototype Build event. | 8 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | Ramesh |  |  |  |  | No | VM
21253 | BOM Validation ICA | In Production | BOMval_ICA | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | Manufacturing Staffs | Industrial System IT | Excel/VBA tool originally developed by PD Business consist of an Excel/VBA file stored in SharePoint and with a SQL database on the backend. It is used by MP&L PPM and D&R Engineers to confirm the Parts listed in the GPIRS BOM are accurate for a specific Build before ordering them for that Build. The tool contains Part numbers and usages retrieved from GPIRS and provides a point-in-time copy of the GPIRS BOM for an upcoming Prototype Build event. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-11-18 | 2024-11-18 | 2024-11-18 | Complete | Blue | 2025-01-20 | 2025-01-20 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Ramesh | 2025-03-10 |  |  |  | No | SQL
21382 | Paint End-of-line Dirt Detection System | In Production | PEDDS | ISIT | SKING68 | JLYNN1 | GKESAVAR | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | This system stores the images from the vision systems and analyzes those images for paint problem determination |  |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-07-31 | 2024-07-31 | 2024-07-31 | Complete | Blue | 2024-11-22 | 2024-11-19 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Priya | 2025-03-04 |  |  | DB modernized to GCP PostgreSQL | No | SQL
21592 | FRame Eng Design Order Manufacturing System | In Production | FREDOM | ISIT | SKING68 | JRICH264 | RCHANDA | AELANGO | Silver | Non S-Ox | 211 | No | Yes | In-House | SKING68 | RTHIRUV1 | Advanced PD and Tech | Industrial System IT | Frame Hole Management System |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [9 empty] | Ramesh |  |  |  |  | No | SQL
526 | Global Tooling System/variset | In Production | GTSV | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | SKING68 | Manufacturing Engineering | - | GTSV allows for the entry and storage of all tooling information required for effective tool management in a single application. Goal is to reduce production costs by controlling tool usage, inventory, rework and purchases. Key Features Include: Tool life monitoring Inventory tracking Cutter grind management Tool pre-setter interface Central data repository Rework tracking and mgmt Tool presetting & gauge interface |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
20295 | Global Test Data Management System | In Production | GTDM | ISIT | JKOONS | TBROWN99 | SPILLA12 | JLUCAS1 | Bronze | Non S-Ox | 222 | No | Yes | In-House | JKOONS | JKOONS | PD Operations and Quality | Industrial System IT | GTDM is a global application adopting the industry standard ASAM-ODS (Open Data Service) to manage and enable efficient central storage, provide global data access, data retention management, global data sharing/analysis of high quality physical test data which will help engineers to make a quick and good decision on product. It currently manages Engine Dyno Data, Vehicle Durability, Emission, Powertrain Control and Calibration, Body Interior, Safety Crash and NVH data |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
21847 | Global Safety Data Portal | In Production | GSDP | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | Advanced PD and Tech | Industrial System IT | The Global Safety Data Portal will be a single portal for all safety-related documents and test data. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-07-29 | 2024-07-29 | 2024-07-29 | Complete | Blue | 2024-08-16 | 2024-08-27 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Ramesh | 2025-03-10 |  |  |  | No | SQL
20295 | Global Test Data Management System | In Production | GTDM | ISIT | JKOONS | TBROWN99 | SPILLA12 | JLUCAS1 | Bronze | Non S-Ox | 222 | No | Yes | In-House |  |  | PD Operations and Quality | Industrial System IT | GTDM is a global application adopting the industry standard ASAM-ODS (Open Data Service) to manage and enable efficient central storage, provide global data access, data retention management, global data sharing/analysis of high quality physical test data which will help engineers to make a quick and good decision on product. It currently manages Engine Dyno Data, Vehicle Durability, Emission, Powertrain Control and Calibration, Body Interior, Safety Crash and NVH data |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23042 | Global Technical Assistance Center | In Production | GTAC | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 212 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | The Technical Assistance Centre application empowers dealer technicians to collaborate with Service Engineers for expert assistance in resolving Technical service or repair issues of a vehicle that the technician cannot resolve on his/her own. The seamless integration of GTAC interactions into the GCQIS application enables Product Concern Engineers to identify key areas of focus regarding vehicle repair and quality concerns through advanced data analysis. The three types of requests supported in Global tech assistance are TSR - Technical support request PA - Prior Approval and TIS - Technical Information support |  |  | YES | 3 | RKENNEL | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
17966 | Parts & Accessories Datawarehouse (PAR) | In Production | PAR | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Ford Customer Service | - | Database with P&A information that is used by P&A staff to get information abd compose some business report. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | VM
23042 | Global Technical Assistance Center | In Production | GTAC | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 212 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | The Technical Assistance Centre application empowers dealer technicians to collaborate with Service Engineers for expert assistance in resolving Technical service or repair issues of a vehicle that the technician cannot resolve on his/her own. The seamless integration of GTAC interactions into the GCQIS application enables Product Concern Engineers to identify key areas of focus regarding vehicle repair and quality concerns through advanced data analysis. The three types of requests supported in Global tech assistance are TSR - Technical support request PA - Prior Approval and TIS - Technical Information support |  |  | YES | 3 | RKENNEL | PLM | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
11714 | Global Supplier Database | In Production | GSDB | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | A Global Supplier Data Base which maintains key information about many FMC Suppliers |  |  | YES | 3 | TSWEEN16 | PLM | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
11714 | Global Supplier Database | In Production | GSDB | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | A Global Supplier Data Base which maintains key information about many FMC Suppliers |  |  | YES | 3 | TSWEEN16 | PLM | Mainframe | Q4 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11714 | Global Supplier Database | In Production | GSDB | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | A Global Supplier Data Base which maintains key information about many FMC Suppliers |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
11426 | GLOBAL STUDY PROCESS ALLOCATION SYSTEM | In Production | GSPAS | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Silver | Non S-Ox | 322 | No | Yes | In-House | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | Global Study Process Allocation System (GSPAS)GSPAS - The Global Study Process Allocation System is the global repository of engineering data and standardized processes for assembling all Ford vehicles, including the related parts, tools, and standard labor times using AI and MODAPTS. GSPAS is comprised of several integrated modules - GSPAS Core (Process, Authorization, Study), Allocations Planning Tool (APT), Time Study (TS), Operator Work Pattern (OWP), and e-QPS; and is used in the daily activites of over 7000 Manufacturing Engineers, Industrial Engineers, and Plant Workgroup Teams through NA, SA, EU, and FAP. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
11426 | GLOBAL STUDY PROCESS ALLOCATION SYSTEM | In Production | GSPAS | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Silver | Non S-Ox | 322 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Global Study Process Allocation System (GSPAS)GSPAS - The Global Study Process Allocation System is the global repository of engineering data and standardized processes for assembling all Ford vehicles, including the related parts, tools, and standard labor times using AI and MODAPTS. GSPAS is comprised of several integrated modules - GSPAS Core (Process, Authorization, Study), Allocations Planning Tool (APT), Time Study (TS), Operator Work Pattern (OWP), and e-QPS; and is used in the daily activites of over 7000 Manufacturing Engineers, Industrial Engineers, and Plant Workgroup Teams through NA, SA, EU, and FAP. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
21847 | Global Safety Data Portal | In Production | GSDP | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | Advanced PD and Tech | Industrial System IT | The Global Safety Data Portal will be a single portal for all safety-related documents and test data. | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-07-29 | 2024-07-29 | 2024-07-29 | Complete | Blue | 2024-08-16 | 2024-08-27 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Ramesh | 2025-03-10 |  |  |  | No | VM
23044 | Global Service Parts Packaging System | In Production | PS&L GSPPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | This application manages FCSD packaging specification data at a global level and assures that packaging specifications are common, where appropriate, among the regions/markets. |  |  | YES | 5 | RKENNEL | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
23044 | Global Service Parts Packaging System | In Production | PS&L GSPPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | This application manages FCSD packaging specification data at a global level and assures that packaging specifications are common, where appropriate, among the regions/markets. |  |  | YES | 5 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
23044 | Global Service Parts Packaging System | In Production | PS&L GSPPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | This application manages FCSD packaging specification data at a global level and assures that packaging specifications are common, where appropriate, among the regions/markets. |  |  | YES | 5 | RKENNEL | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
52427 | Order Exchange Services | In Production | OES | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | PSATISH2 | Bronze | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | A Collection of Order Exchange Services supporting the Ford Volkswagen Alliance. | 3 |  | YES | 3 | NKANDULA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 | 2024-09-23 | Complete | Blue | 2024-12-15 | 2024-10-29 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
23044 | Global Service Parts Packaging System | In Production | PS&L GSPPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | This application manages FCSD packaging specification data at a global level and assures that packaging specifications are common, where appropriate, among the regions/markets. |  |  | YES | 5 | RKENNEL | PLM | WAS | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
22480 | Design Benchmarking Application | In Development | DESBEN | ISIT | SBONNICI | KRAMMOHA | RHARIKR2 | GRAO3 | Copper | Non S-Ox | 212 | Yes | No | In-House | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | This a data management tool used to facilitate the Design Benchmarking role which is currently Excel based, with the vision of converting to a database system that would expand use of existing and future competitive data sets and improve productivity by eliminating manual data management. The purpose of this application is to Convert from an Excel based data management system to a Database structure to enable automated data management, Convert existing Excel based data management tools to integrate with database structure creating a user friendly data management interface, Convert existing competitive vehicle audit excel data into formats compatible with database structure, Incorporate the database enabled environment on touch screen capable tablet devices for preforming critical job functions in the field (requires purchase of new touch screen capable tablet devices) | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-07-30 | 2025-01-15 | 2025-01-03 | Complete | Blue | 2025-01-18 | 2025-01-20 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Priya | 2025-03-06 |  |  | Moved out of VMs Application moved to GCP (App tier to cloud run & DB to GCP PostgreSQL)in 2024 & Decommission complete in Q1 2025 | No | VM
24411 | Onsite (Reserve/Navigate/Stop Leaks) | In Production | FSMA | OCETO | TSWEEN16 | KADOMKAI | PPOBURSK | ESTILESK | Copper | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Enterprise Technology | Staffs IT | An application to provide end users the ability and ease to smoothly carryon the activities that will increase workplace productivity, efficiency, collaboration, and will transform the way we work by being able to find or spot needed spaces, tools, or people. | 4 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21376 | Global S&R Paynter | In Production | GSRP | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | PD Operations and Quality | Industrial System IT | This application will provide program teams in NVH the ability to create dashboards and paynter charts on programs based on input from plants ( VO and VE development Teams ) on S&R issues. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23354 | QMarkets for Innovation Portal | In Production | IdeaPlace | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SBONNICI | SBONNICI | Advanced PD and Tech | Industrial System IT | Establish a collaborative, community based innovation portal and Idea Place tool that enables the Global users to exchange ideas, propose improvements, connect with knowledge sources, and showcase inventions/patents and technical awards using Q-Markets for Innovation Portal. | 6 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to SaaS | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | VM
21376 | Global S&R Paynter | In Production | GSRP | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | PD Operations and Quality | Industrial System IT | This application will provide program teams in NVH the ability to create dashboards and paynter charts on programs based on input from plants ( VO and VE development Teams ) on S&R issues. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
50573 | Material Forecasting | In Production | MF | M&S TECH | FHIRSH | SBINO | SBINO | PSATISH2 | Silver | Non S-Ox | 231 | No | Yes | - | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | MF is an application generates 53 weeks of constrainted feature forecast and sends the fully expanded orders to cmms. It takes inputs from various applications like PDO, SPCPS, SAC, OAR, OPA, CFF to arrive at the forecast. This application contains a COTS product called Kinaxis. MF product is a package of Order Forecasting (OF) , Controllable Feature Forecast (CFF) and Global Operating plan ( OPA). | 6 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | DB on VM is mordenized to SQL Server in GCP | No | VM
14736 | Global Risk Management Web Site | In Production | GRM | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | TSAILESH | Bronze | Non S-Ox | 111 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | Global Risk Management Web Site aka Risk Monitoring Dashboard Report |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | Java < v21
23362 | CO2 and Fuel Economy Calculator (WLTP) | In Production | CO2FEC | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Gold | Non S-Ox | 233 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | This is the implementation of the WLTP (Worldwide Light Vehicle Test Procedure)legislation in Ford. CO2FEC will use the Service from PAM-AC (#23716) to calculate the weight, roll resistance and aerodynamic drag to interpolate the CO2 and Fuel Economy of a specific vehicle using high and low energy vehicle configurations. CO2 and FE values have to be displayed on Labels, Certificate of Conformity, Web Sites , used for registration etc. | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-09-30 | 2024-09-30 | 2024-09-30 | Complete | Green | 2024-11-07 | 2024-11-07 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | Yes | VM
14923 | Global Rates Info Machines and Materials | In Production | EuFA-GRIMM | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | AKANSKI | PD Operations and Quality | Integrated Enterprise Resource Planning (I-ERP) | Global Rate Information Machine and Materials (GRIMM) Calculates machine and labour rates and stores machine and standard price rates. [Application has been rewritten into J2EE from Mainframe - previous record 6336] | 22 |  | YES | 4 | TSWEEN16 | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
14923 | Global Rates Info Machines and Materials | In Production | EuFA-GRIMM | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | AKANSKI | PD Operations and Quality | Integrated Enterprise Resource Planning (I-ERP) | Global Rate Information Machine and Materials (GRIMM) Calculates machine and labour rates and stores machine and standard price rates. [Application has been rewritten into J2EE from Mainframe - previous record 6336] |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q3 2027 | Rewrite | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
14923 | Global Rates Info Machines and Materials | In Production | EuFA-GRIMM | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | PD Operations and Quality | Integrated Enterprise Resource Planning (I-ERP) | Global Rate Information Machine and Materials (GRIMM) Calculates machine and labour rates and stores machine and standard price rates. [Application has been rewritten into J2EE from Mainframe - previous record 6336] |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-15 | Complete | Blue | 2025-06-13 | 2025-01-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | Migrated to PostgreSQL and servers decommissioned in Jan | No | Oracle
14923 | Global Rates Info Machines and Materials | In Production | EuFA-GRIMM | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | AKANSKI | PD Operations and Quality | Integrated Enterprise Resource Planning (I-ERP) | Global Rate Information Machine and Materials (GRIMM) Calculates machine and labour rates and stores machine and standard price rates. [Application has been rewritten into J2EE from Mainframe - previous record 6336] |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q3 2027 | Rewrite | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
23362 | CO2 and Fuel Economy Calculator (WLTP) | In Production | CO2FEC | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Gold | Non S-Ox | 233 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | This is the implementation of the WLTP (Worldwide Light Vehicle Test Procedure)legislation in Ford. CO2FEC will use the Service from PAM-AC (#23716) to calculate the weight, roll resistance and aerodynamic drag to interpolate the CO2 and Fuel Economy of a specific vehicle using high and low energy vehicle configurations. CO2 and FE values have to be displayed on Labels, Certificate of Conformity, Web Sites , used for registration etc. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-09-30 | 2024-09-30 | 2024-09-30 | Complete | Green | 2024-11-07 | 2024-11-07 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | Yes | SQL
51962 | Global Product Representation Services | In Production | GPRS | M&S TECH | FHIRSH | GVIJI | STHANGAV | JCOY3 | Gold | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | Common services and UI for the GPRS portfolio of applications (GForCE, GPRIME, GPAS, GPRICE). Serving captivating product information to people who shop, buy, own, and sell Ford/Lincoln vehicles. Software crafted by product teams passionate about continuously delivering value.The GPRS application Utilizes GForCE (v3), GPRIME, GRPICE and GPAS and provides capabilities across the GPRS suite including a UI and common services. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 | 2025-02-22 | Complete | Blue | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | This is not partial. Timeline is correct | Yes | SQL
23362 | CO2 and Fuel Economy Calculator (WLTP) | In Production | CO2FEC | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Gold | Non S-Ox | 233 | No | Yes | In-House |  |  | Policy | Industrial System IT | This is the implementation of the WLTP (Worldwide Light Vehicle Test Procedure)legislation in Ford. CO2FEC will use the Service from PAM-AC (#23716) to calculate the weight, roll resistance and aerodynamic drag to interpolate the CO2 and Fuel Economy of a specific vehicle using high and low energy vehicle configurations. CO2 and FE values have to be displayed on Labels, Certificate of Conformity, Web Sites , used for registration etc. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-09-30 | 2024-09-30 | 2024-09-30 | Complete | Green | 2024-11-07 | 2024-11-07 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | [5 empty] | Yes | Java < v21
51962 | Global Product Representation Services | In Production | GPRS | M&S TECH | FHIRSH | GVIJI | STHANGAV | JCOY3 | Gold | Non S-Ox | 221 | No | Yes | In-House |  |  | Marketing & Sales | Marketing, Sales and Service | Common services and UI for the GPRS portfolio of applications (GForCE, GPRIME, GPAS, GPRICE). Serving captivating product information to people who shop, buy, own, and sell Ford/Lincoln vehicles. Software crafted by product teams passionate about continuously delivering value.The GPRS application Utilizes GForCE (v3), GPRIME, GRPICE and GPAS and provides capabilities across the GPRS suite including a UI and common services. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2025-02-22 | 2024-12-20 | 2024-12-20 | Complete | Blue | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | This is not partial. Timeline is correct | Yes | Java < v21
50990 | Global Product Representation Information Manageme | In Production | GPRIME | M&S TECH | FHIRSH | GVIJI | NNAVANEE | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | 223 | A global, single-source authoring product marketing content management, WERS product oriented, publishing and validation tool leveraging the latest web and cloud native technologies, in a presentation and experience agnostic way. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2025-02-22 | 2024-12-20 | 2024-12-20 | Complete | Blue | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | [5 empty] | Yes | Java < v21
50990 | Global Product Representation Information Manageme | In Production | GPRIME | M&S TECH | FHIRSH | GVIJI | NNAVANEE | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | A global, single-source authoring product marketing content management, WERS product oriented, publishing and validation tool leveraging the latest web and cloud native technologies, in a presentation and experience agnostic way. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 | 2025-02-22 | Complete | Blue | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | Yes | SQL
23432 | Global Track & Trace | In Production | GT&T | ISIT | VVIJAY55 | RADAM10 | SMAHES11 | SSENTH15 | Silver | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Global Track and Trace Purpose of this application is to consume non PII vehicle plant to dealership shipment data from various applications like VMACS, GLADS, GVDS, QLS and NGAVS, standardize the data into the GTT Database and transmit the data to the vendor, Freight Verify (EAMS App# 52009), who are integrated with partners and will populate a dashboard for Ford business customers and provide the ability to run reports. |  |  | YES | 5 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2025-01-06 | 2024-12-20 | 2024-12-20 | Complete | Blue | 2025-01-06 | 2025-01-06 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Priya | 2025-03-06 |  |  | App migration completed in Q4 2024 & Infra Decommission complete on Q1 2025 | No | SQL
50076 | Global Product Asset Services | In Production | GPAS | M&S TECH | FHIRSH | GVIJI | PDEEPA4 | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | 223 | GPAS is a scalable, secure, highly responsive/performant digital asset solution capable of associating (with high fidelity) assets with product configuration so that FORD can provide a truly world-class set of digital asset, configuration based services, supporting digital experiences that our consumers love. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2025-02-22 | 2024-12-20 | 2024-12-20 | Complete | Blue | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | This is not partial. Timeline is correct | Yes | Java < v21
50076 | Global Product Asset Services | In Production | GPAS | M&S TECH | FHIRSH | GVIJI | PDEEPA4 | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | GPAS is a scalable, secure, highly responsive/performant digital asset solution capable of associating (with high fidelity) assets with product configuration so that FORD can provide a truly world-class set of digital asset, configuration based services, supporting digital experiences that our consumers love. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 | 2025-02-22 | Complete | Blue | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | This is not partial. Timeline is correct | Yes | SQL
52221 | LiveAction | In Production | LiveAction | EPEO | MCRNKOVI | SSOLTANI | CCRAIG39 | CCRAIG39 | Bronze | Non S-Ox | 122 | No | Yes | - | MCRNKOVI | SSOLTANI | Enterprise Technology | EPEO | Real-time network visualization. | 3 |  | YES | 1 | SWALIMBE | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned | [17 empty] | VM
50887 | Global Pricing Calculation Engine | In Production | GPRICE | M&S TECH | FHIRSH | GVIJI | STHANGAV | JCOY3 | Gold | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | GPriCE is a scalable, secure, highly responsive/performant digital *product* pricing solution capable of associating pricing information with product configuration so that FORD can provide a truly world-class set of digital pricing information and product taxation calculations to omni-channels. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 | 2025-02-22 | Complete | Blue | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | This is not partial. Timeline is correct | Yes | SQL
18043 | LGT - MP&L Datawarehous (MP) | In Production | LGT | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | - | Database with logistics information (MP and G3 Systems) that is used by MP&L staff to get information and compose some business reports. | 5 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | No VMs in latest VM Data file | No | VM
50887 | Global Pricing Calculation Engine | In Production | GPRICE | M&S TECH | FHIRSH | GVIJI | STHANGAV | JCOY3 | Gold | Non S-Ox | 233 | No | Yes | In-House |  |  | Marketing & Sales | Marketing, Sales and Service | GPriCE is a scalable, secure, highly responsive/performant digital *product* pricing solution capable of associating pricing information with product configuration so that FORD can provide a truly world-class set of digital pricing information and product taxation calculations to omni-channels. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2025-02-22 | 2024-12-20 | 2024-12-20 | Complete | Blue | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 |  |  |  |  | This is not partial. Timeline is correct | Yes | Java < v21
18516 | Global Personal Identifier/GPID | In Production | GPID | EPEO | NOKEEFE | MSNYDER5 | DDALKOVS | GSIENKIE | Silver | Non S-Ox | 122 | Yes | No | In-House | NOKEEFE | NOKEEFE | Enterprise Technology | EPEO | A process (developed by BP)with an underlying web based infrastructure used to identify people uniquely, acurately and practically within Ford Motor Company without the use of personal (risky) information |  |  | YES | 3 | SWALIMBE | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
18516 | Global Personal Identifier/GPID | In Production | GPID | EPEO | NOKEEFE | MSNYDER5 | DDALKOVS | GSIENKIE | Silver | Non S-Ox | 122 | Yes | No | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | A process (developed by BP)with an underlying web based infrastructure used to identify people uniquely, acurately and practically within Ford Motor Company without the use of personal (risky) information |  |  | YES | 3 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
24566 | IT Data Hub | In Production | ITDH | OCETO | TVASU | KBALAS13 | JEKAMBA3 | WJUSTICE | Copper | Non S-Ox | 311 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | A single data repository for various IT4IT applications used to create dashboards, downstreams feeds and APIs to support data driven decision making for business of IT | 3 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | No VMs in latest VM Data file | No | VM
23432 | Global Track & Trace | In Production | GT&T | ISIT | VVIJAY55 | RADAM10 | SMAHES11 | SSENTH15 | Silver | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Global Track and Trace Purpose of this application is to consume non PII vehicle plant to dealership shipment data from various applications like VMACS, GLADS, GVDS, QLS and NGAVS, standardize the data into the GTT Database and transmit the data to the vendor, Freight Verify (EAMS App# 52009), who are integrated with partners and will populate a dashboard for Ford business customers and provide the ability to run reports. |  |  | YES | 5 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2024 | Version Upgrade | Modernize | 2025-01-06 | 2024-12-20 | 2024-12-20 | Complete | Blue | 2025-01-06 | 2025-01-06 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Priya | 2025-03-06 |  |  | App migration completed in Q4 2024 & Infra Decommission complete on Q1 2025 | No | Java < v21
24393 | Global Owner | In Production | OWNER | M&S TECH | RKLEINSM | BMUNIE | JWANG28 | JPOTTE60 | Platinum | Non S-Ox | 222 | No | Yes | COTS |  |  | Enterprise Technology | Marketing, Sales and Service | B2C Global Owner products and platform serving customers on web channel. |  | Springboot | YES | 2 | NKANDULA | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  | 1900-03-30 |  | Planned |  | No | [14 empty] | No | Java < v21
50914 | Global Order Scheduling | In Production | G-OS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 233 | No | Yes | In-House | #N/A | #N/A | Marketing & Sales | 233 | GLOBAL APPLICATION THAT ENABLES SELECTION AND SCHEDULING OF ORDERS TO BE BUILT AT FORD ASSEMBLY PLANTS. |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | Q2 2027 | Version Upgrade | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
9087 | Global OnLine Dealer Database | In Production | GOLDD | M&S TECH | NKANDULA | JLEWIS10 | CVOGLER1 | JHARPER2 | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | 333 | The Global OnLine Dealer Database (GOLDD) is Ford Motor Company's worldwide repository for all retailers of Ford Motor Company products and services. |  | Springboot | YES | 6 | NKANDULA | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
9087 | Global OnLine Dealer Database | In Production | GOLDD | M&S TECH | NKANDULA | JLEWIS10 | CVOGLER1 | JHARPER2 | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | The Global OnLine Dealer Database (GOLDD) is Ford Motor Company's worldwide repository for all retailers of Ford Motor Company products and services. |  |  | YES | 6 | NKANDULA | Modernize Components (Backlog-2024) | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Oracle
9087 | Global OnLine Dealer Database | In Production | GOLDD | M&S TECH | NKANDULA | JLEWIS10 | CVOGLER1 | JHARPER2 | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | The Global OnLine Dealer Database (GOLDD) is Ford Motor Company's worldwide repository for all retailers of Ford Motor Company products and services. | 79 |  | YES | 6 | NKANDULA | PLM | WebFocus | Q2 2025 | Modernize | Modernize | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | 100% | 50% | 25% | 25% | 25% | 25% | 25% | [7 empty] | No | DA
9087 | Global OnLine Dealer Database | In Production | GOLDD | M&S TECH | NKANDULA | JLEWIS10 | CVOGLER1 | JHARPER2 | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | The Global OnLine Dealer Database (GOLDD) is Ford Motor Company's worldwide repository for all retailers of Ford Motor Company products and services. |  |  | YES | 6 | NKANDULA | PLM | Mainframe | Q4 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
9087 | Global OnLine Dealer Database | In Production | GOLDD | M&S TECH | NKANDULA | JLEWIS10 | CVOGLER1 | JHARPER2 | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | The Global OnLine Dealer Database (GOLDD) is Ford Motor Company's worldwide repository for all retailers of Ford Motor Company products and services. |  |  | YES | 6 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
23432 | Global Track & Trace | In Production | GT&T | ISIT | VVIJAY55 | RADAM10 | SMAHES11 | SSENTH15 | Silver | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Global Track and Trace Purpose of this application is to consume non PII vehicle plant to dealership shipment data from various applications like VMACS, GLADS, GVDS, QLS and NGAVS, standardize the data into the GTT Database and transmit the data to the vendor, Freight Verify (EAMS App# 52009), who are integrated with partners and will populate a dashboard for Ford business customers and provide the ability to run reports. | 5 |  | YES | 5 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-02-24 | 2024-12-20 | 2024-12-20 | Complete | Blue | 2025-02-24 | 2025-02-24 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Priya | 2025-03-06 |  |  | No VMs found | No | VM
23340 | Global MFG Online Database (GMOD) | In Production | VOME_PROG | ISIT | OTHERS | BBELL2 | RNICKLA2 | AELANGO | Copper | Non S-Ox | 311 | Yes | No | COTS | ASTEVE43 | JSMIT754 | Manufacturing Engineering | - | Central database and related reporting engine for global Vehicle Operations Manufacturing Engineering vehicle program launch activities |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
23692 | Perceived Quality Audit System | In Production | PQAS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Silver | Non S-Ox | 221 | No | Yes | In-House | JKOONS | TBROWN99 | Advanced PD and Tech | Industrial System IT | Global corporate IT enabled technology to support Vehicle Craftsmanship & Perceived Quality Audit process and provide business capabilities for end to end process integration and decisions support |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-11-25 | 2024-11-25 | 2024-11-25 | Complete | Blue | 2024-11-25 | 2024-11-25 | Complete |  | No | [8 empty] | Decommission | Ramesh | 2025-03-10 |  |  |  | No | SQL
21801 | Global Material Management & Approval | In Production | GMM/GMA | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Silver | Non S-Ox | 221 | No | Yes | COTS | DKAVITHA | UVIJAYAL | PD Operations and Quality | Industrial System IT | Global Materials Management application replaces the existing legacy applications GMIR & Global Material Approval application replaces MATS applications by implementing the COTS product I-point. iPoint offers the solution product providing the capability for global material compliance, vehicle certification, LCA evaluations and conflict mineral compliance. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-01-10 | 2025-01-10 | 2025-01-10 | Complete | Blue | 2025-01-10 | 2025-01-10 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Priya | 2025-03-03 |  |  | WAS Decommission complete. App moved to Oracle SaaS solution in 2024 | No | Java < v21
21801 | Global Material Management & Approval | In Production | GMM/GMA | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Silver | Non S-Ox | 221 | No | Yes | COTS | DKAVITHA | DKAVITHA | PD Operations and Quality | Industrial System IT | Global Materials Management application replaces the existing legacy applications GMIR & Global Material Approval application replaces MATS applications by implementing the COTS product I-point. iPoint offers the solution product providing the capability for global material compliance, vehicle certification, LCA evaluations and conflict mineral compliance. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-06-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Priya | 2025-03-03 |  |  | This app moved to Oracle SAAS solution (App# 53339) | No | Oracle
21682 | GOTD - Order Generation | In Production | GOTD -OG | M&S TECH | FHIRSH | SBINO | VSRINI23 | PSATISH2 | Silver | Non S-Ox | 232 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | OG (Order Generation) application forecasts and generate orders by utilize Sales History and fast turn data as well as a variety of established data sources to predict trends at a dealer level and target specific customer demand requirements. It provides a set of completely specified orders that are selected to turn as quickly as possible given the expected inventory mix rates. Purpose: Recommend orders to dealers to meet customer demand. Recommend Feature Allocation to Dealers. Achieving reduced days on lot through forecasting buildable and saleable orders. | 4 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-16 | Complete | Blue | 2024-12-15 | 2025-01-26 | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
19532 | GLOBAL MATERIAL COST FORECASTING (GMCF) | In Production | GMCF | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 312 | No | Yes | COTS | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Global Material Cost 5-year Budget and Business Planning Model and monthly forecast. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
50120 | GOTD - Global Wholesale Services | In Production | GOTD-GWS | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Contains services to support Global Wholesale processes and integrate with regional tooling. | 5 |  | YES | 3 | NKANDULA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-23 | 2024-12-23 | In-Progress | Green | 2024-12-23 | 2024-12-23 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | Its already completed as part of PCF migration. VMs are decommissioned. | No | VM
19532 | GLOBAL MATERIAL COST FORECASTING (GMCF) | In Production | GMCF | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 312 | No | Yes | COTS | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Global Material Cost 5-year Budget and Business Planning Model and monthly forecast. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
21669 | Global Market Equation Analysis Tool | In Production | MEAT | I-ERP | SFRANCI8 | AKANSKI | RDAVIES6 | LWU14 | Silver | Non S-Ox | 221 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Marketing & Sales | Integrated Enterprise Resource Planning (I-ERP) | MEAT is a global tool to consolidate and analyse marketing and finance data (including price positions, shares, financials, favourable opinion, etc.) in a structural and consistent way, to support decision making and to comply with global reporting requirements. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q3 2026 | Modernize to Cloud Databases | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Oracle
50418 | GOTD - Global Allocation | In Production | GAT | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | GOTD - Allocation Product, to support Dealer allocations | 4 |  | YES | 3 | NKANDULA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-08-11 | 2024-08-11 | Complete | Blue | 2024-10-01 | 2024-10-01 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | Its already completed as part of PCF migration. VMs are decommissioned. | No | VM
22053 | Global Logistics and Documentation Systems - GLADS | In Production | GLADS | M&S TECH | FHIRSH | NGIRISH | SBOINAPA | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | Ford Trading Company logistics application, used to manage invoicing, booking vehicles on vessels, and other deep sea logistics functions. | 83 |  | YES | 2 | NKANDULA | PLM | BO | Q4 2026 | Modernize | Modernize | 2026-12-30 | 2026-12-30 |  | In-Progress | Green | 2027-02-28 |  | Planned |  | No | [8 empty] | New Platform altogether |  |  |  |  | EXCEPTION BASED. Approval from Tom Culler received to remain on platform | No | DA
50302 | GOTD - Customs | In Production | Customs | M&S TECH | FHIRSH | VDONTHY | MCRABB | PSATISH2 | Bronze | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Application to support Customs business process for imports/exports and aiding in the definition of transfer pricing. Used by GOTD and FTC & GTS | 4 |  | YES | 2 | NKANDULA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-10-27 | Complete | Blue | 2024-12-15 | 2024-10-27 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
17408 | Global Lending Analysis System-GLAS | In Production | GLAS | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 322 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | This system is a dealer lending platform that automates the process of creating dealer credit ratings across the globe and facilitates credit package creation and approval process for wholesale lines, dealers loans etc. The system is also used for ongoing risk monitoring and mitigation action documentation. |  |  | YES | 5 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
17408 | Global Lending Analysis System-GLAS | In Production | GLAS | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 322 | No | Yes | In-House | DTAURO | DTAURO | Ford Credit Services | Ford Credit (FMCC) | This system is a dealer lending platform that automates the process of creating dealer credit ratings across the globe and facilitates credit package creation and approval process for wholesale lines, dealers loans etc. The system is also used for ongoing risk monitoring and mitigation action documentation. |  |  | YES | 5 | SRAISIN1 | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
17408 | Global Lending Analysis System-GLAS | In Production | GLAS | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 322 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | This system is a dealer lending platform that automates the process of creating dealer credit ratings across the globe and facilitates credit package creation and approval process for wholesale lines, dealers loans etc. The system is also used for ongoing risk monitoring and mitigation action documentation. |  |  | YES | 5 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
23692 | Perceived Quality Audit System | In Production | PQAS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Silver | Non S-Ox | 221 | No | Yes | In-House | JKOONS | TBROWN99 | Advanced PD and Tech | Industrial System IT | Global corporate IT enabled technology to support Vehicle Craftsmanship & Perceived Quality Audit process and provide business capabilities for end to end process integration and decisions support | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-11-25 | 2024-11-25 | 2024-11-25 | Complete | Blue | 2024-11-25 | 2024-11-25 | Complete |  | No | [8 empty] | Decommission | Ramesh | 2025-03-10 |  |  |  | No | VM
17408 | Global Lending Analysis System-GLAS | In Production | GLAS | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 322 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | This system is a dealer lending platform that automates the process of creating dealer credit ratings across the globe and facilitates credit package creation and approval process for wholesale lines, dealers loans etc. The system is also used for ongoing risk monitoring and mitigation action documentation. |  |  | YES | 5 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
50232 | Global Lending Analysis System - China | In Production | GLAS China | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | NVARADA2 | Bronze | Non S-Ox | 222 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | This system is a dealer lending platform that automates the process of creating dealer credit ratings across the China region and facilitates credit package creation and approval process for wholesale lines, dealers loans etc. The system is also used for ongoing risk monitoring and mitigation action documentation. |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
18410 | Global In-Vehicle Information System | In Production | GIVIS | EVDD | MJAMWAL | TPINTO3 | IJEBARAJ | MJAFARUL | Silver | Non S-Ox | 222 | No | Yes | In-House | MJAMWAL | TPINTO3 | Advanced PD and Tech | - | Global In Vehicle Information Services (GIVIS) provides a better level of direct customer support by Enabling an accurate automated process for identifying software available to a specific VIN and its ECUs. Enabling creation of a reliable installation package suitable for customer self service for Sync module. Storing vehicle specific application configuration for recovery to a previously working state or transfer to another module. Specifically, support for production deployment of the ECUs requires detailed management of the history of the module hardware and software installed on a vehicle and the availability of software for the vehicle customer. The most significant of these are Tracking ECU software upgrades. Support for reliable and accurate software installation performed at service or by the customer, Distribution of Vehicle ECUs current and historical state. Reliable availability of MGM system and application software for vehicle installation. | 57 |  | YES | 5 | MJONE308 | PLM | BO | Q3 2025 | Migrate to Power BI | Modernize | 2025-09-30 | 2025-09-30 |  | In-Progress | Green | 2025-12-29 |  | Planned | [10 empty] | Power BI | [6 empty] | DA
18410 | Global In-Vehicle Information System | In Production | GIVIS | EVDD | MJAMWAL | TPINTO3 | IJEBARAJ | MJAFARUL | Silver | Non S-Ox | 222 | No | Yes | In-House | MJAMWAL | TPINTO3 | Advanced PD and Tech | - | Global In Vehicle Information Services (GIVIS) provides a better level of direct customer support by Enabling an accurate automated process for identifying software available to a specific VIN and its ECUs. Enabling creation of a reliable installation package suitable for customer self service for Sync module. Storing vehicle specific application configuration for recovery to a previously working state or transfer to another module. Specifically, support for production deployment of the ECUs requires detailed management of the history of the module hardware and software installed on a vehicle and the availability of software for the vehicle customer. The most significant of these are Tracking ECU software upgrades. Support for reliable and accurate software installation performed at service or by the customer, Distribution of Vehicle ECUs current and historical state. Reliable availability of MGM system and application software for vehicle installation. | 919 |  | NO | 5 | MJONE308 | PLM | Datastage |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | DA
18410 | Global In-Vehicle Information System | In Production | GIVIS | EVDD | MJAMWAL | TPINTO3 | IJEBARAJ | MJAFARUL | Silver | Non S-Ox | 222 | No | Yes | In-House | MJAMWAL | TPINTO3 | Advanced PD and Tech | - | Global In Vehicle Information Services (GIVIS) provides a better level of direct customer support by Enabling an accurate automated process for identifying software available to a specific VIN and its ECUs. Enabling creation of a reliable installation package suitable for customer self service for Sync module. Storing vehicle specific application configuration for recovery to a previously working state or transfer to another module. Specifically, support for production deployment of the ECUs requires detailed management of the history of the module hardware and software installed on a vehicle and the availability of software for the vehicle customer. The most significant of these are Tracking ECU software upgrades. Support for reliable and accurate software installation performed at service or by the customer, Distribution of Vehicle ECUs current and historical state. Reliable availability of MGM system and application software for vehicle installation. |  |  | YES | 5 | MJONE308 | PLM | Java Struts | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
18410 | Global In-Vehicle Information System | In Production | GIVIS | EVDD | MJAMWAL | TPINTO3 | IJEBARAJ | MJAFARUL | Silver | Non S-Ox | 222 | No | Yes | In-House | MJAMWAL | MJAMWAL | Advanced PD and Tech | - | Global In Vehicle Information Services (GIVIS) provides a better level of direct customer support by Enabling an accurate automated process for identifying software available to a specific VIN and its ECUs. Enabling creation of a reliable installation package suitable for customer self service for Sync module. Storing vehicle specific application configuration for recovery to a previously working state or transfer to another module. Specifically, support for production deployment of the ECUs requires detailed management of the history of the module hardware and software installed on a vehicle and the availability of software for the vehicle customer. The most significant of these are Tracking ECU software upgrades. Support for reliable and accurate software installation performed at service or by the customer, Distribution of Vehicle ECUs current and historical state. Reliable availability of MGM system and application software for vehicle installation. |  |  | YES | 5 | MJONE308 | PLM | Oracle | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
18410 | Global In-Vehicle Information System | In Production | GIVIS | EVDD | MJAMWAL | TPINTO3 | IJEBARAJ | MJAFARUL | Silver | Non S-Ox | 222 | No | Yes | In-House | MJAMWAL | TPINTO3 | Advanced PD and Tech | - | Global In Vehicle Information Services (GIVIS) provides a better level of direct customer support by Enabling an accurate automated process for identifying software available to a specific VIN and its ECUs. Enabling creation of a reliable installation package suitable for customer self service for Sync module. Storing vehicle specific application configuration for recovery to a previously working state or transfer to another module. Specifically, support for production deployment of the ECUs requires detailed management of the history of the module hardware and software installed on a vehicle and the availability of software for the vehicle customer. The most significant of these are Tracking ECU software upgrades. Support for reliable and accurate software installation performed at service or by the customer, Distribution of Vehicle ECUs current and historical state. Reliable availability of MGM system and application software for vehicle installation. |  |  | YES | 5 | MJONE308 | PLM | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
21988 | Global Interior Quietness Paynter | In Production | GIQP | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | PD Operations and Quality | Industrial System IT | This application will provide program teams in NVH the ability to create dashboards and paynter charts on programs based on input from plants (VO and VE development Teams) on Interior Quietness (IQ)issues. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23910 | PTO Calibration Complexity Matrix | In Production | CCM | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Copper | Non S-Ox | 233 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | Calibration Complexity matrix is a Ford Internal application, to convert the retrieved buildable combination for each power pack from PDO into Calibration Complexity Matrix with the required fields that drives a calibration. CCM applications involves two major group: PTIM Powertrain Integration and Project Management and PCCN Powertrain Controls, Calibration and NVH . The current CCMs are created on excel sheet and shared with group via SharePoint, which makes hard to track. Now CCM will be located in one central database, and approvals will be secured, electronic and stored in database to ensure greater consistency. CCM application also helps in maintaining a standard matrix to record and sort the calibrations for each power pack. | 3 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-09-12 | 2024-09-28 | 2024-09-28 | Complete | Blue | 2024-10-25 | 2024-10-25 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Ramesh | 2025-03-10 |  |  |  | No | VM
21988 | Global Interior Quietness Paynter | In Production | GIQP | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | NLAKSHMA | PD Operations and Quality | Industrial System IT | This application will provide program teams in NVH the ability to create dashboards and paynter charts on programs based on input from plants (VO and VE development Teams) on Interior Quietness (IQ)issues. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
22463 | Global Interactive Test Tool for Configuration | In Production | GLITTC | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Bronze | Non S-Ox | 212 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Application to verify codification setup. Verification of Codification changes at time of TTR/DIR Confirm SOE codification regarding order validation and expansion rules Confirm pricing changes, compare between Test and Production, Confirm non-firm pricing |  |  | YES | 3 | NKANDULA | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-01-26 | 2025-01-26 | Complete | Blue | 2025-04-26 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
23974 | Calibration Data Management Database | In Production | Calipedia | ISIT | JKOONS | MNOVAK1 | JSURESHR | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | The application uploads many various scattered sources of information related to calibration into a single database and keeps it synchronized. Any data that is mastered in the application is entered manually into the database. The data is linked directly or indirectly. The database is used to easily search information based on various parameters to generate calibration guides and provides the ability to export information to excel. | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-09-30 | 2024-11-11 | 2024-11-11 | Complete | Blue | 2024-12-13 | 2024-12-23 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Ramesh | 2025-03-10 |  |  |  | No | VM
22463 | Global Interactive Test Tool for Configuration | In Production | GLITTC | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Bronze | Non S-Ox | 212 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Application to verify codification setup. Verification of Codification changes at time of TTR/DIR Confirm SOE codification regarding order validation and expansion rules Confirm pricing changes, compare between Test and Production, Confirm non-firm pricing |  |  | YES | 3 | NKANDULA | PLM | WAS | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-01-26 | 2025-01-26 | Complete | Blue | 2025-04-26 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | [5 empty] | No | Java < v21
50437 | GLOBAL IMAGE VIEWER - DOCUMENT MANAGEMENT SERVICES | In Production | GIV-DMS | FORD CREDIT | DTAURO | JJACK348 | NBHALWAN | ROBRIEN3 | Silver | Non S-Ox | 332 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | DMS consists of Micro services to retrieve or upload customer related documents. Global Image Viewer(GIV) is part of DMS. GIV allows Ford Credit employees to view or manage customer documents. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50437 | GLOBAL IMAGE VIEWER - DOCUMENT MANAGEMENT SERVICES | In Production | GIV-DMS | FORD CREDIT | DTAURO | JJACK348 | NBHALWAN | ROBRIEN3 | Silver | Non S-Ox | 332 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | DMS consists of Micro services to retrieve or upload customer related documents. Global Image Viewer(GIV) is part of DMS. GIV allows Ford Credit employees to view or manage customer documents. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
23974 | Calibration Data Management Database | In Production | Calipedia | ISIT | JKOONS | MNOVAK1 | JSURESHR | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | 211 | The application uploads many various scattered sources of information related to calibration into a single database and keeps it synchronized. Any data that is mastered in the application is entered manually into the database. The data is linked directly or indirectly. The database is used to easily search information based on various parameters to generate calibration guides and provides the ability to export information to excel. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-09-30 | 2024-11-11 | 2024-11-11 | Complete | Blue | 2024-12-13 | 2024-12-23 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 21 | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
50437 | GLOBAL IMAGE VIEWER - DOCUMENT MANAGEMENT SERVICES | In Production | GIV-DMS | FORD CREDIT | DTAURO | JJACK348 | NBHALWAN | ROBRIEN3 | Silver | Non S-Ox | 332 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | DMS consists of Micro services to retrieve or upload customer related documents. Global Image Viewer(GIV) is part of DMS. GIV allows Ford Credit employees to view or manage customer documents. |  |  | YES | 4 | SRAISIN1 | PLM | WAS | Q2 2025 | Version Upgrade | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | Java < v21
23534 | Global Image Mainframe | In Production | GIMF | FORD CREDIT | NJOSHI21 | HBRUMLEV | VCECCARE | ROBRIEN3 | Silver | Non S-Ox | 311 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | This is a mainframe application that supports the Ford Credit Global Image Repository for FCNA and FAFC. It's comprised of a DB2 Database with supporting batch and online programs |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
21223 | Global Illustrated Launch Timing | In Production | GILT | ISIT | OTHERS | CRISTIC | CSELF | ISIDDIQ6 | Silver | Non S-Ox | 322 | Yes | No | In-House | JLANE15 | CRISTIC | New Model Programs | - | Manage Timing, Status, Metrics and critical issues for vehicle/powertrain launches globally. In addition, manages the launch 'Read-Across' to inform in-flight launch teams of potential issues with critical timing. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
21223 | Global Illustrated Launch Timing | In Production | GILT | ISIT | OTHERS | CRISTIC | CSELF | ISIDDIQ6 | Silver | Non S-Ox | 322 | Yes | No | In-House | JLANE15 | CRISTIC | New Model Programs | - | Manage Timing, Status, Metrics and critical issues for vehicle/powertrain launches globally. In addition, manages the launch 'Read-Across' to inform in-flight launch teams of potential issues with critical timing. |  |  | YES | 4 | BWUNNAVA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | SQL | [5 empty] | No | SQL
50944 | Ford Credit Deal Optimizer | In Production | FCDO | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | JMANI | Silver | Non S-Ox | 321 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | Deal Optimizer provides dealers with an integrated, always-on, self-service tool to rehash specific deal parameters and instantly receive a tier and approval on the restructured deal. | 8 |  | YES | 3 | SRAISIN1 | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned | [17 empty] | VM
21223 | Global Illustrated Launch Timing | In Production | GILT | ISIT | OTHERS | CRISTIC | CSELF | ISIDDIQ6 | Silver | Non S-Ox | 322 | Yes | No | In-House | JLANE15 | CRISTIC | New Model Programs | - | Manage Timing, Status, Metrics and critical issues for vehicle/powertrain launches globally. In addition, manages the launch 'Read-Across' to inform in-flight launch teams of potential issues with critical timing. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23406 | Ford Argentina Consumer Knowledge System (CK) | In Production | ARCK | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Marketing & Sales | - | This is the CRM platform of Ford Argentina. It is a knowledge database, an aid tool for helping the Marketing Team in their decisions. CK is focused on improving both strategic and business benefits, working on the consumer experience. Its main purpose is to centralize consumer data in one database in order to get all the information regarding the relationship between the customer/prospects and Ford as a brand and its products. It also contains competitive information. | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | No VMs in latest VM Data file | No | VM
52876 | GLOBAL HEALTH MONITOR | In Production | GHM | ISIT | SKING68 | KRAMESH | MKRAWCZA | RPRASA22 | Copper | Non S-Ox | 211 | No | Yes | In-House |  |  | Manufacturing Staffs | - | Application designed to monitor the health of FIS application servers at Ford manufacturing plants |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2026 | On-Prem | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
13492 | Global Hardware Database | In Production | GHD | EPEO | SRUNSON | ASTONE31 | JJAFANO | SBARFKNE | Copper | Non S-Ox | 111 | No | Yes | In-House | SRUNSON | ASTONE31 | Enterprise Technology | EPEO | Global PC desktop and mobile computing hardware platforms web site. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
23974 | Calibration Data Management Database | In Production | Calipedia | ISIT | JKOONS | MNOVAK1 | JSURESHR | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | The application uploads many various scattered sources of information related to calibration into a single database and keeps it synchronized. Any data that is mastered in the application is entered manually into the database. The data is linked directly or indirectly. The database is used to easily search information based on various parameters to generate calibration guides and provides the ability to export information to excel. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-09-30 | 2024-11-11 | 2024-11-11 | Complete | Blue | 2024-12-13 | 2024-12-23 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Ramesh | 2025-03-10 |  |  |  | No | SQL
13865 | ENTERPRISE HOST PROTECTION AUDIT SYSTEM | In Production | EHPAS | OCETO | TVASU | KBALAS13 | MAMAREND | WJUSTICE | Copper | Non S-Ox | 211 | No | Yes | In-House |  |  | Enterprise Technology | Technology & Enterprise Services (TES) | EHPAS (The Enterprise Host Protection Audit System) is a tool for discovering, tracking and taking action on configuration variances from the Ford PAH (Properly Administered Host) Standards, as provided by the ITPM (Information Technology Policy Manual). | 3 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2024 | Partial Migration to GCP | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21493 | Global ESB System | In Production | GESB | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | JBROADW4 | RKADAM1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | Global system to support the creation and management of Extended Service Plans using common global processes. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
21493 | Global ESB System | In Production | GESB | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | JBROADW4 | RKADAM1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | Global system to support the creation and management of Extended Service Plans using common global processes. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q4 2027 | On-Prem | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | SQL
24340 | Polarion ALM | In Production | POA | ISIT | MNOWICK1 | PBORGAO1 | SBELSAR1 | GRAO3 | Bronze | Non S-Ox | 321 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Enterprise Technology | Industrial System IT | Application Lifecycle management tool used by PD to support systems engineering initiative by managing end to end application development processes with a single, unified solution for requirements, coding, testing, and release. | 8 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | VM
21493 | Global ESB System | In Production | GESB | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | JBROADW4 | RKADAM1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | Global system to support the creation and management of Extended Service Plans using common global processes. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
21258 | Global Environmental Reserve System | In Production | GERS | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Bronze | Non S-Ox | 221 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Application for the EQO to track environmental liabilities. Global Environmental Reserve System is a collaboration solution that provides an Interface for environmental engineers to input liability costs.Provides a process for approval of the estimate. Provides an interface to maintain quarterly balance/adjustments (Reserve Tracker) Security Environmental Quality Office (EQO) Site update access restricted. Admin Functions to maintain information such as: site list, currency code/name mapping, etc. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
11268 | e-EIS (Executive Information System) | In Production | e-EIS11268 | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 322 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | e-EIS (Executive Information System) Web-based (Intranet)Sales Reporting application that provides key sales, stock, availability and order status information at all organizational levels from Nation to Dealer - supporting Ford, Lincoln Mercury, Ford of Canada, Ford of Mexico, WDMO, Ford Financial plus many additional components within Ford Motor Company. | 5 |  | YES | 1 | NKANDULA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | Decomissioned fully. EAMS status : Decommissioned | No | VM
23919 | Global Enterprise Asset Repository | In Production | GEAR | M&S TECH | RKLEINSM | BMUNIE | MSRINI25 | MPINRED1 | Silver | Non S-Ox | 322 | No | Yes | COTS | RKLEINSM | BMUNIE | Marketing & Sales | Marketing, Sales and Service | To expand Digital Asset Management to all Regions/Markets in response to global vehicle product launches. Specifically to: (1) Centralize a single source of truth for all digital assets for global reuse, (2) Provide end-users, globally, the ability to effectively locate and link to digital assets using best-in-class search functionality, metadata, business rules, naming conventions, data structure and user roles (3) Provide the means to limit views of asset content, by way of filtering (4) Implement business reports to track and measure asset download history and serving as input to continually refine asset development and usage procedures |  |  | YES | 2 | NKANDULA | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
9826 | Domain Name Registration | In Production | DNR | OCETO | TVASU | KBALAS13 | MAMAREND | WJUSTICE | Bronze | Non S-Ox | 111 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | EPEO | Domain Name Registration Application allows users to request Domain Name Registrations outside of Ford, on the Public Internet, for Domain Names that do not end in ford.com | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | GCP Migration completed in 2024 and VMs are decommissioned | No | VM
50045 | TrackLite | In Production | TrackLite | ISIT | SBONNICI | KRAMMOHA | ESANKARA | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SBONNICI | SBONNICI | Enterprise Technology | Industrial System IT | TrackLite is the Next Gen tool for eTracker (ITMS No 12408).eTracker tracks issues, tasks, risks and opportunities or anything else that needs tracking eTracker is broken down into individual projects, which can be tailored to suit the team's specific needs. Rather than forcing a user to choose from a vast array of predefined fields, eTracker allows the administrator for each project to define the necessary fields. Most of the input fields can be customized, new fields may be added, and unused fields, removed. The prompts and default lists associated with the fields can also be customized. Additionally, eTracker's reports may be modified to include any fields desired, using nearly any filter and sort method. Reports can be built by customizing those already in the system, or from scratch, and can be made public or private, as the user desires.Tracklite will be using integration like external SMTP for PEGA SaaS | 13 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to SaaS | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | VM
50070 | Global Emissions Reporting and Forecasting | In Production | GERF | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Policy | Industrial System IT | Global Emissions Monitoring & Reporting for FoE, MEA & NA will ensure regional compliance regarding fleet averages for CO2 and fuel economy, enabling global synergies and avoiding penalties. Heavy Duty GHG & Co2 fleet averages and individual vehicle level monitoring / reporting addresses compliance with fleet average targets for the segment above 7.5 tons globally. | 3 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-09-30 | 2024-09-30 | 2024-09-30 | Complete | Blue | 2024-11-15 | 2024-11-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Priya | 2025-03-13 |  |  |  | No | VM
50070 | Global Emissions Reporting and Forecasting | In Production | GERF | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Silver | Non S-Ox | 211 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Global Emissions Monitoring & Reporting for FoE, MEA & NA will ensure regional compliance regarding fleet averages for CO2 and fuel economy, enabling global synergies and avoiding penalties. Heavy Duty GHG & Co2 fleet averages and individual vehicle level monitoring / reporting addresses compliance with fleet average targets for the segment above 7.5 tons globally. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-09-30 | 2024-09-30 | 2024-09-30 | Complete | Blue | 2024-11-15 | 2024-11-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Priya | 2025-03-13 |  |  |  | No | Java < v21
17689 | Global Emissions Manager | In Production | GEM | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Bronze | Non S-Ox | 211 | No | Yes | COTS | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | The GEM database is a global environmental compliance tool that supports Environmental Operating System (EOS) implementation and the tracking of waste, water, CO2, and environmental scorecard metrics consistent with Manufacturing Business Plans. (GEM was formerly known as GHG - Green House Gases) | 350 |  | YES | 5 | BWUNNAVA | PLM | BO | Q4 2025 | Migrate to QlikSense | Modernize | 2025-12-30 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | QlikSense | [5 empty] | No | DA
17689 | Global Emissions Manager | In Production | GEM | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Bronze | Non S-Ox | 211 | No | Yes | COTS | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | The GEM database is a global environmental compliance tool that supports Environmental Operating System (EOS) implementation and the tracking of waste, water, CO2, and environmental scorecard metrics consistent with Manufacturing Business Plans. (GEM was formerly known as GHG - Green House Gases) |  |  | YES | 5 | BWUNNAVA | PLM | Java Struts | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
17689 | Global Emissions Manager | In Production | GEM | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Bronze | Non S-Ox | 211 | No | Yes | COTS | DKAVITHA | DKAVITHA | Policy | Industrial System IT | The GEM database is a global environmental compliance tool that supports Environmental Operating System (EOS) implementation and the tracking of waste, water, CO2, and environmental scorecard metrics consistent with Manufacturing Business Plans. (GEM was formerly known as GHG - Green House Gases) |  |  | YES | 5 | BWUNNAVA | PLM | Oracle | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Oracle
17689 | Global Emissions Manager | In Production | GEM | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Bronze | Non S-Ox | 211 | No | Yes | COTS | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | The GEM database is a global environmental compliance tool that supports Environmental Operating System (EOS) implementation and the tracking of waste, water, CO2, and environmental scorecard metrics consistent with Manufacturing Business Plans. (GEM was formerly known as GHG - Green House Gases) |  |  | YES | 5 | BWUNNAVA | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
50070 | Global Emissions Reporting and Forecasting | In Production | GERF | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Silver | Non S-Ox | 211 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Global Emissions Monitoring & Reporting for FoE, MEA & NA will ensure regional compliance regarding fleet averages for CO2 and fuel economy, enabling global synergies and avoiding penalties. Heavy Duty GHG & Co2 fleet averages and individual vehicle level monitoring / reporting addresses compliance with fleet average targets for the segment above 7.5 tons globally. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-09-30 | 2024-09-30 | 2024-09-30 | Complete | Blue | 2024-11-15 | 2024-11-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Priya | 2025-03-13 |  |  |  | No | SQL
54480 | Global eCommerce Platform (2.0) | In Production | eComm360 | M&S TECH | KHEMANT | KHEMANT | KDANDUPA | MVAIRAP1 | Gold | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Enterprise Technology | 322 | REENACTMENT OF FORD CURRENT VEHICLE ECOMMERCE PLATFORM FROM A MONOLITHIC VENDOR SOLUTION (SAP HYBRIS) TO A CUSTOM-DEVELOPED CLOUD-NATIVE SOLUTION IN GCP. |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
52879 | Global DV Data Processor | In Development | GDDP | EVDD | NDIMMITT | GKAUR19 | RMENDO42 | JLUCAS1 | Silver | Non S-Ox | 111 | Yes | No | In-House | SHAKIM2 | NDIMMITT | Advanced PD and Tech | 111 | An application that will connect to external tools to fetch data, process it based on the necessary test level. The tool will map the high level test cases to low level test cases to be run manually or automatically, providing all necessary data |  | Springboot | YES | 3 | MJONE308 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
52879 | Global DV Data Processor | In Development | GDDP | EVDD | NDIMMITT | GKAUR19 | RMENDO42 | JLUCAS1 | Silver | Non S-Ox | 111 | Yes | No | In-House | SHAKIM2 | NDIMMITT | Advanced PD and Tech | - | An application that will connect to external tools to fetch data, process it based on the necessary test level. The tool will map the high level test cases to low level test cases to be run manually or automatically, providing all necessary data |  |  | YES | 3 | MJONE308 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | Cloud SQL PostgreSQL | [6 empty] | SQL
50653 | Additive Manufacturing Workflow Management Softwar | In Production | AMWMS | ISIT | SKING68 | JLYNN1 | JRICH264 | AELANGO | Copper | Non S-Ox | 211 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | This AM workflow software is a Additive Manufacturing specific software for 3D Printing that enables a management software that allows ordering, quoting, planning and scheduling of printed jobs that is specific to AM 3D Printing | 3 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23844 | Dealers Objectives and Incentives Solution | In Production | DOIS | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | Dealers Objectives and Incentives is a solution used to: - Track Dealers annual Objectives - Easy incentive parameterization - Compare actual x Planned - Propose dealers incentive accordingly, Currently in development to be applied in Brazil and, later on, in Ford South America | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | No VMs in latest VM Data file | No | VM
50484 | Global DEFT | In Production | GEFT | FORD CREDIT | JCHEN11 | CYANG63 | YFU33 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | - | China - Electronically moves funds between Dealers bank accounts and Ford/Ford Credit bank accounts. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
23519 | Global Dealer Web Reporting | In Production | GDWR | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | Non S-Ox | 222 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | A portal for reports used by dealers in China. |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | Java < v21
50119 | Global DAT TDM system | In Production | DTDM | ISIT | OTHERS | MKEES | KZARSE | GRAO3 | Silver | Non S-Ox | 111 | Yes | No | In-House | SPAFFRA2 | MKEES | Advanced PD and Tech | Industrial System IT | For the development of advanced driver assistance systems (ADAS), a global test data management system is required to manage files from ADAS test drives and to provide meta data storage and search capabilities. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50696 | Knock Down LOT Set Order Management System | In Production | KDLOTSOM | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | 221 | Knock Down LOT Set Order Management System (KDLOTSOM) manages KD Lot-Set Kit orders for both confirmed and forecast period. KD Kits can be ordered in user defined quantities (Lots) to support KD Kit assembly at a non-CMMS enabled 3rd party destination (Partner). This application enables KD Lot-Set program planning, KD Lot-Set order management and KD Lot-Set order tracking. It interacts with PDO upstream system to get the buildability at WERS level and CMMS downstream by providing KD order details at WERS level to drive supplier material release. Other Key functionalities: 1. Orders are driven based on SPCPS Sales allocations & CMMS OP Plan. 2. Triggers Dealer order creation in GOALS 3. Facilitates Physical VIN generation using PVG & communicates to Partner, MVP, NGAVS, GEVIS. 4. Communicates order details to NGAVS to drive PFS related functionalities at partner end. 5. Receives Vehicle Assembly Order Status from Partner systems & communicates to GEVIS. 6. Order Status Tracking from Forecast to Wholesale. |  | Springboot | YES | 4 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
22913 | Global Common Finance Calculator | In Production | FCCFC | FORD CREDIT | IPANKAJ | VSUNDA21 | SBALAGAN | ASAXENA8 | Silver | Non S-Ox | 211 | No | Yes | - | IPANKAJ | VSUNDA21 | Ford Credit Services | 211 | The Global Common Finance Calculator (GFC) is a tool that provides consumers who have selected a new, used passenger car or new commercial vehicle from the User Interface with pricing and vehicle speficication, to calculate a quotation for certain financial products |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
22913 | Global Common Finance Calculator | In Production | FCCFC | FORD CREDIT | IPANKAJ | VSUNDA21 | SBALAGAN | ASAXENA8 | Silver | Non S-Ox | 211 | No | Yes | - | IPANKAJ | VSUNDA21 | Ford Credit Services | Ford Credit (FMCC) | The Global Common Finance Calculator (GFC) is a tool that provides consumers who have selected a new, used passenger car or new commercial vehicle from the User Interface with pricing and vehicle speficication, to calculate a quotation for certain financial products |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
18607 | Global Commodity Hub | In Production | GCH | ISIT | MNOWICK1 | LSRINIVA | GPIOT1 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | This is the Global Commodity Management Hub workstream A. It is an application designed to expose the engineering, purchasing, financial, and manufacturing data necessary to create commodity business plans. The application is being developed with an outside vendor, Endeca. | 1204 |  | YES | 3 | BWUNNAVA | PLM | Datastage | Q2 2025 |  | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | [14 empty] | No | DA
18607 | Global Commodity Hub | In Production | GCH | ISIT | MNOWICK1 | LSRINIVA | GPIOT1 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | This is the Global Commodity Management Hub workstream A. It is an application designed to expose the engineering, purchasing, financial, and manufacturing data necessary to create commodity business plans. The application is being developed with an outside vendor, Endeca. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
21145 | CPMD - Central Product Marketing Data | In Production | CPMD | M&S TECH | FHIRSH | GVIJI | STHANGAV | JCOY3 | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | - | Product marketing solution for FoE Configurator, based on Adobe AEM. CPMD is a central repository for ALL customer-facing (marketing) descriptions. 1) System allows users to assign marketing descriptions to WERS codes. 2) System enables these descriptions to be re-used across models, model years or markets, without re-keying. 3) System facilitates workflow to enable translations/approvals/both. 4) Descriptions are distributed via GForce application (ITMS21144) and can be consumed by any UI that has a GForce applicationID (Web, Mobile, internal, external etc) 5) CPMD enables CV's to be sold as PV's, Vignale to be offered as a brand (if req), selling of global vehicles into EU, Accessories to be integrated into configurator; 'series as a brand' (e.g ST), used vehicle specifications for eUsed and much more. CPMD is a replacement for CDMWEPT application in Europe | 26 |  | YES | 4 | NKANDULA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-23 | 2024-12-23 | Complete | Blue | 2024-12-23 | 2024-12-23 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
21468 | Global Color Management System | In Production | GCMS | ISIT | VVIJAY55 | ABANSA15 | VBHATT | ABANSA15 | Gold | Non S-Ox | 221 | No | Yes | In-House | BGANESH | AFINK4 | Advanced PD and Tech | Industrial System IT | GCMS is the next gen ColorTrax application. The goal of GCMS is to streamline the Color Harmony, Color Release, Design Mastering and Design Quality process. Currently the process depends heavily on manual data entry, subject matter expertise and gaining Ford information from suppliers. GCMS will streamline the color release process by automatically and seamlessly pulling and updating information from upstream systems eliminating the redundant data entry that exists today and providing advanced analytical capabilities to identity gaps/issues earlier in the GPDS process. GCMS will serve as a single global repository for color and materials mastering and appearance item approval tracking and reporting. |  |  | YES | 5 | BWUNNAVA | PLM | Java Struts | TBD | 0 | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
21468 | Global Color Management System | In Production | GCMS | ISIT | VVIJAY55 | ABANSA15 | VBHATT | ABANSA15 | Gold | Non S-Ox | 221 | No | Yes | In-House | BGANESH | AFINK4 | Advanced PD and Tech | Industrial System IT | GCMS is the next gen ColorTrax application. The goal of GCMS is to streamline the Color Harmony, Color Release, Design Mastering and Design Quality process. Currently the process depends heavily on manual data entry, subject matter expertise and gaining Ford information from suppliers. GCMS will streamline the color release process by automatically and seamlessly pulling and updating information from upstream systems eliminating the redundant data entry that exists today and providing advanced analytical capabilities to identity gaps/issues earlier in the GPDS process. GCMS will serve as a single global repository for color and materials mastering and appearance item approval tracking and reporting. | 210 |  | YES | 5 | BWUNNAVA | PLM | WebFocus | Q2 2025 | Modernize | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Saran |  |  |  |  | No | DA
21468 | Global Color Management System | In Production | GCMS | ISIT | VVIJAY55 | ABANSA15 | VBHATT | ABANSA15 | Gold | Non S-Ox | 221 | No | Yes | In-House | BGANESH | AFINK4 | Advanced PD and Tech | Industrial System IT | GCMS is the next gen ColorTrax application. The goal of GCMS is to streamline the Color Harmony, Color Release, Design Mastering and Design Quality process. Currently the process depends heavily on manual data entry, subject matter expertise and gaining Ford information from suppliers. GCMS will streamline the color release process by automatically and seamlessly pulling and updating information from upstream systems eliminating the redundant data entry that exists today and providing advanced analytical capabilities to identity gaps/issues earlier in the GPDS process. GCMS will serve as a single global repository for color and materials mastering and appearance item approval tracking and reporting. |  |  | YES | 5 | BWUNNAVA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50712 | H&C - Regulated Attribute Verification Management | In Production | RAVM | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Silver | Non S-Ox | 211 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | 211 | As part of Homologate & Certify Product supports verification of regulated Attributes, e.g. for COP, ISC, RDE |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-06-28 | 2024-06-28 | 2024-06-29 | Complete | Green | 2024-07-07 | 2024-07-07 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Priya | 2025-03-13 |  |  |  | No | Java < v21
21468 | Global Color Management System | In Production | GCMS | ISIT | VVIJAY55 | ABANSA15 | VBHATT | ABANSA15 | Gold | Non S-Ox | 221 | No | Yes | In-House | BGANESH | AFINK4 | Advanced PD and Tech | Industrial System IT | GCMS is the next gen ColorTrax application. The goal of GCMS is to streamline the Color Harmony, Color Release, Design Mastering and Design Quality process. Currently the process depends heavily on manual data entry, subject matter expertise and gaining Ford information from suppliers. GCMS will streamline the color release process by automatically and seamlessly pulling and updating information from upstream systems eliminating the redundant data entry that exists today and providing advanced analytical capabilities to identity gaps/issues earlier in the GPDS process. GCMS will serve as a single global repository for color and materials mastering and appearance item approval tracking and reporting. |  |  | YES | 5 | BWUNNAVA | PLM | WAS | TBD | 0 | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
22020 | Global Collections System | In Production | FCGCS | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | Non S-Ox | 312 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Global Collections System is used to handle the workflow and attorney network for Bankrupt accounts. Many of the accounts will be worked by a vended solution - AIS starting 8-2023 with majority of existing accounts migrated 2-2024. GCS will continue to handle repo and other specialty accounts going forward. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
22020 | Global Collections System | In Production | FCGCS | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | Non S-Ox | 312 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Global Collections System is used to handle the workflow and attorney network for Bankrupt accounts. Many of the accounts will be worked by a vended solution - AIS starting 8-2023 with majority of existing accounts migrated 2-2024. GCS will continue to handle repo and other specialty accounts going forward. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Rewrite | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
11395 | Global Capacity Planning System | In Production | GCP | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | FHIRSH | Manufacturing Staffs | Marketing, Sales and Service | Computer application designed to aid in the planning of Capacity requirements for Ford Motor Company. It is a global process that calculates part volumes for assembly plant end items. |  |  | YES | 3 | NKANDULA | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Oracle
11395 | Global Capacity Planning System | In Production | GCP | M&S TECH | FHIRSH | SBINO | GSELVAKU | PSATISH2 | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | SBINO | Manufacturing Staffs | Marketing, Sales and Service | Computer application designed to aid in the planning of Capacity requirements for Ford Motor Company. It is a global process that calculates part volumes for assembly plant end items. |  |  | YES | 3 | NKANDULA | PLM | Java Struts | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
50712 | H&C - Regulated Attribute Verification Management | In Production | RAVM | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Silver | Non S-Ox | 211 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | As part of Homologate & Certify Product supports verification of regulated Attributes, e.g. for COP, ISC, RDE |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-06-28 | 2024-06-28 | 2024-06-29 | Complete | Green | 2024-07-07 | 2024-07-07 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Priya | 2025-03-13 |  |  |  | No | SQL
212 | Global Business Management Database | In Production | GBMDB | M&S TECH | NKANDULA | JLEWIS10 | TMCKEE2 | JHARPER2 | Gold | Non S-Ox | 212 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | GBMDB is a Ford IT Business Led application to support an outside Vendor application called FBMI (SoA 2018-513). Both applications are managed by the applicable Business Units. The role of GBMDB is an integral application in creating/providing the following: Dealer Attributes, Dealer Association, Dealer Financial Statement, Sales, Registration, OneCX, Certified Pre-Owned, Lead Internet Sales, Extended Service Plan, Working Capital, Sales Expectancy, Dealer Billing, MMO Dealer Billing, NASA - Customer Billing, President's Award, NADA & Performance data. GBMDB was totally redesigned in 2012, which resulted in the new ACR 2012-148. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q4 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
212 | Global Business Management Database | In Production | GBMDB | M&S TECH | NKANDULA | JLEWIS10 | TMCKEE2 | JHARPER2 | Gold | Non S-Ox | 212 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | GBMDB is a Ford IT Business Led application to support an outside Vendor application called FBMI (SoA 2018-513). Both applications are managed by the applicable Business Units. The role of GBMDB is an integral application in creating/providing the following: Dealer Attributes, Dealer Association, Dealer Financial Statement, Sales, Registration, OneCX, Certified Pre-Owned, Lead Internet Sales, Extended Service Plan, Working Capital, Sales Expectancy, Dealer Billing, MMO Dealer Billing, NASA - Customer Billing, President's Award, NADA & Performance data. GBMDB was totally redesigned in 2012, which resulted in the new ACR 2012-148. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
20062 | Global Brand Protection System | In Production | GBPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Copper | Non S-Ox | 111 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | This application will track brand protection exemption requests and approvals. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | 50% | 0% | [6 empty] | Cloud Run | [5 empty] | No | Java < v21
20062 | Global Brand Protection System | In Production | GBPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Copper | Non S-Ox | 111 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | This application will track brand protection exemption requests and approvals. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
50712 | H&C - Regulated Attribute Verification Management | In Production | RAVM | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Policy | Industrial System IT | As part of Homologate & Certify Product supports verification of regulated Attributes, e.g. for COP, ISC, RDE | 2 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-06-28 | 2024-06-28 | 2024-06-29 | Complete | Green | 2024-07-07 | 2024-07-07 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Priya | 2025-03-13 |  |  |  | No | VM
20062 | Global Brand Protection System | In Production | GBPS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Copper | Non S-Ox | 111 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | This application will track brand protection exemption requests and approvals. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | [5 empty] | No | Java < v21
436 | Global 8D | In Production | G8D | ISIT | JDEGUZMA | RMEHTA3 | RJAMBUNA | ISIDDIQ6 | Bronze | Non S-Ox | 211 | No | Yes | COTS | JDEGUZMA | JDEGUZMA | PD Operations and Quality | Industrial System IT | Global 8D 8 steps to problem solving to Prevent problem reoccurrence. Team oriented. Global web application used worldwide and with suppliers.Global 8D on the web (Global 8 Disciplines) is the corporate problem solving tool that supports the Global 8D process and is used world-wide throughout Ford Motor Company and it suppliers. The Global 8D process (an FTEP requirement) assists by providing an effective framework for problem solving by integrating the different skills required to solve problems and prevent their reoccurrence into a step-by-step approach that has been tested over time and proven effective. Primary Users: Manufacturing and Product Development. |  |  | YES | 1 | BWUNNAVA | PLM | Oracle | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
51137 | GL Essbase | In Production | GL Essbase | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 222 | No | Yes | COTS | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | This application is a subsect of PSGL Suite of applications |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
50740 | Gravity Sketch | In Production | GS | ISIT | SBONNICI | KRAMMOHA | IWEITZER | IWEITZER | Bronze | Non S-Ox | 311 | Yes | No | - | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | Gravity Sketch is a VR (virtual reality) design creative tool. Feasibility and reference data (including 3D data and imagery) can be imported and 3D data can be exported for use downstream in the design process. | 9 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to SaaS | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | VM
53317 | BookitLab | In Production | bookitlab | OCETO | PMILLIGA | TYOUNG91 | RDOLLETE | WJUSTICE | Bronze | Non S-Ox | 211 | No | Yes | COTS | TGEIGER | TYOUNG91 | Enterprise Technology | - | Bookit-Lab is a comprehensive and easy to use Lab & Asset Management tool to manage and maintain software and hardware assets, reservations and storage of test results. | 4 |  | YES | 2 | PMILLIGA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | No VMs in latest VM Data file | No | VM
9056 | GIROBS: GLOBAL INV REVIEW OBSOLESCENCE SYS | In Production | GIROBS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Bronze | Non S-Ox | 121 | No | Yes | In-House | NBAECKER | NBAECKER | Ford Customer Service | FCSD Tech | GIROBS is a web-based application that is a long term forecasting system for parts which have gone out of production. Forecast is based on demand in the year the part went out of production. The GIROBS application does the majority of the data manipulation on the mainframe. Any modifications that occur on the web are applied on the mainframe on a nightly basis in batch. The tables for GIROBS are DRDA downloaded to Oracle after batch processing on a nightly basis. The application functionality includes: simulation, graphing and maintenance. The target audience for the GIROBS application is the Forecast Analyst & Management. Business Criticality: Med-L Additional Outage Impact includes: Impact to Financial Results. |  |  | YES | 5 | RKENNEL | PLM | Oracle | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Oracle
9056 | GIROBS: GLOBAL INV REVIEW OBSOLESCENCE SYS | In Production | GIROBS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Bronze | Non S-Ox | 121 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | GIROBS is a web-based application that is a long term forecasting system for parts which have gone out of production. Forecast is based on demand in the year the part went out of production. The GIROBS application does the majority of the data manipulation on the mainframe. Any modifications that occur on the web are applied on the mainframe on a nightly basis in batch. The tables for GIROBS are DRDA downloaded to Oracle after batch processing on a nightly basis. The application functionality includes: simulation, graphing and maintenance. The target audience for the GIROBS application is the Forecast Analyst & Management. Business Criticality: Med-L Additional Outage Impact includes: Impact to Financial Results. |  |  | YES | 5 | RKENNEL | PLM | Mainframe | Q2 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9056 | GIROBS: GLOBAL INV REVIEW OBSOLESCENCE SYS | In Production | GIROBS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Bronze | Non S-Ox | 121 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | GIROBS is a web-based application that is a long term forecasting system for parts which have gone out of production. Forecast is based on demand in the year the part went out of production. The GIROBS application does the majority of the data manipulation on the mainframe. Any modifications that occur on the web are applied on the mainframe on a nightly basis in batch. The tables for GIROBS are DRDA downloaded to Oracle after batch processing on a nightly basis. The application functionality includes: simulation, graphing and maintenance. The target audience for the GIROBS application is the Forecast Analyst & Management. Business Criticality: Med-L Additional Outage Impact includes: Impact to Financial Results. |  |  | YES | 5 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
50779 | H&C-Heavy Duty Verify | In Production | HD Verify | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 231 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | As part of Homologate & Certify Product supporting the Heavy duty dyno cert process for EPA & CARB |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | SQL
9056 | GIROBS: GLOBAL INV REVIEW OBSOLESCENCE SYS | In Production | GIROBS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Bronze | Non S-Ox | 121 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | GIROBS is a web-based application that is a long term forecasting system for parts which have gone out of production. Forecast is based on demand in the year the part went out of production. The GIROBS application does the majority of the data manipulation on the mainframe. Any modifications that occur on the web are applied on the mainframe on a nightly basis in batch. The tables for GIROBS are DRDA downloaded to Oracle after batch processing on a nightly basis. The application functionality includes: simulation, graphing and maintenance. The target audience for the GIROBS application is the Forecast Analyst & Management. Business Criticality: Med-L Additional Outage Impact includes: Impact to Financial Results. |  |  | YES | 5 | RKENNEL | PLM | WAS | Q2 2026 | Version Upgrade | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
12815 | GIM Online Annual File Review | In Production | OnlineAFR | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Copper | Non S-Ox | 221 | No | Yes | In-House | DDESAI | KADOMKAI | Policy | Staffs IT | Support the Annual File Review application - this application presents records from EDMS (electronic records) and Accutrac (hardcopy records) for users to review. |  |  | YES | 1 | TSWEEN16 | PLM | WAS | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-15 | Complete | Blue | 2025-06-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 75% |  | Cloud Run |  |  |  |  | BO component migrated to GCP, Security tools integration is pending | No | Java < v21
19544 | GIM Accutrac | In Production | Accutrac | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Silver | Non S-Ox | 221 | No | Yes | COTS | DDESAI | KADOMKAI | Policy | Staffs IT | Ford's implementation of Iron Mountain's Accutrac software provides a total records management solution, one that manages active and inactive records wherever they reside, from a single interface. Accutrac software supports a full range of capabilities required for physical records management. Manage records through their entire lifecycle Reduce overall storage costs Mitigate legal, regulatory and compliance risks and provide clear audit trails. Streamline records retrieval onsite or offsite. Create standard and customized reports. Extend enterprise content management or document management investments Accutrac software helps companies apply a consistent and compliant records management program in line with documented policies. As a DoD 5015.2 certified application, it offers enterprise-scale, configurable workflows for the classification and indexing of records to support robust retention management, legal holds, and final disposition. Replaced GARMS application, ITMS 12076. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | SQL
50779 | H&C-Heavy Duty Verify | In Production | HD VERIFY | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 231 | No | Yes | In-House |  |  | Policy | Industrial System IT | As part of Homologate & Certify Product supporting the Heavy duty dyno cert process for EPA & CARB | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20379 | ARG. PLANT ACCESS REPORT (AR) | In Production | ARAR | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Land | Staffs IT | System that receives feed from the corporate card access system and other HR interfaces in order to be able to get reports online of: - Badge Audit trails - Presence of personel in an area - Cafeteria control - Monitor Fleet usage - Gas consumption control | 4 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | No VMs in latest VM Data file | No | VM
53277 | GFT_Labtronics | In Production | Labtronics | ISIT | JPITTERL | STHOM124 | AVARADI1 | JLUCAS1 | Bronze | Non S-Ox | 222 | Yes | No | COTS | JPITTERL | STHOM124 | PD Operations and Quality | Industrial System IT | Component testing test bench application |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50986 | Manufacturing Vehicle Distribution - Corrective Action Management | In Production | MVD-CAM | ISIT | VVIJAY55 | RADAM10 | VDODDAMR | SSENTH15 | Silver | Non S-Ox | 122 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | The purpose of Manufacturing Vehicle Distribution - Corrective Action Management is to assist with the handling of exceptions when a VIN is off-plan between vehicle production and delivery to the final destination. This can include facilitating Spot Buys, Diversions, Manual Invoice submission and approvals, and telematics alerts based on various business thresholds and KPI criteria. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-09-30 | 2024-12-16 | 2024-12-09 | Complete | Blue | 2025-01-31 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Ramesh | 2025-03-10 |  |  |  | No | SQL
51218 | GFT_Jedox-BI | In Production | Jedox | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SFRANCI8 | AKANSKI | Manufacturing Plants | - | Datawarehousing solution for financial reporting and planning |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
15910 | Workforce Management | In Production | WFM | FORD CREDIT | IPANKAJ | VSUNDA21 | VSANGEE6 | SMOCK6 | Silver | Non S-Ox | 111 | No | Yes | COTS | IPANKAJ | IPANKAJ | Ford Credit Services | Ford Credit (FMCC) | WFM Workforce application leveraged Verint Workforce Management, Verint Performance Management, Verint Desktop & Process Analytics, Nonvoice products of Verint. eWFM is used to create flexible and efficient agent work schedules, forecast future call volumes, determine the number of agents needed throughout the day and respond immediately to changes in call patterns and agent availability. All the ford credit application data feeds will flow into Verint via eWorkforce application It gives managers the information they need to work with individual agents to help them better adhere to their schedules, makes overall staffing plans more effective. Easily readable desktop windows show how many minutes early or late an agent logs on, when the agent logs out, and when the agent is on break or otherwise unavailable. A status bar constantly compares number of agents scheduled to the number actually logged in and signals when an agent has spent more than a specified amount of time in predetermined activity. | 21 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2025-06-15 |  | Planned | [17 empty] | VM
22772 | GFORCE3 | In Production | GFORCE3 | M&S TECH | FHIRSH | GVIJI | GYANIT | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | 223 | Global Ford Configurator Engine (GForCE) provides services to quickly communicate the compatibility, completeness, and context of features defining a vehicle. For example, applications that support dealer ordering or consumer build and price sites would use configuration services when allowing end users to understand what features are available and to select features that make up a vehicle. |  | Springboot | YES | 4 | NKANDULA | PLM | Java < v21 | Q2 2025 | Version Upgrade | Modernize | 2025-06-15 | 2025-04-30 |  | In-Progress | Green | 2025-07-29 |  | Planned |  | No | 100% | 100% | 100% | 75% | 100% | 100% | 100% |  | Java 17 | [5 empty] | Yes | Java < v21
22772 | GFORCE3 | In Production | GFORCE3 | M&S TECH | FHIRSH | GVIJI | GYANIT | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | Global Ford Configurator Engine (GForCE) provides services to quickly communicate the compatibility, completeness, and context of features defining a vehicle. For example, applications that support dealer ordering or consumer build and price sites would use configuration services when allowing end users to understand what features are available and to select features that make up a vehicle. |  |  | YES | 4 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | This is not partial. Timeline is correct | No | DA
22772 | GFORCE3 | In Production | GFORCE3 | M&S TECH | FHIRSH | GVIJI | GYANIT | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | Global Ford Configurator Engine (GForCE) provides services to quickly communicate the compatibility, completeness, and context of features defining a vehicle. For example, applications that support dealer ordering or consumer build and price sites would use configuration services when allowing end users to understand what features are available and to select features that make up a vehicle. |  |  | YES | 4 | NKANDULA | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-04-30 |  | In-Progress | Green | 2025-07-29 |  | Planned |  | No | 100% | 100% | 100% | 75% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | Yes | SQL
19175 | Workflow II | In Production | WorkflowII | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RPARAME4 | Copper | S-Ox In Scope | 321 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Business Process Management application Workflow to support Account Servicing functions at Ford Credit business centers. | 15 |  | YES | 3 | SRAISIN1 | PLM | VM | Q3 2027 | Partial Migration to GCP | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2025-06-15 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
11758 | GEVIS - Global Export Vehicle Info System | In Production | GEVIS | M&S TECH | FHIRSH | NGIRISH | LSCHLEBA | CKEMPSKI | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | GEVIS is one of the FTC suite of systems. It is the status repository for all order and vehicle status information for IMG markets. SLA CIA 2,3,2 Also GEVIS hosts data for AP, S. America and Ford Otosan to support TREAD Act as well as day to day FCSD operations in the Regions (Data in GEVIS is notonly Export but also Domestic and Imports for AP and S. America including Ford Otosan) | 52 |  | YES | 4 | NKANDULA | PLM | Datastage | Q1 2025 |  | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | 100% | 50% | 25% | [11 empty] | No | DA
11758 | GEVIS - Global Export Vehicle Info System | In Production | GEVIS | M&S TECH | FHIRSH | NGIRISH | LSCHLEBA | CKEMPSKI | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | lschleba | Marketing & Sales | Marketing, Sales and Service | GEVIS is one of the FTC suite of systems. It is the status repository for all order and vehicle status information for IMG markets. SLA CIA 2,3,2 Also GEVIS hosts data for AP, S. America and Ford Otosan to support TREAD Act as well as day to day FCSD operations in the Regions (Data in GEVIS is notonly Export but also Domestic and Imports for AP and S. America including Ford Otosan) | 4 |  | YES | 4 | NKANDULA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11758 | GEVIS - Global Export Vehicle Info System | In Production | GEVIS | M&S TECH | FHIRSH | NGIRISH | LSCHLEBA | CKEMPSKI | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | GEVIS is one of the FTC suite of systems. It is the status repository for all order and vehicle status information for IMG markets. SLA CIA 2,3,2 Also GEVIS hosts data for AP, S. America and Ford Otosan to support TREAD Act as well as day to day FCSD operations in the Regions (Data in GEVIS is notonly Export but also Domestic and Imports for AP and S. America including Ford Otosan) |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11758 | GEVIS - Global Export Vehicle Info System | In Production | GEVIS | M&S TECH | FHIRSH | NGIRISH | LSCHLEBA | CKEMPSKI | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | GEVIS is one of the FTC suite of systems. It is the status repository for all order and vehicle status information for IMG markets. SLA CIA 2,3,2 Also GEVIS hosts data for AP, S. America and Ford Otosan to support TREAD Act as well as day to day FCSD operations in the Regions (Data in GEVIS is notonly Export but also Domestic and Imports for AP and S. America including Ford Otosan) |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
8137 | GEVIS | Not In EAMS |  | OTHERS | OTHERS | [5 empty] | - | No | Yes | - | OTHERS | OTHERS | Marketing & Sales |  |  |  |  | YES | 1 | OTHERS | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | DA
121 | GEOS: Global Export Ordering System | In Production | GEOS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | The primary functionality introduced by GEOS is the ability to take stocking and emergency orders for service parts from Ford affiliates and WDMO dealers as well as providing visibility to the Global Liaison Center (GLC) employees. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q3 2026 | Modernize to Cloud Databases | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | SQL
23886 | VMware vSphere x.x Enterprise Data Center | In Production | VSPHXEDC | EPEO | LFULCHER | KMAHAJAN | GBRADFO3 | GBRADFO3 | Copper | Non S-Ox | 111 | No | Yes | COTS | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | For use in the Enterprise Data Center only. VMware vSphere Version 6.x server virtualization software -- includes vCenter (client and server), Site Recovery Manager (SRM), VMwareConverter, ESXi, Log Insight, vRealize Operations Manager, vRealize Business Enterprise, vSAN, vSphere replication and vSphere Automation suite (includes VRA and VRO). | 3 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
121 | GEOS: Global Export Ordering System | In Production | GEOS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House |  |  | Ford Customer Service | FCSD Tech | The primary functionality introduced by GEOS is the ability to take stocking and emergency orders for service parts from Ford affiliates and WDMO dealers as well as providing visibility to the Global Liaison Center (GLC) employees. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  | Springboot | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
24003 | VMware SRM vCenter x.x (VCXSRM) | In Production | VCXSRM | EPEO | LFULCHER | KMAHAJAN | GBRADFO3 | GBRADFO3 | Silver | Non S-Ox | 112 | No | Yes | - | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | Latest version of VMware server virtualization software -- includes vCenter (client and server), Site Recovery Manager (SRM), VMwareConverter, ESXi, Log Insight, vRealize Operations Manager, vRealize Business Enterprise, vSAN, vSphere replication and vSphere Automation suite (includes VRA and VRO). | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
12343 | VMACS - Vehicle Monitoring and Control System | In Production | VMACS (EU) | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | S-Ox In Scope | 231 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Monitoring and Control System. VMACS is the centralized Ford system used in Europe to track the flow of new vehicles from the point of order entry to the point of sale (dealer delivered/retail sold) | 9 |  | YES | 6 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q3 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
653 | GEMSS (Global Engineering Management Support Sys) | In Production | GEMSS | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Bronze | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | GEMSS Global Engineering Management Support Sys GEMSS is a personal computer application that generates graphs and printed reports of selected Programs and Activities using data extracted daily from WERS Worldwide Engineering Release System. | 45 |  | YES | 5 | BWUNNAVA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
653 | GEMSS (Global Engineering Management Support Sys) | In Production | GEMSS | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Bronze | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | GEMSS Global Engineering Management Support Sys GEMSS is a personal computer application that generates graphs and printed reports of selected Programs and Activities using data extracted daily from WERS Worldwide Engineering Release System. |  |  | YES | 5 | BWUNNAVA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
653 | GEMSS (Global Engineering Management Support Sys) | In Production | GEMSS | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Bronze | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | MNOWICK1 | Advanced PD and Tech | Industrial System IT | GEMSS Global Engineering Management Support Sys GEMSS is a personal computer application that generates graphs and printed reports of selected Programs and Activities using data extracted daily from WERS Worldwide Engineering Release System. |  |  | YES | 5 | BWUNNAVA | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
653 | GEMSS (Global Engineering Management Support Sys) | In Production | GEMSS | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Bronze | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | GEMSS Global Engineering Management Support Sys GEMSS is a personal computer application that generates graphs and printed reports of selected Programs and Activities using data extracted daily from WERS Worldwide Engineering Release System. | 45 |  | YES | 5 | BWUNNAVA | PLM | WebFocus | Q3 2025 | Migrate to QlikSense | Modernize | 2025-09-15 | 2025-09-15 |  | In-Progress | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | DA
392 | GEDI: Global EDI | In Production | EuMP-GEDI | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Global EDI supports the electronic exchange of CIF830 (Material Releases) and CIF856 (Advanced shipping Notes) between CMMS, FCSD and its european Supply base (Ford & EP) and between EAO and its NA /Australian Supply base (Ford & EP)and also Ford as supplier. GEDI supports data in CIF, VDA. ODETTE and EDIFACT format. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
962 | GEC Hub | In Production | IT-GECHub | OCETO | TVASU | KBALAS13 | CBHARGAV | WJUSTICE | Gold | Non S-Ox | 333 | No | Yes | COTS | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | Data Hub for all Ford's EDI communications for Material Releases, Shipping Schedules, Advanced Shipping Notification etc. with 7000+ suppliers, Internal Applications i.e. CMMS and Ford Assembly and Manufacturing plants on a GLOBAL basis. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q3 2027 | On-Prem | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | SQL
50414 | Verint Call Recording Global | In Production | VCR-Global | FORD CREDIT | KDELTA | PBINGI | RGUTOWS3 | SMOCK6 | Silver | Non S-Ox | 311 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | Application to record contact agent calls with customers | 61 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
21540 | GDT Syntax Checker | In Production | GDTSC | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | GDT syntax checking tool to verify the Geometry Tolerance syntax for each dimentions to meet the GDT standards |  | Springboot | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
22162 | SCRA -Servicemembers Civil Relief Act | In Production | SCRA | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | Non S-Ox | 311 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The SCRA application collects Active Duty Military status data from the US Dept of Defense for use in the handling of 'adverse events' (e.g., charge-offs and repossessions) by Ford Credit applications. | 3 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
9827 | GDS: Global Distribution System | In Production | GDS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | NBAECKER | Ford Customer Service | FCSD Tech | GDS accepts aftermarket service parts orders for NA sourced vehicles from FORD dealerships located outside North America, Ford Affilate locations (eg. FORD of Venezuela, FORD of Australia, etc.) and from association partners MAZDA and NISSAN. Additional Outage Impacts include: Customer Complaint and Impact to Productivity. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Oracle will be decomissioned, PDO confirmed. | No | Oracle
9827 | GDS: Global Distribution System | In Production | GDS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | GDS accepts aftermarket service parts orders for NA sourced vehicles from FORD dealerships located outside North America, Ford Affilate locations (eg. FORD of Venezuela, FORD of Australia, etc.) and from association partners MAZDA and NISSAN. Additional Outage Impacts include: Customer Complaint and Impact to Productivity. |  |  | YES | 4 | RKENNEL | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9827 | GDS: Global Distribution System | In Production | GDS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | GDS accepts aftermarket service parts orders for NA sourced vehicles from FORD dealerships located outside North America, Ford Affilate locations (eg. FORD of Venezuela, FORD of Australia, etc.) and from association partners MAZDA and NISSAN. Additional Outage Impacts include: Customer Complaint and Impact to Productivity. |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
21640 | SAS Real Time Decision Manager | In Production | SAS RDM | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | TSAILESH | Gold | Non S-Ox | 333 | No | Yes | COTS | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | SAS vendor client/server software that provides centralized control of development/delivery of tailored collections and originations strategies and scorecards (risk engine) across all portfolios and migrates them through all environments. It replaces Experian's New Business strategy Manager scoring engine software for Originations and Experian's Probe Strategy Manager scoring engine software for Collections. This software also provides a repository for scorecards, strategies and metadata. | 14 |  | YES | 1 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
12967 | GDS Online | In Production | gdsonl | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | NBAECKER | Ford Customer Service | FCSD Tech | Provides online access for GDS business partners. GDS accepts aftermarket service parts orders for NA sourced vehicles from FORD dealerships located outside North America, Ford Affilate locations (eg. FORD of Venezuela, FORD of Australia, etc.) and from association partners MAZDA and NISSAN. Additional Outage Impacts include: Customer Complaint and Impact to Productivity. |  |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Oracle will be decomissioned, PDO confirmed. | No | Oracle
50563 | Onesumx for Risk Management | In Production | RiskPro | FORD CREDIT | RMINHAS3 | PSRIKIR1 | RMRINAL2 | NKALE | Gold | Non S-Ox | 332 | No | Yes | COTS | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | WK Regulatory & Liquidity Reporting System | 10 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
12967 | GDS Online | In Production | gdsonl | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House |  |  | Ford Customer Service | FCSD Tech | Provides online access for GDS business partners. GDS accepts aftermarket service parts orders for NA sourced vehicles from FORD dealerships located outside North America, Ford Affilate locations (eg. FORD of Venezuela, FORD of Australia, etc.) and from association partners MAZDA and NISSAN. Additional Outage Impacts include: Customer Complaint and Impact to Productivity. |  | Springboot | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Java 21 | [5 empty] | No | Java < v21
51082 | GDIA Reporting | In Production | GDIA-R | GDIA | CBUCKL19 | KJINNA | SMAHAPA1 | MPATEL20 | Bronze | Non S-Ox | 211 | No | Yes | - | EBLOCH | LDESHPAN | Enterprise Technology | - | A reporting engine built using Business Objects that allows users to build their own interactive or static reports using CKS-A, CKS-W Teradata databse and SDE Hadoop database. | 57 |  | NO | 1 | FRANBELL | PLM | BO | Q4 2024 | Already Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-31 | 2024-12-31 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
51716 | GDIA Discovery Zone - NAS & SQL Storage | In Production | GDIANASSQL | GDIA | AFRADKIN | PKHARE2 | JROSS119 | GARUNAC1 | Bronze | Non S-Ox | 312 | No | Yes | In-House | EBLOCH | PKHARE2 | Enterprise Technology | - | This represents the Inputs and Outputs (Files and Data Tables) as well as the development artifacts (Workflows and Dashboards) that GDIA teams and Democratized users use for the Alteryx (23288) workflows and Qlik dashboards they create. |  |  | YES | 2 | FRANBELL | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 | 2025-02-20 | Complete | Blue | 2025-03-31 |  | Planned |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | SQL
52577 | Nuance NLU & TTS Services | In Production | NLU | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Silver | Non S-Ox | 111 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | Application consists of Nuance ASR and TTS services | 14 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
15406 | NextGen DM | In Production | NextGen | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | NextGen DM is the new recovery management system that manages the charged-off accounts through the recovery process. This system interfaces with vendors and internal systems to process financial transactions for charged-off accounts. RMS2 is implemented in FICO Debt Manager solution. | 8 |  | YES | 5 | SRAISIN1 | PLM | VM | Q3 2027 | EDC New Hypervisor | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
52931 | GDIA Command Center Platform | In Production | GDIA CCPfm | GDIA | EBLOCH | PKHARE2 | HMCCORM7 | GARUNAC1 | Silver | Non S-Ox | 111 | No | Yes | In-House | EBLOCH | PKHARE2 | Enterprise Technology | 111 | Platform to support the collection, transformation, and visualization of Data Quality, Data Relevancy, and Operational Metrics to support GDIA Command Center Operations and GDIA products |  | Springboot | NO | 3 | FRANBELL | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
52931 | GDIA Command Center Platform | In Production | GDIA CCPfm | GDIA | EBLOCH | PKHARE2 | HMCCORM7 | GARUNAC1 | Silver | Non S-Ox | 111 | No | Yes | In-House | EBLOCH | PKHARE2 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Platform to support the collection, transformation, and visualization of Data Quality, Data Relevancy, and Operational Metrics to support GDIA Command Center Operations and GDIA products |  |  | NO | 3 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
15438 | MD&R/PARMS | In Production | PARMS | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | This Application ID applies to both the Plan and Rate Management System PARMS and Mechanized Discounting and Rate MD&R applications. . MD&R performs Loan Originations contract validations and contract data management . PARMS is a user interface for the development and launching of finance plans, and, rate structures for retail, lease and TRAC products. The Business Application Data Owners are: PARMS: kdudley1 MD&R: mmanion; lmervyn | 4 |  | YES | 4 | SRAISIN1 | PLM | VM | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
23779 | GDIA - Informatica Tools | Active | INFA | GDIA | CPELTZE1 | MWILLI20 | MMAES | RPOLLO13 | Silver | Non S-Ox | - | No | - | - | MLYONS23 | MLYONS23 | Information Technology | Global Data Insight and Analytics (GDIA) | This tool covers data management, and Self service solutions for GDIA. Includes the following components: Big Data Management (BDM), Enterprise Data Catalog (EDC). and Data Privacy Management (DPM). |  |  | NO | 2 | FRANBELL | PLM | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize |  | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
15470 | Lending Automotive-LA Applications (FCNA and FAFC) | In Production | LA | FORD CREDIT | IPANKAJ | RRAJESH8 | TNARAYA2 | NVARADA2 | Silver | S-Ox In Scope | 332 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Externally hosted - FCNA and FAFC Lending Automotive (LA) system is designed to track all retail installment loans and customer leases from booking to conclusion, including payments, disbursements, account closing, late charges and fees. | 1 |  | YES | 4 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
53115 | GDIA - Informatica (ADM)(INFA-ADM) | Active | INFA-ADM | EPEO | SKULKA52 | MWILLI20 | MMAES | RPOLLO13 | Bronze | Non S-Ox | - | No | - | - | CMIRABIT | CMIRABIT | Information Technology | Global Data Insight and Analytics (GDIA) | This is a PLACEHOLDER EAMS entry, per the 'IT Application Portfolio Management' guidelines. Customers of this service are required to raise their own EAMS entries, complete GRC App Assessments, etc. as required. This tool covers the 'GDIA - Informatica Tools (23779)' Engineering/Development environment used by GDIA. This tool covers data management, and self-service solutions for GDIA. Includes the following components: Big Data Management (BDM), Enterprise Data Catalog (EDC) and Data Privacy Management (DPM). This is not an 'Application'. This EAMS record is required to manage server ownership, and other contact information needed by Server Hosting. |  |  | YES | 2 | SWALIMBE | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
21472 | IT Spending Agreement | In Production | ITSA | OCETO | TVASU | SANANTH | PMCAULIF | WJUSTICE | Copper | Non S-Ox | 211 | No | Yes | In-House | TVASU | SANANTH | Enterprise Technology | Technology & Enterprise Services (TES) | The IT Spending Agreement workflow application is used by teams that need to establish financial commitments and support billing of IT services. The ITSA tool is used to obtain electronic approvals for the commitments. | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q3 2027 | Partial Migration to GCP | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23288 | GDIA - Alteryx | Active | Alteryx | EPEO | SKULKA52 | MWILLI20 | TCULLER | GARUNAC1 | Silver | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | GDIA | Global Data Insight and Analytics (GDIA) | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
20509 | Investor Reporting and Accounting | In Production | GSIRA | FORD CREDIT | DTAURO | SKHAN29 | HMANDA | VPOTTIBO | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Investor reporting and accounting (IRA) is an application to manage retail, lease, and wholesale securitization deals, produce investor reporting and accounting, and manage Cash Wires of the deals. It is an application developed in-house and supported by Ford Credit IT. | 12 |  | YES | 3 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
52528 | GDBP | In Production | GDBP | M&S TECH | OTHERS | NLAKSHMI | TCROCKF4 | TCROCKF4 | Silver | Non S-Ox | 211 | Yes | No | In-House | SJAGADE2 | NLAKSHMI | Marketing & Sales | - | BMIT tool providing capabilities for allocations, forecasting, vehicle mix and bulk order creation |  |  | YES | 2 | NKANDULA | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
19960 | IBM Business Process Manager (BPM) | In Production | BPM | OCETO | TVASU | SANANTH | PMCAULIF | WJUSTICE | Silver | Non S-Ox | 322 | No | Yes | - | TVASU | SANANTH | Enterprise Technology | Technology & Enterprise Services (TES) | This is the entry for the BPM Core / IBM BPM application. This supports BPM common framework and utilities, along with platform services. Many applications use this as part of their overall solution and should define this as part of their architecture manifest. | 115 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q3 2027 | Partial Migration to GCP | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
86 | GCQIS: Global Common Quality Indicator Sys | In Production | GCQIS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 122 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Enterprise Technology | FCSD Tech | GCQIS provides a number of report entry methods for users to document vehicle quality concerns. Users can then analyze reports for trends and concern identification, concerns can be opened and tracked through resolution. A number of downstream customers use GCQIS report data for various purposes including TREAD ACT reporting. | 1 |  | YES | 6 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
86 | GCQIS: Global Common Quality Indicator Sys | In Production | GCQIS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 122 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Enterprise Technology | FCSD Tech | GCQIS provides a number of report entry methods for users to document vehicle quality concerns. Users can then analyze reports for trends and concern identification, concerns can be opened and tracked through resolution. A number of downstream customers use GCQIS report data for various purposes including TREAD ACT reporting. |  |  | YES | 6 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
86 | GCQIS: Global Common Quality Indicator Sys | In Production | GCQIS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 122 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Enterprise Technology | FCSD Tech | GCQIS provides a number of report entry methods for users to document vehicle quality concerns. Users can then analyze reports for trends and concern identification, concerns can be opened and tracked through resolution. A number of downstream customers use GCQIS report data for various purposes including TREAD ACT reporting. |  |  | YES | 6 | RKENNEL | PLM | Mainframe | Q3 2027 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
86 | GCQIS: Global Common Quality Indicator Sys | In Production | GCQIS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 122 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Enterprise Technology | FCSD Tech | GCQIS provides a number of report entry methods for users to document vehicle quality concerns. Users can then analyze reports for trends and concern identification, concerns can be opened and tracked through resolution. A number of downstream customers use GCQIS report data for various purposes including TREAD ACT reporting. |  |  | YES | 6 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
22012 | Global Unified Contact Center Enterprise | Planned | GUCCE | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Silver | Non S-Ox | 223 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | - | Cisco based IP Contact Center infrastructure supporting Ford Contact Center operations across the globe. | 217 |  | YES | 3 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
86 | GCQIS: Global Common Quality Indicator Sys | In Production | GCQIS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 122 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Enterprise Technology | FCSD Tech | GCQIS provides a number of report entry methods for users to document vehicle quality concerns. Users can then analyze reports for trends and concern identification, concerns can be opened and tracked through resolution. A number of downstream customers use GCQIS report data for various purposes including TREAD ACT reporting. |  |  | YES | 6 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
24204 | GCCT - Dynamics 365 | In Production | GCCT | M&S TECH | RAHMED33 | DPOOVATH | AROSS76 | MSCHOLT3 | Silver | Non S-Ox | 322 | No | Yes | COTS | APALAZZO | DPOOVATH | Customer Experience | Marketing, Sales and Service | Assist Customer - Global Contact Center Technology is a platform solution that includes Microsoft Dynamics 365 as the core CRM used for Case Management, and integrates with several Azure services (blob storage, Azure SQL, Cognitive Services, etc.) and multiple internal applications (SAVE-IO, SCA-C, etc.) as well as various third-party applications (BBB, Agero Roadside Assistance, etc.) |  |  | YES | 2 | NKANDULA | PLM | SQL | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
22053 | Global Logistics and Documentation Systems - GLADS | In Production | GLADS | M&S TECH | FHIRSH | NGIRISH | SBOINAPA | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | Ford Trading Company logistics application, used to manage invoicing, booking vehicles on vessels, and other deep sea logistics functions. | 9 |  | YES | 2 | NKANDULA | PLM | VM | Q3 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11296 | GCAT: Global Catalog | In Production | GCAT:11296 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 111 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | 111 | GCAT VB/OSP: Global Catalog VB/OSP Secondary outage impact 'Customer Complaint' |  | Springboot | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
11296 | GCAT: Global Catalog | In Production | GCAT:11296 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 111 | No | Yes | In-House | NBAECKER | NBAECKER | Ford Customer Service | FCSD Tech | GCAT VB/OSP: Global Catalog VB/OSP Secondary outage impact 'Customer Complaint' |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
11296 | GCAT: Global Catalog | In Production | GCAT:11296 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 111 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | GCAT VB/OSP: Global Catalog VB/OSP Secondary outage impact 'Customer Complaint' |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
962 | GEC Hub | In Production | IT-GECHub | OCETO | TVASU | KBALAS13 | CBHARGAV | WJUSTICE | Gold | Non S-Ox | 333 | No | Yes | COTS | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | Data Hub for all Ford's EDI communications for Material Releases, Shipping Schedules, Advanced Shipping Notification etc. with 7000+ suppliers, Internal Applications i.e. CMMS and Ford Assembly and Manufacturing plants on a GLOBAL basis. | 36 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2027 | EDC CaaS and New EDC Hypervisor | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | VM
11577 | GCAMP: Global Campaign Management System | In Production | GCAMP | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | LMADHANM | MIKRAMUL | Silver | S-Ox In Scope | 232 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | Global Campaign Management supports the Recall, Campaign Targeting, and Campaign Reporting functions for the Global Concern Management business process. | 10 |  | YES | 3 | RKENNEL | PLM | BO | Q3 2024 | Already Decommissioned | Decommission | 2024-03-24 | 2024-03-24 | 2024-03-24 | Complete | Blue | 2024-03-24 | 2024-03-24 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
11577 | GCAMP: Global Campaign Management System | In Production | GCAMP | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | LMADHANM | MIKRAMUL | Silver | S-Ox In Scope | 232 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | Global Campaign Management supports the Recall, Campaign Targeting, and Campaign Reporting functions for the Global Concern Management business process. |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q4 2026 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11577 | GCAMP: Global Campaign Management System | In Production | GCAMP | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | LMADHANM | MIKRAMUL | Silver | S-Ox In Scope | 232 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | Global Campaign Management supports the Recall, Campaign Targeting, and Campaign Reporting functions for the Global Concern Management business process. |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
11577 | GCAMP: Global Campaign Management System | In Production | GCAMP | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | LMADHANM | MIKRAMUL | Silver | S-Ox In Scope | 232 | No | Yes | In-House |  |  | ll | FCSD Tech | Global Campaign Management supports the Recall, Campaign Targeting, and Campaign Reporting functions for the Global Concern Management business process. |  | Springboot | YES | 4 | RKENNEL | PLM | Java < v21 | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
54629 | GC&IMG PD Data Insights | In Production | GPDI | ISIT | SBONNICI | KRAMMOHA | ZWAN3 | HYANG80 | Bronze | Non S-Ox | 311 | No | Yes | In-House | SBONNICI | KRAMMOHA | PD Operations and Quality | - | A platform to host dashboards which used by China PD or IMG PD for tracking vehicle program status or resource allocation score etc. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
11293 | GBO: Global Buy Optimization | In Production | GBO: 11293 | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | The GBO Web application will assure the consistent application of buy models that will optimize total inventory carrying and material costs. GBO will also provide support for the maintenance of the buy models. Estimates indicate that this project will deliver 50% of the cost savings identified in the global purchasing system project at 25% of the cost. GBO will also provide worldwide access to the buy models and efficient user interface. GBO provides access for the user to use the Economic Buy Quantity and Balance Out Buy modules by both Europe and the U.S. GBO is sponsored by the Purchasing and Material Flow organizations. Additional Outage Impacts include: Impact to Productivity and Customer Complaint. |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q2 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11293 | GBO: Global Buy Optimization | In Production | GBO: 11293 | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | The GBO Web application will assure the consistent application of buy models that will optimize total inventory carrying and material costs. GBO will also provide support for the maintenance of the buy models. Estimates indicate that this project will deliver 50% of the cost savings identified in the global purchasing system project at 25% of the cost. GBO will also provide worldwide access to the buy models and efficient user interface. GBO provides access for the user to use the Economic Buy Quantity and Balance Out Buy modules by both Europe and the U.S. GBO is sponsored by the Purchasing and Material Flow organizations. Additional Outage Impacts include: Impact to Productivity and Customer Complaint. |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
86 | GCQIS: Global Common Quality Indicator Sys | In Production | GCQIS | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | CRANJIT1 | MIKRAMUL | Silver | Non S-Ox | 122 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Enterprise Technology | FCSD Tech | GCQIS provides a number of report entry methods for users to document vehicle quality concerns. Users can then analyze reports for trends and concern identification, concerns can be opened and tracked through resolution. A number of downstream customers use GCQIS report data for various purposes including TREAD ACT reporting. | 8 |  | YES | 6 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q3 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
120 | GATES: Global Affiliate Trading and Export System | In Production | GATES | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | Route Aftermarket service parts orders from Ford Affiliates to the exporting source. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  |  | YES | 3 | RKENNEL | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
120 | GATES: Global Affiliate Trading and Export System | In Production | GATES | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | Route Aftermarket service parts orders from Ford Affiliates to the exporting source. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q2 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
120 | GATES: Global Affiliate Trading and Export System | In Production | GATES | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | RARUNAC1 | MMEHTA5 | Gold | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | Route Aftermarket service parts orders from Ford Affiliates to the exporting source. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
22779 | Gas Metrology System | In Production | GMS | ISIT | KCHRIST2 | KCHRIST2 | JCICOTTE | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | APTL's Gas Standards Lab (GSL)supplies emission gas standards traceable to NIST for use throughout the facility. Compressed gas cylinders are purchased from outside sources at specified nominal concentrations and are tested to establish their exact concentrations. This gas cylinder naming procedure is accomplished by comparing the unknown gas concentration to working standards for the purpose of establishing the exact concentrations. The existing system includes analyzers, Oracle database and Forms front end. It is obsolete and is being updated to make improved use of the newer mexa that has been put into the mix. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
20507 | Funding Forecaster | In Production | GSFF | FORD CREDIT | DTAURO | SKHAN29 | HMANDA | VPOTTIBO | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | This application provides debt and asset forecasting for all retail, lease and wholesale deals. The application is used in relation to securitization. It is an application developed in-house and supported by Ford Credit IT. | 4 |  | YES | 1 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
22090 | GAPS Documents Distribution | In Production | EuAS GDDS | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Silver | Non S-Ox | 221 | No | Yes | Open Source | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Accepts raw data from GAPS suite for both FSA and FOA markets and transforms outputs into PDF formatted document of Self Billing Invoices SBI Positive Negative and Retro and Debit and Credit Notes Maintain PDF in repository for the threshold period and allow users to download PDF via ePayables Supplier Portal User Interface for managing template forms for the total of 10 documents for both FOA FSA markets Provide an online web service for ePayables to pick display and allow the PDF SBI to be downloaded by the supplier users After threshold period the SBI PDF documents to be pushed to Documentum EDMS Archival solution Debit Credit note TIFF images to be pushed to Odyssey Application |  |  | YES | 3 | TSWEEN16 | PLM | Java Struts | Q2 2027 | Will be Decommissioned | Decommission | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
22090 | GAPS Documents Distribution | In Production | EuAS GDDS | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Silver | Non S-Ox | 221 | No | Yes | Open Source | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Accepts raw data from GAPS suite for both FSA and FOA markets and transforms outputs into PDF formatted document of Self Billing Invoices SBI Positive Negative and Retro and Debit and Credit Notes Maintain PDF in repository for the threshold period and allow users to download PDF via ePayables Supplier Portal User Interface for managing template forms for the total of 10 documents for both FOA FSA markets Provide an online web service for ePayables to pick display and allow the PDF SBI to be downloaded by the supplier users After threshold period the SBI PDF documents to be pushed to Documentum EDMS Archival solution Debit Credit note TIFF images to be pushed to Odyssey Application |  |  | YES | 3 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
21607 | FORD CREDIT LOADRUNNER | Active | FC LR | FORD CREDIT | JBRADB21 | JBRADB21 | SMOHAM98 | VCECCARE | Copper | Non S-Ox | - | No | Yes | - | SRAISIN1 | JBRADB21 | Enterprise Technology | - | Loadrunneris used for automated load testing of line of business applications. | 3 |  | YES | 1 | SRAISIN1 | PLM | VM | Q3 2027 | EDC CaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
6331 | GAPS | In Production | EuAS-GAPS | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | S-Ox In Scope | 233 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | GAPS (General Accounts Payable System) is a financial system which is used in all European companies for supplier payments. SBIs and invoices are fed into GAPS for interfacing with Peoplesoft General Ledger for accounting and to EuroAP for final payment via EFT or Cheques. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
51998 | FVEXDATA | In Production | FVEXDATA | M&S TECH | NKANDULA | TBRYANS1 | PRAO2 | RFERMAN1 | Bronze | Non S-Ox | 222 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Marketing & Sales | - | SQL database that holds lead information |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
23791 | Ford Credit GRC - RSA Archer | In Production | FCGRC | FORD CREDIT | IPANKAJ | RRAJESH8 | TNARAYA2 | RPARAME4 | Silver | Non S-Ox | 211 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Archer Technologies, LLC provides the Global Risk and Compliance application which is leveraged for the following: Daily Review Guides (DRGs) for FCNA & IMG, Risk Assessments/Risk Register for FCNA, FCE, and Germany, Risk Event Management for FCNA, FCE and Germany, Law/Regulatory Change Management for FCNA, China, and FCE, and Incident Reporting for FCNA. This is administered by FC Global Risk Management. | 19 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2027 | EDC New Hypervisor | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
52463 | Funding Services | In Production | GSFS | FORD CREDIT | DTAURO | SKHAN29 | APAUL31 | VPOTTIBO | Silver | Non S-Ox | 233 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | 233 | Ford Credit common service application provides reusable API functions for file conversion and file transfer. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q3 2027 | Version Upgrade | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
52463 | Funding Services | In Production | GSFS | FORD CREDIT | DTAURO | SKHAN29 | APAUL31 | VPOTTIBO | Silver | Non S-Ox | 233 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Ford Credit common service application provides reusable API functions for file conversion and file transfer. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [10 empty] | SQL | [6 empty] | SQL
50539 | Ford Credit Cisco Unified Communication Manager (C | In Production | CUCM | FORD CREDIT | KDELTA | PBINGI | NBUCHMAN | SMOCK6 | Gold | Non S-Ox | 113 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | CUCM is a Linux-based operating system that operates as a software-based call-processing component of IP Telephony. CUCM provides signaling and call control services to Cisco integrated telephony applications as well as to third-party applications | 58 |  | YES | 1 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
21311 | FFAP - FOCUS - CHINA ASIA PACIFIC - CFOCUS | In Production | CFOCUS | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | S-Ox Out of Scope | 332 | No | Yes | - | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | FOCUS system is an account receivable system which controls and manages Retail operations and Wholesale receivables for China. | 1 |  | YES | 3 | SRAISIN1 | PLM | VM | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
20514 | Funding Deal Compliance | In Production | GSFDC | FORD CREDIT | DTAURO | SKHAN29 | APAUL31 | VPOTTIBO | Silver | S-Ox Out of Scope | 232 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Funding Deal Compliance is a web application used to generate and obtain signature approval on mandatory Compliance deliverables for retail, lease, and wholesale Securitization deals. It is an application developed in-house and supported by Ford Credit IT |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20514 | Funding Deal Compliance | In Production | GSFDC | FORD CREDIT | DTAURO | SKHAN29 | APAUL31 | VPOTTIBO | Silver | S-Ox Out of Scope | 232 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Funding Deal Compliance is a web application used to generate and obtain signature approval on mandatory Compliance deliverables for retail, lease, and wholesale Securitization deals. It is an application developed in-house and supported by Ford Credit IT |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
20514 | Funding Deal Compliance | In Production | GSFDC | FORD CREDIT | DTAURO | SKHAN29 | APAUL31 | VPOTTIBO | Silver | S-Ox Out of Scope | 232 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Funding Deal Compliance is a web application used to generate and obtain signature approval on mandatory Compliance deliverables for retail, lease, and wholesale Securitization deals. It is an application developed in-house and supported by Ford Credit IT |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q1 2026 | Version Upgrade | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
16746 | Fuel House Fuel Monitoring System | In Production | FHFMS | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | The Fuel House Fuel Monitoring system tracks fuel levels for inventory management and tank leakage analysis which is an EPA requirement. It also tracks the types of fuels used by each test cell to facilitate EPA mandated fuel consumption reporting, relative to Building emissions. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
50125 | FCNA EUC XenApps | In Production | FCNA XenAP | FORD CREDIT | IPANKAJ | RRAJESH8 | TNARAYA2 | RPARAME4 | Silver | Non S-Ox | 211 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Provide Infrastructure to support to the use of EUC MS Office applications which are going to be affected due to latency issues caused by centralization of file servers from distributed sites to central data centers. This is the NA version of the similar project running Europe | 14 |  | YES | 1 | SRAISIN1 | PLM | VM | Q3 2027 | Partial Migration to GCP | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
18051 | FTM - File Transfer Management | In Production | FTM | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Enterprise Technology | - | The FTM (File Transfer Management) system allows file transfers from server to server through different platforms using a WEB interface. The technology requires System Analyst, Supervisor and ITI analysts. The process begins with the System Development staff supplying all information required in the FTM web page. The next step involves the supervisors responsible for transferring approvals and the last step involves Support Analysts that are responsible to validate all parameters and identify the gaps based on infrastructure information. The FTM has a database to retrieve the parameters (sFTP information). The servers and scripts do the transfers automatically based on the parameters informed by System Analysts and validated by ITI Analysts. The scripts and servers require ITI support to analyze if the servers runs the sFTP script and the analysts will also be responsible to check the servers and update the sFTP script. This technology supports Brazil, Venezuela, Argentina and Mexico ADS teams. |  |  | YES | 3 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
18051 | FTM - File Transfer Management | In Production | FTM | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Enterprise Technology | - | The FTM (File Transfer Management) system allows file transfers from server to server through different platforms using a WEB interface. The technology requires System Analyst, Supervisor and ITI analysts. The process begins with the System Development staff supplying all information required in the FTM web page. The next step involves the supervisors responsible for transferring approvals and the last step involves Support Analysts that are responsible to validate all parameters and identify the gaps based on infrastructure information. The FTM has a database to retrieve the parameters (sFTP information). The servers and scripts do the transfers automatically based on the parameters informed by System Analysts and validated by ITI Analysts. The scripts and servers require ITI support to analyze if the servers runs the sFTP script and the analysts will also be responsible to check the servers and update the sFTP script. This technology supports Brazil, Venezuela, Argentina and Mexico ADS teams. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
20934 | FCE Workflow II | In Production | FCE WF II | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RPARAME4 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | BPM application to perform task and workload management, primarily for the account servicing functions within the FCE Customer Service Centres. Based on the Lombardi Teamworks platform. | 8 |  | YES | 3 | SRAISIN1 | PLM | VM | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
14716 | FST-RA: Reporting - Analytical | In Production | FST-Report | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The FST Application supports implementation of critical accounting and financial processes, and the traceability of financial data. For high precision financial reporting and control, FST will implement a Corporate Information Factory (CIF) model, and all supporting projects must adhere to CIF architectural standards. The new FST application will optimise transaction processing performance and analytic reporting, making it easier to respond to business changes. | 800 |  | YES | 4 | TSWEEN16 | PLM | BO | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-30 | 2026-12-30 |  | In-Progress | Green | 2027-02-28 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | EXCEPTION BASED. Approval from Tom Culler received to remain on platform | No | DA
14716 | FST-RA: Reporting - Analytical | In Production | FST-Report | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The FST Application supports implementation of critical accounting and financial processes, and the traceability of financial data. For high precision financial reporting and control, FST will implement a Corporate Information Factory (CIF) model, and all supporting projects must adhere to CIF architectural standards. The new FST application will optimise transaction processing performance and analytic reporting, making it easier to respond to business changes. |  |  | YES | 4 | TSWEEN16 | PLM | Datastage | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | DA
14716 | FST-RA: Reporting - Analytical | In Production | FST-Report | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | The FST Application supports implementation of critical accounting and financial processes, and the traceability of financial data. For high precision financial reporting and control, FST will implement a Corporate Information Factory (CIF) model, and all supporting projects must adhere to CIF architectural standards. The new FST application will optimise transaction processing performance and analytic reporting, making it easier to respond to business changes. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
21767 | FCE RegPro | In Production | RegPro | FORD CREDIT | RMINHAS3 | PSRIKIR1 | RMRINAL2 | NKALE | Silver | Non S-Ox | 332 | No | Yes | COTS | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | Regulatory reporting application for European markets (UK, Portugal, Spain, Germany, & France). Third party application (RegPro) provided by Wolters Kluwer Financial Services. Receives periodic feeds (manual and automatic) from FCE LOB systems and users which produces reports in mandated format for transmission to the Financial Regulator in each market. | 24 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
14716 | FST-RA: Reporting - Analytical | In Production | FST-Report | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | The FST Application supports implementation of critical accounting and financial processes, and the traceability of financial data. For high precision financial reporting and control, FST will implement a Corporate Information Factory (CIF) model, and all supporting projects must adhere to CIF architectural standards. The new FST application will optimise transaction processing performance and analytic reporting, making it easier to respond to business changes. |  | Springboot | YES | 5 | TSWEEN16 | PLM | Java < v21 | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
14711 | FST-MPA: Manufacturing Parts Accounting | In Production | FST-MPA | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The FST Application supports implementation of critical accounting and financial processes, and the traceability of financial data. For high precision financial reporting and control, FST will implement a Corporate Information Factory (CIF) model, and all supporting projects must adhere to CIF architectural standards. The new FST application will optimise transaction processing performance and analytic reporting, making it easier to respond to business changes. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
14711 | FST-MPA: Manufacturing Parts Accounting | In Production | FST-MPA | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The FST Application supports implementation of critical accounting and financial processes, and the traceability of financial data. For high precision financial reporting and control, FST will implement a Corporate Information Factory (CIF) model, and all supporting projects must adhere to CIF architectural standards. The new FST application will optimise transaction processing performance and analytic reporting, making it easier to respond to business changes. |  |  | YES | 4 | TSWEEN16 | PLM | Mainframe | Q2 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
14711 | FST-MPA: Manufacturing Parts Accounting | In Production | FST-MPA | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | The FST Application supports implementation of critical accounting and financial processes, and the traceability of financial data. For high precision financial reporting and control, FST will implement a Corporate Information Factory (CIF) model, and all supporting projects must adhere to CIF architectural standards. The new FST application will optimise transaction processing performance and analytic reporting, making it easier to respond to business changes. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
24229 | FCE AnaCredit | In Production | AnaCredit | FORD CREDIT | RMINHAS3 | PSRIKIR1 | RMRINAL2 | NKALE | Silver | Non S-Ox | 332 | No | Yes | COTS | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | The aim of this application is to enable the work of the Single Supervisory Mechanism (SSM) by facilitating the work of the European System of Central Banks (ESCB) with respect to a centralized database of credit exposures on a loan-by-loan basis across the Eurozone. The application addressing this requirement is the AnaCredit reporting software solution provided by Wolters Kluwer (WK). This solution uses many of the same funxtionality of RegPro such as data Foundation and Report Generator, plus the TNG or web component for the WK regulatory reporting solutions. | 8 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
15652 | FST-MCA: Material Cost Analysis | In Production | FST-MCA | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 232 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | MCA is used to standardize business practices using a common tool set. In MCA, common practices will include: modeling of all relevant base vehicles and options along with unique options costs which will be available by base vehicle, by market. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
11761 | EMS: QAD -- Ford Trading Co. Invoicing. Sys | In Production | FTC QAD | M&S TECH | FHIRSH | NGIRISH | SBOINAPA | CKEMPSKI | Silver | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | NGIRISH | Finance | Marketing, Sales and Service | QAD is the tool used by Global Trade Services (GTS) for invoicing purpose. The tool has been customized for GTS business rules and use. CIA 2,3,2 | 4 |  | YES | 1 | NKANDULA | PLM | VM | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
19935 | FST-MCA 4.0: Forward Model | In Production | FST MCA FM | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 232 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Material Cost Analysis tool supporting Forward Model Cost Analysis |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
20240 | eHub-ESB | In Production | eHub-ESB | OCETO | TVASU | KBALAS13 | RMODI2 | WJUSTICE | Gold | Non S-Ox | 213 | No | Yes | COTS | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | Biztalk Enterprise Service Bus for internal and external business partner (suppliers, dealers, exchanges) messaging. | 26 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2027 | EDC CaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | VM
14713 | FST-FVA: Finished Vehicle Accounting | In Production | FST-FVA | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Synchronize, aggregate, align and record all vehicle financial events in order to align Ford book of accounts and the external finance community relative to financial analysis and reporting data. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
15912 | Desktop Integrator | In Production | DI | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Silver | Non S-Ox | 111 | No | Yes | In-House | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | Desktop Integrator provides integration to Debt Manager, LA, Bless, Alvaria Dialer, Workflow, Pinnacle and Cisco CVP and CTI servers. It uses IBMs Host on Demand products to interface with LA, Bless and DM screens. For non 3270 applications the Java applets and websocket connections. These custom interfaces allow applications to call DI or DI to call the applications. Finally DI provides a custom GUI for interfacing with Cisco IPTel call control and a menu for a small set of LA transactions. | 3 |  | YES | 1 | SRAISIN1 | PLM | VM | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
17419 | FSN - Ford Suppliers Network (South America) | In Production | FSN SA | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Supply Chain | - | Application controls suppliers website portal where suppliers check payment dates among other supplier related information. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
23685 | China Account Manager | In Production | CAM | FORD CREDIT | JCHEN11 | CYANG63 | YSUN74 | YZHU86 | Copper | Non S-Ox | 311 | No | Yes | - | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | China Account Manager is an Account Management application embedded on the WeChat, FordPass and LincolnWay containers. This mobile application includes features like allowing the customer to view Account details (payment statement), FAQ etc. | 1 |  | YES | 4 | SRAISIN1 | PLM | VM | Q3 2027 | EDC New Hypervisor | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
12466 | FSAVL : FSA VIN Lists | In Production | FSAVL | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | LMADHANM | MIKRAMUL | Silver | Non S-Ox | 222 | No | Yes | In-House |  |  | Ford Customer Service | FCSD Tech | Dealer-facing web system used to display open Field Service Action information (VIN+Owner), by dealer. |  | Springboot | NO | 1 | RKENNEL | PLM | Java < v21 |  |  | Decommission | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | NO VMs found. | No | Java < v21
17851 | FSAO Treasury Export Operations (TR) | In Production | ARTR | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Application for Treasury Export Operations control. Covers the exports process from bill to bank liquidation looking forward to ensure accomplishment with all regulations in force. |  |  | YES | 3 | TSWEEN16 | PLM | Java Struts | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17851 | FSAO Treasury Export Operations (TR) | In Production | ARTR | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | Application for Treasury Export Operations control. Covers the exports process from bill to bank liquidation looking forward to ensure accomplishment with all regulations in force. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q2 2027 | Will be Decommissioned | Decommission | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
51628 | CCOT | In Production | CCOT | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | The Contact Center Optimization Tool (CCOT) is a web based application which allows Ford contact center employees to interact with the configuration files which control call flow within the Cisco UCCE. | 2 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | VM
19254 | FSAO Full Economics (EE) | In Production | AREE | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Manages price increase requests issued by part suppliers and preparing the negotiation strategy based on the analysis of the cost structure of the parts the economic indexes evolution in the market and the impact of the price increases for the Company. Also provide cost forecasting functionality and the impact analysis due to price increase requests. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
19254 | FSAO Full Economics (EE) | In Production | AREE | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Manages price increase requests issued by part suppliers and preparing the negotiation strategy based on the analysis of the cost structure of the parts the economic indexes evolution in the market and the impact of the price increases for the Company. Also provide cost forecasting functionality and the impact analysis due to price increase requests. |  |  | YES | 4 | TSWEEN16 | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
18604 | APA SAP CRM | In Production | CRM SAP | M&S TECH | NKANDULA | SSAURAV1 | PTHAMILA | RFERMAN1 | Gold | Non S-Ox | 312 | No | Yes | COTS | SBAILE17 | TBRYANS1 | Ford Customer Service | Marketing, Sales and Service | SAP based CRM solution used by Asia Pacific and Africa. CRM Next supports the business by providing a single view of the customers and a suite of analytics and reporting tools. With these tools, the business is able to increase sales volume and loyalty through precision marketing in order to utilize the budget to increase profits. SAP CRM replaced the legacy CKS CRM system used by Australia, New Zealand, India, China, South Africa and ASEAN markets. SAP CRM is hosted in Dearborn. Also supports Fleet (AU), VISTA retail reporting, leads distribution to Dealers and Predictive service marketing for IN, AU & NZ | 45 |  | YES | 3 | NKANDULA | PLM | VM | Q3 2027 | Complete Migration to SaaS | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | VM
19254 | FSAO Full Economics (EE) | In Production | AREE | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Manages price increase requests issued by part suppliers and preparing the negotiation strategy based on the analysis of the cost structure of the parts the economic indexes evolution in the market and the impact of the price increases for the Company. Also provide cost forecasting functionality and the impact analysis due to price increase requests. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
14996 | FSAO BR SA-Timekeeping | In Production | TKP | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 321 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | WEB system with the feature of planning process and accounting worked days and hours to generate the base data for month-end payroll calculation. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is decommissioned already. VMs are decommissioned | No | Oracle
14516 | Weld Quality Reporting System | In Production | WQR | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | WQR is a database application analytical tool used by plant personnel in their efforts to identify problem areas and improve weld quality by logging weld teardown data, weld surveillance data, and generating reports on the data collected. A weld teardown is a destructive process of pulling apart an assembly. Weld surveillance is a non-destructive process of visually inspecting and pry testing weld assemblies. | 4 |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
14996 | FSAO BR SA-Timekeeping | In Production | TKP | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 321 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | WEB system with the feature of planning process and accounting worked days and hours to generate the base data for month-end payroll calculation. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is already decommissioned | No | Java < v21
21428 | FSA Government Incentive Program | In Production | FSA GIP | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This application is developed to support the government Incentive Program in South Africa called Automotive Production Development Program (APDP) effective 1st-Jan,2013, which benefits local Auto Manufacturers through Customs saving. The application will collect data as per Customs regulatory requirements and generate reports to support Quarterly Customs Accounts. It will also help to reduce duty payment due to compliance with the APDP. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 25% |  |  | 75% |  | Cloud Run | Praveen | 2025-03-06 |  |  |  | No | Java < v21
21428 | FSA Government Incentive Program | In Production | FSA GIP | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This application is developed to support the government Incentive Program in South Africa called Automotive Production Development Program (APDP) effective 1st-Jan,2013, which benefits local Auto Manufacturers through Customs saving. The application will collect data as per Customs regulatory requirements and generate reports to support Quarterly Customs Accounts. It will also help to reduce duty payment due to compliance with the APDP. |  |  | YES | 4 | TSWEEN16 | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 25% |  |  | 75% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-06 |  |  |  | No | SQL
20504 | Web Based Data Management Website | In Production | WBDM | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | The Web Based Data Management (WBDM) web site (http://www.wbdm.ford.com) is a collection of elements whose function is to provide a means of sending and reporting out on Dimensional Control information at Stamping, Assembly Plants within the Ford enterprise. This project focus on the elements of WBDM that provide Dimensional Control Process Reports to Analysts at many locations globally. The work will focus on development of a process for managing the report files that will result in generation of the interface that will provide users access to these reports. | 5 |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q3 2026 | EDC New Hypervisor | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [14 empty] | No | VM
21428 | FSA Government Incentive Program | In Production | FSA GIP | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This application is developed to support the government Incentive Program in South Africa called Automotive Production Development Program (APDP) effective 1st-Jan,2013, which benefits local Auto Manufacturers through Customs saving. The application will collect data as per Customs regulatory requirements and generate reports to support Quarterly Customs Accounts. It will also help to reduce duty payment due to compliance with the APDP. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 25% |  |  | 75% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | Java < v21
21592 | FRame Eng Design Order Manufacturing System | In Production | FREDOM | ISIT | SKING68 | JRICH264 | RCHANDA | AELANGO | Silver | Non S-Ox | 211 | No | Yes | In-House | SKING68 | RTHIRUV1 | Advanced PD and Tech | Industrial System IT | Frame Hole Management System |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
50986 | Manufacturing Vehicle Distribution - Corrective Action Management | In Production | MVD-CAM | ISIT | VVIJAY55 | RADAM10 | VDODDAMR | SSENTH15 | Silver | Non S-Ox | 122 | No | Yes | In-House |  |  | Manufacturing Staffs | Industrial System IT | The purpose of Manufacturing Vehicle Distribution - Corrective Action Management is to assist with the handling of exceptions when a VIN is off-plan between vehicle production and delivery to the final destination. This can include facilitating Spot Buys, Diversions, Manual Invoice submission and approvals, and telematics alerts based on various business thresholds and KPI criteria. |  | Springboot | YES | 4 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize |  | 2024-12-16 | 2024-12-09 | Complete | Blue | 2025-01-31 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Ramesh | 2025-03-10 |  |  |  | No | Java < v21
22327 | WBDO 2.0 | In Production | WBDO 2.0 | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | WBDO 2.0 is 2nd generation of Web Based Dealer Ordering application - a web-based solution for order entry, amendment and cancellation of unscheduled stock and retail orders for US dealers. The user interface is natural language-based, meaning that three-digit sales codes are no longer used to represent desired product content (this is a first step in moving towards a global solution). Instead, dealers are able to choose features via menus, prohibiting the entry of dirty or non-compatible orders. | 4 |  | YES | 5 | NKANDULA | PLM | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24284 | FPI - Ford Pro Intelligence | In Production | FPI | EVDD | RJOHN813 | SSURYAN3 | BGANGAVA | BGANGAVA | Silver | Non S-Ox | 322 | No | Yes | In-House | MJONE308 | RJOHN813 | Integrated Services | 322 | Suite of telematics tools for fleet management supporting Ford Pro business unit named Ford Pro Intelligence (FPI) |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
11056 | FPC: Finance Productivity Center | In Production | FPC | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | Non S-Ox | 313 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | The Finance Productivity Center (FPC) is a mainframe-FOCUS application, which serves as a central repository of accounts payable and other financial information. It provides plant and global staff locations with ad hoc financial reporting using FOCUS and Teradata. FPC has 9 upstreams: PCAM, ASR AR/GL, DOLVOL, CPARS, CCAPS, MONEX, ICS/MICS, and VOP; 5 downstream systems: Supplier GIMME (47 supplier),EVAT, Michigan Sales Tax, Industrial Reporting (IMR/GPAE), and MATS; and 27 misc.batch extracts.Entry into the system: APIMENU & PTOFOCUS, with several hundred global users spanning the Controller's Office, Quality, General Accounting, Purchasing, FCSD, NA Disbursements, MP&L, Taxation, Variable Mrktng, Corporate Staff, Internal Control, etc. Over 200 reports are generated monthly to assist in journal entries, month end/quarter end reconciliations, S-Ox audits, inventory control, chemical usage reporting, cost analysis, etc. Note: AIS Decomission Strategy utilizes FPC and Teradata for historical reporting. | 103 |  | YES | 2 | TSWEEN16 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11056 | FPC: Finance Productivity Center | In Production | FPC | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | Non S-Ox | 313 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | The Finance Productivity Center (FPC) is a mainframe-FOCUS application, which serves as a central repository of accounts payable and other financial information. It provides plant and global staff locations with ad hoc financial reporting using FOCUS and Teradata. FPC has 9 upstreams: PCAM, ASR AR/GL, DOLVOL, CPARS, CCAPS, MONEX, ICS/MICS, and VOP; 5 downstream systems: Supplier GIMME (47 supplier),EVAT, Michigan Sales Tax, Industrial Reporting (IMR/GPAE), and MATS; and 27 misc.batch extracts.Entry into the system: APIMENU & PTOFOCUS, with several hundred global users spanning the Controller's Office, Quality, General Accounting, Purchasing, FCSD, NA Disbursements, MP&L, Taxation, Variable Mrktng, Corporate Staff, Internal Control, etc. Over 200 reports are generated monthly to assist in journal entries, month end/quarter end reconciliations, S-Ox audits, inventory control, chemical usage reporting, cost analysis, etc. Note: AIS Decomission Strategy utilizes FPC and Teradata for historical reporting. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q3 2025 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
23939 | Foundational Services | In Production | FS | EVDD | JWASNIC1 | JWASNIC1 | HPAPANAS | SSURES76 | Gold | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 322 | FOUNDATIONAL SERVICES IS A SET OF COMMON GLOBAL CAPABILITIES APIS IN USE BY ALL RETAIL CONSUMER FACING APPS SUCH FORDPASS |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
23557 | Foundational Consumer Platforms | In Production | FCP | EVDD | JWASNIC1 | VVINOD3 | CJEYAKUM | MSANDILY | Gold | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 322 | CLOUD BASED APPLICATION THAT ENABLES INTEGRATION OF MARKETING APPLICATIONS INTO THE FORDPASS AND LINCOLN WAY MOBILE APPS. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
19705 | Forms Add-on Database Entry-FADE | In Production | FADE | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Copper | Non S-Ox | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | FADE will allow authorized Central Office users the ability to enter add-on product provider, program and form data which will be stored in DB2 code tables. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
19705 | Forms Add-on Database Entry-FADE | In Production | FADE | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Copper | Non S-Ox | 333 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | FADE will allow authorized Central Office users the ability to enter add-on product provider, program and form data which will be stored in DB2 code tables. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
14794 | FORDSTAR Mainframe DCS Apps | Not In EAMS |  | OTHERS | OTHERS | [5 empty] | - | No | Yes | - |  |  |  | Not in EAMS |  |  |  | YES | 1 | OTHERS | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
54698 | FordPro Insure | In Production | FPInsure | FORD CREDIT | DTAURO | DSHARM61 | SSRIVA23 | VPOTTIBO | Silver | Non S-Ox | 323 | No | Yes | Managed by 3rd Party Purchased Service | DTAURO | DSHARM61 | Finance | 323 | FordPro Insure is the application to manage Auto Insurance for Commercial Customers. It provides full functionality to handle Policy Administration, Quotes, Billing, Claims and Related Regulatory Compliance capabilities. The core functionality is provided by Origami's SaaS Platform with multiple integrations to 3rd party service providers. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
24437 | FordPay | In Production | PSL | FORD CREDIT | IPANKAJ | VNAVEEN1 | PMATHIV3 | ROBRIEN3 | Silver | Non S-Ox | 311 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 311 | FORDPAY IS AN ENTERPRISE PAYMENT PROCESSING PLATFORM WITH A SUITE OF PAYMENT FUNCTIONS, DEVELOPED AND MAINTAINED BY THE FORD CREDIT FORDPAY TEAM. FORDPAY HAS A COLLECTION OF REST APIS THAT CAN BE INTEGRATED WITH A VARIETY OF CHANNELS (MOBILE/WEB), AND PARTNERS. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50878 | FORDMATE (DcOF) | In Production | FMATEDCOF | FORD CREDIT | JBENITO | SHODGSO9 | VFERRARO | AJOGIYAT | Silver | Non S-Ox | 221 | Yes | No | Managed by 3rd Party Purchased Service | JBENITO | SHODGSO9 | Marketing & Sales | - | FORDMATE 14600 DCoF Migration. FORD MATE is Ford of Italy's version of the Dealer Portal used for communicating to Dealers. It a part of the Standard European Portal Rollout. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
14464 | Volumetric Truckload System | In Production | VT | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Parts Ordering for collison parts orders to be entered into the Order Entry Application. | 10 |  | YES | 2 | RKENNEL | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
50806 | FordLabs - Shared | Planned | FLABS | M&S TECH | SVIJAI1 | SVIJAI1 | LSREERAM | COCONN33 | - | Non S-Ox | - | No | Yes | - | APALAZZO | JFORBIS | Enterprise Technology | - | This is an ITMS # to bin any shared infrastructure or other assets that need to be tracked that are owned by FordLabs as a whole. FordLabs isn't actually an application. But, may Ford processes require you to establish an application before you can provision any infrastructure. FordLabs often works on experiments that preceed the definition and identificaiton of applications. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50806 | FordLabs - Shared | Planned | FLABS | M&S TECH | SVIJAI1 | SVIJAI1 | LSREERAM | COCONN33 | - | Non S-Ox | - | No | Yes | - | APALAZZO | JFORBIS | Enterprise Technology | Marketing, Sales and Service | This is an ITMS # to bin any shared infrastructure or other assets that need to be tracked that are owned by FordLabs as a whole. FordLabs isn't actually an application. But, may Ford processes require you to establish an application before you can provision any infrastructure. FordLabs often works on experiments that preceed the definition and identificaiton of applications. |  |  | YES | 3 | NKANDULA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
20949 | VO Data Input Screens | In Production | VODIS | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | VODIS Formerly known as (PFIS) has been renamed(4Q2017)to include data input screens from other organizations Stamping, Paint & Assembly. The application allows for customizable quality data input screens used in plant environment for quality reporting. Captures production data which is sent to Web Base Data Management (WBDM) system for reporting results. | 4 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22242 | Variable Marketing Forecast Essbase | In Production | VMFE | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | S-Ox In Scope | 332 | No | Yes | In-House |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | Asia Pacific Marketing and sales finance system tool to support the Variable Marketing Forecast operation. | 19 |  | YES | 3 | TSWEEN16 | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
52878 | FordJuntos | In Production | FordJuntos | OCETO | DBRIGHEN | DBRIGHEN | NMORALE7 | NMORALE7 | Bronze | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Ford Land | 211 | WORKPLACE EXPERIENCE APPLICATION FOR SOUTH AMERICA INCLUDING THE FOLLOWING FEATURES: RIDE SHARING SOLUTION FOR FORD EMPLOYEES, CHECK-IN ON FORD BUILDINGS, EXTERNAL VISITS MANAGEMENT |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50275 | FordEcat-US | In Production | fordecatus | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 212 | No | Yes | COTS | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Ford service part catalog developed jointly with OEConnection. Hosted and maintained by Ford IT with vendor support. Ford Europe runs a different version of this product on separate infrastructure, covered by 12659 |  |  | YES | 2 | RKENNEL | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
50548 | TrboNet | In Production | TrboNet | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Silver | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | TRBOnet is a suite of professional applications for MOTOTRBO digital two-way radio networks. TRBOnet manages voice and data communication paths across network endpoints. It provides a unified graphical dispatcher workbench interface for the entire range of workforce fleet management tasks. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q3 2026 | EDC New Hypervisor | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
12499 | FordDirect Data Feeds | In Production | FDDF | M&S TECH | VMUTHUPA | VMUTHUPA | AKURAMNA | MPINRED1 | Silver | Non S-Ox | 211 | Yes | No | In-House | RKLEINSM | KPONNUSW | Marketing & Sales | - | The FordDirect Data Feeds system has a defined objective of aggregating data from several sources via flat files and sending out data to the FMC in a single flat file (technology partners Avanade & Microsoft) which in turn expose the data via a bing maps based REST endpoint (Universal Dealer Locator - UDL). This REST endpoint is consumed by several applications and is primarily used by tier 1 websites (ford.com and lincoln.com) and tier 3 websites (roughly 3500+ Ford and Lincoln dealers in USA and Canada). The data is primarily dealer enrolment and geo location data. The data feeds project has about 60+ inbound feeds and several outbound feeds. There are several other tools in the project including a spring based Dealer Maintenance Tool, a tool for downloading the entire data set in excel format (UDLtoExcel) etc. |  |  | YES | 1 | NKANDULA | PLM | Java Struts | Q4 2024 | Rewrite | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Green | 2024-12-15 | 2024-12-15 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
24217 | FordConnect FCON | In Production | FCON | EVDD | JWASNIC1 | RBUITEWE | ABIANC15 | ABIANC15 | Copper | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 211 | A COMMON SET OF CLOUD APIS FOR 3RD PARTIES TO INTEGRATE WITH. THIS MAKES IT EASIER FOR 3RD PARTIES TO SEND VEHICLE COMMANDS, READ VEHICLE DATA, AND MORE. THIS ALSO MASKS FORD'S BACKEND AND PRIVATE APIS WHILE ALLOWING FOR SEAMLESS INTEGRATION WITH VEHICLES ON ANY SDN. INDUSTRY STANDARDS ARE USED FOR APIS AND AUTHENTICATION. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50714 | TRAKA | In Production | TRAKA | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | - | Beyond securing and managing access to keys, Traka solutions can generate unique workflows that support the important processes of your business u2013 require a secondary authorization for master keys, pair key sets to guarantee the lockout of hazardous systems during maintenance, or set curfews which automatically send notifications to administrators, managers or users. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q3 2026 | EDC New Hypervisor | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
54357 | Ford Visualization Pipeline | In Production | FrdVisPipe | ISIT | SBONNICI | KRAMMOHA | RHARIKR2 | GRAO3 | Bronze | Non S-Ox | 122 | No | Yes | In-House | SBONNICI | KRAMMOHA | Advanced PD and Tech | 122 | The Ford Visualization Pipeline is a web enabled application that is a hub for various visualization data inputs to be processed into refined downstream assets that can be consumed in downstream applications, such as the XR Hub. It consists of the Connector Tool, Asset Wizard, and 3D viewer |  | Springboot | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
54357 | Ford Visualization Pipeline | In Production | FrdVisPipe | ISIT | SBONNICI | KRAMMOHA | RHARIKR2 | GRAO3 | Bronze | Non S-Ox | 122 | No | Yes | In-House | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | The Ford Visualization Pipeline is a web enabled application that is a hub for various visualization data inputs to be processed into refined downstream assets that can be consumed in downstream applications, such as the XR Hub. It consists of the Connector Tool, Asset Wizard, and 3D viewer |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
14995 | SIN - Sales Incentive System | In Production | SIN | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | The SIN System is the application that is responsible for control the incentives for Ford Dealers, through of the creation, simulation and approval incentives sales programs. The Ford Dealers are able to search the incentives received by VIN Number. | 4 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11778 | Ford Vehicle Programs | In Production | FVP | M&S TECH | RKLEINSM | MMILBOC1 | DSULLIV5 | MPINRED1 | Silver | Non S-Ox | 111 | No | Yes | In-House | RKLEINSM | MMILBOC1 | Enterprise Technology | Marketing, Sales and Service | Family of B2C web sites support AXZD Vehicle Programs: www.axz.ford.com, www.myplan.ford.com, www.fordpartner.com, dplan.dealerconnection.com. FVP provides the ability for Ford Employees, Dealer Employees and Retirees to generate an AXZD pin for eligible Ford/Lincoln vehicle purchases at a discounted price and also provides incentives. |  |  | YES | 4 | NKANDULA | PLM | Java Struts | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
11778 | Ford Vehicle Programs | In Production | FVP | M&S TECH | RKLEINSM | MMILBOC1 | DSULLIV5 | MPINRED1 | Silver | Non S-Ox | 111 | No | Yes | In-House | RKLEINSM | MMILBOC1 | Enterprise Technology | Marketing, Sales and Service | Family of B2C web sites support AXZD Vehicle Programs: www.axz.ford.com, www.myplan.ford.com, www.fordpartner.com, dplan.dealerconnection.com. FVP provides the ability for Ford Employees, Dealer Employees and Retirees to generate an AXZD pin for eligible Ford/Lincoln vehicle purchases at a discounted price and also provides incentives. |  |  | YES | 4 | NKANDULA | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | SQL
21275 | SA FCSD Executive Dashboard | In Production | FEDB | OCETO | DBRIGHEN | DBRIGHEN | RLOPES3 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Ford Customer Service | - | South America dashboard for FCSD as a bridge solution to the Global FCSD dashboard (UDB/e-React). The regional dashboard is to cover key metrics for FCSD area (Service, PS&L, Marketing). | 8 |  | YES | 3 | TSWEEN16 | PLM | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  |  |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11778 | Ford Vehicle Programs | In Production | FVP | M&S TECH | RKLEINSM | MMILBOC1 | DSULLIV5 | MPINRED1 | Silver | Non S-Ox | 111 | No | Yes | In-House | RKLEINSM | MMILBOC1 | Enterprise Technology | Marketing, Sales and Service | Family of B2C web sites support AXZD Vehicle Programs: www.axz.ford.com, www.myplan.ford.com, www.fordpartner.com, dplan.dealerconnection.com. FVP provides the ability for Ford Employees, Dealer Employees and Retirees to generate an AXZD pin for eligible Ford/Lincoln vehicle purchases at a discounted price and also provides incentives. |  |  | YES | 4 | NKANDULA | PLM | WAS | Q4 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
908 | Ford Supplier Portal (FSP) | In Production | FSP | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Support and maintain the Ford Supplier Portal (FSP) and Covisint Connection and Administration (CCA). FSP was launched 2002 and is hosted by Covisint. |  |  | YES | 4 | TSWEEN16 | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
908 | Ford Supplier Portal (FSP) | In Production | FSP | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Support and maintain the Ford Supplier Portal (FSP) and Covisint Connection and Administration (CCA). FSP was launched 2002 and is hosted by Covisint. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-04-15 |  | In-Progress | Green | 2025-07-14 |  | Planned |  | No | 100% | 100% | 75% | 75% | 75% | 50% | 100% |  | Cloud Run | Praveen | 2025-03-06 |  |  |  | No | Java < v21
908 | Ford Supplier Portal (FSP) | In Production | FSP | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Support and maintain the Ford Supplier Portal (FSP) and Covisint Connection and Administration (CCA). FSP was launched 2002 and is hosted by Covisint. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-04-15 |  | In-Progress | Green | 2025-07-14 |  | Planned |  | No | 100% | 100% | 75% | 75% | 75% | 50% | 100% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-06 |  |  |  | No | Oracle
908 | Ford Supplier Portal (FSP) | In Production | FSP | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Support and maintain the Ford Supplier Portal (FSP) and Covisint Connection and Administration (CCA). FSP was launched 2002 and is hosted by Covisint. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-04-15 |  | In-Progress | Green | 2025-07-14 |  | Planned |  | No | 100% | 100% | 75% | 75% | 75% | 50% | 100% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | Java < v21
19268 | Ford SIV (WebImmat) | In Production | Ford SIV | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 312 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Registration system for Ford of France enabling the registration of new and used vehicles and the French plate conversion to SIV plates. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
19268 | Ford SIV (WebImmat) | In Production | Ford SIV | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 312 | No | Yes | - | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | Vehicle Registration system for Ford of France enabling the registration of new and used vehicles and the French plate conversion to SIV plates. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
51913 | REDIRECT SERVICES | In Production | RS | M&S TECH | RKLEINSM | RKLEINSM | KPONNUSW | JPOTTE60 | Copper | Non S-Ox | 12 | No | Yes | In-House | RKLEINSM | RKLEINSM | Enterprise Technology | Marketing, Sales and Service | Redirects vanity urls to point to ford.com etc. | 3 |  | YES | 2 | NKANDULA | PLM | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19268 | Ford SIV (WebImmat) | In Production | Ford SIV | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 312 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | Vehicle Registration system for Ford of France enabling the registration of new and used vehicles and the French plate conversion to SIV plates. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
56056 | Ford Pro: Parts & Service Billing | In Development | FPSB | FORD PRO & FCSD TECH | SKOVACIC | ESHANKS2 | RBAHRAN | MROSZEL1 | - | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | JSING180 | General Management | Ford Pro | Fleet Parts & Service Billing (Fleet Care) |  | Springboot | YES | 1 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50074 | Ford Pro: NA Fleet Support Applications | In Production | NA-FSA | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Bronze | Non S-Ox | 221 | No | Yes | In-House | RSING163 | RKENNEL | Marketing & Sales | Ford Pro | A suite of web application supporting the NAFLRO business organization. Comprised of customer and Dealer facing website. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | 75% | 75% | 75% | 75% | 75% | 75% | N/A |  | Cloud SQL PostgreSQL |  |  |  |  | Almost 90% Completed. | No | SQL
53997 | Qlik Replicate | In Production | GDIA-Repl | GDIA | CPELTZE1 | ASANKA30 | CRAJAGHA | RPOLLO13 | Bronze | Non S-Ox | 111 | No | Yes | COTS | CPELTZE1 | SS348 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Data Replication Application for Data Factory | 41 |  | YES | 2 | FRANBELL | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [14 empty] | No | VM
50074 | Ford Pro: NA Fleet Support Applications | In Production | NA-FSA | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Bronze | Non S-Ox | 221 | No | Yes | In-House | RSING163 | RKENNEL | Marketing & Sales | Ford Pro | A suite of web application supporting the NAFLRO business organization. Comprised of customer and Dealer facing website. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
23367 | Ford Pro: GBMS Next Gen | In Production | GBMS NG | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Bronze | S-Ox In Scope | 132 | No | Yes | In-House | RSING163 | RKENNEL | General Management | Ford Pro | New Price Concession Management System (aka GBMSNG or GBMS) The Government Price Concession Management System (aka GBMS) provides Ford and L/M dealers an automated facility to request price concessions when participating in federal, state and local government agency competitive bids. Provides Price Protection and ability to track BID results. Online training, point-n-click vehicle configuration, competitor information, online request storage/edit/review, request status tracking, online concession search, email/fax notification of concession and order reference number assignments, win/loss data capture are functionality provided to dealers. Additional functionality for internal personnel includes concession review and status tracking, concession assignment with recent market activity, automated management approval, automated reference number generation, win/loss analysis, concession search, financial performance analysis.) |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
54257 | Part Count Input System | In Development | PCIS | ISIT | KCHRIST2 | HDIXON9 | MSILLMO1 | RPRASA22 | Bronze | Non S-Ox | 111 | Yes | No | In-House | KCHRIST2 | HDIXON9 | Enterprise Technology | - | Tracks manually entry of part inventory not otherwise captured by other systems | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | Q3 2026 | EDC New Hypervisor | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
23367 | Ford Pro: GBMS Next Gen | In Production | GBMS NG | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Bronze | S-Ox In Scope | 132 | No | Yes | In-House | RSING163 | RKENNEL | General Management | Ford Pro | New Price Concession Management System (aka GBMSNG or GBMS) The Government Price Concession Management System (aka GBMS) provides Ford and L/M dealers an automated facility to request price concessions when participating in federal, state and local government agency competitive bids. Provides Price Protection and ability to track BID results. Online training, point-n-click vehicle configuration, competitor information, online request storage/edit/review, request status tracking, online concession search, email/fax notification of concession and order reference number assignments, win/loss data capture are functionality provided to dealers. Additional functionality for internal personnel includes concession review and status tracking, concession assignment with recent market activity, automated management approval, automated reference number generation, win/loss analysis, concession search, financial performance analysis.) |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q3 2025 | Rewrite | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
12621 | Ford Pro: Fleet Operations Support System | In Production | FOSSY | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | ATRIPAT9 | Copper | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | Process direct fleet orders. FOSSY is an intranet application based on J2EE on Linux/Edison to support the sales to direct accounts. Functions/features: - customer and order database - order processing and status tracking - administration of price lists - pricing and administration of svo (special vehicle options) - administration of modification by Ford (Hall N) or external manufacturers - reporting - interfaces to AIMS VMACS DID - initial import from Excel sheets - fileing and administration of correspondence with customers. |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12621 | Ford Pro: Fleet Operations Support System | In Production | FOSSY | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | ATRIPAT9 | Copper | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | Process direct fleet orders. FOSSY is an intranet application based on J2EE on Linux/Edison to support the sales to direct accounts. Functions/features: - customer and order database - order processing and status tracking - administration of price lists - pricing and administration of svo (special vehicle options) - administration of modification by Ford (Hall N) or external manufacturers - reporting - interfaces to AIMS VMACS DID - initial import from Excel sheets - fileing and administration of correspondence with customers. |  |  | YES | 4 | RKENNEL | PLM | ESB | Q3 2025 |  | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | [14 empty] | No | DA
12621 | Ford Pro: Fleet Operations Support System | In Production | FOSSY | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | ATRIPAT9 | Copper | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | Process direct fleet orders. FOSSY is an intranet application based on J2EE on Linux/Edison to support the sales to direct accounts. Functions/features: - customer and order database - order processing and status tracking - administration of price lists - pricing and administration of svo (special vehicle options) - administration of modification by Ford (Hall N) or external manufacturers - reporting - interfaces to AIMS VMACS DID - initial import from Excel sheets - fileing and administration of correspondence with customers. |  |  | YES | 4 | RKENNEL | PLM | Mainframe | Q3 2025 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
12621 | Ford Pro: Fleet Operations Support System | In Production | FOSSY | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | ATRIPAT9 | Copper | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | Process direct fleet orders. FOSSY is an intranet application based on J2EE on Linux/Edison to support the sales to direct accounts. Functions/features: - customer and order database - order processing and status tracking - administration of price lists - pricing and administration of svo (special vehicle options) - administration of modification by Ford (Hall N) or external manufacturers - reporting - interfaces to AIMS VMACS DID - initial import from Excel sheets - fileing and administration of correspondence with customers. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | 25% | [7 empty] | Java 21 | [5 empty] | No | Java < v21
19115 | Ford Pro: Fleet Business Management System | In Production | FBMS | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | RSING163 | RKENNEL | General Management | 232 | FBMS automates the fleet sales proposal(Deal) development and approval process and enables the Fleet Account Managers to administer the variable marketing provided to fleet customers. FBMS also tracks metrics and profit related to the proposed and established proposals. Multiple combinations of incentive types, business segments, sales regions, vehicles and more can be specified as reporting criteria to aid in management decisions. |  | Springboot | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
19115 | Ford Pro: Fleet Business Management System | In Production | FBMS | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | RSING163 | RKENNEL | Marketing & Sales | Ford Pro | FBMS automates the fleet sales proposal(Deal) development and approval process and enables the Fleet Account Managers to administer the variable marketing provided to fleet customers. FBMS also tracks metrics and profit related to the proposed and established proposals. Multiple combinations of incentive types, business segments, sales regions, vehicles and more can be specified as reporting criteria to aid in management decisions. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
22738 | OCR (Payables) | In Production | OCR | I-ERP | SFRANCI8 | RJAYAKU2 | RSRIRA18 | LWU14 | Silver | Non S-Ox | 311 | No | Yes | COTS | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | OCR Application as part of GAPS Suite | 9 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
12557 | Ford Pro: FIN Master | In Production | FIN | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Silver | S-Ox In Scope | 221 | No | Yes | In-House | RSING163 | RKENNEL | General Management | Ford Pro | Maintains the FIN Master Database for all Fleet Accounts. The mainframe application is loaded with data collect from (GFIN) Global Fleet Identification. |  |  | YES | 1 | RKENNEL | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
50195 | FORD PRO: DEALER KEY CODE | In Production | DKC | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Bronze | Non S-Ox | 221 | No | Yes | In-House | RSING163 | RKENNEL | Marketing & Sales | Ford Pro | This online system allows dealers to obtain key code for vehicles that they have in stock or have sold. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL |  |  |  |  | In Progress | No | SQL
18165 | LPG External Website | In Production | LPG EW | ISIT | OTHERS | RTILLEY | GVANNOYE | JLUCAS1 | Silver | Non S-Ox | 11 | Yes | No | In-House | MDUGAN | RTILLEY | PD Operations and Quality | Industrial System IT | The Lommel external facing website will consist of about 30 static html pages presenting available facilities and other useful information to possible customers. | 5 |  | YES | 1 | BWUNNAVA | PLM | VM | Q3 2026 | EDC New Hypervisor | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green | 2026-12-14 |  | Planned |  | No | [14 empty] | No | VM
50195 | FORD PRO: DEALER KEY CODE | In Production | DKC | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Bronze | Non S-Ox | 221 | No | Yes | In-House | RSING163 | RKENNEL | Marketing & Sales | Ford Pro | This online system allows dealers to obtain key code for vehicles that they have in stock or have sold. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-06-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | [8 empty] | Cloud Run |  |  |  |  | WAS Rewrite to start in Q3 | No | Java < v21
50194 | Ford Pro: Commercial Specialty Vehicle Accounts | In Production | CSVA | FORD PRO & FCSD TECH | RKENNEL | JBULSARA | JBULSARA | AHULL19 | Copper | Non S-Ox | 221 | No | Yes | In-House | AKARTHI4 | MMATEEN2 | General Management | Ford Pro | Commercial Speciality Vehicle forecasting website, used by region 86 accounts to forecast the production allocation needed for future months. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  | 2026-03-30 |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
22004 | iProof | In Production | IIT | I-ERP | SFRANCI8 | RJAYAKU2 | RSRIRA18 | LWU14 | Silver | S-Ox In Scope | 331 | No | Yes | COTS | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Workflow solution to validate scanned supplier paper invoices and monitor invoice payment process status | 21 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
50194 | Ford Pro: Commercial Specialty Vehicle Accounts | In Production | CSVA | FORD PRO & FCSD TECH | RKENNEL | JBULSARA | JBULSARA | AHULL19 | Copper | Non S-Ox | 221 | No | Yes | In-House | AKARTHI4 | MMATEEN2 | General Management | Ford Pro | Commercial Speciality Vehicle forecasting website, used by region 86 accounts to forecast the production allocation needed for future months. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
53917 | Ford Pro: Billing & Invoicing | In Production | B&I | FORD PRO & FCSD TECH | SKOVACIC | ESHANKS2 | GHASTIE1 | MNESLER | Gold | Non S-Ox | 231 | No | Yes | In-House | #N/A | #N/A | General Management | 231 | SOFTWARE SUBSCRIPTIONS IS A PLATFORM OF CAPABILITIES TO OPERATE VARIOUS SUBSCRIPTION PATTERNS TO SUPPORT A FORD PRO SUBSCRIPTION BUSINESS. THE PLATFORM CONSISTS OF A FORD APPLICATION (PREVIOUS CALLED SSP) AND A THIRD PARTY APPLICATION CALLED ZUORA. |  | Springboot | YES | 1 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
53819 | Ford Pro: BEV Fit Tools | In Production | BEVFit | FORD PRO & FCSD TECH | DNANDAN | PJEFFRE5 | EGROSS16 | WBHAGGAN | Bronze | Non S-Ox | 222 | No | Yes | In-House | #N/A | #N/A | General Management | 222 | A SUITE OF TOOLS DESIGNED TO EASE UNCERTAINTY AND SIMPLIFY DECISION-MAKING FOR FLEET CUSTOMERS INTERESTED IN MAKING THE ICE TO BEV TRANSITION. |  | Springboot | YES | 1 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
13015 | Ford Pro: AccuQuote / Commercial Truck Tools | In Production | CTT / CVT | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | ATRIPAT9 | Copper | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | RKENNEL | PJEFFRE5 | General Management | Ford Pro | AccuQuote / Commercial Truck (Vehicle) Tools is a web based stand system developed to provide Ford dealers a Medium Duty Truck sales tool. The system has the capability to do sales presentations as well as spec'ing and quoting trucks. The software was developed by vendor Chrome Data / Autodata / JD Power. They were selected and funded by the Ford Commercial Truck Brand Org. The system works in tandem with CTOPS (#12871), the backend, which feeds the US Order Fulfillment systems. CIA 2,1,1 Vendor Chrome Data |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | [13 empty] | Delayed and changed in strategy Instead of decommissioning, they are going to go to CaaS. Planning on decommissioning by end of Q2. This was initially going to be decommissioned but the business team want to extend. | No | SQL
21596 | Interim Volume Mix and Rates | In Production | IVMR | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 311 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | This is an interim contirbution margin and Volume Mix Rate application. | 19 |  | YES | 3 | TSWEEN16 | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
13015 | Ford Pro: AccuQuote / Commercial Truck Tools | In Production | CTT / CVT | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | ATRIPAT9 | Copper | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | RKENNEL | PJEFFRE5 | General Management | Ford Pro | AccuQuote / Commercial Truck (Vehicle) Tools is a web based stand system developed to provide Ford dealers a Medium Duty Truck sales tool. The system has the capability to do sales presentations as well as spec'ing and quoting trucks. The software was developed by vendor Chrome Data / Autodata / JD Power. They were selected and funded by the Ford Commercial Truck Brand Org. The system works in tandem with CTOPS (#12871), the backend, which feeds the US Order Fulfillment systems. CIA 2,1,1 Vendor Chrome Data |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50424 | Ford Pro Marketplace | In Production | FFM | FORD PRO & FCSD TECH | SKOVACIC | ESHANKS2 | RRENGASW | AMARYNOV | Gold | Non S-Ox | 323 | No | Yes | In-House | JSING180 | JJACO130 | General Management | 323 | Part of FordPro. Tool customers use to enroll/unenroll their fleet of vehicles in products. |  | Springboot | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50424 | Ford Pro Marketplace | In Production | FFM | FORD PRO & FCSD TECH | SKOVACIC | ESHANKS2 | RRENGASW | AMARYNOV | Gold | Non S-Ox | 323 | No | Yes | In-House | JSING180 | JJACO130 | General Management | Ford Pro | Part of FordPro. Tool customers use to enroll/unenroll their fleet of vehicles in products. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
19664 | Information Server | Active | ETL-InfSvr | EPEO | SKULKA52 | MWILLI20 | MSIVAANA | RMODI2 | Silver | S-Ox In Scope | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | ITO | Shared Extract-Transform-Load (ETL) infrastructure environment based on IBM's Information Server suite (aka DataStage/QualityStage) to support multiple discrete applications. This is a PLACEHOLDER EAMS entry, per the 'IT Application Portfolio Management' guidelines. Customers of this service are required to raise their own EAMS entries, complete GRC App Assessments, etc. as required. This is not an 'Application'. This EAMS record is required to manage server ownership, and other contact information needed by Server Hosting. | 28 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned | [17 empty] | VM
22836 | Ford Pro Global Fleet Identification Number | In Production | GFIN | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Silver | Non S-Ox | 221 | No | Yes | In-House | RSING163 | RKENNEL | Enterprise Technology | Ford Pro | Global FIN Identification database containing Fleet customer account information. Each FIN (Fleet Identification Number) will follow the new global standard, but a conversion table will be created to convert to local FIN standards during the migration period. The Welcome Package module is used to create a welcome letter & materials for new enrolled Fleet customers. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
21380 | Global Volume Mix and Rate | In Production | GVMR | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Bronze | Non S-Ox | 322 | No | Yes | COTS | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | US and EU Marketing and Sales teams use a separate system and set of processes to collect, calculate and analyze actual and forecasted volumes, vehicle mix and option take rates. This process is also done manually throughout the globe in Canada, Mexico, South America and Asia Pacific. Both the US and EU systems need significant upgrades to operate properly and efficiently. There are discrepancies in the business practices which must be resolved. Manual effort takes up many resources to retrieve data for both systems. Additionally, neither of these systems supports the five year business planning forecasting window or a Fleet vs. Retail forecast split. GVMR is a standardized, lean, flexible global system to collect and report volume/mix/rate and revenue data. The system would enforce common business practices such as budget performance calculations yet allow for global differences such as vehicle definition. | 41 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
22836 | Ford Pro Global Fleet Identification Number | In Production | GFIN | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Silver | Non S-Ox | 221 | No | Yes | In-House | RSING163 | RKENNEL | Enterprise Technology | Ford Pro | Global FIN Identification database containing Fleet customer account information. Each FIN (Fleet Identification Number) will follow the new global standard, but a conversion table will be created to convert to local FIN standards during the migration period. The Welcome Package module is used to create a welcome letter & materials for new enrolled Fleet customers. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
205 | Ford Pro : Vehicle Special Order System (VSO) | In Production | VSO | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | CKEMPSKI | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | Configure, edit, price Dealer Special Orders (i.e., police crusiers, ambulances, etc.) The scope of this application is the VSO Option Inquiry system, VSO Option maintenance and SODDB interface with OPS/Downstream systems. SLA 1, CIA 2,1,1 |  |  | YES | 5 | RKENNEL | PLM | Mainframe | Q2 2025 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
205 | Ford Pro : Vehicle Special Order System (VSO) | In Production | VSO | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | CKEMPSKI | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | Configure, edit, price Dealer Special Orders (i.e., police crusiers, ambulances, etc.) The scope of this application is the VSO Option Inquiry system, VSO Option maintenance and SODDB interface with OPS/Downstream systems. SLA 1, CIA 2,1,1 |  |  | YES | 5 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
205 | Ford Pro : Vehicle Special Order System (VSO) | In Production | VSO | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | CKEMPSKI | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | Configure, edit, price Dealer Special Orders (i.e., police crusiers, ambulances, etc.) The scope of this application is the VSO Option Inquiry system, VSO Option maintenance and SODDB interface with OPS/Downstream systems. SLA 1, CIA 2,1,1 |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
19532 | GLOBAL MATERIAL COST FORECASTING (GMCF) | In Production | GMCF | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 312 | No | Yes | COTS | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Global Material Cost 5-year Budget and Business Planning Model and monthly forecast. | 43 |  | YES | 3 | TSWEEN16 | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
205 | Ford Pro : Vehicle Special Order System (VSO) | In Production | VSO | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | CKEMPSKI | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | Configure, edit, price Dealer Special Orders (i.e., police crusiers, ambulances, etc.) The scope of this application is the VSO Option Inquiry system, VSO Option maintenance and SODDB interface with OPS/Downstream systems. SLA 1, CIA 2,1,1 |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | 25% | [7 empty] | GCP Migration |  |  |  |  | Java > 17 Version for Java. | No | Java < v21
14550 | Ford Performance System 2000 | In Production | TFRS2K | FORD PRO & FCSD TECH | OTHERS | MIGNATOW | AKUCUKAR | VPUNDAMA | Bronze | Non S-Ox | 311 | Yes | No | In-House | MGRUEBE2 | MIGNATOW | Ford Customer Service | - | Ford Performance Parts (ERP) Application supports: Product Development Purchasing Order Entry Sales Data Warehouse & Inventory management. Product development data is used to populate FPP Website Content |  |  | YES | 2 | RKENNEL | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
51137 | GL Essbase | In Production | GL Essbase | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 222 | No | Yes | COTS | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | This application is a subsect of PSGL Suite of applications | 33 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
13533 | Ford Performance Parts | In Production | FPP | FORD PRO & FCSD TECH | OTHERS | MIGNATOW | AKUCUKAR | VPUNDAMA | Copper | Non S-Ox | 321 | Yes | No | In-House | MGRUEBE2 | MIGNATOW | Ford Customer Service | - | Business-to-Consumer brand site for Ford Performance Parts. The website is designed for Brand Enthusiasts to engage and obtain information about parts, check part availability, place part orders, and check part order status. The Ford Performance Parts website is hosted in the Dearborn Data Center. (formerly Ford Racing Performance Parts - FRPP) |  |  | YES | 2 | RKENNEL | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
12363 | FoM Parts Invoicing | In Production | FOMPINV | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 231 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | - | Ford of Mexico Parts Invoicing. This application issues dealer invoices for Service Parts sold to the dealers, based on a shipment confirmation file provided by NEOVIA Logistics. It also handles dealer claims and returns | 4 |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q3 2026 | Partial Migration to GCP | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
18492 | Ford Oracle Security Administration | In Production | FOSA II | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Bronze | Non S-Ox | 331 | No | Yes | In-House | NOKEEFE | NOKEEFE | Enterprise Technology | EPEO | Tool to handle User Administration and password maintenance for Oracle databases |  |  | YES | 3 | SWALIMBE | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
12352 | FMCDealer - (excluding USA & Canada) | In Production | FMCDSP | M&S TECH | NKANDULA | JLEWIS10 | KDAILY | JHARPER2 | Platinum | Non S-Ox | 213 | No | Yes | COTS | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | FMCDealer SP sites are the secured, password protected portals provided by Ford Motor Company to communicate with and provide access to business-critical applications which allow its dealerships to sell, finance, and service FMC vehicles. Market regions included: Asia Pacific, Europe and RoW/Rest of World - GTS/Global Trade Services, Mexico and South America. | 49 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
18492 | Ford Oracle Security Administration | In Production | FOSA II | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Bronze | Non S-Ox | 331 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Tool to handle User Administration and password maintenance for Oracle databases |  |  | YES | 3 | SWALIMBE | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
52013 | Ford Online Store | In Production | FOS | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 311 | No | Yes | Managed by 3rd Party Purchased Service | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | Application to enable customers to buy a vehicle via web, by cash or through a credit application |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | SQL
51551 | FMCC - Informatica Axon | In Production | INFA | FORD CREDIT | IPANKAJ | VGA | BSENTHI1 | VBHUPATH | Bronze | Non S-Ox | 221 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | VGA | Ford Credit Services | Ford Credit (FMCC) | This tool covers the data governance for FMCC. | 4 |  | YES | 1 | SRAISIN1 | PLM | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
19494 | FLEET MANAGEMENT SYSTEM (GVUS REPLACEMENT) | In Production | FMS | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | COTS | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Fleet Management System to manaage the tracking of Company vehicles including Prototype Vehicle Utilization. | 13 |  | YES | 3 | BWUNNAVA | PLM | VM | Q3 2026 | EDC CaaS and New EDC Hypervisor | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | VM
19946 | Ford of Mexico Electronic Invoicing | In Production | MX09FMEI | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Silver | S-Ox In Scope | 332 | No | Yes | COTS | KBERCH | GDIAZ1 | Finance | - | This application will generate and control the Electronic Invoice Application. Implement an electronic solution that process the data invoicing, adding the authorization digital signoff to each fiscal document and maintain the fiscal documentation at least five years. The application should automatically register the emission date. The system must guarantee the integrity of the information and avoid duplicated data. |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
22881 | Fleet Financial Model on Essbase | In Production | FFM ESSBAS | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Bronze | Non S-Ox | 321 | No | Yes | In-House |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | The Fleet Financial Model allows the NAFLRO controller's office analysts to perform volume and financial forecasts. The system integrates Business Plan, Model Year Program development, Budget, Forecast, and Month Close/Actual data entry and reporting for all Fleet financial elements including volume, revenue, marketing cost, profitability, cash flow and other reporting requirements. | 15 |  | YES | 1 | TSWEEN16 | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
18486 | FCLA Mexico - Dealer Extranet | In Production | MDX | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | This is a web application that allows the communication between dealers and Ford Credit's departments. Dealers can see the information regarding on their wholesale operation ; they can submit information in order to ask Ford Credit to approve their vehicles interchanges and validate their wholesale payments; and also they can be redirected to access AIMS App url and login in this App in order to upload their pdf file using AIMS App to be analyzed by Ford Credit's department | 5 |  | YES | 1 | TSWEEN16 | PLM | VM | Q3 2026 | EDC CaaS | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | VM
24175 | Ford of Canada Cognos | In Production | FocCognos | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | Marketing, Sales and Service | Cognos is a web-based integrated Business Intelligence suite by IBM. It provides a toolset for reporting, analysis, scorecarding, and monitoring of events and metrics. The software consists of several components to meet different information requirements in a company. |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
16085 | FCLA Mexico - Account Retail | In Production | MAR | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | RMANGAL | Bronze | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | The Account Retail Application handles the accounts related to the wholesale operation, allowing automatic charge of the opening fee under application and creates dealer accounts statements based on these information that are complemented by ICMS Apps related to FC-Extranet Module on the Month End by Operation. At the end of the month, to produce the debit and credit file to Mexico Operation to send to printing supplier to generate the notes and generates report/file to support the operation | 8 |  | YES | 1 | TSWEEN16 | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [14 empty] | No | VM
12314 | Ford Matter Management System | In Production | FMMS | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | S-Ox In Scope | 331 | No | Yes | COTS | DDESAI | KADOMKAI | Policy | Staffs IT | FMMS (new Matters Management system) to replace LMMS. It is a COTS package by Mitratech inc, with a layer of customization to meet business requirements globally also it includes legal e-Billing (Collaborati). | 338 |  | YES | 4 | TSWEEN16 | PLM | BO | Q1 2025 | Migrate to QlikSense | Modernize | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | [8 empty] | QlikSense |  |  |  |  | Moved to Big query | No | DA
12314 | Ford Matter Management System | In Production | FMMS | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | S-Ox In Scope | 331 | No | Yes | COTS | DDESAI | DDESAI | Policy | Staffs IT | FMMS (new Matters Management system) to replace LMMS. It is a COTS package by Mitratech inc, with a layer of customization to meet business requirements globally also it includes legal e-Billing (Collaborati). |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q3 2026 | Modernize to Cloud Databases | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Oracle
965 | ELECTRONIC RAW MATERIALS ACQUISITION (ERMA) | In Production | eRMA | I-ERP | SARAUJO3 | KSYROCKI | LRUMPTZ | SNAG1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Erma (Electronic Raw Materials Acquistion) will facilitate the purchase and sale of Ford negotiated raw material for non-Ford production part suppliers. | 8 |  | YES | 4 | TSWEEN16 | PLM | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12314 | Ford Matter Management System | In Production | FMMS | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | S-Ox In Scope | 331 | No | Yes | COTS | DDESAI | KADOMKAI | Policy | Staffs IT | FMMS (new Matters Management system) to replace LMMS. It is a COTS package by Mitratech inc, with a layer of customization to meet business requirements globally also it includes legal e-Billing (Collaborati). |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
56710 | Ford Lincoln Protect Portal | In Production | FLPP | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | JBROADW4 | RKADAM1 | Silver | S-Ox In Scope | 231 | No | Yes | In-House |  |  | Ford Customer Service | - | Dealer portal enabling dealers to register, maintain ESB contracts. Generates contracts PDF forms. |  |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
50080 | Customer Service Forecast Consolidation Essbase | In Production | CSFC | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 321 | No | Yes | In-House |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | Standardize and improve Asia Pacific FCSD Financial planning & analysis activities specific to Budget and Forecast and improvement of the Financial Planning & Analysis on FCSD Forecast Reporting which cannot be supported by IMPRS. | 19 |  | YES | 3 | TSWEEN16 | PLM | VM | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
50355 | FORD LAND MAINTENANCE MANAGEMENT SYSTEM | In Production | FLMMS | ISIT | SKING68 | KRAMESH | VGARIMEL | ESTILESK | Copper | S-Ox Out of Scope | 211 | No | Yes | COTS | SKING68 | KRAMESH | Ford Land | Industrial System IT | Facilities Maintenamce and Asset Management application used by Ford Land |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
21068 | Centralized Vehicle Order Services | In Production | CVOS | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Centralized services and globally common interface specifications for vehicle order configuration, pricing, submission, retrieval, amendment, contracting, transfer and supporting analytics. | 4 |  | YES | 5 | NKANDULA | PLM | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50355 | FORD LAND MAINTENANCE MANAGEMENT SYSTEM | In Production | FLMMS | ISIT | SKING68 | KRAMESH | VGARIMEL | ESTILESK | Copper | S-Ox Out of Scope | 211 | No | Yes | COTS | SKING68 | KRAMESH | Ford Land | Industrial System IT | Facilities Maintenamce and Asset Management application used by Ford Land |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
52721 | Ford Land Data Hub | In Production | FLDH | OCETO | TSWEEN16 | KADOMKAI | TJACKS13 | ESTILESK | Bronze | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KADOMKAI | Ford Land | Staffs IT | Information Integration Hub to enable data transfer between Ford Land systems, other corporate system, and other Ford data hubs. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | SQL
19179 | Automated Image Management System-AIMS | In Production | AIMS | FORD CREDIT | DTAURO | JJACK348 | NBHALWAN | ROBRIEN3 | Silver | Non S-Ox | 223 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | The application streamlines incoming faxes to a business unit by eliminating paper faxes and converting incoming faxes to images, tagging incoming images with index information based on bar codes, and storing them in an application for viewing, routing, processing, and archiving. | 12 |  | YES | 4 | SRAISIN1 | PLM | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
52721 | Ford Land Data Hub | In Production | FLDH | OCETO | TSWEEN16 | KADOMKAI | TJACKS13 | ESTILESK | Bronze | Non S-Ox | 211 | No | Yes | In-House |  |  | Ford Land | Staffs IT | Information Integration Hub to enable data transfer between Ford Land systems, other corporate system, and other Ford data hubs. |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
13895 | Ford Java Frameworks | In Development | FJFTest | EA | RRISS | THALL6 | KPRAVE27 | SGURU8 | Copper | Non S-Ox | - | No | Yes | In-House | RRISS | THALL6 | Enterprise Technology | - | Application used to test the suite of Ford Java Frameworks(FJF) prior to release of framework modifications to J2EE applications within Ford, and contain FJF libraries and associated static content. |  |  | YES | 3 | GBRAIL | PLM | SQL | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | SQL
11227 | AFRL - Registration & Licensing (UK) | In Production | AFRL | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 312 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | The Automated First Registration and Licensing System (AFRL) is used by Ford UK dealers to tax and register new vehicles online with direct real-time communication to UK government agency (DVLA). | 8 |  | YES | 4 | NKANDULA | PLM | VM | Q3 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13895 | Ford Java Frameworks | In Development | FJFTest | EA | RRISS | THALL6 | KPRAVE27 | SGURU8 | Copper | Non S-Ox | - | No | Yes | In-House | RRISS | THALL6 | Enterprise Technology | - | Application used to test the suite of Ford Java Frameworks(FJF) prior to release of framework modifications to J2EE applications within Ford, and contain FJF libraries and associated static content. |  |  | YES | 3 | GBRAIL | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
23259 | Ford Immobilizer Codes Online - 2 | In Production | FIMCO 2.0 | EVDD | JREYN149 | TPINTO3 | BCHITTI | CSUBHA1 | Silver | Non S-Ox | 322 | No | Yes | In-House | WFRANTZ | CRAJA1 | Advanced PD and Tech | - | PD Engineers and Supplier Testers will use this application interface to get the Key Values to unlock the ECU Modules so that they can update them or run tests on them. |  |  | YES | 3 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50702 | Warehouse Management System | In Production | WMS | ISIT | VVIJAY55 | BGANESH | AFINK4 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | COTS | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Warehouse Management System for plant small lot warehousing | 45 |  | YES | 1 | BWUNNAVA | PLM | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23259 | Ford Immobilizer Codes Online - 2 | In Production | FIMCO 2.0 | EVDD | JREYN149 | TPINTO3 | BCHITTI | CSUBHA1 | Silver | Non S-Ox | 322 | No | Yes | In-House | WFRANTZ | CRAJA1 | Advanced PD and Tech | - | PD Engineers and Supplier Testers will use this application interface to get the Key Values to unlock the ECU Modules so that they can update them or run tests on them. |  |  | YES | 3 | MJONE308 | PLM | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
51291 | Ford IDP (ADFS Extension) | In Production | FordIdP | EPEO | NOKEEFE | MSNYDER5 | ZZHAN106 | GSIENKIE | Silver | Non S-Ox | 211 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Ford Identity Provider ( a new module of ADFS) provides ADFS login user to authenticate against for Ford FDS. The application will use SAML protocols to communicate with ADFS. The system will support Employee, Retiree, Supplier, Dealer and 2nd Tier Supplier to login from Internet or Intranet. FordIdP will also support SecurID Login. The Architecture Design: 1. Host the Ford Identity in the PCF Foundry. 2. In the initial phase, only deploy the application in EDC1 and scale horizontally. 3. After EDC2 available, we configure the application as active-active between EDC1 and EDC2. 4. Use node.js, MongoDB as implementation tool. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50496 | Warehouse Inventory Next Generation sys- Ordering | In Production | WINGSO | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Ford Customer Service | - | Regional Parts Ordering system for South America. | 5 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-04-30 |  | In-Progress |  | 2025-05-16 |  | Planned |  | No |  | 25% | 25% | [5 empty] | GCP Migration | [5 empty] | No | VM
56890 | Virtual Training Solutions | Planned | VTS | ISIT | SKING68 | JLYNN1 | KKISIEL | AELANGO | Bronze | S-Ox Classification Pending | 111 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | - | VTS is a 3D virtual Learning Solution to upskill the users in Plant Floor | 7 |  | YES | 2 | BWUNNAVA | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | VM
13559 | Ford Fulfillment System | In Production | FFS | M&S TECH | OTHERS | AHROMCO | ELIDDELL | RFERMAN1 | Copper | Non S-Ox | 222 | Yes | No | In-House | GHEDDERM | AHROMCO | Marketing & Sales | - | This is Fulfillment System for Ford and Lincoln. The application is used and maintained by the Agency. The application is hosted in the B2B environment. |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
52718 | Unified e-Commerce Parts and Accessories | In Production | eComm IAL | M&S TECH | VMUTHUPA | VMUTHUPA | RSWAMINA | MPREETH6 | Platinum | S-Ox Out of Scope | 321 | No | Yes | Managed by 3rd Party Purchased Service | KHEMANT | VMUTHUPA | Enterprise Technology | Marketing, Sales and Service | Unified e-Commerce platform for Ford Parts and Accessories providing B2C and B2B webstores and a 3rd party marketplace store | 8 |  | YES | 2 | NKANDULA | PLM | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
11786 | Ford Financial Teradata Costs -Test | In Production | FFTC | FORD CREDIT | DTAURO | SLYNCH11 | SEID4 | ALIGHTHI | Copper | Non S-Ox | - | No | Yes | In-House | DTAURO | LCARVA11 | Enterprise Technology | - | IT BILLING RECORD (see #11556) ... Ford Financial Teradata costs for test -T10 |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
11787 | Ford Financial Teradata Costs - Production | In Production | FFTCP | FORD CREDIT | DTAURO | SLYNCH11 | SEID4 | ALIGHTHI | Copper | Non S-Ox | - | No | Yes | In-House | DTAURO | LCARVA11 | Enterprise Technology | - | IT BILLING RECORD (see #11556) ... Ford Financial Teradata costs for production -T7 |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
9790 | Ford Facing | In Production | FORDFACE | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Silver | Non S-Ox | 212 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | Ford Facing is the central file collection and distribution hub that manages the internal traffic between the Ford corporate application systems and the dealer/supplier inbound/outbound mailboxes on the Warley Mainframe FTP Server. It collects the files from the inbound mailboxes on the FTP Server that European dealerships have sent to Ford by the various BCM and eBCM applications and forwards them to the target application systems at Ford (e.g. ACES, CDOPS) and suppliers (e.g. Clifford Thames, LDC) or by writing the files to target application programs on the Mainframe. It also collects files from Ford applications (e.g. ACES, CDOPS, EUROVAC, EUROVIS) and distributes them into the dealer outbound mailboxes for retrieval via BCM/eBCM. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q4 2025 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
9790 | Ford Facing | In Production | FORDFACE | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Silver | Non S-Ox | 212 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | Ford Facing is the central file collection and distribution hub that manages the internal traffic between the Ford corporate application systems and the dealer/supplier inbound/outbound mailboxes on the Warley Mainframe FTP Server. It collects the files from the inbound mailboxes on the FTP Server that European dealerships have sent to Ford by the various BCM and eBCM applications and forwards them to the target application systems at Ford (e.g. ACES, CDOPS) and suppliers (e.g. Clifford Thames, LDC) or by writing the files to target application programs on the Mainframe. It also collects files from Ford applications (e.g. ACES, CDOPS, EUROVAC, EUROVIS) and distributes them into the dealer outbound mailboxes for retrieval via BCM/eBCM. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
18020 | Ford Facil - Customer Relationship Management | In Production | CRR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Internet system to support dealer sales process with an enhanced customer experience - integration with Ford customer database - lead management |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is already decommissioned | No | Java < v21
18020 | Ford Facil - Customer Relationship Management | In Production | CRR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | Internet system to support dealer sales process with an enhanced customer experience - integration with Ford customer database - lead management |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is decommissioned already. VMs are decommissioned | No | Oracle
20899 | Trucks Ford Service & Ford Protect | In Production | TMAC | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | TMAC is a truck maintenance contract system for the Brazilian Market. This system controls sales of special truck maintenance contracts (MC) for preventive and corrective maintenance of Big Truck Fleet Across the country. Additionally, it enables Ford to improve its competitiveness in the Brazilian heavy truck business. Ford Protect is an additional feature to attend Vehicle ESB. | 7 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
18020 | Ford Facil - Customer Relationship Management | In Production | CRR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Internet system to support dealer sales process with an enhanced customer experience - integration with Ford customer database - lead management |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is already decommissioned | No | Java < v21
21033 | TARDIS Integration Layer | In Production | TARDIS | GDIA | MSPADAF5 | LDESHPAN | RROBI177 | AJOGIYAT | Silver | Non S-Ox | 311 | No | Yes | In-House | EBLOCH | LDESHPAN | Enterprise Technology | - | Consumer integration layer to allow communications between front end applications (e.g.ETIS) and back end applications (e.g. CuPID). | 5 |  | YES | 2 | FRANBELL | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-08-01 | 2025-08-01 |  | In-Progress | Green | 2025-08-01 |  | Planned |  | No | [14 empty] | No | VM
50055 | Ford Energy Rewards | In Production | FER | EVDD | JWOOD38 | RDEBSHAL | JMANKIN | SCOUPER | Bronze | Non S-Ox | 211 | No | Yes | In-House | JWOOD38 | RDEBSHAL | Advanced PD and Tech | 211 | Ford Energy Rewards (aka SmartGrid) connects electric utility companies with Ford to manage grid integrations. |  | Springboot | YES | 3 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50055 | Ford Energy Rewards | In Production | FER | EVDD | JWOOD38 | RDEBSHAL | JMANKIN | SCOUPER | Bronze | Non S-Ox | 211 | No | Yes | In-House | JWOOD38 | RDEBSHAL | Advanced PD and Tech | - | Ford Energy Rewards (aka SmartGrid) connects electric utility companies with Ford to manage grid integrations. |  |  | YES | 3 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
19353 | SQLServer | Active | SQLServer | EPEO | SKULKA52 | NSHAH43 | DPATEL43 | NVAIDYAN | Copper | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | Enterprise Technology | ITO | SQL Server physical implementation information and monitoring | 60 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
24355 | Ford Edge Node Information Exchange | In Production | FENIX | EVDD | AGARBY | FGRABOWS | MSHEIKBA | SSAFEE | Gold | Non S-Ox | 122 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 122 | FENIX |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
52487 | SQL Server Password Expiration Notification | In Production | SQLPEN | EPEO | SKULKA52 | NSHAH43 | DPATEL43 | NVAIDYAN | Copper | S-Ox In Scope | 111 | Yes | No | - | CMIRABIT | NSHAH43 | Enterprise Technology | - | The SQL Server PEN- Password Expiration Notification process collects data from all of the supported SQL instances globally. This allows email notifications to customers when the passwords for their SQL Server authenticated logins will expire. This process is required to enforce the Access Control policies documented in the ISP (Information Security Policy). | 2 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
12619 | Ford Direct Stock Exchange | In Production | FDSE | FORD PRO & FCSD TECH | TJUNIPER | RHOWEL46 | RRAKESH4 | JCOY3 | Silver | Non S-Ox | 211 | No | Yes | In-House | TJUNIPER | TJUNIPER | Marketing & Sales | - | A B2B application (Company to Dealer), enabling Dealers to purchase premium used vehicles direct from Ford. |  |  | YES | 3 | RKENNEL | PLM | Oracle | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | modernized to Postgres SQL | No | Oracle
11591 | SLA: Service Loss Analysis | In Production | SLA | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Bronze | Non S-Ox | 111 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | The Service Loss Assignment system's main goal is to determine the reason for service loss (i.e., local fill & system fill loss) for PDC stocked parts in N.A. The SLA output data will be used as the basis for applying operational or system changes to help improve fill. SLA fill calculations were designed to match the currently used PA0012PR Fill report from MMP Network12 & will provide drill-down capability into the data. The reason for all service loss will be gauged by probing the entire supply chain (from supplier shipment to final PDC stockkeep transaction) to show where a process may have been over standard. SLA will use data processed by the IMAS application to decide the cause for service loss. IT Architecture: SLA information is staged on DB2 to facilitate DB2 table lookups & then stored on Teradata & accessed via both interactive web screens & a data analysis-reporting tool called Business Objects. Business Criticality: Med-H Additional Outage Impact includes: Impact to Financial Results. | 5 |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12619 | Ford Direct Stock Exchange | In Production | FDSE | FORD PRO & FCSD TECH | TJUNIPER | RHOWEL46 | RRAKESH4 | JCOY3 | Silver | Non S-Ox | 211 | No | Yes | In-House | TJUNIPER | RHOWEL46 | Marketing & Sales | - | A B2B application (Company to Dealer), enabling Dealers to purchase premium used vehicles direct from Ford. |  |  | YES | 3 | RKENNEL | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | [8 empty] | GCP Migration |  |  |  |  | Java > 21 | No | Java < v21
21671 | FORD DIAGNOSTIC SERVICE PLATFORM | In Production | FDSP | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 322 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Global services for vehicle diagnostic applications. Back-end functionality, derived from FordEtis, PTS and IDS functionality which provide services to Diagnostic tools (including GFDRS, PTS and FordEtis) supporting diagnostics and RMI activities. Services deployed globally, supporting NA, EU and Ap&A regions and accessed through the tools used within the region. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-30 |  | In-Progress | Green | 2025-12-29 |  | Planned |  | No | 100% | [7 empty] | Cloud Run | [5 empty] | No | Java < v21
21671 | FORD DIAGNOSTIC SERVICE PLATFORM | In Production | FDSP | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 322 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Global services for vehicle diagnostic applications. Back-end functionality, derived from FordEtis, PTS and IDS functionality which provide services to Diagnostic tools (including GFDRS, PTS and FordEtis) supporting diagnostics and RMI activities. Services deployed globally, supporting NA, EU and Ap&A regions and accessed through the tools used within the region. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-30 |  | In-Progress | Green | 2025-12-29 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
54299 | Silverfort | In Production | Silverfort | EPEO | NOKEEFE | MSNYDER5 | ZZHAN106 | GSIENKIE | Platinum | Non S-Ox | 211 | Yes | No | COTS | NOKEEFE | MSNYDER5 | Enterprise Technology | - | Silverfort applies a layer of protection on top of existing authentication protocols, eliminates the need to deploy any agents and proxies, or to make any changes to existing servers and applications. This enables organizations to protect assets that don't support secure authentication today without having to modify them, and to extend protection to interfaces that are not covered by any other MFA solution. | 32 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
21671 | FORD DIAGNOSTIC SERVICE PLATFORM | In Production | FDSP | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 322 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Global services for vehicle diagnostic applications. Back-end functionality, derived from FordEtis, PTS and IDS functionality which provide services to Diagnostic tools (including GFDRS, PTS and FordEtis) supporting diagnostics and RMI activities. Services deployed globally, supporting NA, EU and Ap&A regions and accessed through the tools used within the region. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-30 |  | In-Progress | Green | 2025-12-29 |  | Planned |  | No | 100% | [7 empty] | Cloud Run | [5 empty] | No | Java < v21
21243 | Ford Credit Treasury Insurance Risk System - TIRS | In Production | FCTIRS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 231 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Ford Treasurys Corporate Insurance Department will use the Treasury Insurance Risk System, known as TIRS, to assess risk and conduct insurance risk management. The application will automate Corporate Insurances process for collecting data and provide industry-standard reporting to facilitate risk management analysis and to manage internal risk related to insurance matters, support insurance claims, and the purchasing of insurance. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
21243 | Ford Credit Treasury Insurance Risk System - TIRS | In Production | FCTIRS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 231 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Ford Treasurys Corporate Insurance Department will use the Treasury Insurance Risk System, known as TIRS, to assess risk and conduct insurance risk management. The application will automate Corporate Insurances process for collecting data and provide industry-standard reporting to facilitate risk management analysis and to manage internal risk related to insurance matters, support insurance claims, and the purchasing of insurance. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
24202 | SCOM for Directory Services (SCOM - DS) | In Production | SCOMDS | EPEO | NOKEEFE | MSNYDER5 | CQI | GSIENKIE | Silver | Non S-Ox | 111 | Yes | No | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Microsoft System Center Operations Manager (SCOM) implemented for Directory Services Environment that supports integrated event management. MS-SCOM version 20xx with SCOM agent and recommended management packs installed is the monitoring solution of choice for Ford Directory Services Infrastructure. MS-SCOM 20xx is an application and server management solution capable of monitoring the availability, performance and security of Directory Services servers and utility servers. SCOM also gathers performance counter used to generate metrics. | 2 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
21243 | Ford Credit Treasury Insurance Risk System - TIRS | In Production | FCTIRS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 231 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Ford Treasurys Corporate Insurance Department will use the Treasury Insurance Risk System, known as TIRS, to assess risk and conduct insurance risk management. The application will automate Corporate Insurances process for collecting data and provide industry-standard reporting to facilitate risk management analysis and to manage internal risk related to insurance matters, support insurance claims, and the purchasing of insurance. |  |  | YES | 4 | SRAISIN1 | PLM | WAS | Q1 2027 | Rewrite | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | Java < v21
54501 | Ford Credit SRE | Planned | FCSRE | FORD CREDIT | IPANKAJ | VNAVEEN1 | SNATAR30 | RMANGAL | - | Non S-Ox | - | No | Yes | In-House | IPANKAJ | VNAVEEN1 | Ford Credit Services | Ford Credit (FMCC) | Ford Credit SRE - DevSecOps & Cloud Engineering |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q2 2025 | Version Upgrade | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | Java < v21
51697 | Ford Credit Smart Secure Documents | In Production | FCSSD | FORD CREDIT | DTAURO | DTAURO | EGOMATH1 | ASAXENA8 | Copper | Non S-Ox | 311 | No | Yes | In-House | DTAURO | EGOMATH1 | Ford Credit Services | 311 | Ford Credit Smart Secure Document Management utilizing Adobe Forms connected to Customer and Account Data Feeds to create customer letters and forms. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q1 2026 | Version Upgrade | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
51697 | Ford Credit Smart Secure Documents | In Production | FCSSD | FORD CREDIT | DTAURO | DTAURO | EGOMATH1 | ASAXENA8 | Copper | Non S-Ox | 311 | No | Yes | In-House | DTAURO | EGOMATH1 | Ford Credit Services | Ford Credit (FMCC) | Ford Credit Smart Secure Document Management utilizing Adobe Forms connected to Customer and Account Data Feeds to create customer letters and forms. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | SQL
50717 | SCA Consent Platform | In Production | CP | GDIA | CBUCKL19 | KKB | PSIRISIN | SDUTTA9 | Silver | Non S-Ox | 212 | No | Yes | In-House | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Manage and service Consumer Consents | 7 |  | YES | 3 | FRANBELL | PLM | VM | Q3 2025 | Will be Decommissioned | Modernize | 2025-09-15 | 2025-09-15 | 2025-02-28 | Complete | Blue | 2025-09-15 | 2025-02-28 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | VMS have been decommissioned | No | VM
53280 | Ford Credit Residual Equipment Tool | In Production | FC RET | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | JMANI | Bronze | Non S-Ox | 112 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | RET provides dealers with the ability to configure, price and residualize vehicle accessories during the financing process |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | SQL
51181 | Regulatory User Interface | In Production | RegUI | FORD CREDIT | IPANKAJ | PSRIKIR1 | RMRINAL2 | NKALE | Bronze | Non S-Ox | 323 | No | Yes | Open Source | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | FCE Regulatory User Interface is utility to enter data that is not available in the source for FCE regulatory and liquidity monitoring & reporting | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
53280 | Ford Credit Residual Equipment Tool | In Production | FC RET | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | JMANI | Bronze | Non S-Ox | 112 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | RET provides dealers with the ability to configure, price and residualize vehicle accessories during the financing process |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
50687 | Ford Credit Receivable Account Information Service | In Production | FCRAIS | FORD CREDIT | NJOSHI21 | HBRUMLEV | XZHOU110 | ROBRIEN3 | Gold | Non S-Ox | 232 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | 232 | Suite of micro services that access Ford Credit receivable account data |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
50687 | Ford Credit Receivable Account Information Service | In Production | FCRAIS | FORD CREDIT | NJOSHI21 | HBRUMLEV | XZHOU110 | ROBRIEN3 | Gold | Non S-Ox | 232 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | Suite of micro services that access Ford Credit receivable account data |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50687 | Ford Credit Receivable Account Information Service | In Production | FCRAIS | FORD CREDIT | NJOSHI21 | HBRUMLEV | XZHOU110 | ROBRIEN3 | Gold | Non S-Ox | 232 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | Suite of micro services that access Ford Credit receivable account data |  |  | YES | 4 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
18111 | REGISTRY (VOPISO) | In Production | Registry | ISIT | JDEGUZMA | RMEHTA3 | RJAMBUNA | ISIDDIQ6 | Silver | Non S-Ox | 111 | No | Yes | In-House | JDEGUZMA | RMEHTA3 | PD Operations and Quality | Industrial System IT | Registry is a WEB-based system to publish the required quality management system documentation in line with the general system requirements of the ISO 9001 for Global Business use. All necessary information can be stored and provided to all Business Units & departments affected. The Registry provides each department the possibility to create its own Master Document List (MDL), one of the five pillars of the quality management system. This application was migrated to IT Compliant infrastructure on 20-May-2014. Formerly known as VOPISO = Vehicle Operations Manufacturing Engineering ISO Homepage. | 9 |  | YES | 3 | BWUNNAVA | PLM | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50279 | FORD CREDIT PROCESS AUTOMATION | In Production | FCPA | FORD CREDIT | IPANKAJ | VM56 | RVIGNE24 | RPARAME4 | Silver | Non S-Ox | 332 | No | Yes | In-House | IPANKAJ | VNAVEEN1 | Ford Credit Services | Ford Credit (FMCC) | Development and Technical support for Automation owned by Ford Credit. Its primary aim is to keep automating based on baseline design document provided by the business. This record was used for UI path and now it is being used for Pega automations. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
22338 | RAPTOR | In Production | RAPTOR | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | JMANI | Bronze | Non S-Ox | 221 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit pricing platform for New and Used US Standard Retail rates. It delivers pricing rates to the PARMS application. | 7 |  | YES | 4 | SRAISIN1 | PLM | VM | Q3 2025 | EDC CaaS | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
50279 | FORD CREDIT PROCESS AUTOMATION | In Production | FCPA | FORD CREDIT | IPANKAJ | VM56 | RVIGNE24 | RPARAME4 | Silver | Non S-Ox | 332 | No | Yes | In-House | IPANKAJ | VNAVEEN1 | Ford Credit Services | Ford Credit (FMCC) | Development and Technical support for Automation owned by Ford Credit. Its primary aim is to keep automating based on baseline design document provided by the business. This record was used for UI path and now it is being used for Pega automations. |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
23876 | Ford Credit Optim Test Data Management | Active | FCOPTIM | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | VCECCARE | Copper | Non S-Ox | - | No | Yes | - | PTABOR5 | DTAURO | ENTERPRISE TECHNOLOGY | - | #N/A |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | SQL
11770 | Quality Analysis and Reporting System | In Production | QARSPD | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Silver | Non S-Ox | 221 | No | Yes | COTS | JDEGUZMA | RMEHTA3 | Quality | Industrial System IT | Quality Analysis and Reporting Systems (QARS) provide web based Quality Analysis capability; and standardized Quality Reporting for PD, VO organizations (Common Metrics). The Quality Analysis Data Cubes provide real-time, web-based analytical functions, using a common interface for Warranty, Market Research and other data. The analyst interacts with the Data Cubes directly, allowing continuity of thought during the analysis process, as well as permitting 'What if?' questions to be answered immediately. Warranty analysis can be performed on data from North America, Europe, Australia and Mazda (Thailand), and Market Research information is available for North America and Europe. Primary Users: Analysts in Quality, Engineering, Finance, Market Research, 6-Sigma Black Belts, Vehicle Operations and Powertrain Plants. | 9 |  | YES | 2 | BWUNNAVA | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | VM
18375 | Ford Credit Mainframe Technical Support | In Production | TECHSUPP | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | DSINACOL | Copper | Non S-Ox | 111 | No | Yes | In-House | KDELTA | TLEWIS84 | Ford Credit Services | - | RACF RECORD (see #18200) ... Infrastructure Support for Ford Credit |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
11556 | Ford Credit Mainframe | Planned | FFMC | FORD CREDIT | DTAURO | SLYNCH11 | SEID4 | ALIGHTHI | Copper | Non S-Ox | - | No | Yes | In-House | DTAURO | LCARVA11 | Enterprise Technology | - | MF Application used by all Ford Credit apps for shared services |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50113 | PowerBroker PAM | In Production | PBPAM | EPEO | NOKEEFE | MSNYDER5 | GGEARY | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | COTS | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | PowerBroker Password Safe is an automated password and privileged session management solution offering secure access control, auditing, alerting and recording for any privileged account Planned replacement product for TPAM. | 31 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
22631 | Ford Credit InfoSphere (IBM) Annex (DataStage) | In Production | FCInfoSpA | FORD CREDIT | IPANKAJ | VGA | BSENTHI1 | VBHUPATH | Bronze | Non S-Ox | 323 | No | Yes | COTS | IPANKAJ | VGA | Ford Credit Services | Ford Credit (FMCC) | Shared Extract-Transform-Load (ETL) infrastructure environment utilizing DataStage to support multiple discrete applications. |  |  | YES | 3 | SRAISIN1 | PLM | Datastage | Q3 2026 |  | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  |  |  | Planned | [17 empty] | DA
22631 | Ford Credit InfoSphere (IBM) Annex (DataStage) | In Production | FCInfoSpA | FORD CREDIT | IPANKAJ | VGA | BSENTHI1 | VBHUPATH | Bronze | Non S-Ox | 323 | No | Yes | COTS | IPANKAJ | VGA | Ford Credit Services | Ford Credit (FMCC) | Shared Extract-Transform-Load (ETL) infrastructure environment utilizing DataStage to support multiple discrete applications. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
23735 | Paycult CARUS Datacenter | In Production | EuHR-PayDC | OCETO | TSWEEN16 | KADOMKAI | MMUPPITA | ESTILESK | Copper | Non S-Ox | 111 | No | Yes | COTS | DDESAI | KADOMKAI | Ford Land | Staffs IT | Pay card management tool and sales data consolidation and reporting for loader and vending units. The pay cards are used in German sites at canteens, shops, and vending machines. This is a COTS application called CARUS datacentre and a CARUS card reader, both supplied by Paycult GmbH & Co KG Hamburg Germany. | 2 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23791 | Ford Credit GRC - RSA Archer | In Production | FCGRC | FORD CREDIT | IPANKAJ | RRAJESH8 | TNARAYA2 | RPARAME4 | Silver | Non S-Ox | 211 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Archer Technologies, LLC provides the Global Risk and Compliance application which is leveraged for the following: Daily Review Guides (DRGs) for FCNA & IMG, Risk Assessments/Risk Register for FCNA, FCE, and Germany, Risk Event Management for FCNA, FCE and Germany, Law/Regulatory Change Management for FCNA, China, and FCE, and Incident Reporting for FCNA. This is administered by FC Global Risk Management. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
21382 | Paint End-of-line Dirt Detection System | In Production | PEDDS | ISIT | SKING68 | JLYNN1 | GKESAVAR | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | This system stores the images from the vision systems and analyzes those images for paint problem determination | 10 |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-30 | 2025-09-30 |  | Not Started | Green | 2025-12-29 |  | Planned |  | No | [7 empty] | 2 | EDC Hypervisor | Priya | 2025-03-04 |  |  |  | No | VM
54937 | Ford Credit Foundational Dashboard | In Production | FCFD | FORD CREDIT | NJOSHI21 | HBRUMLEV | PDAVI180 | ASAXENA8 | Silver | Non S-Ox | 212 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | Ford Credit Foundational Dashboard that simplifies the current process of data access for business users. Initial use case we focus on Receivables Data. More Foundational capabilities and enhancements will be developed as part of this Dashboard. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
18119 | Ford Credit Finance Analytical System-FCFAS | In Production | FCFAS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | Non S-Ox | 222 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The objective of the Forecast project is to improve Ford Credit's borrowing cost forecasting capability using: 1 - An integrated system for assets and liabilities. 2 - Revised organizational roles and responsibilities. 3 - Common inputs and assumptions. 4 - A new analytical capability - through the creation of an analytical data base to provide 'historical' asset/liability measures via Excel based Olap reporting |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
18119 | Ford Credit Finance Analytical System-FCFAS | In Production | FCFAS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | Non S-Ox | 222 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The objective of the Forecast project is to improve Ford Credit's borrowing cost forecasting capability using: 1 - An integrated system for assets and liabilities. 2 - Revised organizational roles and responsibilities. 3 - Common inputs and assumptions. 4 - A new analytical capability - through the creation of an analytical data base to provide 'historical' asset/liability measures via Excel based Olap reporting |  |  | YES | 3 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
11561 | Order Fulfillment Data Warehouse | In Production | OFM/DW | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | The Order Fulfillment Metrics Data Warehouse provides standard reports, metrics, and analysis capability across the Order Fulfillment Enterprise Process (MS&S, MP&L, and Manufacturing) for North America and Europe and primarily includes data pertaining to vehicle order and part forecasting, scheduling, manufacturing, transportation, and delivery along with accruals and reconciliations to support the controllers office. | 4 |  | YES | 4 | BWUNNAVA | PLM | VM | Q3 2025 | Partial Migration to GCP | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19419 | ORACLE DRDA DOWNLOAD | Active | DRDA DL | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | - | No | Yes | - | AFRADKIN | JLIDDLE1 | Enterprise Technology | Marketing, Sales and Service | Oracle DRDA Download is an application that is used to replicate DB2 data into Oracle. It uses Oracles DRDA gateway to connect to DB2 from Oracle DB environment. Customers of this application use it to configure and monitor download jobs to selectively download DB2 data into their own Oracle database. | 3 |  | YES | 3 | TSWEEN16 | PLM | VM | Q3 2025 | Partial Migration to GCP | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23201 | Ford Credit Dealer Toolkit | In Production | FCDT | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | JMANI | Silver | Non S-Ox | 312 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | Web site for Ford Credit dealers. It will provide a one-way broadcast message, Single Sign On with RouteOne, and the existing Branded Interface functions such as ETA, link to Smart Vincent, etc. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | Q4 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
23201 | Ford Credit Dealer Toolkit | In Production | FCDT | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | JMANI | Silver | Non S-Ox | 312 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | Web site for Ford Credit dealers. It will provide a one-way broadcast message, Single Sign On with RouteOne, and the existing Branded Interface functions such as ETA, link to Smart Vincent, etc. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
17698 | Ford Credit Dealer Finance-DF | In Production | DF-FC | FORD CREDIT | RMINHAS3 | GSHAH3 | SMANE4 | VPOTTIBO | Silver | Non S-Ox | 232 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | DF Mainframe jobs that support the DF-FIS vended GUI/Host Dealer Finance solution #51964. Implemented 1/2/07 |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50944 | Ford Credit Deal Optimizer | In Production | FCDO | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | JMANI | Silver | Non S-Ox | 321 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | Deal Optimizer provides dealers with an integrated, always-on, self-service tool to rehash specific deal parameters and instantly receive a tier and approval on the restructured deal. |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | Q4 2024 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned | [17 empty] | Mainframe
50944 | Ford Credit Deal Optimizer | In Production | FCDO | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | JMANI | Silver | Non S-Ox | 321 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | Deal Optimizer provides dealers with an integrated, always-on, self-service tool to rehash specific deal parameters and instantly receive a tier and approval on the restructured deal. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned | [17 empty] | SQL
22770 | Nexus | In Production | Nexus | EA | RRISS | SHE1 | PSHAH | SGURU8 | Silver | Non S-Ox | 111 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | - | A Repository Management tool that organizes artifacts (storing and retrieving binary components during the software development lifecycle), enable collaboration and increase efficiency. | 7 |  | YES | 1 | GBRAIL | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
50944 | Ford Credit Deal Optimizer | In Production | FCDO | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | JMANI | Silver | Non S-Ox | 321 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Deal Optimizer provides dealers with an integrated, always-on, self-service tool to rehash specific deal parameters and instantly receive a tier and approval on the restructured deal. |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned | [17 empty] | Java < v21
24857 | Ford Credit Customer Information Services | In Production | FCCIS | FORD CREDIT | NJOSHI21 | HBRUMLEV | VCECCARE | ROBRIEN3 | Gold | Non S-Ox | 232 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | Suite of micro services that manages Ford Credit customer data including Customer Communication Permissions, Customer Activity Service, and Customer Information Management Customer Communication Permissions CRUD for Ford Credit customer's permissions (e.g. Opt In / Opt Out) by communication channel (e.g. email, text, etc). Customer Activity Service CR for customer account activities (feeds Pinnacle contacts) Customer Information Management Service retrieves receivable customer data |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
24857 | Ford Credit Customer Information Services | In Production | FCCIS | FORD CREDIT | NJOSHI21 | HBRUMLEV | VCECCARE | ROBRIEN3 | Gold | Non S-Ox | 232 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | Suite of micro services that manages Ford Credit customer data including Customer Communication Permissions, Customer Activity Service, and Customer Information Management Customer Communication Permissions CRUD for Ford Credit customer's permissions (e.g. Opt In / Opt Out) by communication channel (e.g. email, text, etc). Customer Activity Service CR for customer account activities (feeds Pinnacle contacts) Customer Information Management Service retrieves receivable customer data |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | SQL
50071 | NextGen VHCOS | In Production | VHCOSNG | ISIT | SBONNICI | KRAMMOHA | MJESKA | JLUCAS1 | Bronze | Non S-Ox | 331 | No | Yes | COTS | SBONNICI | SBONNICI | Policy | Industrial System IT | VHCOS Next Gen - using Planisware software - enables the full integration of VH&C project management and change control processes, with PD tools like Global Integrator or FEDE. Allowing easy integration with existing vehicle program milestones. | 11 |  | YES | 3 | BWUNNAVA | PLM | VM | Q3 2025 | Complete Migration to SaaS | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | VM
52452 | Ford Credit Contact Center Orchestration Services | In Production | FCCCOS | FORD CREDIT | JMALETZ | DTAURO | SJOSHI1 | ASAXENA8 | Silver | Non S-Ox | 311 | No | Yes | - | #N/A | #N/A | Ford Credit Services | 311 | SUITE OF ORCHESTRATION AND PROCESSING API SERVICES CREATED AND USED BY SLT. IT'S PRIMARY FUNCTION IS TO ORCHESTRATE CALLS TO MULTIPLE DOWNSTREAM MICRO SERVICES LIKE FCCIS, FCRAIS, DISNE, ETC AND PROCESSES DATA TO SUIT JSON TO CATER TO SLT NEEDS. IT ALSO HAS TRANSACTION MANAGER API THAT TAKES OVER RESPONSIBILITY OF HANDLING MULTIPLE ACCOUNT UPDATES TO THE DIFFERENT DOWNSTREAM SERVICES |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
22051 | Ford Credit Communication Messaging Services-NA | In Production | FCCMS | FORD CREDIT | IPANKAJ | DSINACOL | SVYSYARA | RPARAME4 | Silver | Non S-Ox | 321 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | 321 | The Ford Credit Communication Messaging Services - North America provides the technical resources for triggering text (SMS) and e-mail notifications to Ford Credit customers. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
22051 | Ford Credit Communication Messaging Services-NA | In Production | FCCMS | FORD CREDIT | IPANKAJ | DSINACOL | SVYSYARA | RPARAME4 | Silver | Non S-Ox | 321 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit Communication Messaging Services - North America provides the technical resources for triggering text (SMS) and e-mail notifications to Ford Credit customers. |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20269 | NCIPHER HARDWARE SECURITY MODULE | In Production | HSM | EPEO | NOKEEFE | VNACHIMU | BSARAV20 | WJUSTICE | Gold | Non S-Ox | - | No | Yes | - |  |  | Enterprise Technology | - | nCipher Hardware Security Module | 6 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
51603 | Ford Credit Communication Messaging Services-China | In Production | FCCMS | FORD CREDIT | JCHEN11 | CYANG63 | YFU33 | YZHU86 | Silver | Non S-Ox | 321 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 321 | THE FORD CREDIT COMMUNICATION MESSAGING SERVICES - CHINA PROVIDES THE TECHNICAL RESOURCES FOR TRIGGERING TEXT (SMS) NOTIFICATIONS TO FORD CREDIT CUSTOMERS. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
50723 | Ford Credit Command Center Monitoring Portal | In Production | FCCCMP | FORD CREDIT | KDELTA | NINDURTI | GHANRAHA | ROBRIEN3 | Bronze | Non S-Ox | 311 | No | Yes | In-House | KDELTA | NINDURTI | Ford Credit Services | Ford Credit (FMCC) | This is an internal application used by the Ford Credit Command Center in order to track key application information in order to assist with the quick resolution of production issues. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50723 | Ford Credit Command Center Monitoring Portal | In Production | FCCCMP | FORD CREDIT | KDELTA | NINDURTI | GHANRAHA | ROBRIEN3 | Bronze | Non S-Ox | 311 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | This is an internal application used by the Ford Credit Command Center in order to track key application information in order to assist with the quick resolution of production issues. |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
20843 | MPS - VIRTUAL PRINT | Active | VirtPrint | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | MANGELE3 | Copper | Non S-Ox | - | No | Yes | - | SRUNSON | PSIMONTE | Enterprise Technology | - | Windows virtual print servers in EDC and Niehl data centers to support the reduction of physical print servers. BCA Rating of B | 18 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
18281 | Ford Credit Batch Management Tools | Planned | FCBMT | FORD CREDIT | KDELTA | KDELTA | ALIGHTHI | ALIGHTHI | Copper | Non S-Ox | - | No | Yes | In-House | SRAISIN1 | KDELTA | Ford Credit Services | - | Cross reference ITMS 18186 |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20151 | MPS - SEMI COPY CENTER SOFTWARE | Active | MPS - SCCS | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | MANGELE3 | Copper | Non S-Ox | - | No | Yes | - | SRUNSON | PSIMONTE | Enterprise Technology | - | Website for Copy Center services hosted in the Dearborn data center. | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
16480 | Ford Component Sales Website Suite Application | In Production | FCS B2CWeb | FORD PRO & FCSD TECH | RKENNEL | RANGEL | RANGEL | MMEHTA5 | Copper | Non S-Ox | 221 | Yes | No | In-House | TCANNIS | CBILLS1 | Ford Customer Service | - | Allow FCS customers to view status of orders, view products offered and for dealers to place accessories orders. |  |  | YES | 2 | RKENNEL | PLM | Java Struts | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
16480 | Ford Component Sales Website Suite Application | In Production | FCS B2CWeb | FORD PRO & FCSD TECH | RKENNEL | RANGEL | RANGEL | MMEHTA5 | Copper | Non S-Ox | 221 | Yes | No | In-House | TCANNIS | CBILLS1 | Ford Customer Service | - | Allow FCS customers to view status of orders, view products offered and for dealers to place accessories orders. |  |  | YES | 2 | RKENNEL | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
19665 | Ford Component Sales - FESG Multimedia Ordering | In Production | FCS FESG | FORD PRO & FCSD TECH | RKENNEL | RANGEL | RANGEL | MMEHTA5 | Copper | Non S-Ox | 211 | Yes | No | In-House | TCANNIS | CBILLS1 | Ford Customer Service | - | Ford Component Sales (FCS) application to allow submission of orders for the Mulitimedia & Cluster Program for Ford dealers and other select customers. |  |  | YES | 2 | RKENNEL | PLM | Java Struts | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
19665 | Ford Component Sales - FESG Multimedia Ordering | In Production | FCS FESG | FORD PRO & FCSD TECH | RKENNEL | RANGEL | RANGEL | MMEHTA5 | Copper | Non S-Ox | 211 | Yes | No | In-House | TCANNIS | CBILLS1 | Ford Customer Service | - | Ford Component Sales (FCS) application to allow submission of orders for the Mulitimedia & Cluster Program for Ford dealers and other select customers. |  |  | YES | 2 | RKENNEL | PLM | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
24478 | MP Fire | In Production | EuHR-MPF | OCETO | TSWEEN16 | KADOMKAI | MMUPPITA | ESTILESK | Copper | Non S-Ox | 211 | No | Yes | COTS | DDESAI | KADOMKAI | Ford Land | Staffs IT | Application supports Cologne fire brigade business: (1) Equipment Maintenance, (2) Issue Report, (3) Run Report. The application uses a purchased package MP Feuer (https://mp-feuer.de/) which runs on Citrix. | 6 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50047 | Ford Cloud Portal | In Production | FCPO | EPEO | SJOHN172 | SJOHN172 | TWOODS19 | BPEDERS1 | Copper | Non S-Ox | 111 | No | Yes | In-House | SJOHN172 | SJOHN172 | Enterprise Technology | 111 | Ford Cloud Portal is self-developed/managed application which provides self service capabilities for developers to provision and manage services that are part of the Ford Cloud. FCP allows developers to enable easy user experience to provision ITO services in minutes. It allows to create database, PCF, VM & relevant tools & accelerate application delivery. |  | Springboot | YES | 3 | SWALIMBE | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50047 | Ford Cloud Portal | In Production | FCPO | EPEO | SJOHN172 | SJOHN172 | TWOODS19 | BPEDERS1 | Copper | Non S-Ox | 111 | No | Yes | In-House | SJOHN172 | SJOHN172 | Enterprise Technology | EPEO | Ford Cloud Portal is self-developed/managed application which provides self service capabilities for developers to provision and manage services that are part of the Ford Cloud. FCP allows developers to enable easy user experience to provision ITO services in minutes. It allows to create database, PCF, VM & relevant tools & accelerate application delivery. |  |  | YES | 3 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50882 | MONGODB OPERATIONS MANAGER | Active | MDBOpsMgr | EPEO | SKULKA52 | NSHAH43 | RYALAVAR | RYALAVAR | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | Enterprise Technology | ITO | MongoDB Operations Manager is part of MongoDB Enterprise (7016287). MongoDB Ops Manager required to deploy MongoDB database, Monitor, Backup and automations. | 9 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
21886 | MOBILITY UTILITIES | Active | MOUTL | EPEO | MCRNKOVI | JPRESNEL | CPOLK | CPOLK | Bronze | Non S-Ox | - | No | Yes | - | MCRNKOVI | JPRESNEL | Enterprise Technology | - | Mobility Utilities (NCAT and PowerDNS) | 3 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
23057 | Ford Auto Finance China Bureau | In Production | PBOCNCIIC | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | Non S-Ox | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | FAFC Bureau communicates between the mainframe credit analysis and scoring programs and the NCIIC and PBOC. The java programs sends the request for data to PBOC and NCIIC and receives data back. The PBOC program scrapes the credit bureau data off the html response, stores it in a table for the mainframe scoring program to retrieve and send to Magnum. The NCIIC program stores the data received from the NCIIC in DB2 for use by Pinnacle CA. |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
23406 | Ford Argentina Consumer Knowledge System (CK) | In Production | ARCK | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Marketing & Sales | - | This is the CRM platform of Ford Argentina. It is a knowledge database, an aid tool for helping the Marketing Team in their decisions. CK is focused on improving both strategic and business benefits, working on the consumer experience. Its main purpose is to centralize consumer data in one database in order to get all the information regarding the relationship between the customer/prospects and Ford as a brand and its products. It also contains competitive information. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | Database servers & EAMS Status decommissioned | No | SQL
21458 | MAINFRAME ENGINEERING | Active | MF Eng | EPEO | SKULKA52 | CGIACOBB | COLIVE34 | COLIVE34 | Copper | Non S-Ox | - | No | Yes | - | CMIRABIT | CGIACOBB | Enterprise Technology | - | Enterprise Mainframe Engineering | 3 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
23406 | Ford Argentina Consumer Knowledge System (CK) | In Production | ARCK | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Marketing & Sales | - | This is the CRM platform of Ford Argentina. It is a knowledge database, an aid tool for helping the Marketing Team in their decisions. CK is focused on improving both strategic and business benefits, working on the consumer experience. Its main purpose is to centralize consumer data in one database in order to get all the information regarding the relationship between the customer/prospects and Ford as a brand and its products. It also contains competitive information. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
51581 | Ford Application for eLectronic CONtracting | In Production | FALCON | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Silver | Non S-Ox | 211 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Middleware application that provides electronic signature services |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
17826 | M&S Executive Dashboard | In Production | EDB | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Bronze | Non S-Ox | 221 | No | Yes | In-House |  |  | Marketing & Sales | Marketing, Sales and Service | The M&S Executive Dashboard is a reporting tool and data refresh process for a well-defined set of business drivers and measures. | 3 |  | YES | 7 | NKANDULA | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
51581 | Ford Application for eLectronic CONtracting | In Production | FALCON | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Middleware application that provides electronic signature services |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
24924 | Ford Agile Simulation Tool | In Development | FASTER | ISIT | OTHERS | FSMITH22 | MWINDELE | AELANGO | Copper | Non S-Ox | 111 | Yes | No | - | LTURNER3 | FSMITH22 | Manufacturing Staffs | - | FASTER is a user interface designed to simplify the process of building Power Train Assembly & Machining line models within the Witness software application. The tool allows selection of Ford proprietary modules representing the various pieces of production equipment within Bill of Process manufacturing lines. The user is presented with the relevant input fields in familiar terminology to capture the required simulation input data. FASTER then builds these elements and input data into the Witness software and applies logic to model the desired part flow. Overall, this tool allows manufacturing engineers to rapidly build accurate models of manufacturing facilities for data driven assessment of manufacturing feasibility and comparison of various strategies. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
12350 | LDS EU (Lead Delivery System) | In Production | LDS | FORD PRO & FCSD TECH | TJUNIPER | GRIST | SRAVI6 | AJOGIYAT | Silver | Non S-Ox | 321 | No | Yes | In-House | TJUNIPER | GRIST | Marketing & Sales | Marketing, Sales and Service | LDS is a web service based application designed to deliver EU prospects (leads) to Dealer DMS systems. It enables DMS systems to send updates (feedback the progress they have made on following up those leads) to the leads as well. | 4 |  | YES | 3 | RKENNEL | PLM | VM | Q3 2025 | EDC CaaS | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | [14 empty] | No | VM
50809 | Font Management System | In Production | Fontera | ISIT | JKOONS | CDODD7 | SJAIMES | JLUCAS1 | Copper | Non S-Ox | 211 | Yes | No | - | JKOONS | NLAKSHMA | Advanced PD and Tech | - | A font management system for global vehicle programs |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
50809 | Font Management System | In Production | Fontera | ISIT | JKOONS | CDODD7 | SJAIMES | JLUCAS1 | Copper | Non S-Ox | 211 | Yes | No | - | JKOONS | NLAKSHMA | Advanced PD and Tech | - | A font management system for global vehicle programs |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51203 | Landscape Management Software | In Production | LMS | EPEO | SRUNSON | ASTONE31 | CHOSSEIN | BNABOZNY | Copper | Non S-Ox | 211 | No | Yes | COTS | SRUNSON | ASTONE31 | Enterprise Technology | EPEO | Software delivery infrastructure for Ford Ubuntu Clients | 3 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
56066 | JFrog Enterprise Plus | In Production | JFA | EA | RRISS | SHE1 | PSHAH | SGURU8 | Gold | Non S-Ox | 233 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | - | A software suite and repository through which Ford (1) manages and releases Model e control software binaries, application packages and installers, container images, libraries, and configuration files, and (2) reviews build process analytics and insights. | 5 |  | YES | 2 | GBRAIL | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
50222 | FoM Reporting Application for Dealers | In Production | FOMRAD | M&S TECH | RKLEINSM | BMUNIE | EGARRO | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | RKLEINSM | BMUNIE | Marketing & Sales | - | This is a smart, real time, mobile and device agnostic reporting platform for all Ford of Mexico Marketing, Sales and Service KPIs, that provides information to many business customers (Ford and Dealers) about performance metrics | 857 |  | YES | 3 | NKANDULA | PLM | WebFocus | Q1 2025 | Migrate to QlikSense | Modernize | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | 100% | 100% | 75% | 75% | 75% | 75% | 75% |  | QlikSense | [5 empty] | No | DA
50222 | FoM Reporting Application for Dealers | In Production | FOMRAD | M&S TECH | RKLEINSM | BMUNIE | EGARRO | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | RKLEINSM | BMUNIE | Marketing & Sales | - | This is a smart, real time, mobile and device agnostic reporting platform for all Ford of Mexico Marketing, Sales and Service KPIs, that provides information to many business customers (Ford and Dealers) about performance metrics |  |  | YES | 3 | NKANDULA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
24073 | ICI Decisioning | In Production | ICI DSP | M&S TECH | NKANDULA | TBRYANS1 | MMEADOR | RFERMAN1 | Copper | Non S-Ox | 311 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Enterprise Technology | Marketing, Sales and Service | Sense and respond machine learning and BRMS application. | 80 |  | YES | 2 | NKANDULA | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
12368 | FoM PeopleSoft Human Resources | In Production | FoM HR App | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | MBALAN2 | Bronze | Non S-Ox | 331 | No | Yes | COTS | KBERCH | KBERCH | Human Resources | - | Ford of Mexico PeopleSoft Human Resources Applications as Awards, Overtime, Vacations, Performance Review, the letters modules, self service module |  |  | YES | 2 | NKANDULA | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
100 | GSLTS: Global Service Labor Time Standards | In Production | GSLTS | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RSRINI38 | Bronze | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Labor Time Schedule Database - Provides labor time information for use by dealers in the preparation of Warranty Claims and customer invoices, and for the validation of Warranty Claims by the ACES system. | 9 |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q3 2025 | Partial Migration to GCP | Modernize | 2025-09-15 | 2025-09-30 |  | In-Progress | Green | 2025-12-29 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12372 | FoM Payments to Suppliers | In Production | FoM PtS | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | - | This system receives information from CCAPS system. With this information, checks are generated and printed. Text files are generated in order to send them to the bank. Receives CCAPS files to separate it in three different ways of payment like: EFT DAP Printed Checks |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
12372 | FoM Payments to Suppliers | In Production | FoM PtS | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | KBERCH | KBERCH | Finance | - | This system receives information from CCAPS system. With this information, checks are generated and printed. Text files are generated in order to send them to the bank. Receives CCAPS files to separate it in three different ways of payment like: EFT DAP Printed Checks |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
14736 | Global Risk Management Web Site | In Production | GRM | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | TSAILESH | Bronze | Non S-Ox | 111 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | Global Risk Management Web Site aka Risk Monitoring Dashboard Report | 5 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2025 | Complete Migration to SaaS | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
12372 | FoM Payments to Suppliers | In Production | FoM PtS | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | - | This system receives information from CCAPS system. With this information, checks are generated and printed. Text files are generated in order to send them to the bank. Receives CCAPS files to separate it in three different ways of payment like: EFT DAP Printed Checks |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
12363 | FoM Parts Invoicing | In Production | FOMPINV | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 231 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | - | Ford of Mexico Parts Invoicing. This application issues dealer invoices for Service Parts sold to the dealers, based on a shipment confirmation file provided by NEOVIA Logistics. It also handles dealer claims and returns | 1084 |  | YES | 5 | NKANDULA | PLM | WebFocus | Q1 2025 | Modernize | Modernize | 2025-03-31 | 2025-03-31 | 2025-03-14 | Complete | Blue | 2025-06-29 | 2025-03-14 | Complete |  | No | 100% | 100% | 75% | 75% | 75% | 75% | 75% |  | New Platform altogether | [5 empty] | No | DA
12363 | FoM Parts Invoicing | In Production | FOMPINV | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 231 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | - | Ford of Mexico Parts Invoicing. This application issues dealer invoices for Service Parts sold to the dealers, based on a shipment confirmation file provided by NEOVIA Logistics. It also handles dealer claims and returns |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
12363 | FoM Parts Invoicing | In Production | FOMPINV | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 231 | No | Yes | In-House | KBERCH | KBERCH | Finance | - | Ford of Mexico Parts Invoicing. This application issues dealer invoices for Service Parts sold to the dealers, based on a shipment confirmation file provided by NEOVIA Logistics. It also handles dealer claims and returns |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | Oracle | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Oracle
21258 | Global Environmental Reserve System | In Production | GERS | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Bronze | Non S-Ox | 221 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Application for the EQO to track environmental liabilities. Global Environmental Reserve System is a collaboration solution that provides an Interface for environmental engineers to input liability costs.Provides a process for approval of the estimate. Provides an interface to maintain quarterly balance/adjustments (Reserve Tracker) Security Environmental Quality Office (EQO) Site update access restricted. Admin Functions to maintain information such as: site list, currency code/name mapping, etc. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q3 2025 | Partial Migration to GCP | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12363 | FoM Parts Invoicing | In Production | FOMPINV | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 231 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | - | Ford of Mexico Parts Invoicing. This application issues dealer invoices for Service Parts sold to the dealers, based on a shipment confirmation file provided by NEOVIA Logistics. It also handles dealer claims and returns |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
16179 | FOM Onbase | In Production | FOMONBASE | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Bronze | Non S-Ox | 312 | No | Yes | COTS | KBERCH | GDIAZ1 | Finance | - | Software from Simmpapel supplier designed to digitize hard copy online electronic information and preserve it for consulting purposes. Also provide a solution to the dealers with accurate documentation, on time in daily basis to support the dealers accounting re-conciliations and provision. To track dealers transactions for a better cash flow control. Support 18 month of fiscal documentations for the dealers. Provide in daily basis dealers statements of: Vehicles in pesos and dollars, parts and accessories statements, incentive statements Support Ford and Lincoln. Reduce the administration processes, telephone calls and the times that the dealer representatives have to come to get and send fiscal documentation. Expected reduction on telephone calls between dealers and Ford Database will allow Dealers to retrieve information by queries in order to get specific data (range of dates, specific vehicle line, specific document numbers, etc.)Dealers will be allowed to storage fiscal documentation digitally. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
24204 | GCCT - Dynamics 365 | In Production | GCCT | M&S TECH | RAHMED33 | DPOOVATH | AROSS76 | MSCHOLT3 | Silver | Non S-Ox | 322 | No | Yes | COTS | APALAZZO | DPOOVATH | Customer Experience | Marketing, Sales and Service | Assist Customer - Global Contact Center Technology is a platform solution that includes Microsoft Dynamics 365 as the core CRM used for Case Management, and integrates with several Azure services (blob storage, Azure SQL, Cognitive Services, etc.) and multiple internal applications (SAVE-IO, SCA-C, etc.) as well as various third-party applications (BBB, Agero Roadside Assistance, etc.) | 8 |  | YES | 2 | NKANDULA | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
12364 | FoM Mexican Vehicle Information System | In Production | MEVIS | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | - | Mexican Vehicles Information System. This application contains vehicle tracking and invoicing data. The application receives vehicle data from NAVIS and Invoicing data from the US Vehicle Invoicing Application and produces the local dealer invoices. | 517 |  | YES | 5 | NKANDULA | PLM | WebFocus | Q1 2025 | Migrate to QlikSense | Modernize | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No |  | 100% | 100% | 75% | 75% | 75% | 75% |  | QlikSense | [5 empty] | No | DA
12364 | FoM Mexican Vehicle Information System | In Production | MEVIS | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | - | Mexican Vehicles Information System. This application contains vehicle tracking and invoicing data. The application receives vehicle data from NAVIS and Invoicing data from the US Vehicle Invoicing Application and produces the local dealer invoices. |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
12364 | FoM Mexican Vehicle Information System | In Production | MEVIS | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | KBERCH | KBERCH | Enterprise Technology | - | Mexican Vehicles Information System. This application contains vehicle tracking and invoicing data. The application receives vehicle data from NAVIS and Invoicing data from the US Vehicle Invoicing Application and produces the local dealer invoices. |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
11778 | Ford Vehicle Programs | In Production | FVP | M&S TECH | RKLEINSM | MMILBOC1 | DSULLIV5 | MPINRED1 | Silver | Non S-Ox | 111 | No | Yes | In-House | RKLEINSM | MMILBOC1 | Enterprise Technology | Marketing, Sales and Service | Family of B2C web sites support AXZD Vehicle Programs: www.axz.ford.com, www.myplan.ford.com, www.fordpartner.com, dplan.dealerconnection.com. FVP provides the ability for Ford Employees, Dealer Employees and Retirees to generate an AXZD pin for eligible Ford/Lincoln vehicle purchases at a discounted price and also provides incentives. | 4 |  | YES | 4 | NKANDULA | PLM | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-15 | 2025-01-15 | Complete | Blue | 2025-12-14 | 2025-01-15 | Complete |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12364 | FoM Mexican Vehicle Information System | In Production | MEVIS | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | - | Mexican Vehicles Information System. This application contains vehicle tracking and invoicing data. The application receives vehicle data from NAVIS and Invoicing data from the US Vehicle Invoicing Application and produces the local dealer invoices. |  |  | YES | 5 | NKANDULA | Modernize Components (Backlog-2024) | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
12362 | FoM Dealer Parts Ordering (PAC) | In Production | PAC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Ford Customer Service | - | Pedidos Especiales y Atencion a Clientes (PAC) is a Web application that manages parts orders and the confirmation sent from the NEOVIA Logistics warehouse, manages parts on sale (ofertanet), Discount Scales according sales volume (motorcraft) and provides the Parts Price List to the Dealers (Price Bulletins). It also manages dealer returns and claims related to the orders. Dealers submit a request regarding units down and unrecognized parts. | 6 |  | YES | 3 | NKANDULA | PLM | WebFocus | Q2 2025 | Modernize | Modernize | 2025-06-30 | 2025-06-30 | 2025-03-14 | Complete | Blue | 2025-09-28 | 2025-03-14 | Complete |  | No | 100% | 50% | 25% | 25% | 25% | 25% | 25% | [7 empty] | No | DA
12362 | FoM Dealer Parts Ordering (PAC) | In Production | PAC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Ford Customer Service | - | Pedidos Especiales y Atencion a Clientes (PAC) is a Web application that manages parts orders and the confirmation sent from the NEOVIA Logistics warehouse, manages parts on sale (ofertanet), Discount Scales according sales volume (motorcraft) and provides the Parts Price List to the Dealers (Price Bulletins). It also manages dealer returns and claims related to the orders. Dealers submit a request regarding units down and unrecognized parts. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | SQL
23367 | Ford Pro: GBMS Next Gen | In Production | GBMS NG | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Bronze | S-Ox In Scope | 132 | No | Yes | In-House | RSING163 | RKENNEL | General Management | Ford Pro | New Price Concession Management System (aka GBMSNG or GBMS) The Government Price Concession Management System (aka GBMS) provides Ford and L/M dealers an automated facility to request price concessions when participating in federal, state and local government agency competitive bids. Provides Price Protection and ability to track BID results. Online training, point-n-click vehicle configuration, competitor information, online request storage/edit/review, request status tracking, online concession search, email/fax notification of concession and order reference number assignments, win/loss data capture are functionality provided to dealers. Additional functionality for internal personnel includes concession review and status tracking, concession assignment with recent market activity, automated management approval, automated reference number generation, win/loss analysis, concession search, financial performance analysis.) | 3 |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q3 2025 | Partial Migration to GCP | Modernize | 2025-09-15 | 2025-09-30 |  | In-Progress | Green | 2025-12-29 |  | Planned |  | No | 25% | 25% | [6 empty] | Cloud Run | [5 empty] | No | VM
12369 | FoM Dealer Current Accounts | In Production | FoM DCC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This application generates dealer statements based on accounting transactions received from Vehicles and Parts & Accesories Invoicing, Debits and Credits Memos by Incentives, Warranties, miscellaneous Invoices, P&A Material returns (PA20), P&A Material not received (PA293), bank deposits and Ford Credit payments, also receive information from Corporate Systems in a file to extract and add manual transactions and miscellaneous invoices generated during the month for each dealer, which should be matched with the transactions and balances of General Ledger records. This System is a batch Application. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
12369 | FoM Dealer Current Accounts | In Production | FoM DCC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KBERCH | KBERCH | Finance | Integrated Enterprise Resource Planning (I-ERP) | This application generates dealer statements based on accounting transactions received from Vehicles and Parts & Accesories Invoicing, Debits and Credits Memos by Incentives, Warranties, miscellaneous Invoices, P&A Material returns (PA20), P&A Material not received (PA293), bank deposits and Ford Credit payments, also receive information from Corporate Systems in a file to extract and add manual transactions and miscellaneous invoices generated during the month for each dealer, which should be matched with the transactions and balances of General Ledger records. This System is a batch Application. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
19115 | Ford Pro: Fleet Business Management System | In Production | FBMS | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | RSING163 | RKENNEL | Marketing & Sales | Ford Pro | FBMS automates the fleet sales proposal(Deal) development and approval process and enables the Fleet Account Managers to administer the variable marketing provided to fleet customers. FBMS also tracks metrics and profit related to the proposed and established proposals. Multiple combinations of incentive types, business segments, sales regions, vehicles and more can be specified as reporting criteria to aid in management decisions. | 7 |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12369 | FoM Dealer Current Accounts | In Production | FoM DCC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This application generates dealer statements based on accounting transactions received from Vehicles and Parts & Accesories Invoicing, Debits and Credits Memos by Incentives, Warranties, miscellaneous Invoices, P&A Material returns (PA20), P&A Material not received (PA293), bank deposits and Ford Credit payments, also receive information from Corporate Systems in a file to extract and add manual transactions and miscellaneous invoices generated during the month for each dealer, which should be matched with the transactions and balances of General Ledger records. This System is a batch Application. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
19741 | FoM Company Cars | In Production | MX09FNCC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | - | Application to support the Company Vehicles as Pools, Vehicles assigned to Manage Level Personnel, Demo units and Enginering vehicles. This application is used to manage Company Vehicle inventory, LL6+ vehicle selection, Finance conciliation process vs. physical invetory and the tracking of these vehicles since the order proces until the delivery. | 78 |  | YES | 5 | NKANDULA | PLM | WebFocus | Q1 2025 | Rewrite | Modernize | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | 100% | 100% | 75% | 75% | 75% | 75% | 75% |  | New Platform altogether | [5 empty] | No | DA
19741 | FoM Company Cars | In Production | MX09FNCC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | - | Application to support the Company Vehicles as Pools, Vehicles assigned to Manage Level Personnel, Demo units and Enginering vehicles. This application is used to manage Company Vehicle inventory, LL6+ vehicle selection, Finance conciliation process vs. physical invetory and the tracking of these vehicles since the order proces until the delivery. |  |  | YES | 5 | NKANDULA | PLM | Java Struts | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
19741 | FoM Company Cars | In Production | MX09FNCC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | - | Application to support the Company Vehicles as Pools, Vehicles assigned to Manage Level Personnel, Demo units and Enginering vehicles. This application is used to manage Company Vehicle inventory, LL6+ vehicle selection, Finance conciliation process vs. physical invetory and the tracking of these vehicles since the order proces until the delivery. |  |  | YES | 5 | NKANDULA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
205 | Ford Pro : Vehicle Special Order System (VSO) | In Production | VSO | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | CKEMPSKI | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | Configure, edit, price Dealer Special Orders (i.e., police crusiers, ambulances, etc.) The scope of this application is the VSO Option Inquiry system, VSO Option maintenance and SODDB interface with OPS/Downstream systems. SLA 1, CIA 2,1,1 | 4 |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-30 |  | Not Started |  | 2025-12-29 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19741 | FoM Company Cars | In Production | MX09FNCC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | - | Application to support the Company Vehicles as Pools, Vehicles assigned to Manage Level Personnel, Demo units and Enginering vehicles. This application is used to manage Company Vehicle inventory, LL6+ vehicle selection, Finance conciliation process vs. physical invetory and the tracking of these vehicles since the order proces until the delivery. |  |  | YES | 5 | NKANDULA | PLM | WAS | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
24359 | FoM Anti Money Laundering | In Production | FoM AML | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | MBALAN2 | Silver | Non S-Ox | 222 | No | Yes | In-House | KBERCH | KBERCH | Policy | - | The application receives information about payments done by vehicle sales (Imports, Exports, Company Cars and Donatives) in order to be reported to Mexican Tax Authority and avoid fines. The Authority's objective is detect any suspicious transaction and ensure that is not a Money Laundering activity. |  |  | YES | 2 | NKANDULA | Modernize Components (Backlog-2024) | Oracle | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
24359 | FoM Anti Money Laundering | In Production | FoM AML | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | MBALAN2 | Silver | Non S-Ox | 222 | No | Yes | In-House | KBERCH | GDIAZ1 | Policy | - | The application receives information about payments done by vehicle sales (Imports, Exports, Company Cars and Donatives) in order to be reported to Mexican Tax Authority and avoid fines. The Authority's objective is detect any suspicious transaction and ensure that is not a Money Laundering activity. |  |  | YES | 2 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Will be Decomissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
14924 | FoM 3040s System | In Production | MX 3040s | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Copper | Non S-Ox | 112 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This System is used to automate 3040s process which moves vehicles from different accounts within ford such as: marketing, preproduction, public affairs, etc. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
22379 | Ford of Canada United Way | In Production | FOC UW | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Human Resources | Marketing, Sales and Service | Web application that allows UW Coordinators to control the campaign and employees to make a pledge. A UW Coordinator is able to track the campaign progress using Report functionality and create payroll transactions. | 12 |  | YES | 1 | NKANDULA | PLM | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13547 | FOCUS FCLA FEXCO System | In Production | FEXCO | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Credit Services | Ford Credit (FMCC) | FEXCO is a FCLA-developed system that serves to manage the retail contract in loss recovery transferred to external agencies and attorneys by establishing controls regarding the assigned portfolio |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
21671 | FORD DIAGNOSTIC SERVICE PLATFORM | In Production | FDSP | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 322 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Global services for vehicle diagnostic applications. Back-end functionality, derived from FordEtis, PTS and IDS functionality which provide services to Diagnostic tools (including GFDRS, PTS and FordEtis) supporting diagnostics and RMI activities. Services deployed globally, supporting NA, EU and Ap&A regions and accessed through the tools used within the region. | 5 |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-30 |  | In-Progress | Green | 2025-12-29 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13547 | FOCUS FCLA FEXCO System | In Production | FEXCO | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | FEXCO is a FCLA-developed system that serves to manage the retail contract in loss recovery transferred to external agencies and attorneys by establishing controls regarding the assigned portfolio |  |  | YES | 3 | TSWEEN16 | PLM | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
15421 | FOCUS FCLA FACT SYSTEM | In Production | FACT | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | RMANGAL | Bronze | Non S-Ox | 222 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | Ford Credit (FMCC) | Internal Web Application responsible for generating wholesale accounting transacionts and manage their transacions, interfacing with Wholesale Application and SAP-Shana |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
23876 | Ford Credit Optim Test Data Management | Active | FCOPTIM | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | VCECCARE | Copper | Non S-Ox | - | No | Yes | - | PTABOR5 | DTAURO | Enterprise Technology | - | Tool used in Ford Credit to perform data propagations | 2 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
15421 | FOCUS FCLA FACT SYSTEM | In Production | FACT | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | RMANGAL | Bronze | Non S-Ox | 222 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Ford Credit (FMCC) | Internal Web Application responsible for generating wholesale accounting transacionts and manage their transacions, interfacing with Wholesale Application and SAP-Shana |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
21683 | FOCUS | Active | FOCUS | EPEO | SKULKA52 | CGIACOBB | JKOOPMA3 | JKOOPMA3 | Copper | Non S-Ox | - | No | - | - | CMIRABIT | CGIACOBB | Information Technology | ITO | FOUCS is a mainframe 4 generation language used primarily for reporting. Business Users and IT can create ad hoc reports quickly to obtain information to make business decisions. The FOCUS vendor is Information Builders (IBI) | 42 |  | YES | 1 | SWALIMBE | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned | [17 empty] | DA
12046 | FOCFPSD:FOCUS Ford Parts & Service Div. | In Production | FOCFPSD | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | Copies of MMP tables for ad hoc reporting using FOCUS, MS Access and Business Objects. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. | 323 |  | YES | 3 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
12046 | FOCFPSD:FOCUS Ford Parts & Service Div. | In Production | FOCFPSD | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | Copies of MMP tables for ad hoc reporting using FOCUS, MS Access and Business Objects. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q2 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
12046 | FOCFPSD:FOCUS Ford Parts & Service Div. | In Production | FOCFPSD | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | RAHMAD3 | VRAMASA6 | Silver | Non S-Ox | 211 | No | Yes | In-House | AKARTHI4 | RRADHA4 | Ford Customer Service | FCSD Tech | Copies of MMP tables for ad hoc reporting using FOCUS, MS Access and Business Objects. Additional Outage Impacts include: Impact to Financial Results and Impact to Productivity. |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
21575 | FoA-Line Balancing ADP Interface | In Production | LBAI | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DDESAI | PTOCCO | Human Resources | Staffs IT | Line Balancing to ADP Interface application. This replaces existing Midnight Technologies interface to PeopleSoft Payroll. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-04 | Complete | Blue | 2025-06-13 |  | Planned | REQ0146552 & REQ0146556 | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | SaaS |  |  |  |  | Migrated to Power BI | No | Java < v21
21575 | FoA-Line Balancing ADP Interface | In Production | LBAI | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DDESAI | PTOCCO | Human Resources | Staffs IT | Line Balancing to ADP Interface application. This replaces existing Midnight Technologies interface to PeopleSoft Payroll. |  |  | YES | 4 | TSWEEN16 | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-04 | Complete | Blue | 2025-06-13 |  | Planned | REQ0146552 & REQ0146556 | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Microsoft SQL on Azure |  |  |  |  | MS SQL on Azure | No | SQL
50047 | Ford Cloud Portal | In Production | FCPO | EPEO | SJOHN172 | SJOHN172 | TWOODS19 | BPEDERS1 | Copper | Non S-Ox | 111 | No | Yes | In-House | SJOHN172 | SJOHN172 | Enterprise Technology | EPEO | Ford Cloud Portal is self-developed/managed application which provides self service capabilities for developers to provision and manage services that are part of the Ford Cloud. FCP allows developers to enable easy user experience to provision ITO services in minutes. It allows to create database, PCF, VM & relevant tools & accelerate application delivery. | 9 |  | YES | 3 | SWALIMBE | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
21575 | FoA-Line Balancing ADP Interface | In Production | LBAI | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DDESAI | PTOCCO | Human Resources | Staffs IT | Line Balancing to ADP Interface application. This replaces existing Midnight Technologies interface to PeopleSoft Payroll. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-04 | Complete | Blue | 2025-06-13 |  | Planned | REQ0146552 & REQ0146556 | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | SaaS |  |  |  |  | Migrated to Power BI | No | Java < v21
21580 | FOA Historical Vehicle Sales | In Production | FOA-HVS | M&S TECH | RAHMED33 | DPOOVATH | SPARVESH | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | In-House | APALAZZO | DPOOVATH | Ford Customer Service | - | Database to capture historical vehicle sales data for the Australian Market |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
12362 | FoM Dealer Parts Ordering (PAC) | In Production | PAC | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Ford Customer Service | - | Pedidos Especiales y Atencion a Clientes (PAC) is a Web application that manages parts orders and the confirmation sent from the NEOVIA Logistics warehouse, manages parts on sale (ofertanet), Discount Scales according sales volume (motorcraft) and provides the Parts Price List to the Dealers (Price Bulletins). It also manages dealer returns and claims related to the orders. Dealers submit a request regarding units down and unrecognized parts. | 13 |  | YES | 3 | NKANDULA | PLM | VM | Q3 2025 | Partial Migration to GCP | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51903 | FNV2 Test Automation Analytics | In Production | TANALYTICS | EVDD | NDIMMITT | DCHAMB77 | AAVALOS7 | AAVALOS7 | Copper | Non S-Ox | 111 | Yes | No | In-House | NDIMMITT | DCHAMB77 | Advanced PD and Tech | - | FNV2 (Fully Network Vehicle) test automation analytics is a data science and machine learning project. The objective of this project is to gather automated software verification data from hundreds of Jenkins slave machines that are verifying the software quality in each dev pull request made on Ford GITHUB. The end goal is to gather the metadata and use them for data science and machine learning. Some examples are as follows: Predict software quality trends based on millions of data-point, generate heatmap on problem areas in production code that happens 1 in a million, resource planning based on data insight, monitor lab fleet dynamically using a data-driven Dashboard. |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
23150 | FCE Multi Risk Insurance | In Production | FCE MRI | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Copper | Non S-Ox | 321 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | The application supports the Ford Bank Germany Insurance Department managing a multi purpose insurance product for the dealers (offered by insurance provider Helvetia). | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q3 2025 | EDC CaaS | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
22032 | FCE Commission Payment Tool | In Production | CPT | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Bronze | Non S-Ox | 321 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | For the new pan-European Motor Insurance provider Allianz, Ford Credit Germany has to set up intermediary contracts with the dealer and pay commission to these dealers. The Commission Payment Tool will be used to set up intermediary details for the dealer, to create sales reports and to create payment files for the dealer commission. | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q3 2025 | EDC CaaS | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
24564 | FNV Automated Testing | In Production | FNV TAT | EVDD | NDIMMITT | DCHAMB77 | AAVALOS7 | AAVALOS7 | Copper | Non S-Ox | 111 | Yes | No | In-House | NDIMMITT | DCHAMB77 | Advanced PD and Tech | - | FNV2 (Fully Networked Vehicle) involves 3 main components: SYNC4 (infotainment console), TCU (mobile radio), and ECG (Enhanced Central Gateway). Objective is to develop and execute automated testing for these components. The testing includes the following: Pre-submit: tests whenever a software developer submits a code change Sanity: daily testing to ensure main features are functional Stability: long duration testing to verify mean time between failures |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
54409 | FCE Business Ecommerce Eco System | In Production | FCE-BEES | FORD CREDIT | JBENITO | JCOCKWIL | JGOLDST4 | AGALLAG9 | Gold | Non S-Ox | 323 | No | Yes | In-House | JBENITO | JCOCKWIL | Ford Credit Services | Ford Credit (FMCC) | FCE InDealership and Customer Ecommerce platform. This will be used by Dealers & Customers across all 5 European Markets, in order to propose Finance Applications to FCE. | 1 |  | YES | 2 | SRAISIN1 | PLM | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
24435 | FNV Analytics | In Production | FNVA | EVDD | GJABLONS | PZU1 | RMAURICE | DMOOR349 | Copper | Non S-Ox | 211 | No | Yes | In-House | GJABLONS | GJABLONS | Advanced PD and Tech | 211 | SYNC Analytics is an device/server application that Product Development will be using to help us understand HOW users are using the SYNC module and also capture software failure data to improve quality of the module before release. |  | Springboot | YES | 3 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
24435 | FNV Analytics | In Production | FNVA | EVDD | GJABLONS | PZU1 | RMAURICE | DMOOR349 | Copper | Non S-Ox | 211 | No | Yes | In-House | GJABLONS | GJABLONS | Advanced PD and Tech | - | SYNC Analytics is an device/server application that Product Development will be using to help us understand HOW users are using the SYNC module and also capture software failure data to improve quality of the module before release. |  |  | YES | 3 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
20459 | Enterprise System Center Operations Manager | Active | eSCOM | EPEO | SKULKA52 | NSHAH43 | HLIN13 | SGABLE | Silver | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | Enterprise Technology | ITO | System Center Operations Manager infrastructure setup and SCOM Agents physical implementation information and monitoring | 10 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
51931 | Enterprise Search | In Production | AzrSearch | EPEO | SRUNSON | PWILL357 | GSARAV13 | GSIENKIE | Silver | Non S-Ox | 111 | No | Yes | In-House | SRUNSON | PWILL357 | Enterprise Technology | EPEO | SaaS Search Online Hybrid solution using Search and O365 Search Online. | 6 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
51093 | Enterprise Identity Management | In Production | EIdM | EPEO | NOKEEFE | MSNYDER5 | DDALKOVS | GSIENKIE | Silver | Non S-Ox | 231 | No | Yes | Managed by 3rd Party Purchased Service | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | To replace SILAS for Enterprise Identity lifecycle and profile management. It bases on Microsoft Identity Manager (MIM) product. | 21 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
50386 | FMCDealer - AEM | In Production | FMCDUS | M&S TECH | NKANDULA | JLEWIS10 | KDAILY | JHARPER2 | Platinum | Non S-Ox | 213 | No | Yes | COTS |  |  | Marketing & Sales | Marketing, Sales and Service | FMCDealer AEM is the secured, password protected portal provided by Ford Motor Company to communicate with and provide access to business-critical applications which allow its dealerships to sell, finance, and service FMC vehicles. Brands and business units supported include: Ford and Lincoln, Ford Motor Credit/FMCC, Extended Service Coverage/ESC, MCDistributor/MCD/Motorcraft, Quick Lane/QL, Ford Authorized Distributors/FAD, Ford Customer Service Division/FCSD and Retailer Education & Training/RE&T. Market regions included: USA and Canada |  | Springboot | YES | 2 | NKANDULA | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
12352 | FMCDealer - (excluding USA & Canada) | In Production | FMCDSP | M&S TECH | NKANDULA | JLEWIS10 | KDAILY | JHARPER2 | Platinum | Non S-Ox | 213 | No | Yes | COTS | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | FMCDealer SP sites are the secured, password protected portals provided by Ford Motor Company to communicate with and provide access to business-critical applications which allow its dealerships to sell, finance, and service FMC vehicles. Market regions included: Asia Pacific, Europe and RoW/Rest of World - GTS/Global Trade Services, Mexico and South America. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-11-17 | 2024-11-18 | Complete | Blue | 2024-12-15 | 2025-01-06 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | Completed as a part of PCF | No | Java < v21
12352 | FMCDealer - (excluding USA & Canada) | In Production | FMCDSP | M&S TECH | NKANDULA | JLEWIS10 | KDAILY | JHARPER2 | Platinum | Non S-Ox | 213 | No | Yes | COTS | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | FMCDealer SP sites are the secured, password protected portals provided by Ford Motor Company to communicate with and provide access to business-critical applications which allow its dealerships to sell, finance, and service FMC vehicles. Market regions included: Asia Pacific, Europe and RoW/Rest of World - GTS/Global Trade Services, Mexico and South America. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
11889 | DMS - Drawing Management System | In Production | DMS | ISIT | SKING68 | JLYNN1 | JRICH264 | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | KCHRIST2 | GECHOLS | Manufacturing Engineering | Industrial System IT | Global Document Management System (DMS) provides plant and central staff personnel with electronic storage/retrieval and management of all engineering drawings (machine, tool, gage, controls, and so on) in use at Ford Powertrain facilities. | 14 |  | YES | 2 | BWUNNAVA | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | VM
12352 | FMCDealer - (excluding USA & Canada) | In Production | FMCDSP | M&S TECH | NKANDULA | JLEWIS10 | KDAILY | JHARPER2 | Platinum | Non S-Ox | 213 | No | Yes | COTS | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | FMCDealer SP sites are the secured, password protected portals provided by Ford Motor Company to communicate with and provide access to business-critical applications which allow its dealerships to sell, finance, and service FMC vehicles. Market regions included: Asia Pacific, Europe and RoW/Rest of World - GTS/Global Trade Services, Mexico and South America. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-11-17 | 2024-11-18 | Complete | Blue | 2024-12-15 | 2025-01-06 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | Completed as a part of PCF | No | Java < v21
15539 | Delegate+ | In Production | EuHR-Deleg | OCETO | TSWEEN16 | KADOMKAI | MMUPPITA | ESTILESK | Bronze | Non S-Ox | 111 | No | Yes | COTS | DDESAI | KADOMKAI | Ford Land | Staffs IT | Delegate is a system that manages information on canteen materials currently in stock and estimate future demand of such materials. It is also used to manage orders of food stock for the Cantines in Niehl. | 7 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
21225 | DB2-LUW | Active | DB2LUW | EPEO | SKULKA52 | SKRISH30 | MKUMARA5 | NVAIDYAN | Silver | Non S-Ox | - | No | Yes | - | CMIRABIT | SKRISH30 | Enterprise Technology | ITO | This is an infrastructure that is used by applications to store data | 12 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
53971 | Database Strategy | Active | DBStrategy | EPEO | SKULKA52 | NSHAH43 | BCAPATIN | BCAPATIN | Copper | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | Enterprise Technology | - | Database Strategy for FORD motor Company Landscape | 4 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
53660 | Database Migration Service | Active | dbmig | EPEO | SKULKA52 | NSHAH43 | HLIN13 | HLIN13 | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | Enterprise Technology | ITO | Database migration service includes multiple database migration tools that support various migration use cases from on-prem to GCP and Azure/AWS to GCP. | 1 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
18610 | FLEXnet Manager | In Production | FNM | EPEO | SKULKA52 | CPENNEY | DECKART1 | DECKART1 | Copper | Non S-Ox | 211 | No | Yes | COTS | CMIRABIT | CPENNEY | Enterprise Technology | EPEO | FLEXnet License Manager is the industry standard tool used by Ford's Central License System (CLS). This project will upgrade FLEXnet to improve consumption management and reporting capabilities, including support for IBM's LUM (Catia license manager). |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
19947 | Database Activity Monitoring | Active | DAM | EPEO | SKULKA52 | NSHAH43 | AVELMURU | AVELMURU | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | Enterprise Technology | ITO | Database Activity Monitoring (DAM) is a process which uses one or more database security software to monitor the data change activities performed by Global Database Service Teams. This process is mandatory to provide compliance for data change activities for applications that are classified as S-Ox or Secret (C=3). | 9 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
50560 | Fleet Remarketing Information System | In Production | eFRIS | FORD CREDIT | DTAURO | PBALUSU | LSTARZYK | RPARAME4 | Silver | Non S-Ox | 232 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | e-FRIS is part of the UVIS System that manages all Fleet Repurchase and Non-Return programs for NAFLRO (North American Fleet Leasing and Repurchasing Operations). |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q3 2027 | Rewrite | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
19494 | FLEET MANAGEMENT SYSTEM (GVUS REPLACEMENT) | In Production | FMS | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | COTS | JKOONS | JKOONS | PD Operations and Quality | Industrial System IT | Fleet Management System to manaage the tracking of Company vehicles including Prototype Vehicle Utilization. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | Q3 2027 | On-Prem | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started | Green | 2027-12-14 |  | Planned |  | No | [14 empty] | No | Oracle
19494 | FLEET MANAGEMENT SYSTEM (GVUS REPLACEMENT) | In Production | FMS | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | COTS | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Fleet Management System to manaage the tracking of Company vehicles including Prototype Vehicle Utilization. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q2 2026 | Version Upgrade | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
23321 | Cyber Security Center Extract Transfer Load Server | In Production | CSC ETL | OCETO | PMILLIGA | PLUBAS | RKLOMAN | WJUSTICE | Copper | Non S-Ox | 223 | No | Yes | In-House | PMILLE12 | PLUBAS | Enterprise Technology | - | CDC internal tools server. This will support CDC internal applications, integrations, orchestrations, and an interactive webex chatbot to assist with integration health monitoring and error troubleshooting | 4 |  | YES | 1 | PMILLIGA | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
6287 | CVMS | In Production | CVMS | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | CVMS - Company Vehicle Management System (US Only). Manages the company vehicle asset from order through disposal. Tightly integrated with MFV application. | 4 |  | YES | 4 | NKANDULA | PLM | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
53691 | Fleet Enrollments | In Production | FPI_ENR | FORD PRO & FCSD TECH | RKENNEL | ESHANKS2 | CSTAUFF2 | EHEIKKI3 | Gold | Non S-Ox | 221 | No | Yes | In-House | #N/A | #N/A | General Management | 221 | SOFTWARE FULFILLMENTS IS THE GATEWAY FOR THE END-TO-END PROCESS THAT ENABLES A COMMERCIAL CONSUMER TO ENROLL TO A PRODUCT WHICH INCLUDES THE SUBSCRIPTION AND ALL SUBSEQUENT SETUPS AND CONFIGURATIONS THAT ARE REQUIRED IN BOTH THE COMMERCIAL CONNECTED VEHICLE AND THE CLOUD APPLICATIONS. |  | Springboot | YES | 1 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
22372 | Coordination of Benefits and Flex Benefits | In Production | COB FLEX | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Human Resources | Marketing, Sales and Service | Provides a self-serve mechanism for salaried employees to make their elections regarding allocation of Flex Benefit funds and collects Co-Ordination of Benefits information to manage benefits coverage. The resulting data is extracted by HR and sent to Morneau for processing. | 12 |  | YES | 1 | NKANDULA | PLM | VM | Q3 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
167 | FITS: Financial Inventory Transaction System | In Production | FITS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DNANDAN | DWIERZBI | Finance | FCSD Tech | utilized to value the U.S. service part inventory for the Corporate General Ledger System, provide billing and credit data to the Customer Billing System, and part sales receipt data to the Corporate Payables System. | 6 |  | YES | 3 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
167 | FITS: Financial Inventory Transaction System | In Production | FITS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | NBAECKER | DWIERZBI | Finance | FCSD Tech | utilized to value the U.S. service part inventory for the Corporate General Ledger System, provide billing and credit data to the Customer Billing System, and part sales receipt data to the Corporate Payables System. |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
167 | FITS: Financial Inventory Transaction System | In Production | FITS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | NBAECKER | DWIERZBI | Finance | FCSD Tech | utilized to value the U.S. service part inventory for the Corporate General Ledger System, provide billing and credit data to the Customer Billing System, and part sales receipt data to the Corporate Payables System. |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
20536 | Cisco Unified Communication Manager (CUCM) | In Production | CUCM | EPEO | SRUNSON | PWILL357 | DPETRIE | DPETRIE | Silver | Non S-Ox | 111 | No | Yes | COTS | SRUNSON | PWILL357 | Enterprise Technology | EPEO | CUCM is a Linux-based operating system that operates as a software-based call-processing component of IP Telephony. CUCM provides signaling and call control services to Cisco integrated telephony applications as well as to third-party applications | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
15875 | FIS FORD CUSTOM REPORTS | In Production | FISFCR | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 211 | No | Yes | In-House |  |  | Manufacturing Staffs | Industrial System IT | FIS reports created for Ford VO and PTO operations. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
13569 | First Page | In Production | FP | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 211 | No | Yes | COTS | SKING68 | SKING68 | Manufacturing Staffs | Industrial System IT | Purchased package to manage configuration and messaging for alarming and escalation, and messaging to pagers. |  |  | NO | 3 | BWUNNAVA | PLM | Oracle |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
13569 | First Page | In Production | FP | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 211 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Staffs | Industrial System IT | Purchased package to manage configuration and messaging for alarming and escalation, and messaging to pagers. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2026 | On-Prem | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
50188 | Checkmarx CxSAST | In Production | CHKMX | OCETO | PMILLIGA | SNAMBIVE | SHEMALAT | WJUSTICE | Silver | Non S-Ox | 221 | Yes | No | COTS | MCHRIS38 | SNAMBIVE | Enterprise Technology | - | A static application testing tool used to identify vulnerabilities in application code. | 28 |  | YES | 2 | PMILLIGA | PLM | VM | Q3 2025 | Complete Migration to SaaS | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20267 | Certificate Lifecycle Manager | In Production | FIM CM | EPEO | NOKEEFE | VNACHIMU | BSARAV20 | GSIENKIE | Copper | Non S-Ox | 221 | No | Yes | COTS | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | Provides management of secure e-mail certificates. | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
53802 | FinTech Platform (EU) | In Production | FQEU | FORD PRO & FCSD TECH | TJUNIPER | RHOWEL46 | SBOULDS | JCOY3 | Silver | Non S-Ox | 222 | No | Yes | In-House | #N/A | #N/A | Marketing & Sales | 222 | ECOMMERCE FINANCE APPLICATION EUROPE INTEGRATION AND ABSTRACTION LAYER. |  | Springboot | YES | 1 | RKENNEL | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
52654 | FinApp EU | In Production | FinApp EU | FORD PRO & FCSD TECH | TJUNIPER | RHOWEL46 | SBOULDS | JCOY3 | Gold | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Marketing & Sales | 322 | ECOMMMERCE BUY FINANCE APPLICATION FOR EU REGION |  | Springboot | YES | 1 | RKENNEL | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
17780 | Finance documents control management | In Production | MIG | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Scope: Venezuela, Colombia Main system functionalities: - Generates vehicle credit notes - Generates and approval process for accounting notes for all Andina local systems - Documents Issuance Control(sequence): Invoices, 3040 |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17780 | Finance documents control management | In Production | MIG | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | Scope: Venezuela, Colombia Main system functionalities: - Generates vehicle credit notes - Generates and approval process for accounting notes for all Andina local systems - Documents Issuance Control(sequence): Invoices, 3040 |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
23854 | Azure AD Connect | In Production | AAC | EPEO | NOKEEFE | MSNYDER5 | CQI | GSIENKIE | Silver | Non S-Ox | 213 | Yes | No | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Strategic implementation to support existing Azure AD Accounts in AZUREFORD. CHINAFORD to remain as tactical solution and will not be part of this HA implemented solution. Enterprise Systems Management Description - This project will provide one way synchronization of internal Ford Active Directory user accounts to existing Azure AD accounts in such a way that all internal Ford users for an Azure Tenant will be managed by an internal Ford Active Directory system so that there is a single identity source for all existing Azure AD accounts which have been issued to users who existing within Fords internal Active Directory. BCE Rating E OLA2. | 6 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
17780 | Finance documents control management | In Production | MIG | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Scope: Venezuela, Colombia Main system functionalities: - Generates vehicle credit notes - Generates and approval process for accounting notes for all Andina local systems - Documents Issuance Control(sequence): Invoices, 3040 |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17971 | FIN - Finance DataWarehouse | In Production | FIN | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | Finance Data Warehouse that it is used by Finance Staff to take information and compose some business report concerning Finance requirements. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
54903 | Azure AD Application Proxy | Planned | AADAppProx | EPEO | NOKEEFE | MSNYDER5 | ZZHAN106 | GSIENKIE | Gold | Non S-Ox | 211 | No | Yes | COTS | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Using Azure AD Application Proxy to publish on-premises apps for remote users. | 6 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
196 | FIMPS: Fleet Incentive Marketing Program System | In Production | FIMPS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | KHEMANT | RANANDAL | Finance | - | FIMPS controls incentive payment processing for NAFLRO, integrated with CPA, the Extended Service Plan system (ESP) and the Qualified Vehicle Modifier system (QVM). Continuous review edits for post-release off-invoice government price concessions, CPA and national fleet incentives are designed to comply with corporate internal control requirements. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
196 | FIMPS: Fleet Incentive Marketing Program System | In Production | FIMPS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | KHEMANT | RANANDAL | Finance | - | FIMPS controls incentive payment processing for NAFLRO, integrated with CPA, the Extended Service Plan system (ESP) and the Qualified Vehicle Modifier system (QVM). Continuous review edits for post-release off-invoice government price concessions, CPA and national fleet incentives are designed to comply with corporate internal control requirements. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
21332 | File Transfer Management System (VE) | In Production | FTMS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Enterprise Technology | - | Scope: Venezuela Main system functionalities: - Control of inbound and outbound transmissions(Control file version) |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
21332 | File Transfer Management System (VE) | In Production | FTMS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Enterprise Technology | - | Scope: Venezuela Main system functionalities: - Control of inbound and outbound transmissions(Control file version) |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
23643 | Attunity Replicate | Active | RATTUNIT | EPEO | SKULKA52 | NSHAH43 | NVAIDYAN | RPOLLO13 | Silver | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | Enterprise Technology | - | Attunity Replicate is a Data Ingestion tool (software) that replicates data from source systems (SQL Server, Oracle, DB2 z/OS, Teradata, and unstructured formats) to target Hadoop and Greenplum infrastructure | 4 |  | YES | 2 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
20537 | Field Communication System | In Production | FCS | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | 112 | No | Yes | COTS |  |  | Ford Customer Service | Technology & Enterprise Services (TES) | EDMS-FCS(Field Communication Systems) serving Marketing,Sales,and Service (MS&S) has its own room and has its own managed workflow process wherein the online communications are raised by marketing, dealer relations, Motorcraft, technical services personnel which goes for a review ,approval and release process before it reaches the end users who receive electronic field communications(eFC). The is a common repository of marketing, sales, and service information. It is a secured, controlled environment that provides web access to create, store, and retrieve information to support business requirements. Content stored in the EDMS-FCS is limited to documents/content owned and/or managed by organizations within MS&S. Depending on security requirements, documents/content can be made available for viewing by all employees of Ford Motor Company.Dealer communications(eDC) are accessed by FMCDealer content managers who ultimately post the information designated as Dealer Communication to FMCDealer. |  | WAS | YES | 1 | TSWEEN16 | PLM | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
13488 | FGTI-Internal Website | In Production | FGTI Web | OCETO | TSWEEN16 | BLALLY | VCHEA | MBALAN2 | Copper | Non S-Ox | 111 | Yes | No | In-House | SCROLEY | JSTEC1 | Policy | Staffs IT | Internal website for the Ford Global Technologies, LLC business activity. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | SQL
17832 | Arg. Customs Vehicle BoM Classification (CTC) | In Production | ARCT | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Bronze | Non S-Ox | 11 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | - | Manages classification of the BoM of each vehicle built in Argentina. For that, it uses harmonized codes for all trading goods. Finally, it creates all the legally required documents to be presented to the Government (Secretaria de Industria y Comercio). The documentation created by this system is required to be able to use RAF customs benefits in Argentina. | 4 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
16096 | FFLA Brazil Ford Credit Web Site (TLK) | In Production | TLK | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Credit Services | - | The purpose of this system is to have available in the public internet, the Ford Credit Brazil Web Site, to provide information to FCB customers, non customers, dealers Ford and non Ford. FCB employees assigned to provide data maintenance have grants in the intranet. Customers can access personal data of their operation with FCB accessing the web through a password. Part of this application is based on Intranet application, such as: CRM backoffice, Payment Slip(wholesale and retail) and Parameters to Ford Credit Brazil Web Site (finance rates, programs, etc.) This application has others functions available to the Dealers in B2B process, such as the Input in an on-line transaction of the Used Vehicle to finance under FVU program and fill up a form to request authorization to move units from one sales point to another. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Oracle
23318 | AP B2C Services Layer | In Production | APB2CSL | M&S TECH | VMUTHUPA | DSHANKA1 | RPURUSH3 | MPREETH6 | Silver | Non S-Ox | 212 | No | Yes | In-House | VMUTHUPA | DSHANKA1 | Marketing & Sales | Marketing, Sales and Service | AP B2C Service layer application provides list of webservices and data that enables functionality for Ford and Lincoln customer facing Digital channels. Ford including Brand websites in AP, Mex, MEA, and South America. Lincoln including Brand websites in China, South Korea, Middle East, Puerto Rico and Mexico. | 8 |  | YES | 3 | NKANDULA | PLM | VM | Q3 2025 | Partial Migration to GCP | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
16101 | FFLA Brazil Accounting Reconciliation-CBB | In Production | CBB | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NMORALE7 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | The system performs the automatic banking and accounting reconciliation. There are two modules for Reconciliation: Account and Bank, also there is a module to Manual Repair Reconciliation. There is an Inquiry Module and a Report Module to extract files and Reports. There is a Module for inquiry General Ledger records from 1996 to 2003 which are initially loaded at once and no longer will be updated. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Oracle
11044 | Anaqua | In Production | Anaqua | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Silver | Non S-Ox | 331 | No | Yes | COTS | DDESAI | KADOMKAI | Policy | Staffs IT | The Anaqua application manages Ford's Intellectual Property (IP). Launched on commercial version 6.2 in December 2009. ANAQUA 8.5.5 upgrade went live in 4/2017 | 8 |  | YES | 2 | TSWEEN16 | PLM | VM | Q3 2025 | Partial Migration to GCP | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
16101 | FFLA Brazil Accounting Reconciliation-CBB | In Production | CBB | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NMORALE7 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | The system performs the automatic banking and accounting reconciliation. There are two modules for Reconciliation: Account and Bank, also there is a module to Manual Repair Reconciliation. There is an Inquiry Module and a Report Module to extract files and Reports. There is a Module for inquiry General Ledger records from 1996 to 2003 which are initially loaded at once and no longer will be updated. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
24464 | FFLA Brazil - Easy Way Tributos (EWT) | In Production | EWT | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | ROBRIEN3 | Silver | Non S-Ox | 211 | No | Yes | COTS | DBRIGHEN | RCORDEI1 | Ford Credit Services | - | Easy-Tributos and Easy-SPED apps support Tax and Accounting departments of Ford Credit Brazil, respectively. Easy-tributos provides tax reports and Easy-SPED provides holding Tax (REINF) and Financial Operations of the Bank Ford with dealers reports, all of these reports feed IRS - Internal Revenue Service of Brazil. Those apps are developed and supported by a Brazilian company named Easy-Way of Brasil. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
50579 | Alvaria Outbound Dialer | In Production | AlvariaDLR | FORD CREDIT | KDELTA | PBINGI | RGUTOWS3 | SMOCK6 | Silver | Non S-Ox | 311 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | Outbound dialer | 87 |  | YES | 1 | SRAISIN1 | PLM | VM | Q3 2025 | Complete Migration to SaaS | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
21311 | FFAP - FOCUS - CHINA ASIA PACIFIC - CFOCUS | In Production | CFOCUS | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | S-Ox Out of Scope | 332 | No | Yes | - | IPANKAJ | IPANKAJ | Ford Credit Services | Ford Credit (FMCC) | FOCUS system is an account receivable system which controls and manages Retail operations and Wholesale receivables for China. |  |  | YES | 3 | SRAISIN1 | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
18605 | Active Directory Domain Services | In Production | AD | EPEO | NOKEEFE | MSNYDER5 | CQI | GSIENKIE | Gold | Non S-Ox | 333 | Yes | No | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | The Microsoft Windows Active Directory glossary defines an Active Directory as a structure supported by Windows that lets any object on a network be tracked and located. Active Directory is the directory service used in Windows Server and provides the foundation for Windows distributed networks. A directory service provides the methods for storing directory data and making this data available to network users and administrators. For example, Active Directory stores information about user accounts, such as names, phone numbers, and so on, and enables other authorized users on the same network to access this information. The AD, or Active Directory, is a database based on the LDAP (Lightweight Directory Access Protocol) standard, which makes the information contained within the AD easily available to other applications across different platforms. The AD contains user accounts, computer accounts, organizational units, security groups, and group policy object - all of which have a unique name and a unique | 8 |  | YES | 1 | SWALIMBE | PLM | VM | Q3 2025 | EDC New Hypervisor | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | VM
21311 | FFAP - FOCUS - CHINA ASIA PACIFIC - CFOCUS | In Production | CFOCUS | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | S-Ox Out of Scope | 332 | No | Yes | - | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | FOCUS system is an account receivable system which controls and manages Retail operations and Wholesale receivables for China. |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
24357 | FENIX Large Aggregated Release Entity | In Production | FLARE | EVDD | JWASNIC1 | CRAJA1 | RWASIM | RWASIM | Copper | Non S-Ox | 123 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 123 | VEHICLE DISCOVERY FOR MASS OVER THE AIR UPDATES. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
13402 | Federal Order Management System | In Production | FOMS | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | ATRIPAT9 | Bronze | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | FOMS automates the manual process of receiving GSA Motor Vehicle Delivery Orders (MVDO), editing them to the contractual agreement with the GSA,and enter the order into CONCEPS. FOMS adds an order tracking feature not currently available. SLA 4 CIA 2,1,1 |  |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
13402 | Federal Order Management System | In Production | FOMS | FORD PRO & FCSD TECH | RKENNEL | PJEFFRE5 | DAYRES1 | ATRIPAT9 | Bronze | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | PJEFFRE5 | General Management | Ford Pro | FOMS automates the manual process of receiving GSA Motor Vehicle Delivery Orders (MVDO), editing them to the contractual agreement with the GSA,and enter the order into CONCEPS. FOMS adds an order tracking feature not currently available. SLA 4 CIA 2,1,1 |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
23451 | FEDEBOM | In Production | FEDEBOM | ISIT | MNOWICK1 | LSRINIVA | HKUMAR7 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | 211 | FEDEBOM is a solution to Product Development D&R Engineers to author Vehicle Bill Of Material and planned to replace AVBOM2 and will support Engineers out WERS. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23451 | FEDEBOM | In Production | FEDEBOM | ISIT | MNOWICK1 | LSRINIVA | HKUMAR7 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | FEDEBOM is a solution to Product Development D&R Engineers to author Vehicle Bill Of Material and planned to replace AVBOM2 and will support Engineers out WERS. |  |  | YES | 3 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
24011 | WhatsupGold | In Production | WUG | ISIT | KCHRIST2 | GECHOLS | CDENARD1 | AVARADY | Copper | Non S-Ox | 111 | No | Yes | COTS | KCHRIST2 | GECHOLS | Enterprise Technology | Industrial System IT | What's Up Gold Tool for Plants. Plant IT utility for pro-active infrastructure monitoring. Runs on DxD's at each individual plant, licenses handled by plants. (this is put in FPS Workstream but supports multiple portfolios: maint., quality, etc) | 1 |  | YES | 1 | BWUNNAVA | PLM | VM | Q2 2027 | EDC New Hypervisor | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started | Green | 2027-09-13 |  | Planned |  | No | [14 empty] | No | VM
20330 | FEDE Workbench | Planned | FEDEWB | ISIT | JKOONS | NLAKSHMA | KRAJES33 | GRAO3 | Silver | S-Ox Classification Pending | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | 311 | PD Systems Engineering initiatives |  | Springboot | YES | 4 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
20330 | FEDE Workbench | Planned | FEDEWB | ISIT | JKOONS | NLAKSHMA | KRAJES33 | GRAO3 | Silver | S-Ox Classification Pending | 311 | No | Yes | COTS | JKOONS | JKOONS | Advanced PD and Tech | Industrial System IT | PD Systems Engineering initiatives |  |  | YES | 4 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
20330 | FEDE Workbench | Planned | FEDEWB | ISIT | JKOONS | NLAKSHMA | KRAJES33 | GRAO3 | Silver | S-Ox Classification Pending | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | PD Systems Engineering initiatives |  |  | YES | 4 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
12740 | Web Information Systems Request (WebISR) | In Production | IntranetIT | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | Marketing, Sales and Service | There are several IT tools incorporated under this EAMS #. It includes WebISR, Time Tracker and Annual Access Review. The Web ISR is an integrated work flow tool that facilitates the initiation, approval, assignment, reporting, documentation and billing for Information Systems Requests. User roles are defined within the tool to support the various functions within IT. The tool ensures all projects adhere to the ITPM and SDM while also ensuring that documentation and audit requirements are met. As part of the IT intranet services the following sub-application is also included, Annual Access Review. | 12 |  | YES | 2 | NKANDULA | PLM | VM | Q2 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19235 | Feature Management System | In Production | WFC | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 111 | No | Yes | In-House | JKOONS | JKOONS | Advanced PD and Tech | Industrial System IT | Feature Management System (FMS) is a suite of integrated toolsets deployed through Ford Intranet and CAD Integration (in multiCAD environment) for management of design features and collaboration b/w PD and ME organizations for feature based design and manufacturing process. Note: This tool is sometimes referred to as Web Feature Chart (WFC). |  |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
19235 | Feature Management System | In Production | WFC | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 111 | No | Yes | In-House | MNOVAK1 | mgerman | Advanced PD and Tech | Industrial System IT | Feature Management System (FMS) is a suite of integrated toolsets deployed through Ford Intranet and CAD Integration (in multiCAD environment) for management of design features and collaboration b/w PD and ME organizations for feature based design and manufacturing process. Note: This tool is sometimes referred to as Web Feature Chart (WFC). |  | WAS | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13017 | FCSD Remanufacturing System | In Production | REMAN | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | KPATEL77 | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | MAMUDHA | Ford Customer Service | FCSD Tech | The REMAN application supports: 1) core recover from dealers, 2) core payment to dealers and 3) core management in the remanufacturing pipeline. It is built on SAP technology. | 15 |  | YES | 7 | RKENNEL | PLM | BO | Q2 2024 | Already Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-31 | 2024-12-31 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | DA
13017 | FCSD Remanufacturing System | In Production | REMAN | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | KPATEL77 | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | MAMUDHA | Ford Customer Service | FCSD Tech | The REMAN application supports: 1) core recover from dealers, 2) core payment to dealers and 3) core management in the remanufacturing pipeline. It is built on SAP technology. |  |  | YES | 7 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13017 | FCSD Remanufacturing System | In Production | REMAN | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | KPATEL77 | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | MAMUDHA | Ford Customer Service | FCSD Tech | The REMAN application supports: 1) core recover from dealers, 2) core payment to dealers and 3) core management in the remanufacturing pipeline. It is built on SAP technology. |  |  | YES | 7 | RKENNEL | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
13017 | FCSD Remanufacturing System | In Production | REMAN | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | KPATEL77 | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | MAMUDHA | Ford Customer Service | FCSD Tech | The REMAN application supports: 1) core recover from dealers, 2) core payment to dealers and 3) core management in the remanufacturing pipeline. It is built on SAP technology. |  |  | YES | 7 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
13017 | FCSD Remanufacturing System | In Production | REMAN | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | KPATEL77 | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | MAMUDHA | Ford Customer Service | FCSD Tech | The REMAN application supports: 1) core recover from dealers, 2) core payment to dealers and 3) core management in the remanufacturing pipeline. It is built on SAP technology. |  |  | YES | 7 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
16748 | TDE Web Site | In Production | TDE_WS | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | - | Official Automatic Transmission Engineering Operations (TDE) Web site | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started | Green | 2027-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13017 | FCSD Remanufacturing System | In Production | REMAN | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | KPATEL77 | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | MAMUDHA | Ford Customer Service | FCSD Tech | The REMAN application supports: 1) core recover from dealers, 2) core payment to dealers and 3) core management in the remanufacturing pipeline. It is built on SAP technology. |  |  | YES | 7 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
23762 | FCSD Parts Sales Management System | In Production | FPSMS | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | HMONTANO | Ford Customer Service | - | Venezuela, Colombia Main system functionalities: 1. Customers Definitions. 2. Vendors Definitions. 3. Sales objectives Definitions. 4. Salesman Visit Schedules. 5. Customers Sales Statistics. 6. Prices Parts List Process. 7. Customers Parts Orders. 8. Customers Invoice Request Orders Process. 9. Parts Invoice recollection and package process. 10. Credits and Debits Notes. 11. Backorders Management. 12. Customers Claims Process. 13. Sales Information Inquiry. 14. Sales Reports. 15. Basic Sales Definitions | 400 |  | YES | 4 | TSWEEN16 | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
23762 | FCSD Parts Sales Management System | In Production | FPSMS | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Customer Service | - | Venezuela, Colombia Main system functionalities: 1. Customers Definitions. 2. Vendors Definitions. 3. Sales objectives Definitions. 4. Salesman Visit Schedules. 5. Customers Sales Statistics. 6. Prices Parts List Process. 7. Customers Parts Orders. 8. Customers Invoice Request Orders Process. 9. Parts Invoice recollection and package process. 10. Credits and Debits Notes. 11. Backorders Management. 12. Customers Claims Process. 13. Sales Information Inquiry. 14. Sales Reports. 15. Basic Sales Definitions |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
21808 | QAD Archival Tool | In Production | QAT | I-ERP | SFRANCI8 | RJAYAKU2 | RSRIRA18 | LWU14 | Silver | Non S-Ox | 311 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | - | Application to store, view and create reports of QAD data.This application will hold QAD data post QAD Exit. | 11 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23762 | FCSD Parts Sales Management System | In Production | FPSMS | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Customer Service | - | Venezuela, Colombia Main system functionalities: 1. Customers Definitions. 2. Vendors Definitions. 3. Sales objectives Definitions. 4. Salesman Visit Schedules. 5. Customers Sales Statistics. 6. Prices Parts List Process. 7. Customers Parts Orders. 8. Customers Invoice Request Orders Process. 9. Parts Invoice recollection and package process. 10. Credits and Debits Notes. 11. Backorders Management. 12. Customers Claims Process. 13. Sales Information Inquiry. 14. Sales Reports. 15. Basic Sales Definitions |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q4 2027 | Rewrite | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
23763 | FCSD Parts Purchasing Management System | In Production | FPPMS | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Gold | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Customer Service | - | Scope: Venezuela, Colombia Main system functionalities: - Procurement process for local and imported parts |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2026 | On-Prem | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
15658 | Powertrain Control Module Interface Spec | In Production | PCM Spec | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Copper | Non S-Ox | 221 | Yes | No | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | - | The website is a live source of information detailing the electrical interfaces between the powertrain control module (PCM) and vehicle sensors and actuators. The PCM is currently made by Visteon and Motorola. In the future other PCM manufactures will begin working with Ford and will need access to the specifications | 8 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started | Green | 2027-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23763 | FCSD Parts Purchasing Management System | In Production | FPPMS | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Gold | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Customer Service | - | Scope: Venezuela, Colombia Main system functionalities: - Procurement process for local and imported parts |  |  | YES | 3 | TSWEEN16 | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
11585 | FCSD Imaging and Workflow | In Production | Warranty | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SDEENAD1 | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | RKENNEL | Ford Customer Service | FCSD Tech | This application provides document storage and management services to Ford Global Warranty claims processing. Warranty Imaging FileNet |  |  | YES | 2 | RKENNEL | PLM | Oracle | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
9044 | PfeP: Plan for Every Part - Pro | In Production | EUMP-PFEP | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 211 | No | Yes | In-House |  |  | Manufacturing Staffs | Industrial System IT | Plan-for-Every-Part from Supplier via dock/market place to vehicle line | 2 |  | YES | 3 | BWUNNAVA | PLM | VM | Q2 2027 | EDC New Hypervisor | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started | Green | 2027-09-13 |  | Planned |  | No | [14 empty] | No | VM
20753 | FCSD Dashboard | In Production | FCSD DshBd | M&S TECH | KPINNU | KHILLERT | GAJAY | JHARPER2 | Copper | Non S-Ox | 111 | Yes | No | In-House | KPINNU | KHILLERT | Marketing & Sales | - | This application covers the presentation layer for the Global UDB Dashboard Reporting. The reporting layer is being built by Information Builders using Web Focus and is being supported by IB. Hosting is internal at the Ford data center. | 4526 |  | YES | 3 | NKANDULA | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned |  | No | [8 empty] | Webfocus 9 | [5 empty] | No | DA
20753 | FCSD Dashboard | In Production | FCSD DshBd | M&S TECH | KPINNU | KHILLERT | GAJAY | JHARPER2 | Copper | Non S-Ox | 111 | Yes | No | In-House | KPINNU | KHILLERT | Marketing & Sales | - | This application covers the presentation layer for the Global UDB Dashboard Reporting. The reporting layer is being built by Information Builders using Web Focus and is being supported by IB. Hosting is internal at the Ford data center. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
20972 | NextGen Data ModelingTool | In Production | NG-DMT | OCETO | TVASU | MWAWZYSK | SFAN21 | KTRACY8 | Bronze | Non S-Ox | 111 | No | Yes | COTS | NSENTHI1 | MWAWZYSK | Enterprise Technology | Technology & Enterprise Services (TES) | A Data Modeling tool is used to develop and document data models for IT applications. Logical and physical data model designs are created and updated by data architects. Business Analysts, Developers and Database Administrators also use the data modeling tool to update data model metadata information. The information entered into the tool should be able to create graphical drawings (ER diagrams, Server Model diagrams, etc.) and DDL script files. The tool will be maintained by Enterprise Architecture. | 6 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2027 | Partial Migration to GCP | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22233 | FCO Tooling Leasing System | In Production | FCOTLS | I-ERP | SFRANCI8 | SDHANAL3 | PSATHIS3 | LWU14 | Silver | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | A new application to handle FCO Tooling Leasing business process, it is to develop by FCO Tooling Project (ITMS 21607) |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
22233 | FCO Tooling Leasing System | In Production | FCOTLS | I-ERP | SFRANCI8 | SDHANAL3 | PSATHIS3 | LWU14 | Silver | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | A new application to handle FCO Tooling Leasing business process, it is to develop by FCO Tooling Project (ITMS 21607) |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
22036 | GOTD - Order Production Scheduling & Sequencing | In Production | GOTD -OPSS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | OPSS streamlines, simplifies and enhances the Replanning and Sequencing business processes and supporting systems within the Marketing & Sales and Material Planning & Logistics organizations. | 94 |  | YES | 2 | NKANDULA | PLM | VM | Q2 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22233 | FCO Tooling Leasing System | In Production | FCOTLS | I-ERP | SFRANCI8 | SDHANAL3 | PSATHIS3 | LWU14 | Silver | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | A new application to handle FCO Tooling Leasing business process, it is to develop by FCO Tooling Project (ITMS 21607) |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
22090 | GAPS Documents Distribution | In Production | EuAS GDDS | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Silver | Non S-Ox | 221 | No | Yes | Open Source | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Accepts raw data from GAPS suite for both FSA and FOA markets and transforms outputs into PDF formatted document of Self Billing Invoices SBI Positive Negative and Retro and Debit and Credit Notes Maintain PDF in repository for the threshold period and allow users to download PDF via ePayables Supplier Portal User Interface for managing template forms for the total of 10 documents for both FOA FSA markets Provide an online web service for ePayables to pick display and allow the PDF SBI to be downloaded by the supplier users After threshold period the SBI PDF documents to be pushed to Documentum EDMS Archival solution Debit Credit note TIFF images to be pushed to Odyssey Application | 7 |  | YES | 3 | TSWEEN16 | PLM | VM | Q2 2027 | Will be Decommissioned | Decommission | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
51250 | FCNA Dealer API Service Layer | In Production | FCDLRAPI | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | NVARADA2 | Gold | Non S-Ox | 332 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | Ford Credit Dealer Services API provides Restful-based service to provide dealer audit information to Dealer Risk (GLAS). |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
17851 | FSAO Treasury Export Operations (TR) | In Production | ARTR | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Application for Treasury Export Operations control. Covers the exports process from bill to bank liquidation looking forward to ensure accomplishment with all regulations in force. | 4 |  | YES | 3 | TSWEEN16 | PLM | VM | Q2 2027 | Will be Decommissioned | Decommission | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | VM
51250 | FCNA Dealer API Service Layer | In Production | FCDLRAPI | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | NVARADA2 | Gold | Non S-Ox | 332 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Ford Credit Dealer Services API provides Restful-based service to provide dealer audit information to Dealer Risk (GLAS). |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
53113 | FCNA Dealer Advisor Application | In Production | DA | FORD CREDIT | NJOSHI21 | GSHAH3 | SMANE4 | NVARADA2 | Silver | Non S-Ox | 211 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit Dealer Advisor (DA) is a responsive web-based tool that will allow Dealers to self-serve their latest Ford Credit performance data and valuable insights through an interactive dashboard. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
19965 | Ford Credit Documentum | In Production | Documentum | OCETO | TVASU | KBALAS13 | DNATARA1 | AGALLAG9 | Silver | Non S-Ox | 312 | No | Yes | COTS | TVASU | NSENTHI1 | Ford Credit Services | - | Document management frontend system which provides search and retrieve capability. Used for (a) retail contract documentation and correspondences used to service retail contracts, (b) dealer invoices and SoA, (c) misc documents. | 9 |  | YES | 1 | TSWEEN16 | PLM | VM | Q2 2027 | EDC New Hypervisor | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | VM
53113 | FCNA Dealer Advisor Application | In Production | DA | FORD CREDIT | NJOSHI21 | GSHAH3 | SMANE4 | NVARADA2 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit Dealer Advisor (DA) is a responsive web-based tool that will allow Dealers to self-serve their latest Ford Credit performance data and valuable insights through an interactive dashboard. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
50385 | B2D-CMS-Foundation | In Production | B2DCMS | M&S TECH | NKANDULA | JLEWIS10 | KDAILY | JHARPER2 | Platinum | Non S-Ox | 213 | No | Yes | COTS | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | Foundation infrastructure for CMS implementations used for Business-to-Dealer, providing components common to all tenants. Tenant dealer CMS applications will reference this as their foundation. Content will reside in those tenants. | 40 |  | YES | 2 | NKANDULA | PLM | VM | Q2 2027 | Complete Migration to SaaS | Decommission | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
16105 | FCLA Mexico - ICMS | In Production | MIC | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | RMANGAL | Bronze | Non S-Ox | 321 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | The ICMS (Integral Cash Management System) is application that manages the payments which Mexico Bank files are loaded by Mex Treasury Team. Mex BOSS Team runs the process consolidating the banks files and separating wholesale payment and retail payment. The Wholesale and Retail payments file are transferred to WFOCUS App and BLESS App based on Business option on ICMS screen according to the operation. It also manages the approvals of wholesale exchange operations, wholesale month end files loading applied Mex BOSS team showed in the Dealer Extranet and allow Mex Treasury team controls operation files. ICMS App has connection with Webfocus tool using restful connection to execute their reports and also allows the other Mexico Local Applications using the same connection to execute the reports.ICMS is facilitator between FoM Apps and WFOCUS App, transferring to WFOCUS APP, the Ford/Lincoln invoice information posted by FoM in the FC shared drive server. | 121 |  | YES | 3 | TSWEEN16 | PLM | WebFocus | Q2 2025 | Modernize | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | [8 empty] | QlikSense |  |  |  |  | On track to complete by end of Q2 Current status = 65 reports decommissioned or migrated. 22 reports yet to be converted. | No | DA
16105 | FCLA Mexico - ICMS | In Production | MIC | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | RMANGAL | Bronze | Non S-Ox | 321 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | The ICMS (Integral Cash Management System) is application that manages the payments which Mexico Bank files are loaded by Mex Treasury Team. Mex BOSS Team runs the process consolidating the banks files and separating wholesale payment and retail payment. The Wholesale and Retail payments file are transferred to WFOCUS App and BLESS App based on Business option on ICMS screen according to the operation. It also manages the approvals of wholesale exchange operations, wholesale month end files loading applied Mex BOSS team showed in the Dealer Extranet and allow Mex Treasury team controls operation files. ICMS App has connection with Webfocus tool using restful connection to execute their reports and also allows the other Mexico Local Applications using the same connection to execute the reports.ICMS is facilitator between FoM Apps and WFOCUS App, transferring to WFOCUS APP, the Ford/Lincoln invoice information posted by FoM in the FC shared drive server. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q2 2026 | Modernize to Cloud Databases | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
17913 | Arg. Consortium Online Sales (VOPA) | In Production | ARWC | OCETO | DBRIGHEN | RCORDEI1 | EGARCI98 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | The Web Page contains information about products their features and Dealers availability. | 9 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2027 | Partial Migration to GCP | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
16021 | Arg. & Chile Vehicle Invoicing (VH) | In Production | ARVH | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | S-Ox In Scope | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Ford Argentina&Chile Invoicing System. Manages the following tasks: Domestic &Export Dispatching / Invoicing Ford-Mazda-PAG Units Operations. Dealers Limits Credit affectation Floor & No-Floor. Taxing registration according Gov regulations. Accounting recording Domestic & Export operations. Models & Customer (Dealers included)Master Files. Built Certificate generation. Units Price Lists administration. Freight quotation and Payment to Carriers. Domestic Operations involved: Dealers Fleet Consignment Consortium Harvest Plan Employees Used others. Export Operations involved: Ford Locs Non-affiliates. Miscelaneous DB-CR notes generation regarding: Incentives Pricing adjm Consortium others. ACR 2004-3709. | 13 |  | YES | 4 | TSWEEN16 | PLM | VM | Q2 2027 | Will be Decommissioned | Decommission | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | VM
19111 | Applus (Inc@Web) | In Production | Applus | ISIT | JDEGUZMA | RMEHTA3 | RJAMBUNA | ISIDDIQ6 | Bronze | Non S-Ox | 211 | No | Yes | COTS | JDEGUZMA | RMEHTA3 | PD Operations and Quality | Industrial System IT | Applus is a modified off the shelf package provided by www.novosoft.es The application is used to record and store internal audit data for the whole of Ford of Europe, MEA, Ford Sollers & Ford Otosan. This data is required in support of ISO 9001 Compliance for Ford of Europe etc. The application provides the ability for all contributing functions / organisations to submit internal audit data to one central data base for Ford of Europe etc. The application has analysis tools within it to allow the centralised/Regional Quality OCM's to analyse the internal audit results and provide direction for Quality Operating System improvements. This is a purchased application from a company called Novotec (www.novatec.es) and is also known as Inc@Web | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2027 | EDC New Hypervisor | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started | Green | 2027-09-13 |  | Planned |  | No | [14 empty] | No | VM
50062 | Vehicle Customer Order South America | In Production | VECTOR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Provide services to attend South America Sales & Marketing Order Fulfillment process that is based on SAMIS application (mainframe/db2). | 4 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
15425 | FCLA FOCUS WHOLESALE APPLICATION - WFOCUS | In Production | WFOCUS | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 322 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit FOCUS system manages wholesale operation for Mexico Ford Credit, and it is called as WFOCUS. WFOCUS System is a core application for Ford Credit Mexico to manage/control wholesale invoice transferred from FMM for wholesale dealer financing and Ford Motor Subsidy, allows FCM Operation to control the dealer limit, dealer floor plan, wholesale payments, dealer risk management, besides to provide wholesale information to Business to report Credit Bureau files and Regulatory Reports. WFOCUS is also responsible for transferring information to Securitization Application-GS. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
51589 | Tricentis Tosca | In Production | TOSCA | FORD CREDIT | JMALETZ | SHE1 | KBALAS30 | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | COTS | JMALETZ | NVENKAT2 | Enterprise Technology | - | Tricentis Tosca is a Continuous Testing platform that accelerates testing to keep pace with Agile and DevOps. | 8 |  | YES | 2 | SRAISIN1 | PLM | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
15425 | FCLA FOCUS WHOLESALE APPLICATION - WFOCUS | In Production | WFOCUS | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 322 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit FOCUS system manages wholesale operation for Mexico Ford Credit, and it is called as WFOCUS. WFOCUS System is a core application for Ford Credit Mexico to manage/control wholesale invoice transferred from FMM for wholesale dealer financing and Ford Motor Subsidy, allows FCM Operation to control the dealer limit, dealer floor plan, wholesale payments, dealer risk management, besides to provide wholesale information to Business to report Credit Bureau files and Regulatory Reports. WFOCUS is also responsible for transferring information to Securitization Application-GS. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
15182 | FCLA Brazil Wholesale Operations Controls (WAP) | In Production | WAP | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | Improve Systems and Controls to support Wholesale Operations in Brazil to avoid losses or frauds and to migrate mandatory controls from manual to automatic. Business Issue and / or Opportunity 1.There are many manual controls over all the steps of the Wholesale process. 2.The Wholesale charge off routine (USA GAAP) has manual adjustments to be in compliance with the Global Policy. 3.All collection activities are done manually without a system support. 4.There is no management tool to allow operational analysis over the daily operation. 5.Part of the COI collection process has no system to support it. 6.The COIs need be within a structured system to avoid controls problems, including the control of the properties received as payment-in-kind. 7.The collaterals appraisals and environment risk assessment needs to be controlled through a system. 8.There is an opportunity to build an automatic interface by downloading the Dealer Financial Statement data to ADCP to avoid data transfer bugs and speed up the |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
15182 | FCLA Brazil Wholesale Operations Controls (WAP) | In Production | WAP | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | Improve Systems and Controls to support Wholesale Operations in Brazil to avoid losses or frauds and to migrate mandatory controls from manual to automatic. Business Issue and / or Opportunity 1.There are many manual controls over all the steps of the Wholesale process. 2.The Wholesale charge off routine (USA GAAP) has manual adjustments to be in compliance with the Global Policy. 3.All collection activities are done manually without a system support. 4.There is no management tool to allow operational analysis over the daily operation. 5.Part of the COI collection process has no system to support it. 6.The COIs need be within a structured system to avoid controls problems, including the control of the properties received as payment-in-kind. 7.The collaterals appraisals and environment risk assessment needs to be controlled through a system. 8.There is an opportunity to build an automatic interface by downloading the Dealer Financial Statement data to ADCP to avoid data transfer bugs and speed up the |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
50288 | Theorem Digital Reality Platform | In Production | TDRP | ISIT | SKING68 | JLYNN1 | KKISIEL | AELANGO | Bronze | Non S-Ox | 311 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Theorem Digital Reality server is used to convert industry standard CAD, JT data to FBX. The server also provides AR/VR/MR client applications for Manufacturing engineering around Ford. | 6 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
15182 | FCLA Brazil Wholesale Operations Controls (WAP) | In Production | WAP | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | Improve Systems and Controls to support Wholesale Operations in Brazil to avoid losses or frauds and to migrate mandatory controls from manual to automatic. Business Issue and / or Opportunity 1.There are many manual controls over all the steps of the Wholesale process. 2.The Wholesale charge off routine (USA GAAP) has manual adjustments to be in compliance with the Global Policy. 3.All collection activities are done manually without a system support. 4.There is no management tool to allow operational analysis over the daily operation. 5.Part of the COI collection process has no system to support it. 6.The COIs need be within a structured system to avoid controls problems, including the control of the properties received as payment-in-kind. 7.The collaterals appraisals and environment risk assessment needs to be controlled through a system. 8.There is an opportunity to build an automatic interface by downloading the Dealer Financial Statement data to ADCP to avoid data transfer bugs and speed up the |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
20934 | FCE Workflow II | In Production | FCE WF II | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RPARAME4 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | BPM application to perform task and workload management, primarily for the account servicing functions within the FCE Customer Service Centres. Based on the Lombardi Teamworks platform. |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20934 | FCE Workflow II | In Production | FCE WF II | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RPARAME4 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DTAURO | DTAURO | Ford Credit Services | Ford Credit (FMCC) | BPM application to perform task and workload management, primarily for the account servicing functions within the FCE Customer Service Centres. Based on the Lombardi Teamworks platform. |  |  | YES | 3 | SRAISIN1 | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
11147 | SPRITE V1.4 | In Production | SPRITE | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Silver | Non S-Ox | 221 | No | Yes | In-House | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | SPRITE - Safety Processing Realtime Integrated Testing Environment. SPRITE Request Manager (web) has 1 database instance. SPRITE Test Stand(Client) has 17 installations on PCs. SPRITE also include KT Test, Test Stand Control System and FARO CMM System. | 8 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
20934 | FCE Workflow II | In Production | FCE WF II | FORD CREDIT | DTAURO | SKHAN29 | MWALKE19 | RPARAME4 | Copper | Non S-Ox | 311 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | BPM application to perform task and workload management, primarily for the account servicing functions within the FCE Customer Service Centres. Based on the Lombardi Teamworks platform. |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
51091 | FCE Vehicle Configuration Service | In Production | VCS | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | 311 | Data repository that holds vehicle entity and factory fitted options data plus pricing, residual values and finance plans data. Also acts as a service to feed this data to other relevant systems within Ford Credit |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
51091 | FCE Vehicle Configuration Service | In Production | VCS | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Data repository that holds vehicle entity and factory fitted options data plus pricing, residual values and finance plans data. Also acts as a service to feed this data to other relevant systems within Ford Credit |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | SQL
14217 | SLD Website - Dearborn Safety Lab Test Data | In Production | SLD WS | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | The Safety Lab Website provides vehicle crash results. This site provides the following information: digital images, digital videos instrumentation data, film analysis plots, test reports, test log info QAT Reports, and HDF files (complete and GPP compatible). This website was developed and launched before 1999. | 5 |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
17434 | FCE Translog | In Production | TRANSLOG | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Silver | Non S-Ox | 311 | No | Yes | In-House | JBENITO | GACKROYD | Ford Credit Services | Ford Credit (FMCC) | The application provides a standard interface to distribute customer and dealer data to external print provider Deutsche Post for letter printing, DAD for Title Document management and FCE Documentum to archive images. It manages the communication process with the external parties and provides status information for reconciliation purposes. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
22394 | FCE Svenson Suite (Austria) | In Production | Svenson | FORD CREDIT | RMINHAS3 | PSRIKIR1 | RMRINAL2 | NKALE | Silver | Non S-Ox | 321 | No | Yes | COTS | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | Software package for administration and registration/reporting of the required data (statistic bank data) due to the Austria Banking Act which clearly specify the laws for banking business in Austria. One part of this law is the regular reporting of statistic data to the Austian Central Bank. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q3 2027 | On-Prem | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | SQL
53224 | SA Credit Limit app | In Production | SACIM | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NMORALE7 | Gold | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | South America application to whosale financing control | 3 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20978 | FCE Scriptura | In Production | FCE Script | FORD CREDIT | JBENITO | MLOPEZ31 | MSIMON12 | AGALLAG9 | Silver | Non S-Ox | 321 | No | Yes | COTS | JBENITO | MLOPEZ31 | Ford Credit Services | Ford Credit (FMCC) | This component is the printing solution for the BLESS Suite applications (BLESS CAPS, BLESS Receivables, BLESS Wholesale & BLESS WTF) |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q3 2027 | Modernize to Cloud Databases | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | SQL
24524 | Quick Lane Canada Dealer Applications Website | In Production | FOCQL | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Ford Customer Service | Marketing, Sales and Service | Dealer Facing Quick Lane co-op automation tool to help manage and track co-op payments related to Quick Lane Sales and Marketing. | 4 |  | YES | 3 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20143 | FCE Scope | In Production | FCE Scope | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 321 | No | Yes | COTS | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Data repository for monthly extracts from FFE originations and receivables systems, prior to transmission to SAS for reporting and statistical analysis. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
19519 | Quality Center ALM | In Production | QC ALM | FORD CREDIT | JMALETZ | SHE1 | KBALAS30 | SGURU8 | Bronze | Non S-Ox | 111 | No | Yes | COTS | JMALETZ | NVENKAT2 | Enterprise Technology | - | Micro Focus ALM/Quality Center is a comprehensive, unified, flexible and extensible application lifecycle management product. It provides the teams with visibility across all enterprise projects and the complete application lifecycle. It establishes consistent, repeatable processes for managing requirements, tests, and business components, effectively increasing speed, improving quality and reducing cost. | 5 |  | YES | 2 | SRAISIN1 | PLM | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
9835 | PENTA - Pan European National Type Approval | In Production | PENTA | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 212 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | PENTA is mainly a batch application for pre-registration of vehicles (i.e. providing governments/government agencies whatever is needed to be able to register the vehicle in the given market). Where governments provide registration details (mainly first registration date) PENTA is able to captures these and pass them on to downstream applications like MPS, VISTA. PENTA also has an internal facing web application, used by internal users to monitor/intervene in the results of the batch processes. It supports 16 EU markets. | 2 |  | YES | 3 | NKANDULA | PLM | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
15824 | FCE SalesPartner | In Production | sp | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | IPANKAJ | Ford Credit Services | Ford Credit (FMCC) | Credit Application Entry application. Used by dealers. Currently SalesPartner application is only active for UK market |  |  | YES | 3 | SRAISIN1 | PLM | Oracle | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Oracle
22734 | OnTrack MIS | In Production | OnTrack | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Silver | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Engineering | Industrial System IT | The OnTrack MIS is the next generation of Production monitoring and downtime tracking for all Ford Stamping Plants. The application is COTS and includes interfaces to several other applications (Marquee Manager, First Page, MFM, PCON, JEDI and CMMS). In addtion to prduction monitoring, On Track MIS provides live inventory updates, schedule execution, direct labor metrics, and Die-change planning and execution, Scrap/Reject entry, tracking and reporting. Primary focus is on the part being produced. | 15 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
15824 | FCE SalesPartner | In Production | sp | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Credit Application Entry application. Used by dealers. Currently SalesPartner application is only active for UK market |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
51104 | FCE Risk Service | In Production | FCE-RISK | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 321 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Set of microservices to handle risk score evaluation for marketplace, store risk data, integrate with PCO and share exposure value and evaluation result to marketplace underwriting system |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
11503 | OHSIM | In Production | OHSIM | OCETO | TSWEEN16 | SCHILAKA | WPETER58 | MBALAN2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DDESAI | SCHILAKA | Human Resources | Staffs IT | Occupational Health and Safety Information Management: Plant based application which tracks safety incidents (IIM), Electronic Medical Records (EMR), Medical Scheduling (MSM) and data analysis (DAM).GERT and Safety Pyramid modules are also integrated into OHSIM. OHSIM is an integrated web-based information management system. It is comprised of related tools designed to optimize resources for the protection and promotion of employee health and safety through the effective management of risks. | 16 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
51104 | FCE Risk Service | In Production | FCE-RISK | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 321 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Set of microservices to handle risk score evaluation for marketplace, store risk data, integrate with PCO and share exposure value and evaluation result to marketplace underwriting system |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q3 2025 | Version Upgrade | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
23477 | FCE Retail Deposits - Core Capability | In Production | FCERD Core | FORD CREDIT | JBENITO | JCOCKWIL | CWILL663 | AGALLAG9 | Bronze | S-Ox In Scope | 332 | No | Yes | Managed by 3rd Party Purchased Service | JBENITO | PLABROSS | Ford Credit Services | Ford Credit (FMCC) | This application supports the FCE required process to deliver the Retail Deposits Business capability to both the FCE UK Market and FBG DE market. The operational processing is all performed by an outsource partner (NSSSL for UK, FIS for FBG), who send us a daily overnight feed of information. This information (for both markets: UK & DE), is updated within an FCE owned database for processing and then management reporting and transmission of data to other FCE and FMC systems. | 176 |  | YES | 2 | SRAISIN1 | PLM | WebFocus | Q2 2025 | Migrate to QlikSense | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | DA
13821 | Occupational Health Manager | In Production | OHM | OCETO | TSWEEN16 | SCHILAKA | WPETER58 | MBALAN2 | Copper | Non S-Ox | 311 | No | Yes | COTS | DDESAI | SCHILAKA | Human Resources | Staffs IT | This application software supports audiometric testing, evaluation, calculations, and reporting for all Ford sites in Canada, US and Mexico, with interfaces to legacy applications(internal and external). 2/3/05- changed app name from HEARTRAC2 to OHM and placed IN PRODUCTION (vs IN DEVELOPMENT). | 10 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
50758 | FCE Residual Value Setting Tool | In Production | RVST | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | 311 | This setting tool is used to aid facilitate the business setting Residual Values against defined vehicle configurations mileage bands and Optional Final Payments. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | Java < v21
50758 | FCE Residual Value Setting Tool | In Production | RVST | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | This setting tool is used to aid facilitate the business setting Residual Values against defined vehicle configurations mileage bands and Optional Final Payments. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
50490 | New Global Integrator | In Production | GI/TI | ISIT | SBONNICI | KRAMMOHA | MJESKA | JLUCAS1 | Silver | Non S-Ox | 322 | No | Yes | Managed by 3rd Party Purchased Service | SBONNICI | SBONNICI | PD Operations and Quality | Industrial System IT | New Global Integrator is a common global tool that encompasses and replaces the functionality of two existing applications: GI (Global Integrator) and TI (Technology Integrator). GI perspective: The New Integrator will be used by Vehicle Programs, Powertrain and Functions to track and maintain deliverables status, in support of the GPDS (Global Product Development System) process. TI perspective: The New Integrator will be used by Research & Advanced Engineering teams to track and maintain deliverable status, in support of four processes: (1) Discovery QOS (Quality Operating System), (2) Product GTDS (Global Technology Development System) QOS, (3) Process GTDS QOS, and (4) Corporate Support. In both GI and TI, teams update timing, assessments and attach supporting documents/evidence to relevant deliverables. | 27 |  | YES | 3 | BWUNNAVA | PLM | VM | Q2 2026 | Complete Migration to SaaS | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
50582 | FCE Renewals | In Production | FCERN | FORD CREDIT | JBENITO | JCOCKWIL | CWILL663 | AGALLAG9 | Bronze | Non S-Ox | 332 | No | Yes | In-House | JBENITO | PLABROSS | Ford Credit Services | Ford Credit (FMCC) | The FCE Renewals platform is used to collate, validate and transform Core FCE data in order for it to be processed by parallel capability to generate Renewals Leads. This platform then collects the leads generated and provides them to various downstream systems. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
51089 | MS&S - RPA | In Production | MSSRPA | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | RSUBRA17 | SDHANAS2 | Copper | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | RKENNEL | Ford Customer Service | Marketing, Sales and Service | MS&S RPA Projects based on Pega & Chatbot | 3 |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
50582 | FCE Renewals | In Production | FCERN | FORD CREDIT | JBENITO | JCOCKWIL | CWILL663 | AGALLAG9 | Bronze | Non S-Ox | 332 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | The FCE Renewals platform is used to collate, validate and transform Core FCE data in order for it to be processed by parallel capability to generate Renewals Leads. This platform then collects the leads generated and provides them to various downstream systems. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
21767 | FCE RegPro | In Production | RegPro | FORD CREDIT | RMINHAS3 | PSRIKIR1 | RMRINAL2 | NKALE | Silver | Non S-Ox | 332 | No | Yes | COTS | RMINHAS3 | RMINHAS3 | Ford Credit Services | Ford Credit (FMCC) | Regulatory reporting application for European markets (UK, Portugal, Spain, Germany, & France). Third party application (RegPro) provided by Wolters Kluwer Financial Services. Receives periodic feeds (manual and automatic) from FCE LOB systems and users which produces reports in mandated format for transmission to the Financial Regulator in each market. |  |  | YES | 2 | SRAISIN1 | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
18584 | Manufacturing eXecution Advanced Planning and Sche | In Production | MX_APS | ISIT | SKING68 | JLYNN1 | GKESAVAR | AELANGO | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Provides up-front capacity planning and sourcing for new model programs for press subassemblies, racks, direct and indirect labour. This application is now global since 18 August 2015. | 5 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
51211 | FCE Proposal Service | In Production | FCE-PROP | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | 322 | Set of microservices to handle proposal data management for marketplace, validate customer input, enrich customer IP & Dealer data, manage proposal state and send state update notification to marketplace orchestrator |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q3 2025 | Version Upgrade | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
51211 | FCE Proposal Service | In Production | FCE-PROP | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Set of microservices to handle proposal data management for marketplace, validate customer input, enrich customer IP & Dealer data, manage proposal state and send state update notification to marketplace orchestrator |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
22565 | LoadRunner Global | Active | LR | EA | RRISS | THALL6 | JSAJID | PSHAH | Copper | Non S-Ox | - | No | Yes | - | RRISS | MPREETH2 | Enterprise Technology | - | LoadRunner is a performance and load testing product for examining system behavior and performance, while generating actual load. LoadRunner can emulate thousands of users to put the application through the rigors of real-life user loads, while collecting information from key infrastructure components. The results can be analysed in detail, to explore the reasons for particular behavior. | 22 |  | YES | 1 | GBRAIL | PLM | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
20933 | FCE Pinnacle Account Servicing - Mainframe | In Production | FCE PinASV | FORD CREDIT | NJOSHI21 | HBRUMLEV | VCECCARE | ROBRIEN3 | Silver | Non S-Ox | 311 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | Mainframe DB2 database, interfaces and batch for the FCE Pinnacle Account Servicing application (20932). |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20932 | FCE Pinnacle Account Servicing | In Production | FCE PinASV | FORD CREDIT | NJOSHI21 | HBRUMLEV | VCECCARE | ROBRIEN3 | Silver | Non S-Ox | 233 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | Primary account servicing applicaton for the FCE Customer Service Centres. Interfaces with Fidelity LA Receivables, LPS Originations, ZV Clearing, Translog, Debt Manager, DISNE and Workflow II to provide user with customer, account and dealer information and facilitate submission of transactions to the above internal systems and external vendors. Also provides the database of record for all customer interactions (contacts) throughout the lifecycle of an acccount. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20932 | FCE Pinnacle Account Servicing | In Production | FCE PinASV | FORD CREDIT | NJOSHI21 | HBRUMLEV | VCECCARE | ROBRIEN3 | Silver | Non S-Ox | 233 | No | Yes | In-House | NJOSHI21 | HBRUMLEV | Ford Credit Services | Ford Credit (FMCC) | Primary account servicing applicaton for the FCE Customer Service Centres. Interfaces with Fidelity LA Receivables, LPS Originations, ZV Clearing, Translog, Debt Manager, DISNE and Workflow II to provide user with customer, account and dealer information and facilitate submission of transactions to the above internal systems and external vendors. Also provides the database of record for all customer interactions (contacts) throughout the lifecycle of an acccount. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
15780 | FCE Operational Reporting System | In Production | OPRPTSYS | FORD CREDIT | JBENITO | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 322 | No | Yes | In-House | JBENITO | CMUELLEN | Finance | Ford Credit (FMCC) | Cross Application Reporting - Provides data out of Retail Finance & Lease, Wholesale and Current Account for operational and legal reporting requirements which could not be satisfied within MIS |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
19660 | FCE Operational Reporting Online | In Production | FCEOpRptng | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Silver | Non S-Ox | 211 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Web application to Operational Reporting System provides various predefined ad hoc reports for FFG sales support. Also known as SARES (SAles REporting System). |  |  | YES | 2 | SRAISIN1 | PLM | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
19660 | FCE Operational Reporting Online | In Production | FCEOpRptng | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Silver | Non S-Ox | 211 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Web application to Operational Reporting System provides various predefined ad hoc reports for FFG sales support. Also known as SARES (SAles REporting System). |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
53259 | FCE On Line Document Enterprise Repository | In Production | FOLDER | FORD CREDIT | JBENITO | MLOPEZ31 | MSIMON12 | AGALLAG9 | Silver | Non S-Ox | 322 | No | Yes | In-House | JBENITO | MLOPEZ31 | Ford Credit Services | 322 | Document Sharing Tool (mostly for documents from FC to dealers and vice versa) where documents are transient. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
53259 | FCE On Line Document Enterprise Repository | In Production | FOLDER | FORD CREDIT | JBENITO | MLOPEZ31 | MSIMON12 | AGALLAG9 | Silver | Non S-Ox | 322 | No | Yes | In-House | JBENITO | MLOPEZ31 | Ford Credit Services | Ford Credit (FMCC) | Document Sharing Tool (mostly for documents from FC to dealers and vice versa) where documents are transient. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | Cloud SQL PostgreSQL | [6 empty] | SQL
52817 | InnovMetric Dataloop in PD | In Production | IDiPD | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Bronze | Non S-Ox | 311 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | InnovMetric DataLoop is a scalable data management solution that allows you to optimally handle the vast amount of data produced by your 3D measurement activities by storing your inspection projects, their revisions, and 3D measurement data in a centralized database | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
23150 | FCE Multi Risk Insurance | In Production | FCE MRI | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Copper | Non S-Ox | 321 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | The application supports the Ford Bank Germany Insurance Department managing a multi purpose insurance product for the dealers (offered by insurance provider Helvetia). |  |  | YES | 3 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
10012 | HVBOM: Historical Vehicle Bill of Material | In Production | HVBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 122 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | The HVBOM web-based system is a tool that will be used by Ford dealership service and parts personnel to view a vehicle bill of material by VIN in order to identify correct service part numbers. Secondary outage impact is 'Impact to Productivity'. | 7 |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
23150 | FCE Multi Risk Insurance | In Production | FCE MRI | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Copper | Non S-Ox | 321 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | The application supports the Ford Bank Germany Insurance Department managing a multi purpose insurance product for the dealers (offered by insurance provider Helvetia). |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
15407 | FCE Major Daily Rental Operations (MDRO) | In Production | FCE MDRO | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Fleet Financing for Major Daily Rentals |  |  | YES | 3 | SRAISIN1 | PLM | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
15407 | FCE Major Daily Rental Operations (MDRO) | In Production | FCE MDRO | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Fleet Financing for Major Daily Rentals |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | Q4 2025 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
15407 | FCE Major Daily Rental Operations (MDRO) | In Production | FCE MDRO | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Fleet Financing for Major Daily Rentals |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
15802 | FCE Mainframe Proposal Processing | In Production | FCE MPP | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 212 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Mainframe Proposal Processing (MPP) application in Germany is to provide Ford Bank Aktuel dealers (Germany) with automatic credit acceptance validation. MPP processes new proposals, resent proposals and enquiries from a source system . The source system send data and initiate a transaction which will perform basic data validation to determine the data can be rejected / accepted. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
15449 | FCE Loan Processing System | In Production | FCE LPS | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | S-Ox In Scope | 332 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Loan Processing System is loan origination system to access the customer proposals and to decide to purchase or reject |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | Q4 2025 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
15449 | FCE Loan Processing System | In Production | FCE LPS | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | S-Ox In Scope | 332 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Loan Processing System is loan origination system to access the customer proposals and to decide to purchase or reject |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
15665 | FCE Lending Automotive | In Production | LA UKDEU | FORD CREDIT | IPANKAJ | RRAJESH8 | TNARAYA2 | NVARADA2 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Retail Receivables for UK (Finance) and Germany (Finance and Lease) |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50594 | FCE Italy Local Applications | In Production | FCEITALA | FORD CREDIT | JBENITO | SHODGSO9 | VFERRARO | AGALLAG9 | Gold | Non S-Ox | 332 | Yes | No | In-House | JBENITO | SHODGSO9 | Ford Credit Services | - | The following MS Access DB have been migrated onto a Web Based solution hosted in US in DCoF. FCEClient/FCELocalApp.import/CASH/GEIS/IFK/BOI(Finco)/CSCUtenti/CFSUtenti/DocFIliali/Lettere/DB Dealer/ControlloGrandiRischi/Ordini di Acquisto FCE/IVASS/FollowUpIF/IdeaFord/ManutFrog/OperationReport/LogDlrService/SitGiorn/AUI-BRIDGE/ImmFOI/INBIX/JIF/API CSCUtenti/SSIS/Master DB su SQL/ScorMarketing Francia/FCELocalApp.import_France/ScorMarketing Italia/Ordini di Acquisto FOI/Credit Bureau/FCELocalApp.import_Spain |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q1 2026 | On-Prem | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | SQL
17702 | GPA - Manufacturing FPS Action Plan Management | In Production | GPA | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Silver | Non S-Ox | 111 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Staffs | - | FPS measurable Toll. The system manages the improvement opportunities identified in the work groups (GNTs). Global system which supports Manufacturing plants in all regions : SA, NA, Europe and APA. | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
53773 | FCE German Tax Reporting | In Production | FCEDETAX | FORD CREDIT | JMALETZ | CMUELLEN | GSEIPELT | AGALLAG9 | Copper | Non S-Ox | 321 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 321 | APPLICATION TO PROVIDE LEGALLY REQUIRED TAX REPORTING TO GERMAN AUTHORITIES |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
18203 | FCE GDPdU Tax Archive | In Production | GDPDUTAX | FORD CREDIT | JBENITO | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 211 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | 211 | Infrastructure to archive tax relevant data for tax audits (Legal requirement) |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
18203 | FCE GDPdU Tax Archive | In Production | GDPDUTAX | FORD CREDIT | JBENITO | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 211 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Infrastructure to archive tax relevant data for tax audits (Legal requirement) |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
51018 | FCE Ford Credit Originations Back Office Services | In Production | FOBOS | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 332 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | 332 | Ford credit Originations Back Office Services (FOBOS) for underwriting, pre-purchase checks and purchase of credit proposals |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
51018 | FCE Ford Credit Originations Back Office Services | In Production | FOBOS | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 332 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Ford credit Originations Back Office Services (FOBOS) for underwriting, pre-purchase checks and purchase of credit proposals |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
14716 | FST-RA: Reporting - Analytical | In Production | FST-Report | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The FST Application supports implementation of critical accounting and financial processes, and the traceability of financial data. For high precision financial reporting and control, FST will implement a Corporate Information Factory (CIF) model, and all supporting projects must adhere to CIF architectural standards. The new FST application will optimise transaction processing performance and analytic reporting, making it easier to respond to business changes. | 6 |  | YES | 4 | TSWEEN16 | PLM | VM | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
20051 | FCE European Liquidity Monitoring-ELM | In Production | FCEELM | FORD CREDIT | IPANKAJ | PSRIKIR1 | RMRINAL2 | NKALE | Bronze | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Daily liquidity reporting in line with requirement from the UK Financial Services Authority (FSA). Utilising daily input from key receivables, accounting & treasury applications and manual input from all FFE locations | 811 |  | YES | 1 | SRAISIN1 | PLM | WebFocus | Q4 2024 | Decommission | Decommission | 2024-11-15 | 2024-11-15 | 2024-11-15 | Complete | Blue | 2024-11-30 | 2024-11-30 | Complete | [15 empty] | Do not recognize this as a WebFOCUS app, not in my tracker. (KW 3-14-25) |  | DA
19659 | FCE eBLESS CAPS | In Production | FFEeCAPS | FORD CREDIT | MLOPEZ31 | MVILLASE | ACUESTA | AGALLAG9 | Silver | Non S-Ox | 332 | No | Yes | In-House | MLOPEZ31 | MVILLASE | Ford Credit Services | Ford Credit (FMCC) | e-enabled presentation layer of CAPS Origination System |  |  | YES | 2 | SRAISIN1 | PLM | Java Struts | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
19659 | FCE eBLESS CAPS | In Production | FFEeCAPS | FORD CREDIT | MLOPEZ31 | MVILLASE | ACUESTA | AGALLAG9 | Silver | Non S-Ox | 332 | No | Yes | In-House | MLOPEZ31 | MVILLASE | Ford Credit Services | Ford Credit (FMCC) | e-enabled presentation layer of CAPS Origination System |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
15433 | FCE Debt Manager | In Production | FCEDEBTMGR | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | Non S-Ox | 212 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Collections, Bankruptcies & Charge-Offs - Ford Financial Europe |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
15782 | FCE Dealer Database | In Production | DLRDBASEAD | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Silver | Non S-Ox | 312 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Master Dealer Database for FFG. This application manages all information around FFG Dealers centrally. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | Q2 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
24765 | FCE Contextual Help Guide Tool | In Production | COHETO | FORD CREDIT | JBENITO | MLOPEZ31 | MSIMON12 | AGALLAG9 | Copper | Non S-Ox | 111 | No | Yes | In-House | JBENITO | MLOPEZ31 | Ford Credit Services | Ford Credit (FMCC) | Application (web-based) for storing software documentation training guide and linked with the BLESS/Suite applications for show contextual help to application customers |  |  | YES | 1 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
24765 | FCE Contextual Help Guide Tool | In Production | COHETO | FORD CREDIT | JBENITO | MLOPEZ31 | MSIMON12 | AGALLAG9 | Copper | Non S-Ox | 111 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Application (web-based) for storing software documentation training guide and linked with the BLESS/Suite applications for show contextual help to application customers |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
22032 | FCE Commission Payment Tool | In Production | CPT | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Bronze | Non S-Ox | 321 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | For the new pan-European Motor Insurance provider Allianz, Ford Credit Germany has to set up intermediary contracts with the dealer and pay commission to these dealers. The Commission Payment Tool will be used to set up intermediary details for the dealer, to create sales reports and to create payment files for the dealer commission. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
14711 | FST-MPA: Manufacturing Parts Accounting | In Production | FST-MPA | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The FST Application supports implementation of critical accounting and financial processes, and the traceability of financial data. For high precision financial reporting and control, FST will implement a Corporate Information Factory (CIF) model, and all supporting projects must adhere to CIF architectural standards. The new FST application will optimise transaction processing performance and analytic reporting, making it easier to respond to business changes. | 30 |  | YES | 4 | TSWEEN16 | PLM | VM | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
22032 | FCE Commission Payment Tool | In Production | CPT | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Bronze | Non S-Ox | 321 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | For the new pan-European Motor Insurance provider Allianz, Ford Credit Germany has to set up intermediary contracts with the dealer and pay commission to these dealers. The Commission Payment Tool will be used to set up intermediary details for the dealer, to create sales reports and to create payment files for the dealer commission. |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
15452 | FCE CAS | In Production | CAS | FORD CREDIT | JBENITO | CMUELLEN | GSEIPELT | AGALLAG9 | Silver | Non S-Ox | 311 | No | Yes | In-House | JBENITO | GACKROYD | Ford Credit Services | Ford Credit (FMCC) | Reporting system for UK retail receivables. The system holds a daily snapshot of selected data from LA and LPS to generate automated internal reports and provides predefined ad-hoc queries to users in Accounting and Marketing/Sales. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
54409 | FCE Business Ecommerce Eco System | In Production | FCE-BEES | FORD CREDIT | JBENITO | JCOCKWIL | JGOLDST4 | AGALLAG9 | Gold | Non S-Ox | 323 | No | Yes | In-House | JBENITO | JCOCKWIL | Ford Credit Services | Ford Credit (FMCC) | FCE InDealership and Customer Ecommerce platform. This will be used by Dealers & Customers across all 5 European Markets, in order to propose Finance Applications to FCE. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
15652 | FST-MCA: Material Cost Analysis | In Production | FST-MCA | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 232 | No | Yes | In-House |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | MCA is used to standardize business practices using a common tool set. In MCA, common practices will include: modeling of all relevant base vehicles and options along with unique options costs which will be available by base vehicle, by market. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
54409 | FCE Business Ecommerce Eco System | In Production | FCE-BEES | FORD CREDIT | JBENITO | JCOCKWIL | JGOLDST4 | AGALLAG9 | Gold | Non S-Ox | 323 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | FCE InDealership and Customer Ecommerce platform. This will be used by Dealers & Customers across all 5 European Markets, in order to propose Finance Applications to FCE. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
15418 | FCE BOSS II (M/F Menu System Only) | In Production | BOSSII | FORD CREDIT | JBENITO | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 312 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Boss II provides a toolset for user administation to other mainframe applications - menu structure - user table maintenance - event table maintenance - authorisation features Boss II does not perform any financial transaction |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
21107 | FCE BLESS/WAV | In Production | BLESS/WAV | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Bronze | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Wholesale Assests Verification module within the BLESS/Suite. Mainframe, WEB and Mobile access. |  |  | YES | 2 | SRAISIN1 | PLM | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
21107 | FCE BLESS/WAV | In Production | BLESS/WAV | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Bronze | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Wholesale Assests Verification module within the BLESS/Suite. Mainframe, WEB and Mobile access. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
19153 | FCE BLESS WWTF | In Production | BLESSWTF | FORD CREDIT | JBENITO | MLOPEZ31 | MSIMON12 | AGALLAG9 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 332 | MANAGE THE RECEIVABLES PORTFOLIO WHICH SUPPORT WORLD TRADE FINANCE BUSINESS |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
15414 | FCE Bless Rec | In Production | BLESSREC | FORD CREDIT | MLOPEZ31 | MVILLASE | SCASCO1 | AGALLAG9 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | MLOPEZ31 | MVILLASE | Ford Credit Services | 332 | FCE BLESS Rec is a receivable system which permit finance (retail & leasing) vehicles to Ford Credit for private customers and companies. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
15414 | FCE Bless Rec | In Production | BLESSREC | FORD CREDIT | MLOPEZ31 | MVILLASE | SCASCO1 | AGALLAG9 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | MLOPEZ31 | MVILLASE | Ford Credit Services | Ford Credit (FMCC) | FCE BLESS Rec is a receivable system which permit finance (retail & leasing) vehicles to Ford Credit for private customers and companies. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [10 empty] | Cloud SQL PostgreSQL | [6 empty] | SQL
19935 | FST-MCA 4.0: Forward Model | In Production | FST MCA FM | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 232 | No | Yes | In-House |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | Material Cost Analysis tool supporting Forward Model Cost Analysis | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
24229 | FCE AnaCredit | In Production | AnaCredit | FORD CREDIT | RMINHAS3 | PSRIKIR1 | RMRINAL2 | NKALE | Silver | Non S-Ox | 332 | No | Yes | COTS | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | The aim of this application is to enable the work of the Single Supervisory Mechanism (SSM) by facilitating the work of the European System of Central Banks (ESCB) with respect to a centralized database of credit exposures on a loan-by-loan basis across the Eurozone. The application addressing this requirement is the AnaCredit reporting software solution provided by Wolters Kluwer (WK). This solution uses many of the same funxtionality of RegPro such as data Foundation and Report Generator, plus the TNG or web component for the WK regulatory reporting solutions. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q3 2027 | On-Prem | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | SQL
14713 | FST-FVA: Finished Vehicle Accounting | In Production | FST-FVA | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | S-Ox In Scope | 232 | No | Yes | In-House |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | Synchronize, aggregate, align and record all vehicle financial events in order to align Ford book of accounts and the external finance community relative to financial analysis and reporting data. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
22573 | FCE Account Manager | In Production | FCE-AM | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 331 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | 331 | Provides customer account self-servicing functionality for Ford Credit Europe customers. Application is currently available in UK, DE, ES, IT, FR & MX markets. |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
22573 | FCE Account Manager | In Production | FCE-AM | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 331 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Provides customer account self-servicing functionality for Ford Credit Europe customers. Application is currently available in UK, DE, ES, IT, FR & MX markets. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
22573 | FCE Account Manager | In Production | FCE-AM | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 331 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Provides customer account self-servicing functionality for Ford Credit Europe customers. Application is currently available in UK, DE, ES, IT, FR & MX markets. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
52013 | Ford Online Store | In Production | FOS | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 311 | No | Yes | Managed by 3rd Party Purchased Service | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | Application to enable customers to buy a vehicle via web, by cash or through a credit application | 9 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [14 empty] | No | VM
50927 | FC Integration Abstraction Layer | In Production | FC-IAL | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | 322 | Integration abstraction layer for Ford Credit applications, exposed as API |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q3 2025 | Version Upgrade | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
50927 | FC Integration Abstraction Layer | In Production | FC-IAL | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Integration abstraction layer for Ford Credit applications, exposed as API |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
24924 | Ford Agile Simulation Tool | In Development | FASTER | ISIT | OTHERS | FSMITH22 | MWINDELE | AELANGO | Copper | Non S-Ox | 111 | Yes | No | - | LTURNER3 | FSMITH22 | Manufacturing Staffs | - | FASTER is a user interface designed to simplify the process of building Power Train Assembly & Machining line models within the Witness software application. The tool allows selection of Ford proprietary modules representing the various pieces of production equipment within Bill of Process manufacturing lines. The user is presented with the relevant input fields in familiar terminology to capture the required simulation input data. FASTER then builds these elements and input data into the Witness software and applies logic to model the desired part flow. Overall, this tool allows manufacturing engineers to rapidly build accurate models of manufacturing facilities for data driven assessment of manufacturing feasibility and comparison of various strategies. | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
16179 | FOM Onbase | In Production | FOMONBASE | M&S TECH | RAHMED33 | GDIAZ1 | EDURAN10 | LWU14 | Bronze | Non S-Ox | 312 | No | Yes | COTS | KBERCH | GDIAZ1 | Finance | - | Software from Simmpapel supplier designed to digitize hard copy online electronic information and preserve it for consulting purposes. Also provide a solution to the dealers with accurate documentation, on time in daily basis to support the dealers accounting re-conciliations and provision. To track dealers transactions for a better cash flow control. Support 18 month of fiscal documentations for the dealers. Provide in daily basis dealers statements of: Vehicles in pesos and dollars, parts and accessories statements, incentive statements Support Ford and Lincoln. Reduce the administration processes, telephone calls and the times that the dealer representatives have to come to get and send fiscal documentation. Expected reduction on telephone calls between dealers and Ford Database will allow Dealers to retrieve information by queries in order to get specific data (range of dates, specific vehicle line, specific document numbers, etc.)Dealers will be allowed to storage fiscal documentation digitally. | 13 |  | YES | 2 | NKANDULA | PLM | VM | Q2 2026 | Complete Migration to SaaS | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
15989 | FC GLOBAL WHOLESALE | In Production | BLESSEWHOL | FORD CREDIT | MLOPEZ31 | OLOPEZ7 | PGUILLEN | AGALLAG9 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | MLOPEZ31 | OLOPEZ7 | Ford Credit Services | Ford Credit (FMCC) | Dealer and back-office application to operate the wholesale finance portfolio for FCE / IMG / China. It includes the former entry 15416 FCE BLESS Wholesale. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | SQL
13547 | FOCUS FCLA FEXCO System | In Production | FEXCO | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | FEXCO is a FCLA-developed system that serves to manage the retail contract in loss recovery transferred to external agencies and attorneys by establishing controls regarding the assigned portfolio | 7 |  | YES | 3 | TSWEEN16 | PLM | VM | Q2 2026 | Partial Migration to GCP | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
15989 | FC GLOBAL WHOLESALE | In Production | BLESSEWHOL | FORD CREDIT | MLOPEZ31 | OLOPEZ7 | PGUILLEN | AGALLAG9 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | MLOPEZ31 | OLOPEZ7 | Ford Credit Services | Ford Credit (FMCC) | Dealer and back-office application to operate the wholesale finance portfolio for FCE / IMG / China. It includes the former entry 15416 FCE BLESS Wholesale. |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
53543 | FC Foundational Systems | In Development | FCFS | FORD CREDIT | IPANKAJ | VNAVEEN1 | VRUKMANG | ROBRIEN3 | Gold | Non S-Ox | 211 | No | Yes | In-House | IPANKAJ | VNAVEEN1 | Ford Credit Services | Ford Credit (FMCC) | Suite of APIs to introduce new foundational capabilities and enhance existing capabilities in Ford Credit |  |  | YES | 1 | SRAISIN1 | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
53543 | FC Foundational Systems | In Development | FCFS | FORD CREDIT | IPANKAJ | VNAVEEN1 | VRUKMANG | ROBRIEN3 | Gold | Non S-Ox | 211 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Suite of APIs to introduce new foundational capabilities and enhance existing capabilities in Ford Credit |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
53542 | FC Enablement Systems | In Production | FCES | FORD CREDIT | IPANKAJ | VNAVEEN1 | VRUKMANG | ROBRIEN3 | Silver | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | VNAVEEN1 | Ford Credit Services | Ford Credit (FMCC) | Suite of APIs developed to support Ford Credit Enabling API product. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
15421 | FOCUS FCLA FACT SYSTEM | In Production | FACT | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | RMANGAL | Bronze | Non S-Ox | 222 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Ford Credit (FMCC) | Internal Web Application responsible for generating wholesale accounting transacionts and manage their transacions, interfacing with Wholesale Application and SAP-Shana | 3 |  | YES | 3 | TSWEEN16 | PLM | VM | Q2 2026 | Partial Migration to GCP | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53542 | FC Enablement Systems | In Production | FCES | FORD CREDIT | IPANKAJ | VNAVEEN1 | VRUKMANG | ROBRIEN3 | Silver | Non S-Ox | 221 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Suite of APIs developed to support Ford Credit Enabling API product. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
22391 | FC Atlas | In Production | FC Atlas | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | Non S-Ox | 311 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | FC Atlas is a new web-based application to house dealer/commercial entities for Ford Credit China. This system is the single source of dealer data, streamlining interfaces to this platform. Information entered in this system will be based on the business relationship between the FMCC business operations and the dealers. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
22391 | FC Atlas | In Production | FC Atlas | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | Non S-Ox | 311 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | FC Atlas is a new web-based application to house dealer/commercial entities for Ford Credit China. This system is the single source of dealer data, streamlining interfaces to this platform. Information entered in this system will be based on the business relationship between the FMCC business operations and the dealers. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
9956 | FAO-Industry: FAO - Industry | In Production | FAO | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Copper | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The FAO Industry system generates monthly reports for all the cars and trucks sold in the North American market. This data is used for the market analysis of the automobile industry. It has both On-line and Batch components. | 1 |  | YES | 2 | NKANDULA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
9956 | FAO-Industry: FAO - Industry | In Production | FAO | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Copper | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The FAO Industry system generates monthly reports for all the cars and trucks sold in the North American market. This data is used for the market analysis of the automobile industry. It has both On-line and Batch components. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q1 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Mainframe
13829 | FAME: Forecasted & Available Machinery & Equipment | In Production | FAME | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Support Ford Asset Disposal Process, as described in the Finance Mannual. |  |  | YES | 1 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
51638 | FAFC Pinnacle Table Maintenance Application | In Production | fafctma | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 322 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | FAFCTMA is an application that business will use to view and update business tables. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
51638 | FAFC Pinnacle Table Maintenance Application | In Production | fafctma | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 322 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | FAFCTMA is an application that business will use to view and update business tables. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
52129 | FAFC Dealer Connection | In Production | FDConnect | FORD CREDIT | JCHEN11 | CYANG63 | YSUN74 | YZHU86 | Silver | Non S-Ox | 11 | No | Yes | - | JCHEN11 | CYANG63 | Ford Credit Services | - | A website worked as entries for financing and leasing applicationed used by China dealer and customer |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned | [17 empty] | Java < v21
51612 | FAFC Customer Preference Center | In Production | FAFCCPC | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 333 | No | Yes | In-House | JCHEN11 | CXUE7 | Ford Credit Services | Ford Credit (FMCC) | FAFC Customer Preference Center is an application used for China to update customer demographic details like Address, Phone and Email information. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
51612 | FAFC Customer Preference Center | In Production | FAFCCPC | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 333 | No | Yes | In-House | JCHEN11 | CXUE7 | Ford Credit Services | Ford Credit (FMCC) | FAFC Customer Preference Center is an application used for China to update customer demographic details like Address, Phone and Email information. |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
53373 | FMCC Google Cloud Analytics Platform | In Production | FMCC GCAP | FORD CREDIT | RMINHAS3 | SSINGH14 | SASIF | VBHUPATH | Bronze | Non S-Ox | 322 | No | Yes | - | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | Ford Credit Google Cloud Analytics | 3 |  | YES | 1 | SRAISIN1 | PLM | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
56919 | FAFC Communication Messaging System | Planned | FAFCCMS | FORD CREDIT | JCHEN11 | CYANG63 | YFU33 | YZHU86 | Silver | Non S-Ox | 321 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | FAFC Communication Messaging System - China provides the technical resources for triggering messaging notifications to Ford Credit customers. |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | Q1 2026 | Version Upgrade | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
56413 | FAFC China Collection System | In Production | CNGCS | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 312 | No | Yes | - | JCHEN11 | CXUE7 | Ford Credit Services | Ford Credit (FMCC) | China collection system |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
50973 | FAFC Anti Money and Fraud services | In Production | FAFCAMLAF | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | Non S-Ox | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | 332 | FAFC Anti Money Laundering service helps to screen new and existing customers in Ford Credit Originations and Account servicing processes. New and existing customers will be screened against Sanction, PEP and high country risk lists. Data from Accuity Vendor will be pulled using SFTP and loaded into DB. FAFC Anti-Fraud service helps to validate customers submitted by dealer against BaiHang Interface during Ford Credit Originations processes. This service consumes a BaiHang service to retrieve the special attention lists of a customer which will be stored in GLO. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
50973 | FAFC Anti Money and Fraud services | In Production | FAFCAMLAF | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | Non S-Ox | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | FAFC Anti Money Laundering service helps to screen new and existing customers in Ford Credit Originations and Account servicing processes. New and existing customers will be screened against Sanction, PEP and high country risk lists. Data from Accuity Vendor will be pulled using SFTP and loaded into DB. FAFC Anti-Fraud service helps to validate customers submitted by dealer against BaiHang Interface during Ford Credit Originations processes. This service consumes a BaiHang service to retrieve the special attention lists of a customer which will be stored in GLO. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
18488 | FCLA Mexico - Internal Security | In Production | MSE | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | Provides a single point of for access administration and reporting services for locally developed applications at Ford Credit Mexico, control the Data Retention Housekeeping module and manage the Job Monitoring loading | 8 |  | YES | 1 | TSWEEN16 | PLM | VM | Q2 2026 | EDC CaaS | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
12241 | FAD SRS - FAD Sales Reporting | In Production | FSR | M&S TECH | KPINNU | KHILLERT | GAJAY | JHARPER2 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | FAD Sales Reporting - Provides info on what FAD locations are selling to dealerships/aftermkt | 53 |  | YES | 5 | NKANDULA | PLM | BO | Q1 2026 | Migrate to QlikSense | Modernize | 2026-03-31 | 2026-03-31 |  | In-Progress | Green | 2026-06-29 |  | Planned |  | No | [8 empty] | QlikSense | [5 empty] | No | DA
12241 | FAD SRS - FAD Sales Reporting | In Production | FSR | M&S TECH | KPINNU | KHILLERT | GAJAY | JHARPER2 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | FAD Sales Reporting - Provides info on what FAD locations are selling to dealerships/aftermkt |  |  | YES | 5 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12241 | FAD SRS - FAD Sales Reporting | In Production | FSR | M&S TECH | KPINNU | KHILLERT | GAJAY | JHARPER2 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | FAD Sales Reporting - Provides info on what FAD locations are selling to dealerships/aftermkt |  |  | YES | 5 | NKANDULA | PLM | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
12241 | FAD SRS - FAD Sales Reporting | In Production | FSR | M&S TECH | KPINNU | KHILLERT | GAJAY | JHARPER2 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | FAD Sales Reporting - Provides info on what FAD locations are selling to dealerships/aftermkt |  |  | YES | 5 | NKANDULA | PLM | Mainframe | Q4 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
12241 | FAD SRS - FAD Sales Reporting | In Production | FSR | M&S TECH | KPINNU | KHILLERT | GAJAY | JHARPER2 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | FAD Sales Reporting - Provides info on what FAD locations are selling to dealerships/aftermkt |  |  | YES | 5 | NKANDULA | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
16115 | FCLA Mexico - Gerencia Staff | In Production | MGS | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | The main function is to generate wholesale reports using Mexico Local Applications information. Manage dealers general information for the Mexico local Applications. Allow Wholesale Operation to generate wholesale reports/files, and also allow Wholesale operation loading Sales & Stock files and generate reports for analysis. | 8 |  | YES | 1 | TSWEEN16 | PLM | VM | Q2 2026 | EDC CaaS | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
12876 | Factory Information System | In Production | FIS | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 211 | No | Yes | COTS | SKING68 | SKING68 | Manufacturing Staffs | Industrial System IT | FIS is the next generation of equipment monitoring for Ford plants. The application is primarily based on a commercial package (Activplant) and includes interfaces to several other applications (Marquee Manager, First Page, Enterprise Gateway) for managing PCB's, paging, TEM, PCON, and CSI. The primary functions of FIS is to reduce the launch curve for new model programs and break production bottlenecks in on-going production operations. |  |  | NO | 3 | BWUNNAVA | PLM | Oracle |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
12876 | Factory Information System | In Production | FIS | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 211 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Staffs | Industrial System IT | FIS is the next generation of equipment monitoring for Ford plants. The application is primarily based on a commercial package (Activplant) and includes interfaces to several other applications (Marquee Manager, First Page, Enterprise Gateway) for managing PCB's, paging, TEM, PCON, and CSI. The primary functions of FIS is to reduce the launch curve for new model programs and break production bottlenecks in on-going production operations. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2026 | On-Prem | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
15425 | FCLA FOCUS WHOLESALE APPLICATION - WFOCUS | In Production | WFOCUS | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 322 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit FOCUS system manages wholesale operation for Mexico Ford Credit, and it is called as WFOCUS. WFOCUS System is a core application for Ford Credit Mexico to manage/control wholesale invoice transferred from FMM for wholesale dealer financing and Ford Motor Subsidy, allows FCM Operation to control the dealer limit, dealer floor plan, wholesale payments, dealer risk management, besides to provide wholesale information to Business to report Credit Bureau files and Regulatory Reports. WFOCUS is also responsible for transferring information to Securitization Application-GS. | 7 |  | YES | 3 | TSWEEN16 | PLM | VM | Q2 2026 | Partial Migration to GCP | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22310 | FACTON - Enterprise Product Costing | In Production | FACTON EPC | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 211 | No | Yes | COTS | SFRANCI8 | AKANSKI | PD Operations and Quality | Integrated Enterprise Resource Planning (I-ERP) | Cost Estimating Application that enables cross CBG estimate comparisons. This tool will replace the legacy CAPE tool. |  |  | YES | 3 | TSWEEN16 | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
22310 | FACTON - Enterprise Product Costing | In Production | FACTON EPC | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 211 | No | Yes | COTS | SFRANCI8 | AKANSKI | PD Operations and Quality | Integrated Enterprise Resource Planning (I-ERP) | Cost Estimating Application that enables cross CBG estimate comparisons. This tool will replace the legacy CAPE tool. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
11594 | ECI: Enhanced Concern Identification | In Production | ECI-CDR | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 231 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Identify/verify emerging potentially critical product concerns faster and increase Customer Satisfaction by improving access to corporate quality & satisfaction data repositories & analysis. | 6 |  | YES | 4 | BWUNNAVA | PLM | VM | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-06-15 |  | Planned |  | No | [14 empty] | No | VM
9960 | FAAS: Ford As A Supplier | In Production | FAAS | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SDEENAD1 | SDHANAS2 | Gold | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | Ford As A Supplier is the mechanism by which Ford is billed for vehicles which are built by Ford , but sold under the Mazda nameplate. |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
9960 | FAAS: Ford As A Supplier | In Production | FAAS | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SDEENAD1 | SDHANAS2 | Gold | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | Ford As A Supplier is the mechanism by which Ford is billed for vehicles which are built by Ford , but sold under the Mazda nameplate. |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
21865 | EZ Budget Tracking System | In Production | EZB | ISIT | MNOWICK1 | LSRINIVA | ESATISH | JLUCAS1 | Copper | Non S-Ox | 211 | Yes | No | In-House | JKOONS | JKOONS | PD Operations and Quality | - | EZ Budget Tracking System for Powertrain FNA. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
23041 | Dragonfly 2.0 | In Production | DFY2 | M&S TECH | VMUTHUPA | DSHANKA1 | RPURUSH3 | WABDUL1 | Silver | Non S-Ox | 322 | No | Yes | In-House | VMUTHUPA | DSHANKA1 | Marketing & Sales | Marketing, Sales and Service | Dragonfly 2 is the upgraded version of Dragonfly which supports web publishing for Ford Brand and Lincoln Brand websites. Market scope below, Ford brand includes AP, Mex, MEA, and South America. Lincoln brand includes China, SK, Middle East, Puerto Rico and Mexico.Ford Credit Account Manager (FCAM) front-end will be hosted in Dragonfly 2 stack to support LATAM market requirements. FMA integrated for LaTam market. | 61 |  | YES | 1 | NKANDULA | PLM | VM | Q2 2026 | Complete Migration to SaaS | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
401 | EXTRAC: Excess Transportation Control | In Production | EuMP-EXTRA | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | EXTRAC application is used to track Non routine transportation which incurs costs in excess of the normal transportation (called EXCESS Transportation Cost). EXTRAC provides a means for authorizing and controlling all excess transportation costs.. Extrac application running in Mainframe technology. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q4 2026 | Move to Pega | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
15094 | External Customs Interface | In Production | ECIS | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Gold | Non S-Ox | 222 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | External Customs Interface System (ECIS) is a compilation of feeds supporting data provided to Ford's Customs Service Providers. The required feeds provide data to vendors that have the responsibility of performing Customs related activities for Ford. Interfaces from MP&L Customs systems required by Customs Application presently being supported by outside supplier, Livingston International. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q3 2027 | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
51416 | Extended CO2 Forecasting Service | In Production | ECO2 | ISIT | MNOWICK1 | LSRINIVA | DESPINOS | JLUCAS1 | Bronze | Non S-Ox | 231 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Marketing & Sales | Industrial System IT | Service to provide CO2 at the entity-level for a 24-month forecast. |  |  | YES | 1 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51416 | Extended CO2 Forecasting Service | In Production | ECO2 | ISIT | MNOWICK1 | LSRINIVA | DESPINOS | JLUCAS1 | Bronze | Non S-Ox | 231 | No | Yes | In-House |  |  | Marketing & Sales | Industrial System IT | Service to provide CO2 at the entity-level for a 24-month forecast. |  | Springboot | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
50816 | Experience API | In Production | XAPI | EVDD | NROTH4 | RBUITEWE | DSHEMENS | JHAAS28 | Platinum | Non S-Ox | 222 | No | Yes | - | #N/A | #N/A | Advanced PD and Tech | 222 | MOBILE APP SPECIFIC SERVICE APIS |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
12627 | Computer Mgmt Interface | In Production | CMI | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Interface for Dealer Facing Web Based Training. https://web.cmi.dealerconnection.com/servlet/cmi2.ExternalAccessServlet?SA=USA&studentLangPref=en&requestTo=HomePageServlet | 20 |  | YES | 4 | NKANDULA | PLM | VM | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
11850 | Exhaust Emissions Measurement System | In Production | EEMS | ISIT | KCHRIST2 | KCHRIST2 | JCICOTTE | JLUCAS1 | Copper | Non S-Ox | 111 | Yes | No | In-House | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | The EEMS application is utilized to divert production vehicles to the APTL test facility for testing. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
16720 | CM4D | In Production | CM4D | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Silver | Non S-Ox | 211 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | CM4D (Coordinate Measurement Machine Management Mechanism for Data) Plant Process(es) Quality Reporting Tool. Produces Variables Charts and basic Attrbute Charts. Data is fed from Measuring Devices such as CMMs, Perceptrons, DataMytes etc. | 68 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
13905 | Exemption Label System | In Production | ELS | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Bronze | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Policy | 111 | THE EXEMPTION LABEL SYSTEM IS A WEB-BASED SEARCHABLE ORACLE DATABASE APPLICATION WHICH ALLOWS THE APPLICATION OWNER TO ENSURE COMPLIANCE WITH FEDERAL EMISSIONS REGULATIONS (SPECIFICALLY 40 CFR PART 85 SUBPART R) IN RECORDKEEPING AND LABELING REQUIREMENTS BY MANAGING THE SUBMISSION OF ALL REQUESTS FOR PRE-CERTIFICATION AND FIELD TEST EXEMPTIONS FOR MOTOR VEHICLES AND MOTOR VEHICLE ENGINES AS WELL AS THE ISSUANCE AND PRINTING OF THE EXEMPTION LABELS. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q4 2027 | Version Upgrade | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
755 | Certificate of Conformity | In Production | COC | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Bronze | Non S-Ox | 211 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Creation of Certificate of Conformity (CoC) in the National Sales Companies. Used within Ford EU and Ford Otosan. A mainframe Telon Cobol facility that generates CoC VIN data for specific vehicles in line with EU legislative requirements together with feed to central client server application which prints the Certificate of conformity (CoC) in the National Sales Companies. The data held on the system is also used to aid the registration systems. Being enhanced during 2015 to enable Digital Transmission of data via Registration Applications. Cross functionally managed - Business Owner MP&L; Consumption Funding EMS&S; BIT SESE; Project funding dependant on which skill team requests the change and what the change consists of. | 5 |  | YES | 4 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize |  | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [9 empty] | Priya | 2025-03-06 |  |  | CUPS Printing servers in VM | No | VM
9083 | Exchange Core Tracking System | In Production | ECTS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | KPATEL77 | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | MAMUDHA | Ford Customer Service | FCSD Tech | Exchange Core Tracking System (ECTS) is a WEB based application for on-line tracking of Dirty Core Exchange Parts from the Dealers to the Remanufacturers. All involved parties i.e. dealers, carriers, consolidators, remanufacturers, parts recall centers and FCSD-E are integrated |  |  | YES | 3 | RKENNEL | PLM | Oracle | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
9083 | Exchange Core Tracking System | In Production | ECTS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | KPATEL77 | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | MAMUDHA | Ford Customer Service | FCSD Tech | Exchange Core Tracking System (ECTS) is a WEB based application for on-line tracking of Dirty Core Exchange Parts from the Dealers to the Remanufacturers. All involved parties i.e. dealers, carriers, consolidators, remanufacturers, parts recall centers and FCSD-E are integrated |  |  | YES | 3 | RKENNEL | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | Java < v21
9083 | Exchange Core Tracking System | In Production | ECTS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | KPATEL77 | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | MAMUDHA | Ford Customer Service | FCSD Tech | Exchange Core Tracking System (ECTS) is a WEB based application for on-line tracking of Dirty Core Exchange Parts from the Dealers to the Remanufacturers. All involved parties i.e. dealers, carriers, consolidators, remanufacturers, parts recall centers and FCSD-E are integrated |  |  | YES | 3 | RKENNEL | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | Java < v21
497 | EWOS - European Work Order System | In Production | EuAS-EWOS | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | LWU14 | Gold | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Accounting System for labour,material & overhead costs per workorder. Links to OSCAR, CMMS3, GAPS, CORA, MEARS, GENERAL LEDGER, PCAM. Online and batch input processing. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q4 2026 | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
50526 | EVSS - Electric Vehicle Specific Services China | In Production | EVSS - CN | EVDD | DHE14 | QJI4 | YGONG6 | WJIN12 | Silver | Non S-Ox | 321 | No | Yes | In-House | #N/A | #N/A | Marketing & Sales | 321 | SERVICES TO CONNECT CN CMS WITH FORD APPLICATIONS |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50292 | EVSS - Electric Vehicle Specific Services | In Production | EVSS | EVDD | JWOOD38 | MBANYAY | SWACKER1 | TKAMPERM | Gold | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 211 | SERVICES TO CONNECT REGIONAL CMS (EU AND NA) TO FORD |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
54036 | Event Router | In Production | ER | EVDD | JWASNIC1 | JVEDANAY | PPANDYA1 | CHOWEL12 | Silver | Non S-Ox | 221 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 221 | EVENT ROUTER IS A PLATFORM TO RECEIVE, DECODE, PROCESS AND ENRICH, EVENTS THAT ARE RECEIVED FROM VEHICLES TO THE CLOUD. THE EVENTS CAN BE FROM TMC OR FROM VSDN. THE PROCESSED EVENTS WILL BE SENT TO CONSUMERS THROUGH DEDICATED KAFKA TOPICS. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
6316 | EVCS: European Vehicle Cost System | Not In EAMS |  | OTHERS | OTHERS | [5 empty] | - | No | Yes | - |  |  |  | Not in EAMS |  |  |  | YES | 1 | OTHERS | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
11479 | EVAT | In Production | EuAS-eVAT | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Gold | S-Ox In Scope | 132 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | eVAT is a global Value Added Tax system which handles VAT decisions and VAT reporting (excluding North America) eVAT covers the following tax types: * VAT * AT = Acquisition Tax * RC = Reverse Charge * Withholding VAT Process integrated to provide Vertex data file with tax rates to some applications. Allocated to eVAT is also a processing task of a monthly file from Vertex. | 99 |  | YES | 2 | TSWEEN16 | PLM | WebFocus | Q4 2024 | Migrate to QlikSense | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-30 | 2024-12-30 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | QlikSense | [5 empty] | No | DA
11479 | EVAT | In Production | EuAS-eVAT | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Gold | S-Ox In Scope | 132 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | eVAT is a global Value Added Tax system which handles VAT decisions and VAT reporting (excluding North America) eVAT covers the following tax types: * VAT * AT = Acquisition Tax * RC = Reverse Charge * Withholding VAT Process integrated to provide Vertex data file with tax rates to some applications. Allocated to eVAT is also a processing task of a monthly file from Vertex. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q2 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
53514 | EV DevOps | In Development | EV DevOps | EVDD | RJOHN813 | SLYTLE | LKINNAIR | LKINNAIR | Bronze | Non S-Ox | - | No | Yes | - | RJOHN813 | SLYTLE | Advanced PD and Tech | - | EV DevOps Placeholder |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
12700 | CDS CUPID - CDS Customer Module (VISTA) | In Production | CDSCUPID | M&S TECH | FHIRSH | NSIVASA1 | BRAMA3 | PSATISH2 | Gold | Non S-Ox | 311 | No | Yes | In-House | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | CDS CUPID is the CDS front end to the CUPID mainframe system. It enables dealers to search and maintain customers for the other CDS platform applications. | 3 |  | YES | 2 | NKANDULA | PLM | VM | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
12345 | eUsed (FDO2 and gebrauchtwagen)(Eur) | In Production | eUsed | FORD PRO & FCSD TECH | TJUNIPER | RHOWEL46 | RRAKESH4 | JCOY3 | Silver | Non S-Ox | 211 | No | Yes | In-House | TJUNIPER | RHOWEL46 | Marketing & Sales | - | eUsed is a B2C (Company to consumer) application provides the web-users with functionality to locate (search engine) the used vehicles owned by Ford and Ford Dealers. Vehicle data are obtained from different sources for each market. UK dealers also have the option to add any other Ford vehicle they wish to advertise, using the eUsed dealer admin site |  |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-31 | 2025-03-10 | Complete | Blue | 2025-06-29 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | Got the confirmation as well. | No | SQL
20897 | Autodesk Vault | In Production | Vault/DMS | ISIT | SKING68 | JLYNN1 | JRICH264 | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | COTS | KCHRIST2 | GECHOLS | Manufacturing Engineering | Industrial System IT | Multi-user DWG data base for Ford Land, PTO, and VO. Mutiple users work collaboratively without overwriting other data including version controls. Includes Vault Enterprise Add-On function for clients. Includes Vault Auto-Naming Utility (add-on). | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
9104 | EUROVIS - European Vehicle Information System | In Production | EuroVIS | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | System to collect orders for new vehicles from Dealers, NSCs, NDCs and Central Sales. It allows orders to be amended, and scheduled for manufacture by the appropriate plants in line with allocations, priorities and constraints.EUROVIS is a centralized corporate system used in all European and Rest of World markets to collect orders for new vehicles from Dealers, National Sales Companies NSCs), National Distribution Companies (NDCs) and Central Sales. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | TBD | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9104 | EUROVIS - European Vehicle Information System | In Production | EuroVIS | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | System to collect orders for new vehicles from Dealers, NSCs, NDCs and Central Sales. It allows orders to be amended, and scheduled for manufacture by the appropriate plants in line with allocations, priorities and constraints.EUROVIS is a centralized corporate system used in all European and Rest of World markets to collect orders for new vehicles from Dealers, National Sales Companies NSCs), National Distribution Companies (NDCs) and Central Sales. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
933 | EUROVAC | In Production | EuAS-VAC | I-ERP | SFRANCI8 | SDHANAL3 | CSRIRAM | LWU14 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | European vehicle Accounting System Produces invoices for all new vehicles. Also tracks financial inventory movements. Feeds to AR, GL and F@ST. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
609 | EUROPUCS - European Petrol Usage Control System | In Production | EuME-PUCS | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Gold | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Human Resources | Integrated Enterprise Resource Planning (I-ERP) | EUROPUCS (European Petrol Usage Control System) application stores the usage details of ARAL Fuel Credit Cards for all card users. Card users use the cards to buy fuel at ARAL gas stations. EUROPUCs receive daily and monthly data feeds from ARAL which contain transactional data regarding the usage of the cards and we send the data to PeopleSoft and TACCS on a monthly basic. EUROPUCS handles all new card requests. New card orders are electronically requested via an OFTP link (Ford Net Mailbox) which fed into system and send to ARAL for the new card. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
13551 | European VBOM | In Production | EuMP-VBOM | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | The VBOM process provides Vehicle Bill of Materials for all non US plants. This includes mainstream European assembly plants, FAB plants, plants within the emerging markets process suite and KD plants. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
15051 | European Safety Lab Web Site | In Production | EuPV-SWEB | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Copper | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | PD Operations and Quality | Industrial System IT | Web site holding safety lab data and reports |  |  | YES | 1 | BWUNNAVA | PLM | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
22510 | European Liquidity Monitoring User Interface | In Production | ELMUI | FORD CREDIT | IPANKAJ | PSRIKIR1 | RMRINAL2 | NKALE | Bronze | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | ELMUI provides entry of manual and derived cash flows and GL Control for the European Liquidity Monitoring (ELM) process. The application forms part of the enhanced liquidity framework consisting of enhanced systems and controls developed by FCE to meet the requirements of the new liquidity regime specified by the UK Financial Services Authority (FSA). The appliaction also achieves FSA Compliance, improves senior management oversight, removes manual work from locations and maximizes use and cost of capital by ensuring that minimal liquidity buffer requirements are required in FCE's Individual Liquidity Guidance. |  |  | YES | 1 | SRAISIN1 | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
9825 | European Company Vehicle Management System | In Production | EuAS-EVMS | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | European Vehicle Management System (EVMS also known as CVMS by most European business partners) is used to track Company Vehicles in the UK. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
9825 | European Company Vehicle Management System | In Production | EuAS-EVMS | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | European Vehicle Management System (EVMS also known as CVMS by most European business partners) is used to track Company Vehicles in the UK. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
13668 | EuroMIVIS Reporting | In Production | Eu_EMRep | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Marketing & Sales | Integrated Enterprise Resource Planning (I-ERP) | Reporting frontend of European Remarketing System EuroMivis (Appl Id. 8624) | 152 |  | YES | 2 | TSWEEN16 | PLM | Datastage | Q4 2024 | Migrate to QlikSense + Big Query | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | QlikSense + Big Query | Praveen | 2025-03-06 |  |  | PDO is yet to decomission the WebFocus and Datastage part as there are some data missmatch issue between the existing and current report | No | DA
13668 | EuroMIVIS Reporting | In Production | Eu_EMRep | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Marketing & Sales | Integrated Enterprise Resource Planning (I-ERP) | Reporting frontend of European Remarketing System EuroMivis (Appl Id. 8624) | 2759 |  | YES | 2 | TSWEEN16 | PLM | WebFocus | Q4 2024 | Migrate to QlikSense + Big Query | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-30 | 2024-12-30 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | QlikSense + Big Query |  |  |  |  | PDO is yet to decomission the WebFocus and Datastage part as there are some data missmatch issue between the existing and current report | No | DA
8624 | EuroMivis | In Production | EuAS-EMIVI | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Marketing & Sales | Integrated Enterprise Resource Planning (I-ERP) | Administration Of Used vehicles in Europe: The function of E-MIVIS is to record and control awaiting sale inventories for vehicles pending second hand sale and to raise the necessary documentation to wholesale these vehicles once the sale has occurred and pass the necessary financial records to downstream systems. The inventories concerned are owned by either Ford Motor Company Limited (FMC) or Ford Credit Europe Bank (FCEB) and are held as assets in the respective books of account governed by that ownership. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
8624 | EuroMivis | In Production | EuAS-EMIVI | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Marketing & Sales | Integrated Enterprise Resource Planning (I-ERP) | Administration Of Used vehicles in Europe: The function of E-MIVIS is to record and control awaiting sale inventories for vehicles pending second hand sale and to raise the necessary documentation to wholesale these vehicles once the sale has occurred and pass the necessary financial records to downstream systems. The inventories concerned are owned by either Ford Motor Company Limited (FMC) or Ford Credit Europe Bank (FCEB) and are held as assets in the respective books of account governed by that ownership. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Yellow | 2025-08-13 |  | Planned |  | Yes | 100% | 50% | 25% |  |  |  | 25% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | Java < v21
6312 | Euro-AP | In Production | EuAS-EurAP | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | S-Ox In Scope | 332 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | EuroAP is the application used by Ford and other affiliate companies for managing disbursements to Suppliers, Dealerships and other associated companies to whom payments are due. EuroAP's functions include managing payment schedules; calculating payment due dates; selecting appropriate bank accounts; choosing payment methods, whether through EFT, wire or via cheque; creating appropriate reports and sending feedback to various systems to enable general ledger postings. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
510 | EU KD Lot | In Production | EuMP-KDLOT | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | KDLot supports the Cat Code to EOC conversion. KDLot tables are loaded daily to QAD, SVD and EMFS. The plants supported are Taiwan, Vietnam and China. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q4 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
53008 | ATLAS Load Frame System | In Production | ALFS | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | The Humanetics ATLAS (Advanced Testing, Laboratory Acquisition System) is a state of the art Load Cell Test and Calibration equipment with unique capabilities of minimizing human effort and maximizing product quality. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
22364 | Assigned Cars - Taxable Benefits | In Production | ASGND CARS | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Marketing & Sales | Marketing, Sales and Service | This application is used to manage the taxable benefits of company vehicles assigned to sales and executive employees. | 12 |  | YES | 1 | NKANDULA | PLM | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13128 | Ethernet Broadcast | In Production | EBC | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Copper | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Ethernet Based Broadcast System. Utilized in broadcasting vehicle build information to plant floor operators, displays, computers, and interfaces. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | SQL | Priya | 2025-03-05 |  |  | Solution will continue to use SQL 2016. Plan to replace EBC is being developed. Database VM will be migrated to OSV AS-IS. No changes will be made to the application. Timeline depends on OSV availability | No | SQL
12877 | ASR Systems & Infrastructure | In Production | ASR | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | CWADE | Gold | Non S-Ox | 11 | No | Yes | COTS | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Systems and Infrastructure required for maintaining PeopleSoft suite of applications for Finance & Accounting functions. This includes feeder systems as well. | 6 |  | YES | 3 | TSWEEN16 | PLM | VM | Q2 2026 | Partial Migration to GCP | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
94 | ESPS: Extended Service Plan System | In Production | ESPS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | KMUKESH | SDHANAS2 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | Extended Service Plan System (ESPS) is an on-line computer system used to support the administration of the Ford Extended Service Plan (ESP). The ESP coverage offers protection against high repair costs after a vehicle is out of its manufacturer warranty period. Dealers sell the ESP product to retail customers. Most sales are from retail customers and often the contract is purchased at the same time they buy the vehicle. Fleets also purchase coverage for their company cars (e.g., Hertz). This application provides for the procesing and maintenance of a significant volume of high margin revenue sales for the Ford Customer Service Division. |  |  | YES | 6 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | 100% | 25% | [6 empty] | Cloud Run | [5 empty] | No | Java < v21
94 | ESPS: Extended Service Plan System | In Production | ESPS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | KMUKESH | SDHANAS2 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | Extended Service Plan System (ESPS) is an on-line computer system used to support the administration of the Ford Extended Service Plan (ESP). The ESP coverage offers protection against high repair costs after a vehicle is out of its manufacturer warranty period. Dealers sell the ESP product to retail customers. Most sales are from retail customers and often the contract is purchased at the same time they buy the vehicle. Fleets also purchase coverage for their company cars (e.g., Hertz). This application provides for the procesing and maintenance of a significant volume of high margin revenue sales for the Ford Customer Service Division. |  |  | YES | 6 | RKENNEL | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
94 | ESPS: Extended Service Plan System | In Production | ESPS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | KMUKESH | SDHANAS2 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | Extended Service Plan System (ESPS) is an on-line computer system used to support the administration of the Ford Extended Service Plan (ESP). The ESP coverage offers protection against high repair costs after a vehicle is out of its manufacturer warranty period. Dealers sell the ESP product to retail customers. Most sales are from retail customers and often the contract is purchased at the same time they buy the vehicle. Fleets also purchase coverage for their company cars (e.g., Hertz). This application provides for the procesing and maintenance of a significant volume of high margin revenue sales for the Ford Customer Service Division. |  |  | YES | 6 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
94 | ESPS: Extended Service Plan System | In Production | ESPS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | KMUKESH | SDHANAS2 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | Extended Service Plan System (ESPS) is an on-line computer system used to support the administration of the Ford Extended Service Plan (ESP). The ESP coverage offers protection against high repair costs after a vehicle is out of its manufacturer warranty period. Dealers sell the ESP product to retail customers. Most sales are from retail customers and often the contract is purchased at the same time they buy the vehicle. Fleets also purchase coverage for their company cars (e.g., Hertz). This application provides for the procesing and maintenance of a significant volume of high margin revenue sales for the Ford Customer Service Division. |  |  | NO | 6 | RKENNEL | Modernize Components (Backlog-2024) | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
22891 | Artificial Intelligence Natural Lang. Processing | In Production | AINLP | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Silver | Non S-Ox | 322 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Systems and corresponding services based on Artificial Intelligence and Computational Linguistics to support intelligent-systems engineering, hybrid language translations, unstructured text mining, knowledge representation and reasoning, knowledge based engineering, big data support, advanced analytics, machine learning, autonomous systems, and advanced decision support. Technologies include AI, NLP, Semantic Web, Taxonomy, Ontology, Statistics, Analytics Visualization. | 5 |  | YES | 1 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
94 | ESPS: Extended Service Plan System | In Production | ESPS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | KMUKESH | SDHANAS2 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | Extended Service Plan System (ESPS) is an on-line computer system used to support the administration of the Ford Extended Service Plan (ESP). The ESP coverage offers protection against high repair costs after a vehicle is out of its manufacturer warranty period. Dealers sell the ESP product to retail customers. Most sales are from retail customers and often the contract is purchased at the same time they buy the vehicle. Fleets also purchase coverage for their company cars (e.g., Hertz). This application provides for the procesing and maintenance of a significant volume of high margin revenue sales for the Ford Customer Service Division. |  |  | YES | 6 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | 100% | 25% | [6 empty] | Cloud Run | [5 empty] | No | Java < v21
11180 | ESPARS : Extended Service Plan Analysis & Rpt sys | In Production | ESPARS | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | SSUBRA38 | VRAMASA6 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | RSING163 | SKOVACIC | Ford Customer Service | FCSD Tech | The Extended Service Plan Analysis & Reporting System (ESPARS) is a SOX critical application which supports the ESP business through Sales & Marketing reporting, calculation of Incentive/Bonus payments, Pricing Analysis, Financial Analysis and the production of month end journal entry input figures and recociliations. System also supports Ford Credit Insurance operations with the preparation of quarterly and year end income statements for reinsurance / retrospective agreement companies. ESPARS is a data-warehousing environment used by North America and Europe which brings together data from multiple sources - GOLDD (dealer), SOVID (EU), and Snap-on (Used Vehicle sales), NAVIS (New Vehicle Sales), GACES (ESP Claims), Account Distribution System, 3rd Party Contract registration confirmations, Contract Registration Details (ESPS). ESPARS employs the Business Objects (BO) reporting tool to allow users to query the data warehouse via either structured reports or user developed AD-HOC queries. | 119 |  | YES | 5 | RKENNEL | PLM | BO | Q2 2025 | Migrate to QlikSense | Modernize | 2026-09-30 | 2026-09-30 |  | In-Progress | Green | 2026-12-29 |  | Planned |  | No | [8 empty] | QlikSense |  |  |  |  | App team descoped the work for the supplier, made some changes to the plan to point BO reports to BQ in 2025 and decommission BO later | No | DA
11180 | ESPARS : Extended Service Plan Analysis & Rpt sys | In Production | ESPARS | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | SSUBRA38 | VRAMASA6 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | RSING163 | SKOVACIC | Ford Customer Service | FCSD Tech | The Extended Service Plan Analysis & Reporting System (ESPARS) is a SOX critical application which supports the ESP business through Sales & Marketing reporting, calculation of Incentive/Bonus payments, Pricing Analysis, Financial Analysis and the production of month end journal entry input figures and recociliations. System also supports Ford Credit Insurance operations with the preparation of quarterly and year end income statements for reinsurance / retrospective agreement companies. ESPARS is a data-warehousing environment used by North America and Europe which brings together data from multiple sources - GOLDD (dealer), SOVID (EU), and Snap-on (Used Vehicle sales), NAVIS (New Vehicle Sales), GACES (ESP Claims), Account Distribution System, 3rd Party Contract registration confirmations, Contract Registration Details (ESPS). ESPARS employs the Business Objects (BO) reporting tool to allow users to query the data warehouse via either structured reports or user developed AD-HOC queries. | 99 |  | YES | 5 | RKENNEL | PLM | Datastage | Q3 2025 | Modernize | Modernize | 2025-09-15 |  |  | In-Progress | Green | 1900-03-30 |  | Planned |  | No | [14 empty] | No | DA
11180 | ESPARS : Extended Service Plan Analysis & Rpt sys | In Production | ESPARS | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | SSUBRA38 | VRAMASA6 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | RSING163 | SKOVACIC | Ford Customer Service | FCSD Tech | The Extended Service Plan Analysis & Reporting System (ESPARS) is a SOX critical application which supports the ESP business through Sales & Marketing reporting, calculation of Incentive/Bonus payments, Pricing Analysis, Financial Analysis and the production of month end journal entry input figures and recociliations. System also supports Ford Credit Insurance operations with the preparation of quarterly and year end income statements for reinsurance / retrospective agreement companies. ESPARS is a data-warehousing environment used by North America and Europe which brings together data from multiple sources - GOLDD (dealer), SOVID (EU), and Snap-on (Used Vehicle sales), NAVIS (New Vehicle Sales), GACES (ESP Claims), Account Distribution System, 3rd Party Contract registration confirmations, Contract Registration Details (ESPS). ESPARS employs the Business Objects (BO) reporting tool to allow users to query the data warehouse via either structured reports or user developed AD-HOC queries. |  |  | YES | 5 | RKENNEL | PLM | Mainframe | Q2 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | Change in Approach for Q2 timeline , Will be delayed as per PDO to 2026 | No | Mainframe
11180 | ESPARS : Extended Service Plan Analysis & Rpt sys | In Production | ESPARS | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | SSUBRA38 | VRAMASA6 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | RSING163 | SKOVACIC | Ford Customer Service | FCSD Tech | The Extended Service Plan Analysis & Reporting System (ESPARS) is a SOX critical application which supports the ESP business through Sales & Marketing reporting, calculation of Incentive/Bonus payments, Pricing Analysis, Financial Analysis and the production of month end journal entry input figures and recociliations. System also supports Ford Credit Insurance operations with the preparation of quarterly and year end income statements for reinsurance / retrospective agreement companies. ESPARS is a data-warehousing environment used by North America and Europe which brings together data from multiple sources - GOLDD (dealer), SOVID (EU), and Snap-on (Used Vehicle sales), NAVIS (New Vehicle Sales), GACES (ESP Claims), Account Distribution System, 3rd Party Contract registration confirmations, Contract Registration Details (ESPS). ESPARS employs the Business Objects (BO) reporting tool to allow users to query the data warehouse via either structured reports or user developed AD-HOC queries. |  |  | YES | 5 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
11180 | ESPARS : Extended Service Plan Analysis & Rpt sys | In Production | ESPARS | FORD PRO & FCSD TECH | ZKOUL | JCOLE195 | SSUBRA38 | VRAMASA6 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | RSING163 | SKOVACIC | Ford Customer Service | FCSD Tech | The Extended Service Plan Analysis & Reporting System (ESPARS) is a SOX critical application which supports the ESP business through Sales & Marketing reporting, calculation of Incentive/Bonus payments, Pricing Analysis, Financial Analysis and the production of month end journal entry input figures and recociliations. System also supports Ford Credit Insurance operations with the preparation of quarterly and year end income statements for reinsurance / retrospective agreement companies. ESPARS is a data-warehousing environment used by North America and Europe which brings together data from multiple sources - GOLDD (dealer), SOVID (EU), and Snap-on (Used Vehicle sales), NAVIS (New Vehicle Sales), GACES (ESP Claims), Account Distribution System, 3rd Party Contract registration confirmations, Contract Registration Details (ESPS). ESPARS employs the Business Objects (BO) reporting tool to allow users to query the data warehouse via either structured reports or user developed AD-HOC queries. |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Delay due to issues Identified during Testing and So-X Application | No | Java < v21
13509 | ESP Prior Approval | In Production | PAWS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TMADHAVA | RSRINI38 | Silver | Non S-Ox | 221 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | ESP Prior Approval Web System (PAWS) is a web based J2EE application which enables the Ford Extended Service Plan (ESP) Call Center to track prior approval requests initiated by the dealers. These requests are for repairs on vehicles which are covered under an ESP contract. It integrates the vehicle inspection processes into a single, seamless process for the ESP Call Center. It also allows dealers to submit prior approval requests and dealer images submission for inspection requests via the Web through the FMC Dealer or InFord portal instead in lieu of placing a call to the ESP Call Center. This will save time, money and provide better service to the dealer body. It also delivers reporting capabilities to better track the call centers time, service and approval dollar amounts. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | 100% | 50% | 50% |  |  |  | 75% |  | Cloud Run | [5 empty] | No | Java < v21
13509 | ESP Prior Approval | In Production | PAWS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TMADHAVA | RSRINI38 | Silver | Non S-Ox | 221 | No | Yes | In-House | ZKOUL | ZKOUL | Ford Customer Service | FCSD Tech | ESP Prior Approval Web System (PAWS) is a web based J2EE application which enables the Ford Extended Service Plan (ESP) Call Center to track prior approval requests initiated by the dealers. These requests are for repairs on vehicles which are covered under an ESP contract. It integrates the vehicle inspection processes into a single, seamless process for the ESP Call Center. It also allows dealers to submit prior approval requests and dealer images submission for inspection requests via the Web through the FMC Dealer or InFord portal instead in lieu of placing a call to the ESP Call Center. This will save time, money and provide better service to the dealer body. It also delivers reporting capabilities to better track the call centers time, service and approval dollar amounts. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-31 | 2025-03-10 | Complete | Blue | 2025-06-29 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | Decom Planned for March. | No | Oracle
13509 | ESP Prior Approval | In Production | PAWS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TMADHAVA | RSRINI38 | Silver | Non S-Ox | 221 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | ESP Prior Approval Web System (PAWS) is a web based J2EE application which enables the Ford Extended Service Plan (ESP) Call Center to track prior approval requests initiated by the dealers. These requests are for repairs on vehicles which are covered under an ESP contract. It integrates the vehicle inspection processes into a single, seamless process for the ESP Call Center. It also allows dealers to submit prior approval requests and dealer images submission for inspection requests via the Web through the FMC Dealer or InFord portal instead in lieu of placing a call to the ESP Call Center. This will save time, money and provide better service to the dealer body. It also delivers reporting capabilities to better track the call centers time, service and approval dollar amounts. |  |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | 100% | 50% | 50% |  |  |  | 75% |  | Cloud Run | [5 empty] | No | Java < v21
21809 | e-Social Employees Records Management | In Production | SCL | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Human Resources | - | Application to support e-Social, a brazilian government program which is part of a broader initiative called SPED. Application goals are to consolidate, manage and send electronic information to the government related to Personal and Payroll related Data of every Ford employee, in accordance with the e-Social regulations. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
9868 | 6-Sigma Project Tracking System (PTS) | In Production | 6-SigmaPTS | ISIT | JDEGUZMA | RMEHTA3 | RJAMBUNA | ISIDDIQ6 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JDEGUZMA | RMEHTA3 | Quality | Industrial System IT | The 6-Sigma Project Tracking System (PTS) system manages projects and resources (skill tracking) to support 6-Sigma projects. It tracks Green Belts and Black Belts and their projects. | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21809 | e-Social Employees Records Management | In Production | SCL | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Human Resources | - | Application to support e-Social, a brazilian government program which is part of a broader initiative called SPED. Application goals are to consolidate, manage and send electronic information to the government related to Personal and Payroll related Data of every Ford employee, in accordance with the e-Social regulations. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
51711 | 3DExperience | In Production | 3DX | ISIT | ACAPONE1 | SGUILLON | SGUILLON | GRAO3 | Bronze | Non S-Ox | 311 | No | Yes | COTS | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | Consists of all applications that are part of basic 3DX platform installation 3D Passport, 3DSwYm, 3DComment, 3DNotification, 3DInxex, 3DDashboard, 3DSpace (CAS, non-CAS), 3DSpaceIndex, File Collaboration Server and 3DOrchestrate | 156 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2026 | EDC New Hypervisor | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | VM
12698 | ESBOL - Extended Service Business Online | In Production | ESBOL | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TBABU | RKADAM1 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | ZKOUL | Ford Customer Service | FCSD Tech | ESB Online (ESBOL) enables European Ford dealer users and internal Admin users to register Optional Vehicle Service (loyalty) Contract coverage online for new and used Ford vehicles. In ESB Online, dealers can inquire for existing contracts, retrieve price information, look up customer information via an interface to SCA-C, and submit new contracts for registration. The registration process completes when ESB Online generates a PDF contract form to be printed and signed. |  |  | YES | 5 | RKENNEL | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
12698 | ESBOL - Extended Service Business Online | In Production | ESBOL | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TBABU | RKADAM1 | Silver | Non S-Ox | 211 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | ESB Online (ESBOL) enables European Ford dealer users and internal Admin users to register Optional Vehicle Service (loyalty) Contract coverage online for new and used Ford vehicles. In ESB Online, dealers can inquire for existing contracts, retrieve price information, look up customer information via an interface to SCA-C, and submit new contracts for registration. The registration process completes when ESB Online generates a PDF contract form to be printed and signed. |  |  | YES | 5 | RKENNEL | PLM | Java Struts | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
12698 | ESBOL - Extended Service Business Online | In Production | ESBOL | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TBABU | RKADAM1 | Silver | Non S-Ox | 211 | No | Yes | In-House | ZKOUL | ZKOUL | Ford Customer Service | FCSD Tech | ESB Online (ESBOL) enables European Ford dealer users and internal Admin users to register Optional Vehicle Service (loyalty) Contract coverage online for new and used Ford vehicles. In ESB Online, dealers can inquire for existing contracts, retrieve price information, look up customer information via an interface to SCA-C, and submit new contracts for registration. The registration process completes when ESB Online generates a PDF contract form to be printed and signed. |  |  | YES | 5 | RKENNEL | PLM | Oracle | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Oracle
22481 | YAST | In Production | YT | EPEO | LFULCHER | KMAHAJAN | TKLEMER | TKLEMER | Bronze | Non S-Ox | 111 | Yes | No | - | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | YAST is a server staging tool. It supports legacy SLES linux. | 5 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
12698 | ESBOL - Extended Service Business Online | In Production | ESBOL | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TBABU | RKADAM1 | Silver | Non S-Ox | 211 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | ESB Online (ESBOL) enables European Ford dealer users and internal Admin users to register Optional Vehicle Service (loyalty) Contract coverage online for new and used Ford vehicles. In ESB Online, dealers can inquire for existing contracts, retrieve price information, look up customer information via an interface to SCA-C, and submit new contracts for registration. The registration process completes when ESB Online generates a PDF contract form to be printed and signed. |  |  | YES | 5 | RKENNEL | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
20981 | ESB Contract Assistance | In Production | DCW-ESBCA | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | JBROADW4 | RKADAM1 | Silver | Non S-Ox | 221 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | This application enables the dealers to submit the contract maintenance requests to Ford Extended Service Business (ESB). It also provides the business process automation (workflow) to streamline the ESB contract management. The application name for the external dealers is called ESB Contract Assistance |  |  | YES | 2 | RKENNEL | PLM | SQL | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
53138 | WPX Analytics | Planned | WPX | EPEO | SRUNSON | JROSCINI | DZDROJEW | YKADIYAL | Bronze | Non S-Ox | - | No | Yes | In-House | SRUNSON | JROSCINI | Enterprise Technology | EPEO | Workplace Experience - Workplace Insights and Analytics | 1 |  | YES | 2 | SWALIMBE | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
12122 | Error Proofing - VO | In Production | EP - CEC | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 111 | Yes | No | Managed by 3rd Party Purchased Service | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | In-Station process control for DC nutrunners |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
24501 | WINDOWS SERVER UPDATE SERVICES | In Production | WSUS | EPEO | LFULCHER | KMAHAJAN | OSHVARTS | CDOSHI | Copper | Non S-Ox | 11 | No | Yes | COTS |  |  | Enterprise Technology | EPEO | Windows Server Update Services are a Client/Server package from Microsoft used to automate the download and distribution of the Windows Operating System updates. | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
54144 | Wholesale Loss Database GDMS | Planned | WhLGDMS | FORD CREDIT | VMADHUSU | TMCCAFFR | SWELCH23 | SWELCH23 | - | S-Ox In Scope | - | Yes | No | COTS | VMADHUSU | TMCCAFFR | Ford Credit Services | - | Global Data Management and Services - Database to write back Wholesale Loss data (FCE) | 3 |  | YES | 2 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
11002 | ERES | In Production | EuAS-ERES | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | ERES evaluates the receipts for the European companies, produces the SBIs for the suppliers and the postings for the ledger. ERES covers the following data types: * Production Material (direct) * Non-production material (indirect) * Retroactive price changes |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
12606 | eProfile | In Production | eProfile | FORD PRO & FCSD TECH | TJUNIPER | GRIST | SRAVI6 | KMADHUMI | Silver | Non S-Ox | 321 | No | Yes | In-House | TJUNIPER | GRIST | Marketing & Sales | Marketing, Sales and Service | eProfile is an application that provides a consistent way of data capture and storage across differing market web sites in accordance with data protection legislation and using a standard set of web consumer data capture templates. |  |  | YES | 2 | RKENNEL | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-30 | 2025-02-05 | Complete | Blue | 2025-09-28 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL SQLServer | [5 empty] | No | SQL
52496 | Visual Cycle Plan | In Development | VCP | ISIT | SBONNICI | KRAMMOHA | IWEITZER | GRAO3 | Silver | Non S-Ox | - | Yes | No | In-House | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | Vehicle Cycle Plan for upper management (Director/VP Level) | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-04-14 |  | Planned |  | No | 100% | 50% | 25% |  |  |  | 25% |  | GCP Migration | Ramesh | 2025-03-11 |  |  | PCF BMIT app in Flight. There is a Possible spill over to Q2 due to Design change. Revised timeline & approval for the date change pending | No | VM
52851 | ePolicy Orchestrator | In Production | ePO | ISIT | SKING68 | KBARTHO1 | JBARGER | RPRASA22 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SKING68 | KBARTHO1 | Manufacturing Engineering | Industrial System IT | Trellix ePolicy Orchestrator (ePO) is a Centralized security Management Tool to help orchestrate and manage your endpoints. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started | Green | 0 |  | Planned |  | No | [14 empty] | No | SQL
53465 | Vaccine Registration & COVID Testing | In Production | VR&T | OCETO | TSWEEN16 | KADOMKAI | PPOBURSK | ESTILESK | Gold | Non S-Ox | 322 | No | Yes | In-House | DDESAI | KADOMKAI | Enterprise Technology | Staffs IT | Vaccine registration system and Weekly COVID test upload: Codename Project Snowball | 3 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
20722 | EPIC. Odette File Transfer Protocol | In Production | EPIC/OFTP2 | EPEO | MCRNKOVI | BBOGEDIN | JMEZQUIT | RMODI2 | Silver | Non S-Ox | 322 | Yes | No | COTS | MCRNKOVI | MCRNKOVI | Enterprise Technology | - | EPIC is an EDI software used to transfer files between Ford apps and Trading Partners. It uses the EDI Protocols OFTP2, SFTP and AS2 |  |  | YES | 2 | SWALIMBE | PLM | SQL | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | SQL
13425 | Used Vehicle Information System-UVIS | In Production | UVIS | FORD CREDIT | DTAURO | PBALUSU | LSTARZYK | RPARAME4 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DTAURO | SKHAN29 | Marketing & Sales | Ford Credit (FMCC) | UVIS is the Ford system that manages all processes related to Vehicle Remarketing Inventory and Sales for the US & Canada. | 4 |  | YES | 4 | SRAISIN1 | PLM | VM | Q2 2025 | EDC New Hypervisor | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
11592 | ePCW (Part Cost and Weight on the web) | In Production | ePCW | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Copper | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Finance | Industrial System IT | Develop and implement a web based interface with an IMS backend to replace the current client server GUI screens PCW. Part Cost and Weight (ePCW) tracks part cost and weight for a forward model vehicle program and using WERS it allows the analyst to track the vehicle program throughout its life cycle (PA to Job 1). |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
23641 | ePAYS S America electronic Payment Solution - ePAY | In Production | ePAYS | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | South America electronic Payment Solution ePAYS to support non-prod account payments, in such way that the miscellaneous account payment process is mechanized in the region. The solution will support Argentina, Brazil, Ford Credit Brazil and National Sales Companies Chile, Colombia, Peru markets. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
22436 | Units Down | In Production | UNITS DOWN | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | Marketing, Sales and Service | This application allows the Customer Service Office (CSO) to focus on the highest priority emergency orders where a customer's vehicle is not drivable due to shortage of parts. It allows FoC Dealers to enter a unit down request and track updates regarding the part availability as they become available. | 13 |  | YES | 1 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-25 |  | In-Progress | Green | 2025-09-23 |  | Planned |  | No | 75% | 25% | [6 empty] | GCP Migration |  |  |  |  | Need to add one more row of DB for the same app. Its missing. | No | VM
23641 | ePAYS S America electronic Payment Solution - ePAY | In Production | ePAYS | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | South America electronic Payment Solution ePAYS to support non-prod account payments, in such way that the miscellaneous account payment process is mechanized in the region. The solution will support Argentina, Brazil, Ford Credit Brazil and National Sales Companies Chile, Colombia, Peru markets. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
11459 | ePayables | In Production | ePay | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Provides suppliers with the capability to view and download 'remittance advices'. also provides functionality to view payment status and details. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 50% | 75% |  | 75% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-06 |  |  |  | No | Oracle
11459 | ePayables | In Production | ePay | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Provides suppliers with the capability to view and download 'remittance advices'. also provides functionality to view payment status and details. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 50% | 75% |  | 75% |  | Cloud Run | Praveen | 2025-03-06 |  |  |  | No | Java < v21
21179 | uBuild | In Production | uBuild | EA | RRISS | SHE1 | LKESHRI | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | - | uBuild is an automated build and test used to assist in application development and testing. | 22 |  | YES | 3 | GBRAIL | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
11459 | ePayables | In Production | ePay | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Provides suppliers with the capability to view and download 'remittance advices'. also provides functionality to view payment status and details. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 50% | 75% |  | 75% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | Java < v21
6304 | EPAS - European Property Accounting System | In Production | EuAS-EPAS | OCETO | TSWEEN16 | KKOEHLER | MRAUTERK | LWU14 | Copper | Non S-Ox | 131 | No | Yes | COTS | DDESAI | DDESAI | Finance | Staffs IT | EPAS (European Property Accouting System)is used to maintain fixed assets/special tool records in a standardized System (SAP FI/AA module). After the launch of PCAM the scope of European Property Accounting System (EPAS) had been reduced. EPAS primary serves as data repository for asset information prior to PCAM launch |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
55058 | Tierpoint MID Server | Planned | TierMid | EPEO | LFULCHER | CDOSHI | JVIZZAC4 | CDOSHI | Bronze | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | LFULCHER | CDOSHI | Enterprise Technology | EPEO | Proxy authentication services for Tierpoint internet portal | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
19809 | EOL Data Exchange | In Production | EOLX | EVDD | MJAMWAL | TPINTO3 | IJEBARAJ | IJEBARAJ | Copper | Non S-Ox | 111 | No | Yes | In-House | MJAMWAL | TPINTO3 | Advanced PD and Tech | - | Data transfer between Global EOL systems and GIVIS. |  |  | YES | 1 | MJONE308 | PLM | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
52177 | Environmental Mass Properties Service | In Production | EMPS | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 222 | No | Yes | In-House | DKAVITHA | UVIJAYAL | PD Operations and Quality | Industrial System IT | Environmental view of vehicle weight data |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize | 2024-10-01 | 2024-10-01 | 2024-05-22 | Complete | Blue | 2024-07-31 | 2024-07-30 | Complete |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
22403 | The Roundtable Process | In Production | ROUNDTABLE | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Marketing & Sales | Marketing, Sales and Service | A website to provide a formalized channel for meaningful, two-way communication between Ford of Canada and its Dealers. Dealers can submit their concerns and opportunities online through the Feedback Form. | 13 |  | YES | 1 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | [6 empty] | GCP Migration |  |  |  |  | Need to add one more row of DB for the same app. Its missing. | No | VM
52177 | Environmental Mass Properties Service | In Production | EMPS | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 222 | No | Yes | In-House |  |  | PD Operations and Quality | Industrial System IT | Environmental view of vehicle weight data |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize | 2024-10-01 | 2024-10-01 | 2024-05-22 | Complete | Blue | 2024-07-31 | 2024-07-30 | Complete |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
50986 | Manufacturing Vehicle Distribution - Corrective Action Management | In Production | MVD-CAM | ISIT | VVIJAY55 | RADAM10 | VDODDAMR | SSENTH15 | Silver | Non S-Ox | 122 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | The purpose of Manufacturing Vehicle Distribution - Corrective Action Management is to assist with the handling of exceptions when a VIN is off-plan between vehicle production and delivery to the final destination. This can include facilitating Spot Buys, Diversions, Manual Invoice submission and approvals, and telematics alerts based on various business thresholds and KPI criteria. | 3 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-09-30 | 2024-12-16 | 2024-12-09 | Complete | Blue | 2025-01-31 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Ramesh | 2025-03-10 |  |  |  | No | VM
51092 | Manufacturing Vehicle Distribution - Dashboards and Analytics | In Production | MVD - DNA | ISIT | VVIJAY55 | RADAM10 | VDODDAMR | SSENTH15 | Silver | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Finished Vehicle logistics operations dashboards |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | SQL
22361 | Technician Message Board | In Production | TECHMSGBRD | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | Marketing, Sales and Service | Provides an electronic Technician-to-Technician message board for posting technical tips and other technical information to encourage the sharing of technical information among technicians and assist technicians to perform their job more effectively. | 13 |  | YES | 1 | NKANDULA | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | Need to add one more row of DB for the same app. Its missing. Action Needed : Need 2 Rows for VM and DB decom and Status is Inprogress | No | VM
24255 | Tasktop | In Production | Tasktop | EA | RRISS | SHE1 | SLOSEY | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | Technology & Enterprise Services (TES) | Integration Tool for maintaining point to point syncing of data | 9 |  | YES | 2 | GBRAIL | PLM | VM | Q2 2025 | Complete Migration to SaaS | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
20910 | Systematic Parts Remote Inventory Technology FoE | In Production | SPRINT FoE | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | TOBERHOF | MMEHTA5 | Silver | S-Ox In Scope | 232 | No | Yes | COTS | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | Makes use of SAP ERP -EAMS #51048- Support dealer's inventory management by optimizing the dealer's inventory profile based on real customer orders overlayed by market demand and by calculating inventory replenishment orders based upon inventory data from the dealer | 13 |  | YES | 1 | RKENNEL | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | 13 LPARS partition was found, Following up with PDO | No | VM
20459 | Enterprise System Center Operations Manager | Active | eSCOM | EPEO | SKULKA52 | NSHAH43 | HLIN13 | SGABLE | Silver | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
11034 | Suspension Orders | In Production | SORP | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DDESAI | KADOMKAI | Policy | Staffs IT | Suspension Orders: increases the effectiveness of Suspension Orders by providing an on-line application that allows for authoring, searching, viewing and reporting of Suspension Orders for all those who work at Ford globally. | 6 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | APP and DB component migrated to GCP, Security tools integration is pending | No | VM
51931 | Enterprise Search | In Production | AzrSearch | EPEO | SRUNSON | PWILL357 | GSARAV13 | GSIENKIE | Silver | Non S-Ox | 111 | No | Yes | In-House | SRUNSON | PWILL357 | Enterprise Technology | EPEO | SaaS Search Online Hybrid solution using Search and O365 Search Online. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
20565 | Supplier Improvement Metrics | In Production | SIM | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | This is the Next Generation Supplier Improvement Metrics application replacing the current Supplier Improvement Metrics system. SIM NG will serve as the data infrastructure for Ford's common, globally integrated supplier quality management processes that ecompass sourcing, launch, and on-going production. Taking input from SUPER G, CMMS, and other systems to calculate key Supplier metrics such as PPM and Q1 Rating. In development 2008 - 2012, SIM Next Gen is planned to replace the existing Supplier Improvement Metrics application. NOTE: as of Nov 11, 2013 this version of SIM will become Q1 scoring System of Record | 4 |  | YES | 6 | TSWEEN16 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19636 | Enterprise PDF Document Generator | In Production | EPDF | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Copper | Non S-Ox | 221 | No | Yes | In-House |  |  | Finance | Technology & Enterprise Services (TES) | Application takes any format input file (e.g. printfile) and renders it into single Page PDF documents. The output is generated in a format ready to load into the Documentum archive (ITMS#19103) including required meta data required for a specific document type. |  | WAS | YES | 1 | TSWEEN16 | PLM | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
53665 | STORAGE OBJECT SERVICES | Active | STAASOS | EPEO | LFULCHER | RMANNING | ICECILIA | RMANNING | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | RMANNING | Enterprise Technology | ITO | Object Storage Services (S3 Protocol) delivered to consumers via Storage as a Service ITO offering. Entry defines the technologies that are used to support this service offering to support global infrastructure deployments. | 4 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
51093 | Enterprise Identity Management | In Production | EIdM | EPEO | NOKEEFE | MSNYDER5 | DDALKOVS | GSIENKIE | Silver | Non S-Ox | 231 | No | Yes | Managed by 3rd Party Purchased Service | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | To replace SILAS for Enterprise Identity lifecycle and profile management. It bases on Microsoft Identity Manager (MIM) product. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53663 | STORAGE FILE SERVICES | Active | STAASFS | EPEO | LFULCHER | RMANNING | DOLSON12 | RMANNING | Bronze | Non S-Ox | - | No | Yes | - | LFULCHER | RMANNING | Enterprise Technology | ITO | File Services (NFS and SMB Protocols) delivered to consumers via Storage as a Service ITO offering. Entry defines the technologies that are used to support this service offering to support global infrastructure deployments. | 94 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
13865 | ENTERPRISE HOST PROTECTION AUDIT SYSTEM | In Production | EHPAS | OCETO | TVASU | KBALAS13 | MAMAREND | WJUSTICE | Copper | Non S-Ox | 211 | No | Yes | In-House | TVASU | mamarend | Enterprise Technology | Technology & Enterprise Services (TES) | EHPAS (The Enterprise Host Protection Audit System) is a tool for discovering, tracking and taking action on configuration variances from the Ford PAH (Properly Administered Host) Standards, as provided by the ITPM (Information Technology Policy Manual). | 42 |  | YES | 4 | TSWEEN16 | PLM | WebFocus | Q4 2024 | Migrate to QlikSense | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-30 | 2024-12-30 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | QlikSense | [5 empty] | No | DA
13865 | ENTERPRISE HOST PROTECTION AUDIT SYSTEM | In Production | EHPAS | OCETO | TVASU | KBALAS13 | MAMAREND | WJUSTICE | Copper | Non S-Ox | 211 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | EHPAS (The Enterprise Host Protection Audit System) is a tool for discovering, tracking and taking action on configuration variances from the Ford PAH (Properly Administered Host) Standards, as provided by the ITPM (Information Technology Policy Manual). |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q3 2025 | Rewrite | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
13865 | ENTERPRISE HOST PROTECTION AUDIT SYSTEM | In Production | EHPAS | OCETO | TVASU | KBALAS13 | MAMAREND | WJUSTICE | Copper | Non S-Ox | 211 | No | Yes | In-House | TVASU | TVASU | Enterprise Technology | Technology & Enterprise Services (TES) | EHPAS (The Enterprise Host Protection Audit System) is a tool for discovering, tracking and taking action on configuration variances from the Ford PAH (Properly Administered Host) Standards, as provided by the ITPM (Information Technology Policy Manual). |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
53664 | STORAGE BLOCK SERVICES | Active | STAASBS | EPEO | LFULCHER | RMANNING | DOLSON12 | RMANNING | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | RMANNING | Enterprise Technology | ITO | Block Services (IP and FC Protocols) delivered to consumers via Storage as a Service ITO offering. Entry defines the technologies that are used to support this service offering to support global infrastructure deployments. | 13 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
23712 | Enterprise GRC - RSA Archer | In Production | GRC | I-ERP | SFRANCI8 | SFRANCI8 | AKANSKI | LWU14 | Copper | Non S-Ox | 321 | No | Yes | COTS | TSWEEN16 | SFRANCI8 | Finance | Enterprise Connectivity - PDO | Internal Control implementation of RSA Archer for Enterprise GRC purposes |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2026 | On-Prem | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
53068 | Single Interface Experience customeR Request Appli | In Production | SIERRA | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 311 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Application that allows agents to receive and process requests to serve customers in a single working environment (Single Pane of Glass) being able to see, execute and track the satisfactory completion of the requests | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
19622 | SHC Resource Center | In Production | SHC-RC | EPEO | LFULCHER | EREYNOL3 | JKADAKIA | MMACKE16 | Silver | Non S-Ox | 111 | No | Yes | In-House | LFULCHER | EREYNOL3 | Enterprise Technology | EPEO | Central repository for servers and applications managed by Hosting Services. | 10 |  | YES | 2 | SWALIMBE | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
18728 | Enterprise Document Print Service | In Production | EDPS | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | 212 | No | Yes | In-House | TVASU | NSENTHI1 | Finance | Technology & Enterprise Services (TES) | The EDPS project covers centralized mass printing of PDF documents archived by the US EDMS project in Documentum docbase. EDPS will be implemented and run as a J2EE web-application on a Linux box. The EDPS project is intended to be started with replacement of the current M/Archive printing. 2015 usage added for South Africa (EUROVAC Vehicle Invoices); also India and Thailand. |  |  | YES | 2 | TSWEEN16 | PLM | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
19103 | ENTERPRISE DOCUMENT MANAGEMENT SYSTEM | In Production | EDMS | EPEO | SRUNSON | PWILL357 | GSARAV13 | GSIENKIE | Silver | Non S-Ox | 322 | No | Yes | COTS | SRUNSON | SRUNSON | Enterprise Technology | EPEO | EDMS for corporate records requiring long term retention and archiving |  |  | YES | 3 | SWALIMBE | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
56878 | ServiceNow ( IT Connect ) | Planned | Snow | EPEO | RHAMMO57 | JGIES | NANDE114 | NAAFTABR | Silver | Non S-Ox | - | No | Yes | COTS | RHAMMO57 | JGIES | Enterprise Technology | - | Ford's IT ticketing system, including the customer user interface (IT Connect), and the IT support team user interface. This is a COTS application from the vendor Service Now | 23 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
19103 | ENTERPRISE DOCUMENT MANAGEMENT SYSTEM | In Production | EDMS | EPEO | SRUNSON | PWILL357 | GSARAV13 | GSIENKIE | Silver | Non S-Ox | 322 | No | Yes | COTS | SRUNSON | PWILL357 | Enterprise Technology | EPEO | EDMS for corporate records requiring long term retention and archiving |  |  | YES | 3 | SWALIMBE | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
15918 | Enterprise Data Warehouse-EDW | In Production | EDW | FORD CREDIT | IPANKAJ | VGA | BSENTHI1 | VBHUPATH | Bronze | Non S-Ox | 323 | No | Yes | In-House | IPANKAJ | VGA | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit Enterprise Data Warehouse is an integrated repository of data sourced from various operational applications intended for analytical and reporting purposes. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20670 | Sell-out reporting | In Production | SOR | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | In-House | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | The Sell-out reporting application (formerly named Wholesale sell-out reporting WSR) provides reporting on dealer sell-out channels related sell data (independent repairers & bodyshops, fleets, authorized Ford repairers, etc). | 4 |  | YES | 6 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | [6 empty] | GCP Migration | [5 empty] | No | VM
18609 | Enterprise Data Warehouse Foundation | In Production | EDW - FDN | I-ERP | SARAUJO3 | CBISWADI | JBAJI | SNAG1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Enterprise Data Warehouse contains company wide information that is used to support enterprise information needs. Link to the EDW interfaces: https://comm.sp.ford.com/sites/EDW/Lists/EDW%20Interfaces/EDW%20Interfaces.aspx | 263 |  | YES | 2 | TSWEEN16 | PLM | Datastage | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | DA
18609 | Enterprise Data Warehouse Foundation | In Production | EDW - FDN | I-ERP | SARAUJO3 | CBISWADI | JBAJI | SNAG1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Enterprise Data Warehouse contains company wide information that is used to support enterprise information needs. Link to the EDW interfaces: https://comm.sp.ford.com/sites/EDW/Lists/EDW%20Interfaces/EDW%20Interfaces.aspx |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q1 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
23081 | ENTERPRISE ARCHITECTURE MANAGEMENT SYSTEM | In Production | EAMS | OCETO | TVASU | MWAWZYSK | PGUNNA | KTRACY8 | Silver | Non S-Ox | 211 | No | Yes | COTS | NSENTHI1 | MWAWZYSK | Enterprise Technology | Technology & Enterprise Services (TES) | The Enterprise Architecture Management System, originally known as 'EATOOL', is a tool suite designated as the official System of Record (SoR) for all enterprise architecture modeling artifacts providing foundational information and support for enterprise blueprints and all other IT business processes. This information includes the application and technology portfolios supporting the technology management (TM), application portfolio management (APM) processes as well as architecture assurance (AAA) and business architecture (BA) activities. EAMS is supported by the Mega Hopex COTS product and a Ford custom developed web interface |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
57586 | REDIS | Active | REDIS | EPEO | SKULKA52 | NSHAH43 | RYALAVAR | RYALAVAR | Copper | Non S-Ox | 0 | No | Yes | Managed by 3rd Party Purchased Service |  |  | Enterprise Technology | EPEO | on-prem Caching Database | 6 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
23081 | ENTERPRISE ARCHITECTURE MANAGEMENT SYSTEM | In Production | EAMS | OCETO | TVASU | MWAWZYSK | PGUNNA | KTRACY8 | Silver | Non S-Ox | 211 | No | Yes | COTS | NSENTHI1 | MWAWZYSK | Enterprise Technology | Technology & Enterprise Services (TES) | The Enterprise Architecture Management System, originally known as 'EATOOL', is a tool suite designated as the official System of Record (SoR) for all enterprise architecture modeling artifacts providing foundational information and support for enterprise blueprints and all other IT business processes. This information includes the application and technology portfolios supporting the technology management (TM), application portfolio management (APM) processes as well as architecture assurance (AAA) and business architecture (BA) activities. EAMS is supported by the Mega Hopex COTS product and a Ford custom developed web interface |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
51107 | Enrollment Gateway | In Production | EG | EVDD | JWASNIC1 | JWASNIC1 | STHOTTE1 | ZBRUCK | Gold | Non S-Ox | 221 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 221 | FORD'S ENROLLMENT ORCHESTRATION PLATFORM PROVIDING CLOUD-TO-CLOUD AND CLOUD-TO-VEHICLE CONFIGURATIONS ACROSS CONNECTED FEATURES (E.G. PHONE AS A KEY, ACTIVE GLIDE, REAL TIME TRAFFIC, ETC.). |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
20388 | Enhanced Laboratory Management Systems | In Production | ELMS | ISIT | OTHERS | JLOPORTO | JNG | JLUCAS1 | Silver | Non S-Ox | 312 | Yes | No | In-House | JSHANAH1 | JLOPORTO | PD Operations and Quality | - | ELMS (Enhanced Laboratory Management System) aids in the management of work flow, test scheduling and resource allocation for a given labaoratory or support group and customers. It will be used by Powertrain labs in North America, by the VEV org in PD. This is a Non-SOX application. VEV is providing day-to-day support of the application software including training. It provides tools to assign tests to facilities and personnel, monitors facility status, and provides performance metrics, and provides access to best practices. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51064 | Red Hat Satellite | In Production | Satellite | EPEO | LFULCHER | KMAHAJAN | OSHVARTS | OSHVARTS | Silver | Non S-Ox | 111 | No | Yes | - | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | Red Hat OS Patch Management | 8 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
21023 | Engineering Statement of Work | In Production | PTO ESOW | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Enterprise Technology | Industrial System IT | Engineering Statement of Work (eSOW) is web-based application used to document and define the requirements between Ford Motor Company and the Supplier in support of target setting, design, development, manufacturing, production process, communication, timing, quality, documentation and warranty. This document establishes a consensus for deliverables and formats to ensure understanding between the Supplier and Ford Motor Company. The SOW also is a guide to the division of responsibilities between Ford Motor Company and the Supplier. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize | 2024-11-15 | 2024-11-15 | 2024-11-11 | Complete | Blue | 2024-12-31 | 2024-12-18 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | priya | 2025-03-13 |  |  |  | No | SQL
24451 | Public Wifi Self-Help Tool | In Production | PWSHT | EPEO | MCRNKOVI | SSOLTANI | SSASINOW | ASALOWI1 | Copper | Non S-Ox | 121 | No | Yes | In-House | MCRNKOVI | SSOLTANI | Enterprise Technology | EPEO | This is a web-based tool which allows public wifi users the capability to reset their public wifi passwords. | 3 |  | YES | 2 | SWALIMBE | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
21023 | Engineering Statement of Work | In Production | PTO ESOW | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Enterprise Technology | Industrial System IT | Engineering Statement of Work (eSOW) is web-based application used to document and define the requirements between Ford Motor Company and the Supplier in support of target setting, design, development, manufacturing, production process, communication, timing, quality, documentation and warranty. This document establishes a consensus for deliverables and formats to ensure understanding between the Supplier and Ford Motor Company. The SOW also is a guide to the division of responsibilities between Ford Motor Company and the Supplier. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17375 | Engineering Job Authorization | In Production | EJA | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | MAKES A CONTROL OF THE BUDGET OF A PROJECT OF ENGINEERING THROUGH WORN-OUT HOURS FOR ACTIVITY OF THIS PROJECT ALSO MAKING VALUE OF THE HOURS PRESENTING A REAL EXPENSE TO THE FORESEEN IN THE MONTH COUNTING THE EXPENSE AND THROWING THE SAME IN THE FIXED ASSETS. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | GCP Migration is completed for Database. VMs are decommissioned | No | Oracle
20423 | Prognosis IP Telephony Manager | Active | UCIPTM | EPEO | SRUNSON | PWILL357 | DPETRIE | CFINLE13 | Copper | Non S-Ox | - | No | Yes | - | SRUNSON | PWILL357 | Enterprise Technology | - | Prognosis monitors Cisco Unified Communications infrastructure, providing vital performance management for core server health and voice quality. | 12 |  | YES | 2 | SWALIMBE | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
1405 | Engine Reporting | Not In EAMS |  | OTHERS | OTHERS | [5 empty] | - | No | Yes | - | OTHERS | OTHERS | PD Operations and Quality |  |  |  |  | YES | 1 | OTHERS | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | DA
20305 | Endevor | Active | ENDV | EPEO | SKULKA52 | CGIACOBB | RJOHNS93 | RJOHNS93 | Copper | Non S-Ox | - | No | - | - | CMIRABIT | CGIACOBB | Information Technology | ITO | Endevor is a Software Configuration Managment vendor tool owned by Computer Associates. Endevor will be the one mainframe solution for Ford. All other SCM mainframe tools will eventually be replaced by Endevor. |  |  | YES | 1 | SWALIMBE | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
23011 | PROARCHIVER | In Production | PROARCH | EPEO | SRUNSON | PWILL357 | GSARAV13 | GSIENKIE | Silver | Non S-Ox | 222 | No | Yes | COTS |  |  | Enterprise Technology | EPEO | ProArchiver is a utility program that parses and loads PDF documents into EDMS | 4 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
21328 | Employee vehicle sales portal (CDV - Arg/Brazil) | In Production | CDV | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Web Internet application to sell vehicles to employees, agency, family, friends, retired and partnership. Those vehicles have the tendency to have lower price than regular market. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-04-30 |  | In-Progress | Green | 2025-04-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
21328 | Employee vehicle sales portal (CDV - Arg/Brazil) | In Production | CDV | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Web Internet application to sell vehicles to employees, agency, family, friends, retired and partnership. Those vehicles have the tendency to have lower price than regular market. |  |  | YES | 4 | TSWEEN16 | PLM | SQL | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-04-30 |  | In-Progress | Green | 2025-04-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | SQL
24562 | Personal Lifetime Communication | In Production | PLC | FORD CREDIT | NJOSHI21 | SFRAGAL1 | KUHL1 | ASAXENA8 | Bronze | Non S-Ox | 311 | No | Yes | In-House | NJOSHI21 | ABARNA10 | Ford Credit Services | Ford Credit (FMCC) | Web facing screen presenting Personal Lifetime Communication to user where applicable | 7 |  | YES | 4 | SRAISIN1 | PLM | VM | Q2 2025 | EDC New Hypervisor | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
21328 | Employee vehicle sales portal (CDV - Arg/Brazil) | In Production | CDV | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Web Internet application to sell vehicles to employees, agency, family, friends, retired and partnership. Those vehicles have the tendency to have lower price than regular market. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-04-30 |  | In-Progress | Green | 2025-04-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
52694 | OGC Legal Case Search System | In Production | CaseSearch | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Gold | Non S-Ox | 321 | No | Yes | In-House | DDESAI | KADOMKAI | Policy | Staffs IT | OGC request this search tool to pull data from call center, which shows the efforts both Company and customer took to resolve the issue prior to litigation. The searches also seek to identify how many other customers are having the same issue and can impact the value of the case and any potential punitive damages. OGC has a legal obligation to comply with requests for information about other customers who may have also complained about a particular product or component. OGC must also be able to pull records relating to customer who have filed suit or made claims against the Company. The search tool allows user to search by model year, model, symptom codes, case categories, VIN number, engine code, keyword in the comments, etc. Note: This new search tool will replace the existing one which used FMC360 as data source (FMC360 was decommissioned in 2019) | 4 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 | 2025-01-25 | Complete | Blue | 2025-09-13 | 2025-02-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | VMs are now decommissioned | No | VM
14258 | Emission non-sensitive VETS 9000 | In Production | APTL VETS | ISIT | KCHRIST2 | KCHRIST2 | JCICOTTE | JLUCAS1 | Copper | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | The Vehicle Emission Test System (VETS) application is wholly developed by Horiba. The Vehicle Emission Test System (VETS) software is used to control a computerized vehicle emissions test system. It is designed to control and document tests measuring the mass of certain compounds emitted by a vehicle under controlled conditions. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
24334 | North America Services API | In Production | NASAPI | M&S TECH | KHEMANT | KDANDUPA | SPOTLUR6 | MPINRED1 | Gold | Non S-Ox | 322 | No | Yes | In-House | KHEMANT | KDANDUPA | Enterprise Technology | - | The North America Services API (NASAPI) powers Ford's digital consumer experiences by providing a variety of web-based services for Products and other Marketing capabilities. Each service has a RESTful Application Programming Interface (API) that can be used to access the resources that the platform offers. | 3 |  | YES | 3 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | GCP Migration |  |  |  |  | Team is working on API modernization | No | VM
22605 | eMIS - Miscellaneous Invoicing System | In Production | eMIS | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Perform issuance of Miscellaneous invoices (Notas Fiscais) for all Ford Brazil plants |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
17599 | NFe - Nota Fiscal Eletronica Brasil | In Production | NFe | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | NFe system is composed by 2 subsystems, NFe (web module), NF & LL (Mainframe module for electronic invoices) that is in charge to validate invoices. Electronic invoice process demands government permission. This permission is granted by means of a webservice communication. The government communication can result in different responses like: Authorization, in this case a Danfe (Printed assisting document for electronic invoice) is emitted and the material is released; Rejection, the invoice must be corrected and resent; or denied, so the invoice cannot be generated. Also is possible to cancel an invoice once respected legal period established by local state rule or turn it unused, in case the invoice will not be resent and its number need to be canceled. | 4 |  | YES | 4 | TSWEEN16 | PLM | VM | Q4 2026 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-05-30 |  | In-Progress | Green | 2025-05-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
22605 | eMIS - Miscellaneous Invoicing System | In Production | eMIS | OCETO | DBRIGHEN | RCORDEI1 | AGERBAUD | NMORALE7 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Perform issuance of Miscellaneous invoices (Notas Fiscais) for all Ford Brazil plants |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
11976 | Emergency Order Referral System | In Production | EORS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Process emergency orders from dealers. |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
11976 | Emergency Order Referral System | In Production | EORS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Process emergency orders from dealers. |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
50814 | NextGen Release Platform(DevSecOps) | In Production | NGRP | EPEO | LFULCHER | KMAHAJAN | TKLEMER | TKLEMER | Copper | Non S-Ox | 11 | No | Yes | - | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | NextGen Release Platform enables teams to perform their Continuous Integrations, Continuous Delivery. | 4 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
52077 | Electronic Whitepaper System | In Production | Whitepaper | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | #N/A | #N/A | Policy | 311 | EWHITEPAPER IS A WEB BASED APPLICATION USED TO CREATE A WHITEPAPER TO EVALUATE THE EFFECT(S) OF HARDWARE OR SOFTWARE CHANGES FOR ONE OR MORE PROGRAMS ON TAILPIPE & EVAPORATIVE EMISSIONS CERTIFICATION, FUEL ECONOMY, OBD, COMPLIANCE, AND OTHER REGULATORY MATTERS. WHITEPAPER PROVIDES SOME BASIC CONFIDENCE THAT THE OBD CALIBRATION IS WORKING PROPERLY ON THE MOST BASIC LEVEL. ALSO IT PREVENTS RECALL DUE TO LATE CHANGES OFTEN OCCUR ON PROGRAMS THAT NEED TO BE VALIDATED FOR UNINTENTIONAL IMPACT TO OBD FUNCTIONALITY. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
965 | ELECTRONIC RAW MATERIALS ACQUISITION (ERMA) | In Production | eRMA | I-ERP | SARAUJO3 | KSYROCKI | LRUMPTZ | SNAG1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | SARAUJO3 | SARAUJO3 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Erma (Electronic Raw Materials Acquistion) will facilitate the purchase and sale of Ford negotiated raw material for non-Ford production part suppliers. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
965 | ELECTRONIC RAW MATERIALS ACQUISITION (ERMA) | In Production | eRMA | I-ERP | SARAUJO3 | KSYROCKI | LRUMPTZ | SNAG1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Erma (Electronic Raw Materials Acquistion) will facilitate the purchase and sale of Ford negotiated raw material for non-Ford production part suppliers. |  |  | YES | 4 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
15659 | NetAgent NA Database | In Production | NetAgentDB | FORD CREDIT | IPANKAJ | DSINACOL | SVYSYARA | RPARAME4 | Bronze | Non S-Ox | 311 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | This application nGenera Netagent has been in use until June 2023. It is a 2-way Secure email SaaS product from vendor Moxie (now under NICE CXone) for use by FC Agents in NA, Canada and Argentina. This functionality has been integrated within MSDynamics using a Microsoft solution. In order retain email communication data as per GIS requirements (C+6), this application has been renamed to Netagent NA Database and the historical data is stored on SQL database ITO080643. Database has to be decommissioned during 2030 AFR unless there is a change in retention period or to retain for any suspension orders. | 1 |  | YES | 2 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
965 | ELECTRONIC RAW MATERIALS ACQUISITION (ERMA) | In Production | eRMA | I-ERP | SARAUJO3 | KSYROCKI | LRUMPTZ | SNAG1 | Silver | S-Ox In Scope | 331 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Erma (Electronic Raw Materials Acquistion) will facilitate the purchase and sale of Ford negotiated raw material for non-Ford production part suppliers. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
22016 | Electronic Pre-Delivery Inspection Database | In Production | ePDI DB | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Bronze | Non S-Ox | 211 | No | Yes | - | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Pre Delivery Inspection checklist for dealer technicians to complete prior to new vehicle delivery. The checklist questions are customized and targeted to specific vehicles. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
22016 | Electronic Pre-Delivery Inspection Database | In Production | ePDI DB | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Bronze | Non S-Ox | 211 | No | Yes | - | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Pre Delivery Inspection checklist for dealer technicians to complete prior to new vehicle delivery. The checklist questions are customized and targeted to specific vehicles. |  |  | YES | 4 | RKENNEL | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
22016 | Electronic Pre-Delivery Inspection Database | In Production | ePDI DB | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Bronze | Non S-Ox | 211 | No | Yes | - | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Pre Delivery Inspection checklist for dealer technicians to complete prior to new vehicle delivery. The checklist questions are customized and targeted to specific vehicles. |  |  | YES | 4 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
22016 | Electronic Pre-Delivery Inspection Database | In Production | ePDI DB | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Bronze | Non S-Ox | 211 | No | Yes | - | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Pre Delivery Inspection checklist for dealer technicians to complete prior to new vehicle delivery. The checklist questions are customized and targeted to specific vehicles. |  |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
13194 | Electronic Powertrain Program Planning | In Production | e3P | ISIT | MNOWICK1 | LSRINIVA | ESATISH | JLUCAS1 | Bronze | Non S-Ox | 311 | No | Yes | In-House | MNOWICK1 | MNOWICK1 | Advanced PD and Tech | Industrial System IT | e3P (Electronic Powertrain Program Planning) is a web-based application for authoring, approval and documentation of Powertrain engineering assumptions and related documents. The Assumption module is used for the authoring, approval and documentation of engineering assumption needed to support Powertrain programs. The 5 Panel module is used for the authoring and documentation of 5 Panel sheets needed to support Powertrain programs. The PTBOM (Powertrain Bill of Material) module is an easy to use tool to view and compare different BOMs (WERS, CMMS and CAD). It also enables the users to manage the Complexity Matrix and audit the Bill of Material. e3P is therefore the central repository of engineering assumptions and CPMT 5 Panel sheets. These are accessible via the Ford internal web with access control. Engineering assumptions are Ford proprietary and 5 Panel are Ford confidential information. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
23752 | NetAgent FCE | In Production | NetAgent | FORD CREDIT | IPANKAJ | DSINACOL | SVYSYARA | RPARAME4 | Bronze | Non S-Ox | 311 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | This NetAgent application (earlier owned by Moxie) is a Vendor SaaS product from NICE CXone for 2-way Secured email communication mainly with Ford Credit Customers and supports Europe markets. Data stored by this application may contain SPII. A new product/solution may replace this in near future as part of Contact Center of the Future (CCOF) program. | 1 |  | YES | 2 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
13194 | Electronic Powertrain Program Planning | In Production | e3P | ISIT | MNOWICK1 | LSRINIVA | ESATISH | JLUCAS1 | Bronze | Non S-Ox | 311 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | e3P (Electronic Powertrain Program Planning) is a web-based application for authoring, approval and documentation of Powertrain engineering assumptions and related documents. The Assumption module is used for the authoring, approval and documentation of engineering assumption needed to support Powertrain programs. The 5 Panel module is used for the authoring and documentation of 5 Panel sheets needed to support Powertrain programs. The PTBOM (Powertrain Bill of Material) module is an easy to use tool to view and compare different BOMs (WERS, CMMS and CAD). It also enables the users to manage the Complexity Matrix and audit the Bill of Material. e3P is therefore the central repository of engineering assumptions and CPMT 5 Panel sheets. These are accessible via the Ford internal web with access control. Engineering assumptions are Ford proprietary and 5 Panel are Ford confidential information. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
11989 | Electronic Parts Return System | In Production | EPRS | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Bronze | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | Ford Authorized Distributors and Powertrain Remanufacturers use this system to submit claims and return parts to Ford |  |  | YES | 1 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
24086 | My Next Vehicle | In Production | MNV | FORD CREDIT | IPANKAJ | VSUNDA21 | GSRINI34 | ROBRIEN3 | Bronze | Non S-Ox | 111 | No | Yes | In-House | IPANKAJ | VSUNDA21 | Ford Credit Services | Ford Credit (FMCC) | Web Application used to increase Retail/Lease Sales by offering Account Manager users options for future Retail/Lease purchases based on account specific data. | 4 |  | YES | 4 | SRAISIN1 | PLM | VM | Q2 2025 | EDC New Hypervisor | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
20372 | Electronic Interchange (EI) | In Production | AREI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | The goal of this system is to fulfill with government regulations with respect to interchange electronics files between Ford and AFIP.This system takes information from Ford Pacheco Invoicing Systems gives them the appropiate format and sends the information to AFIP WEB services. Afterwards it receives the answer from AFIP. |  |  | YES | 5 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
20372 | Electronic Interchange (EI) | In Production | AREI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | The goal of this system is to fulfill with government regulations with respect to interchange electronics files between Ford and AFIP.This system takes information from Ford Pacheco Invoicing Systems gives them the appropiate format and sends the information to AFIP WEB services. Afterwards it receives the answer from AFIP. |  |  | YES | 5 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
20372 | Electronic Interchange (EI) | In Production | AREI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | The goal of this system is to fulfill with government regulations with respect to interchange electronics files between Ford and AFIP.This system takes information from Ford Pacheco Invoicing Systems gives them the appropiate format and sends the information to AFIP WEB services. Afterwards it receives the answer from AFIP. |  |  | YES | 5 | TSWEEN16 | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
55007 | MPL-8502-BROADCAST | Planned | MPL-8502BC | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | SSENTH15 | Copper | Non S-Ox | - | No | Yes | - | SROYCHOU | BGANESH | Manufacturing Staffs | - | DPA solution : 8502 - Solve Code Update for Broadcast Commodities | 16 |  | YES | 3 | BWUNNAVA | PLM | VM | Q2 2025 | Complete Migration to SaaS | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2025-12-15 |  | Planned |  | No | [8 empty] | SaaS | Priya | 2025-03-11 |  |  | Timeline moved from Q2 to Q4 (DB VM will move in Q4 2025) | No | VM
20372 | Electronic Interchange (EI) | In Production | AREI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | The goal of this system is to fulfill with government regulations with respect to interchange electronics files between Ford and AFIP.This system takes information from Ford Pacheco Invoicing Systems gives them the appropiate format and sends the information to AFIP WEB services. Afterwards it receives the answer from AFIP. |  |  | YES | 5 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
52951 | Electronic GCST | In Production | eGCST | I-ERP | SARAUJO3 | KSYROCKI | PBUKKAPA | SNAG1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Supply Chain | 211 | FORD DEVELOPED SOFTWARE FOR PURCHASING TO MANAGE APPROVAL OF SOURCING APPROACH REQUESTS AND DOA REQUESTS TO AWARD CONTRACTS TO SUPPLIERS. |  | Springboot | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-01 | Complete | Blue | 2025-03-15 | 2025-03-01 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Praveen | 2025-03-05 |  |  |  | No | Java < v21
12834 | Electronic Funds Transfer(EFT-CBS) | In Production | 2003CBSEFT | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox Out of Scope | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Finance | FCSD Tech | Add Electronic Fund Transfer capability to the Centralized Billing System. |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12834 | Electronic Funds Transfer(EFT-CBS) | In Production | 2003CBSEFT | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox Out of Scope | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Finance | FCSD Tech | Add Electronic Fund Transfer capability to the Centralized Billing System. |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
52488 | electronic Design Change Management | In Production | eDCM | I-ERP | SARAUJO3 | KSYROCKI | PBUKKAPA | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | JANDE559 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Develop online supplier RFI (Request for Information) process in support of enhanced engineering design change management process. Support increased buyer visibility and involvement to better manage cost creep. |  |  | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-01-03 | 2025-01-01 | Complete | Blue | 2025-01-18 | 2025-01-16 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-05 |  |  | DB Decom Completed. Validated. | No | SQL
52488 | electronic Design Change Management | In Production | eDCM | I-ERP | SARAUJO3 | KSYROCKI | PBUKKAPA | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Develop online supplier RFI (Request for Information) process in support of enhanced engineering design change management process. Support increased buyer visibility and involvement to better manage cost creep. |  | Springboot | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-01 | 2025-03-01 | Complete | Blue | 2025-03-01 | 2025-03-01 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Praveen | 2025-03-05 |  |  |  | No | Java < v21
14583 | Electronic Design Analysis Request | In Production | eDAR | ISIT | MNOWICK1 | LSRINIVA | ESATISH | JLUCAS1 | Copper | Non S-Ox | 111 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Enterprise Technology | Industrial System IT | The Electronic Design Analysis Request (eDAR) system is a web-based application designed to track project requests from inception through completion. The customer requests work to be done via the online interface, an automated email is sent to the department/section supervisor for evaluation. The supervisor can approve or reject project requests. If approved the project is assigned a project leader and team members who can track the projects progress through completion. The numerous individual eDAR systems were merged into the new eDar v2.0 J2EE system in 2007. |  | Java Struts | YES | 2 | BWUNNAVA | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
14583 | Electronic Design Analysis Request | In Production | eDAR | ISIT | MNOWICK1 | LSRINIVA | ESATISH | JLUCAS1 | Copper | Non S-Ox | 111 | No | Yes | In-House | MNOWICK1 | MNOWICK1 | Enterprise Technology | Industrial System IT | The Electronic Design Analysis Request (eDAR) system is a web-based application designed to track project requests from inception through completion. The customer requests work to be done via the online interface, an automated email is sent to the department/section supervisor for evaluation. The supervisor can approve or reject project requests. If approved the project is assigned a project leader and team members who can track the projects progress through completion. The numerous individual eDAR systems were merged into the new eDar v2.0 J2EE system in 2007. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
53848 | Electrification Platform Services | In Production | ELPS | EVDD | RJOHN813 | SLYTLE | CROE10 | ASHARM98 | Silver | Non S-Ox | 222 | No | Yes | - | #N/A | #N/A | Enterprise Technology | 222 | ELECTRIFICATION PLATFORM SERVICES - PLATFORM FOR CONSUMABLE ELECTRIFICATION DATA SERVICES AND EXPERIENCES FOR INTERNAL & EXTERNAL CUSTOMERS |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50293 | ELD Calibration | In Production | ELD Cal | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Silver | Non S-Ox | 12 | Yes | No | COTS | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Engine Lab Calibration Tool |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
54986 | MIcrosoft Office 365 | In Production | Office 365 | EPEO | SRUNSON | ASTONE31 | JJAFANO | KGRIFKA | Copper | Non S-Ox | - | No | Yes | In-House | SRUNSON | ASTONE31 | Enterprise Technology | EPEO | Management of Office 365 cloud environment | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
20240 | eHub-ESB | In Production | eHub-ESB | OCETO | TVASU | KBALAS13 | RMODI2 | WJUSTICE | Gold | Non S-Ox | 213 | No | Yes | COTS | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | Biztalk Enterprise Service Bus for internal and external business partner (suppliers, dealers, exchanges) messaging. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q3 2027 | On-Prem | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | SQL
52066 | Manufacturing Gamification | In Production | MG | ISIT | OTHERS | CGOLDMA4 | LGARDN50 | AELANGO | Copper | Non S-Ox | 211 | Yes | No | In-House | AHOROVIT | CGOLDMA4 | Manufacturing Engineering | - | Application created to provide operators with real-time quality feedback, creating intrinsic motivation to improve and exceed in their work. | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-06-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Priya | 2025-03-05 |  |  | PCF app ready for Decommission. This app is dependent on the parent App 50273- Manf AEP for decommission of the PCF Org | No | VM
21593 | eGlobal Master Timing | In Production | eGMT | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | LSRINIVA | esatish | Advanced PD and Tech | Industrial System IT | eGMT is a web-based tool for tracking Powertrain tasks for vehicle program plans and create a single master program database that would be shared among downstream applications that support Powertrain Operations. Powertrain Project Management Analysts (PMA) and Engineers uses eGMT to oversee areas of responsibility and make revisions as permitted. Powertrain sub-systems include Engine, Transmission, Axles, eDrive/Battery and Calibration for Engine & eDrive of the affected vehicle programs. |  | WAS | YES | 1 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
51092 | Manufacturing Vehicle Distribution - Dashboards and Analytics | In Production | MVD - DNA | ISIT | VVIJAY55 | RADAM10 | VDODDAMR | SSENTH15 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Manufacturing Staffs | Industrial System IT | Finished Vehicle logistics operations dashboards |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13541 | EESE ELECTRICAL DATA MANAGEMENT | In Production | EESEDATA | ISIT | OTHERS | KBERISTA | JPAWLOSK | GRAO3 | Copper | Non S-Ox | 111 | Yes | No | In-House | CPAPADOM | KBERISTA | Advanced PD and Tech | - | management of electrical BOM data. Includes Web interface to existing electrical databases (UniBOM). |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
13541 | EESE ELECTRICAL DATA MANAGEMENT | In Production | EESEDATA | ISIT | OTHERS | KBERISTA | JPAWLOSK | GRAO3 | Copper | Non S-Ox | 111 | Yes | No | In-House | CPAPADOM | CPAPADOM | Advanced PD and Tech | - | management of electrical BOM data. Includes Web interface to existing electrical databases (UniBOM). |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
21939 | LGT - MP&L DATAWAREHOUSE (MASTER) | In Production | LGT | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 211 | No | Yes | In-House |  |  | Manufacturing Staffs | - | Database with MP&L information (Master - KA System) that is used by MP&L staff to get information and compose some business reports. | 4 |  | YES | 1 | TSWEEN16 | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | VM does not exist. To be verified in apptio next month | No | VM
52448 | KX Wind Tunnel Software | Planned | KX | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | - | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | Advanced PD and Tech | Industrial System IT | Kx for Automotive is a high-performance, cost-effective data platform for ingesting, processing and analyzing real-time, streaming and historical data from multiple sources in the automotive world - data that fuels future business models and innovations. From trackside telemetry in F1, to R&D and aerodynamics in wind tunnels, from autonomous cars in motion to their digital twins in simulation, from the sensors that control them to the machines that make them, Kx for Automotive has the power and scalability to provide real-time analytics, instantaneous feedback and valuable insights into the vast amounts of data they produce. | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-03-31 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2 | Decommission | Priya | 2025-03-03 |  |  | Decommission complete. Validation in Progress | No | VM
8994 | EEBPR | In Production | EEBPR | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Gold | Non S-Ox | 211 | Yes | No | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The Engineering Expenses Budget Performance Reporting (EEBPR)system tracks engineering expense and labor data for North American Product Development (NAPD) locations. In addition, EEBPR allocates expenses to work tasks, so that NAPD can track the cost of vehicle programs. EEBPR's labor reporting allows NAPD management to track labor and overtime costs by program and department. Provides Budget Performance Reporting on Expense items, Forecasting, European Cycle Plan, and Business Plan for Product Development/Finance. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
8994 | EEBPR | In Production | EEBPR | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Gold | Non S-Ox | 211 | Yes | No | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The Engineering Expenses Budget Performance Reporting (EEBPR)system tracks engineering expense and labor data for North American Product Development (NAPD) locations. In addition, EEBPR allocates expenses to work tasks, so that NAPD can track the cost of vehicle programs. EEBPR's labor reporting allows NAPD management to track labor and overtime costs by program and department. Provides Budget Performance Reporting on Expense items, Forecasting, European Cycle Plan, and Business Plan for Product Development/Finance. | 79 |  | YES | 3 | TSWEEN16 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
8994 | EEBPR | In Production | EEBPR | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Gold | Non S-Ox | 211 | Yes | No | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | The Engineering Expenses Budget Performance Reporting (EEBPR)system tracks engineering expense and labor data for North American Product Development (NAPD) locations. In addition, EEBPR allocates expenses to work tasks, so that NAPD can track the cost of vehicle programs. EEBPR's labor reporting allows NAPD management to track labor and overtime costs by program and department. Provides Budget Performance Reporting on Expense items, Forecasting, European Cycle Plan, and Business Plan for Product Development/Finance. |  |  | YES | 3 | TSWEEN16 | PLM | Mainframe | Q1 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
22687 | eDesign Order System | In Production | eDOS | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 311 | EDESIGN ORDER SYSTEM (EDOS) IS USED TO PROVIDE DESIGN DIRECTION AND/OR RECORD DESIGN CHANGES THAT MAY OCCUR DURING THE DESIGN PROCESS. EDOS IS ORIGINATED FROM FORD ENGINEERING. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
51175 | EDDMS | In Production | EDDMS | EPEO | ARAJKUMA | MSAGNIA | SPATIL9 | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | In-House | ARAJKUMA | MSAGNIA | Advanced PD and Tech | - | department database |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53724 | iNexus | In Production | iNexus | I-ERP | SARAUJO3 | VANURAD2 | PCHITIYA | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Change Management Tracking system to integrate Ariba and S4 | 4 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 75% | 50% | 50% | 100% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | VM
12418 | eDB: Electronic Document Base | In Production | EuFA-eDB | I-ERP | SFRANCI8 | AKANSKI | RDAVIES6 | LWU14 | Silver | Non S-Ox | 11 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Enterprise Technology | Integrated Enterprise Resource Planning (I-ERP) | eDB is a J-EE based program that runs in WAS Liberty on CAAS. It connects to an Oracle database where it stores application screen definitions, application role based security data and application database connection credentials (Passwords Encrypted). eDB is accessed via web browser. eDB hosts several applications, whereby the users of each application visits the EDB website, plus two URL parameters, Site ID and Screen No. eDB retrieves the requested screen definition from its database using these parameters, and in conjunction with the users CDS ID, dynamically renders the appropriate application screen. The screen will include controls that retrieve application data from the applications database (eDB database does not contain any business data). |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
51747 | I-ERP Direct Material Source to Contract | In Production | IERPSC | I-ERP | SARAUJO3 | CBISWADI | TSUNDARA | SNAG1 | Gold | S-Ox Out of Scope | 221 | No | Yes | Managed by 3rd Party Purchased Service | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | used for requesting supplier quoting events program approval | 3 |  | YES | 3 | TSWEEN16 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 75% | 100% | 75% | 75% | 50% | 50% | 100% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | VM
12418 | eDB: Electronic Document Base | In Production | EuFA-eDB | I-ERP | SFRANCI8 | AKANSKI | RDAVIES6 | LWU14 | Silver | Non S-Ox | 11 | No | Yes | In-House | SFRANCI8 | AKANSKI | Enterprise Technology | Integrated Enterprise Resource Planning (I-ERP) | eDB is a J-EE based program that runs in WAS Liberty on CAAS. It connects to an Oracle database where it stores application screen definitions, application role based security data and application database connection credentials (Passwords Encrypted). eDB is accessed via web browser. eDB hosts several applications, whereby the users of each application visits the EDB website, plus two URL parameters, Site ID and Screen No. eDB retrieves the requested screen definition from its database using these parameters, and in conjunction with the users CDS ID, dynamically renders the appropriate application screen. The screen will include controls that retrieve application data from the applications database (eDB database does not contain any business data). |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q2 2027 | Version Upgrade | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [14 empty] | No | Java < v21
11353 | eCommitment | In Production | ECOMMIT | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Ecommitment is a laptop based application that provides zone managers an input mechanism for vehicle wholesale numbers. The tool is used to submit wholesale commitment to dealers. The applications also provides North American Zone Managers with a means for analysis and tracking of data during monthly wholesale. The ecommit web reports are also part of the application. These reports provide web-based reports to the Zone Managers as to the current state of the wholesale period. |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q4 2026 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11353 | eCommitment | In Production | ECOMMIT | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Ecommitment is a laptop based application that provides zone managers an input mechanism for vehicle wholesale numbers. The tool is used to submit wholesale commitment to dealers. The applications also provides North American Zone Managers with a means for analysis and tracking of data during monthly wholesale. The ecommit web reports are also part of the application. These reports provide web-based reports to the Zone Managers as to the current state of the wholesale period. |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
11353 | eCommitment | In Production | ECOMMIT | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Gold | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Ecommitment is a laptop based application that provides zone managers an input mechanism for vehicle wholesale numbers. The tool is used to submit wholesale commitment to dealers. The applications also provides North American Zone Managers with a means for analysis and tracking of data during monthly wholesale. The ecommit web reports are also part of the application. These reports provide web-based reports to the Zone Managers as to the current state of the wholesale period. |  |  | YES | 4 | NKANDULA | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
50137 | HPe OneView Suite | In Production | HPe-OV | EPEO | LFULCHER | KMAHAJAN | CDOSHI | NMANIVAS | Bronze | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | HPE OneView is a software package which provides easy and centralized management of HPE hardware. | 24 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
53416 | eCommerce Payment Integration | In Production | EPI | FORD CREDIT | IPANKAJ | VNAVEEN1 | PMATHIV3 | ROBRIEN3 | Platinum | Non S-Ox | 312 | No | Yes | In-House | IPANKAJ | VNAVEEN1 | Ford Credit Services | Ford Credit (FMCC) | Capabilities Supporting the Payment Integration layer between GUX, SAP and Payment Vendors |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | SQL
757 | Homologation Document Distribution System | In Production | EuOGC-HDDS | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Bronze | Non S-Ox | 212 | No | Yes | COTS | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Document scanning storing retrieval system for Approval Documents Web enabled document delivery. Product Name TypMaster DD Module by Supplier T-Systems. Also utilised by CGN-Technik for document storage. | 8 |  | YES | 3 | BWUNNAVA | PLM | VM | Q2 2025 | EDC CaaS | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-03-15 |  | Planned |  | No | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8 | GCP Migration | Priya | 2025-03-05 | 3/3/2025 - Initial entry, 3/5/2025 - Updated the PDO timeline |  | Plan is to move to On-Prem EDC CaaS with Oracle running in ExaCC as a first step. Later, move to GCP CaaS along with Postgres in Q4 2025. | No | VM
53416 | eCommerce Payment Integration | In Production | EPI | FORD CREDIT | IPANKAJ | VNAVEEN1 | PMATHIV3 | ROBRIEN3 | Platinum | Non S-Ox | 312 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Capabilities Supporting the Payment Integration layer between GUX, SAP and Payment Vendors |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
56911 | eCommerce Marketplace Portal - EU | Planned | EMP-EU | FORD PRO & FCSD TECH | TJUNIPER | GDRAGAZI | SMOHAM32 | JCOY3 | Bronze | Non S-Ox | 222 | No | Yes | In-House | TJUNIPER | RHOWEL46 | Marketing & Sales | - | eCommerce Marketplace Portal supports Ford's eCommerce program by faciliating dealer onboarding and eCommerce order management |  | Springboot | YES | 2 | RKENNEL | PLM | Java < v21 | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | Java 21 | [5 empty] | No | Java < v21
12402 | HC: Unicare RTW - Return to Work (Ford Side) | In Production | RTW | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | Batch interface process that permits Unicare Disability to query DLORS timekeeing records to determine if employee has returned to work when receiving Disability benefits. | 3 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
56911 | eCommerce Marketplace Portal - EU | Planned | EMP-EU | FORD PRO & FCSD TECH | TJUNIPER | GDRAGAZI | SMOHAM32 | JCOY3 | Bronze | Non S-Ox | 222 | No | Yes | In-House | TJUNIPER | RHOWEL46 | Marketing & Sales | - | eCommerce Marketplace Portal supports Ford's eCommerce program by faciliating dealer onboarding and eCommerce order management |  | Springboot | YES | 2 | RKENNEL | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | SQL
50765 | eCommerce Marketplace Portal | In Production | EMP | M&S TECH | RKLEINSM | MMILBOC1 | TKOPCZY1 | MPINRED1 | Bronze | Non S-Ox | 222 | No | Yes | Managed by 3rd Party Purchased Service | RKLEINSM | MMILBOC1 | Marketing & Sales | 222 | eCommerce Marketplace Portal supports Ford's eCommerce program by facilitating delear onboarding and eCommerce order management |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50765 | eCommerce Marketplace Portal | In Production | EMP | M&S TECH | RKLEINSM | MMILBOC1 | TKOPCZY1 | MPINRED1 | Bronze | Non S-Ox | 222 | No | Yes | Managed by 3rd Party Purchased Service | RKLEINSM | MMILBOC1 | Marketing & Sales | Marketing, Sales and Service | eCommerce Marketplace Portal supports Ford's eCommerce program by facilitating delear onboarding and eCommerce order management |  |  | YES | 3 | NKANDULA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
839 | GSAR: Global System for Analytics & Reporting-AWS | In Production | GSAR | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | JDEGUZMA | RMEHTA3 | PD Operations and Quality | Industrial System IT | Provides a database of warranty claims and vehicle information that supports common global warranty reporting, analysis, and feedback processes for model years 1991 and forward. Customers have the flexibility to request on-line reports using a wide range of selection criteria and a variety of output formats. Primary Users: Analysts in Quality, Engineering, Finance, Vehicle Operations and Powertrain Plants. | 10 |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q2 2025 | EDC CaaS and New EDC Hypervisor | Modernize | 2025-06-15 | 2025-03-15 | 2025-03-15 | Complete | Blue | 2025-03-15 | 2025-03-15 | Complete |  | Yes | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | EDC CaaS | Saran | 2025-03-11 |  |  | Application Architecture is complex, so only PCF portion was handled as a first release. we have total of 7 IBM LPAR AIX servers (they do not use vmarea) 3 Linux servers have been decomissioned . There are Zero VM WARE servers | Yes | VM
52828 | ECOEM | In Production | ECOEM | EVDD | JWASNIC1 | MBOMMANA | SPRADHAN | SPRADHAN | Gold | Non S-Ox | 222 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 222 | ECOEM INTEGRATION APIS |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
55002 | ECOA Letter Process | In Development | ECOA | FORD CREDIT | IPANKAJ | RRAJESH8 | RSUDHIR | JMANI | Silver | Non S-Ox | 332 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | - | ECOA Letter Process is a nighlty batch run to assign ECOA letters to conditioned or rejected offers |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q3 2027 | Version Upgrade | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
11594 | ECI: Enhanced Concern Identification | In Production | ECI-CDR | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 231 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Identify/verify emerging potentially critical product concerns faster and increase Customer Satisfaction by improving access to corporate quality & satisfaction data repositories & analysis. | 72 |  | YES | 4 | BWUNNAVA | PLM | BO | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-30 | 2025-12-30 |  | In-Progress | Green | 2026-02-28 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | EXCEPTION BASED. Approval from Tom Culler received to remain on platform.Does not require any migration, business will be using app til decommission date 31-Dec-2025. For 2026, our team will support business through alternate solution | No | DA
11594 | ECI: Enhanced Concern Identification | In Production | ECI-CDR | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 231 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Identify/verify emerging potentially critical product concerns faster and increase Customer Satisfaction by improving access to corporate quality & satisfaction data repositories & analysis. |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-06-15 |  | Planned |  | No | [14 empty] | No | Java < v21
11594 | ECI: Enhanced Concern Identification | In Production | ECI-CDR | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 231 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Identify/verify emerging potentially critical product concerns faster and increase Customer Satisfaction by improving access to corporate quality & satisfaction data repositories & analysis. |  |  | YES | 4 | BWUNNAVA | PLM | WAS | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-06-15 |  | Planned |  | No | [14 empty] | No | Java < v21
21334 | GOTD - Order Entry and Management | In Production | GOTD-OMCC | M&S TECH | FHIRSH | VDONTHY | PSANDHY4 | CKEMPSKI | Bronze | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Order Entry and Management provides the UI and supporting service functionality that enables dealers, internal user and consumers to create or amend orders in the Global Orderbank. Additional functionality will be provided to support reduced inventory management for the Enterprise and to enable any authorised stakeholder to search for and view an order they are interested in. Several key business functions are in scope including bulk order management, plus various administrative actions such as creating and managing template orders and work in progress. | 6 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q2 2025 | EDC CaaS | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 100% | 75% | 25% | [5 empty] | GCP Migration | [5 empty] | No | VM
6300 | ECDB - European Currency Database | In Production | EuAS-ECDB | I-ERP | SFRANCI8 | AKANSKI | TPRASAD1 | LWU14 | Gold | S-Ox In Scope | 132 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | - | European Currency Database provides a common source of foreign currency exchange rates for use by other application systems and for the generation of online reporting from the database. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
13581 | eCCO UK | In Production | EuHR-eCCO | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | Intranet hosted company car ordering application for Ford Motor Company UK. This enables authorised employees to order company cars, job cars and pool cars on-line. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | Planned Q2 2025 for decommission. Running in ITO servers using .Net technology | No | SQL
50924 | GOTD - Global Order Management Services | In Production | GOMS | M&S TECH | FHIRSH | VDONTHY | NGUDIME1 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | Services to provide Order Management capabilities | 60 |  | YES | 4 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | GCP Migration |  |  |  |  | Decom is confirmed after DB Upgrade. | No | VM
21254 | eCATS Centralized Reporting & Data Repository | In Production | eCATS-RL | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Copper | Non S-Ox | 221 | Yes | No | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | Industrial System IT | eCATS is vend-suppt. sys used by veh.assy plants to program/config/check/record the ECUs in each vehicle & test the veh.fns those ECUs ctrl. Has ReportLogiq(RL) web-reporting, but also feeds corp.sys's for supporting/by vehs in service. Prod.process uses per-plant config of plant floor stns & local plant file/app.svr. Latter acts as receiver of stns' veh.results +/- a distrib&archive of veh.build-specs fr. other systems that steer eCATS stns' veh.procs. Plant hosting aids prod.process resilience. RL & corp.feeds hosted on svrs often at Dearborn unless WAN-perf. &/ JV-rules dictate regional / plant-located. eCATS 2.0 into some plants 2016+ brings unmanned 'Mini' stns for more progr. of ECUs, initially only upstream of existing eCATS areas. W/o user interf. for oper/maint, mgmt of Minis uses plant-based web/service fn AdminLogiq(AL). NB: eCATS often called End-Of-Line - but term neither limited to eCATS nor role. ECU progr. also called flashing - but InPlant Flash is name of NA-only sys w different technol |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
20814 | Global Warranty Finance System | In Production | GWFS | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Common Global IT tool to support Warranty Reserve Process. - Supports consistent application of Warranty Rules of The Road (RoTR). - Elimination of complex manual processes on high risk reserve -- improve control environment. (Wholly Excel based today). - Provides greater granularity at market / vehicle line level to support PF3 reporting and concurrent close (US and Local GAAP). - Enhanced cost analysis reporting based on physicals. - Key enabler to reserve centralization to Europe (delivers cash tax benefit). - Increased employee satisfaction | 10 |  | YES | 5 | TSWEEN16 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | Yes | 100% | 50% | 25% |  |  |  | 25% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | VM
51773 | Ecall | In Production | Ecall | EVDD | JWASNIC1 | JVEDANAY | CRAMESH5 | JVEDANAY | Silver | Non S-Ox | 223 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 223 | THIS APPLICATION IS TO ENABLE THE END CUSTOMER TO GET CONNECTED TO OR DISCONNECTED FROM THE CLOUD. THIS APPLICATION IS INTENDED TO SUPPORT ONLY FOR FB3 EUROPE VEHICLES |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
20811 | ECAD - Zuken E3 | In Production | ECAD E3 | ISIT | MNOWICK1 | PBORGAO1 | IAKLEH | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | COTS | MNOWICK1 | MNOWICK1 | Advanced PD and Tech | Industrial System IT | Application for ECAD - Zuken E3 Project (19057)Zuken E3 is a complete and open CAD solution for design and documentation of electrical and automation systems. It also includes integrated logic-oriented functionality for the creation of cabling and harnesses. Zuken E3 is based upon common component database and symbol libraries and ensures a unique representation of all elements of the circuit diagrams, to produce accurate and error-free documentation. It also allows for creation of block diagrams, under logic control, that provide an overview of all electrical and electronic elements. Connections between functional modules can be achieved using individual conductors, shielded or twisted cables or bundled cables. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
21150 | Global vehicle Distribution Solution | In Production | GVDS | ISIT | VVIJAY55 | RADAM10 | DASHOK1 | SSENTH15 | Gold | S-Ox In Scope | 232 | No | Yes | COTS | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | The Global Vehicle Distribution Solution (GVDS) application has been established in order to support the global vehicle distribution process. Main goal of the application is the implementation of logistics optimization for finished vehicles. | 14 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Decommission | Saran | 2025-03-18 |  |  | App is moving to SaaS | No | VM
20811 | ECAD - Zuken E3 | In Production | ECAD E3 | ISIT | MNOWICK1 | PBORGAO1 | IAKLEH | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | COTS |  |  | Advanced PD and Tech | Industrial System IT | Application for ECAD - Zuken E3 Project (19057)Zuken E3 is a complete and open CAD solution for design and documentation of electrical and automation systems. It also includes integrated logic-oriented functionality for the creation of cabling and harnesses. Zuken E3 is based upon common component database and symbol libraries and ensures a unique representation of all elements of the circuit diagrams, to produce accurate and error-free documentation. It also allows for creation of block diagrams, under logic control, that provide an overview of all electrical and electronic elements. Connections between functional modules can be achieved using individual conductors, shielded or twisted cables or bundled cables. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
53364 | EC GCP MIGRATION | Planned | GcpMigrate | EVDD | JWASNIC1 | GSUMNER2 | FMARZEN | CHOWEL12 | Copper | Non S-Ox | - | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | - | THIS APPLICATION WILL BE USED FOR TRYING OUT VARIOUS GCP SERVICES SO GCP MIGRATION TECH TEAM CAN PROVIDE GUIDANCE TO PRODUCT TEAMS THAT ARE MIGRATING FROM AZURE TO GCP. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
13554 | eBatch Communication Module (eBCM) | In Production | eBCM | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Silver | Non S-Ox | 212 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | eBCMWeb services is the file transfer interface to BCM covering entire Europe(3500) via public internet. eBCM web is the sub-function on the same platform used by approx. 100 Finland /German dealers (out of 3500 in Europe). |  |  | YES | 4 | NKANDULA | PLM | Java Struts | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
13554 | eBatch Communication Module (eBCM) | In Production | eBCM | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Silver | Non S-Ox | 212 | No | Yes | In-House | KPINNU | KPINNU | Marketing & Sales | Marketing, Sales and Service | eBCMWeb services is the file transfer interface to BCM covering entire Europe(3500) via public internet. eBCM web is the sub-function on the same platform used by approx. 100 Finland /German dealers (out of 3500 in Europe). |  |  | YES | 4 | NKANDULA | PLM | Oracle | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
51682 | Global Translation Handler Interface | In Production | GTHI | I-ERP | SFRANCI8 | SDHANAL3 | MWARRE10 | LWU14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Global Translation Handler Interface extracts the feeds with pricing information from VI&D and maps Sales codes to WERS codes with pricing data if available. Then, creates the XML message in the format required by SAP and sends data to SAP or other systems for sales order creation. This application uses SOE VOLFMS webservice to map Sales codes to WERS codes. This interface assumes VOLFMS to return WERS codes from every sales code given as INPUT - every Sales code on the Order is mapped to WERS in SOE. There is no edit in this interface process which how the data is retrieved from VI&D it will be passed on to the SAP or other systems as origin on XML message format. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 50% | 50% |  |  |  | 50% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | VM
13554 | eBatch Communication Module (eBCM) | In Production | eBCM | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Silver | Non S-Ox | 212 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | eBCMWeb services is the file transfer interface to BCM covering entire Europe(3500) via public internet. eBCM web is the sub-function on the same platform used by approx. 100 Finland /German dealers (out of 3500 in Europe). |  |  | YES | 4 | NKANDULA | PLM | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
54276 | EASY Tool | Planned | EASY Tool | ISIT | OTHERS | ZOUYANG | LYANG38 | HYANG80 | Bronze | Non S-Ox | 311 | No | Yes | In-House | BCHEN26 | ZOUYANG | Advanced PD and Tech | 311 | EASY TOOL APPLICATION PROVIDE INTEGRATED AND AUTOMATED ENGINEERING REPORT TO SUPPORT PRODUCT DEVELOPMENT NEEDS, THE APPLICATION INCREASE AUTOMATION, DATA EFFICIENCY, DATA CONNECTING BETWEEN SYSTEMS, REDUCE HUMAN ERRORS, ALSO EMPHASIZE THE DRI RESPONSIBILITY. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
14773 | eAssets | In Production | eAssets | EPEO | SRUNSON | PSIMONTE | JDEBIAS1 | GSIENKIE | Bronze | Non S-Ox | 211 | Yes | No | In-House | SRUNSON | PSIMONTE | Enterprise Technology | - | This application is the authoritative asset management tool/database for PC as well as Distributed Servers. |  |  | YES | 3 | SWALIMBE | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
14773 | eAssets | In Production | eAssets | EPEO | SRUNSON | PSIMONTE | JDEBIAS1 | GSIENKIE | Bronze | Non S-Ox | 211 | Yes | No | In-House | SRUNSON | SRUNSON | Enterprise Technology | - | This application is the authoritative asset management tool/database for PC as well as Distributed Servers. |  |  | YES | 3 | SWALIMBE | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
51962 | Global Product Representation Services | In Production | GPRS | M&S TECH | FHIRSH | GVIJI | STHANGAV | JCOY3 | Gold | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | Common services and UI for the GPRS portfolio of applications (GForCE, GPRIME, GPAS, GPRICE). Serving captivating product information to people who shop, buy, own, and sell Ford/Lincoln vehicles. Software crafted by product teams passionate about continuously delivering value.The GPRS application Utilizes GForCE (v3), GPRIME, GRPICE and GPAS and provides capabilities across the GPRS suite including a UI and common services. | 10 |  | YES | 2 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 75% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | This is not partial. Timeline is correct | Yes | VM
13771 | EAA Services | In Production | EAA | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | WJUSTICE | Gold | S-Ox In Scope | 232 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Repository / Server for EAA Services |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50990 | Global Product Representation Information Manageme | In Production | GPRIME | M&S TECH | FHIRSH | GVIJI | NNAVANEE | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | A global, single-source authoring product marketing content management, WERS product oriented, publishing and validation tool leveraging the latest web and cloud native technologies, in a presentation and experience agnostic way. | 5 |  | YES | 3 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | GCP Migration | [5 empty] | Yes | VM
54574 | EA Tools Manager | In Production | EATM | EA | RRISS | SHE1 | PSHAH | SGURU8 | Bronze | Non S-Ox | 111 | No | Yes | - | RRISS | SHE1 | Enterprise Technology | - | Tool manager for authorization to Development Tools. To support reuse of groups that represent teams across multiple toolsets (e.g. GitHub, Nexus, Fossa, etc), the EATM allows users to create/manage Azure AD security groups. |  | Springboot | YES | 1 | GBRAIL | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
13205 | E2KS - KBE Knowledge System | In Production | E2KS | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | E2KS is an Enterprise Engineering Knowledge System Database Respository and web-based front-end for managing knowledge-based engineering information. Supports Manufacturing Design Specification and DPA checklisting requirements. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
13205 | E2KS - KBE Knowledge System | In Production | E2KS | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | COTS | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | E2KS is an Enterprise Engineering Knowledge System Database Respository and web-based front-end for managing knowledge-based engineering information. Supports Manufacturing Design Specification and DPA checklisting requirements. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | On-Prem | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
13205 | E2KS - KBE Knowledge System | In Production | E2KS | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | E2KS is an Enterprise Engineering Knowledge System Database Respository and web-based front-end for managing knowledge-based engineering information. Supports Manufacturing Design Specification and DPA checklisting requirements. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
50994 | Dynetics EOL CADET Electrical Test System | In Production | EOL Sys | ISIT | SKING68 | DCLEME13 | TPICKERE | RPRASA22 | Silver | Non S-Ox | 112 | Yes | No | COTS | SKING68 | DCLEME13 | Manufacturing Engineering | - | Dynetics EOL CADET Electrical Test System is a specialized application intended to allow for vehicle ECU programming, configuration, diagnostics, and other functional tests. It utilizes an HMI, custom PC-oriented hardware and software, CAN communications, digital I/O, and network communications to facilitate testing, generate test results, and providing reporting |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50076 | Global Product Asset Services | In Production | GPAS | M&S TECH | FHIRSH | GVIJI | PDEEPA4 | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | GPAS is a scalable, secure, highly responsive/performant digital asset solution capable of associating (with high fidelity) assets with product configuration so that FORD can provide a truly world-class set of digital asset, configuration based services, supporting digital experiences that our consumers love. | 10 |  | YES | 3 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | GCP Migration |  |  |  |  | This app has SFTP server running on VM which will be replaced with GecHUB. | No | VM
51710 | Dynamic Central | In Production | DYNCEN | ISIT | AMEHER1 | ADURSO | RHOPKIN4 | RPRASA22 | Bronze | Non S-Ox | 111 | No | Yes | COTS | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Centrally managed application that pushes images to Displaydata displays, it can receive data from external sources through either an API-driven or data-driven interface. It tracks update success, display temperature, and battery life for displays. it also tracks displays tied to dynamic communicators for each location. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50887 | Global Pricing Calculation Engine | In Production | GPRICE | M&S TECH | FHIRSH | GVIJI | STHANGAV | JCOY3 | Gold | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | GPriCE is a scalable, secure, highly responsive/performant digital *product* pricing solution capable of associating pricing information with product configuration so that FORD can provide a truly world-class set of digital pricing information and product taxation calculations to omni-channels. | 5 |  | YES | 2 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 100% | 100% | 100% | 75% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | This is not partial. Timeline is correct | Yes | VM
51356 | DYNA Santorin AVL Puma | In Production | DYNA AVL | ISIT | OTHERS | JLOPORTO | JQUOZIEN | JLUCAS1 | Bronze | Non S-Ox | 122 | Yes | No | Managed by 3rd Party Purchased Service | JLOPORTO | JLOPORTO | PD Operations and Quality | - | Compehensive test cell environement aquisition software |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
21801 | Global Material Management & Approval | In Production | GMM/GMA | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Silver | Non S-Ox | 221 | No | Yes | COTS | DKAVITHA | UVIJAYAL | PD Operations and Quality | Industrial System IT | Global Materials Management application replaces the existing legacy applications GMIR & Global Material Approval application replaces MATS applications by implementing the COTS product I-point. iPoint offers the solution product providing the capability for global material compliance, vehicle certification, LCA evaluations and conflict mineral compliance. | 26 |  | YES | 3 | BWUNNAVA | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-06-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 5 | Decommission | Priya | 2025-03-03 |  |  | This app moved to Oracle SAAS solution (App# 53339) | No | VM
51130 | HoCe Base Services | In Production | HoCe | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 231 | No | Yes | In-House | #N/A | #N/A | Policy | 231 | SET OF BASE SERVICES FOR HOMOLOGATE & CERTIFY PRODUCT WITHIN 10.3.1 PRODUCT LINE TO MANAGE DATA INTEGRITY AND REUSABLE. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
233 | Duty Drawback | In Production | DDB | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Gold | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Duty Drawback allows Ford to reclaim duty paid on goods imported into the United States when those goods are subsequently exported from the United States. Ford's current drawback systems capture drawback from imported parts and steel that are exported as vehicles. Ford does not have a mechanical system to capture drawback for exported parts. The value of the drawback programs is about $12 million per year. The value from drawback has decreased over the years due to programs such as NAFTA and the decrease in duty rates. The Ford system development efforts (Vehicle and Parts / Steel) identify parts eligible for drawback and interface with our customs brokers to file the drawback claim with U.S. Customs. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q3 2027 | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
50140 | Duck Creek | In Production | AMROClaims | FORD CREDIT | DTAURO | DSHARM61 | SGABLE | VPOTTIBO | Silver | S-Ox In Scope | 331 | No | Yes | COTS | DTAURO | DSHARM61 | Ford Credit Services | Ford Credit (FMCC) | Duck Creek manages the entire Ford Credit AMRO claim management lifecycle from First Notice of Loss (FNOL) to investigation, payments, negotiations, reporting, and closure in an integrated solution. | 6 |  | YES | 5 | SRAISIN1 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned | [17 empty] | DA
50140 | Duck Creek | In Production | AMROClaims | FORD CREDIT | DTAURO | DSHARM61 | SGABLE | VPOTTIBO | Silver | S-Ox In Scope | 331 | No | Yes | COTS | DTAURO | DSHARM61 | Ford Credit Services | Ford Credit (FMCC) | Duck Creek manages the entire Ford Credit AMRO claim management lifecycle from First Notice of Loss (FNOL) to investigation, payments, negotiations, reporting, and closure in an integrated solution. |  |  | YES | 5 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
50140 | Duck Creek | In Production | AMROClaims | FORD CREDIT | DTAURO | DSHARM61 | SGABLE | VPOTTIBO | Silver | S-Ox In Scope | 331 | No | Yes | COTS | DTAURO | DTAURO | Ford Credit Services | Ford Credit (FMCC) | Duck Creek manages the entire Ford Credit AMRO claim management lifecycle from First Notice of Loss (FNOL) to investigation, payments, negotiations, reporting, and closure in an integrated solution. |  |  | YES | 5 | SRAISIN1 | PLM | Oracle | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | Oracle
50140 | Duck Creek | In Production | AMROClaims | FORD CREDIT | DTAURO | DSHARM61 | SGABLE | VPOTTIBO | Silver | S-Ox In Scope | 331 | No | Yes | COTS | DTAURO | DSHARM61 | Ford Credit Services | Ford Credit (FMCC) | Duck Creek manages the entire Ford Credit AMRO claim management lifecycle from First Notice of Loss (FNOL) to investigation, payments, negotiations, reporting, and closure in an integrated solution. |  |  | YES | 5 | SRAISIN1 | PLM | SQL | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | SQL
22463 | Global Interactive Test Tool for Configuration | In Production | GLITTC | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Bronze | Non S-Ox | 212 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Application to verify codification setup. Verification of Codification changes at time of TTR/DIR Confirm SOE codification regarding order validation and expansion rules Confirm pricing changes, compare between Test and Production, Confirm non-firm pricing | 4 |  | YES | 3 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Decommission | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | Discussed with PDO and dates already moved from Q1 to Q2. PDO team will raise a SNOW ticket and will decom by Q2 2025. | No | VM
52969 | DTA Service | In Production | DTA | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 222 | No | Yes | In-House | RKENNEL | JCHAUSSE | General Management | FCSD Tech | Service accessed via PTS for Downtime Alert functionality |  |  | YES | 2 | RKENNEL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
22772 | GFORCE3 | In Production | GFORCE3 | M&S TECH | FHIRSH | GVIJI | GYANIT | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | Marketing, Sales and Service | Global Ford Configurator Engine (GForCE) provides services to quickly communicate the compatibility, completeness, and context of features defining a vehicle. For example, applications that support dealer ordering or consumer build and price sites would use configuration services when allowing end users to understand what features are available and to select features that make up a vehicle. | 5 |  | YES | 4 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | GCP CaaS | [5 empty] | Yes | VM
52969 | DTA Service | In Production | DTA | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 222 | No | Yes | In-House |  |  | General Management | FCSD Tech | Service accessed via PTS for Downtime Alert functionality |  | Springboot | YES | 3 | RKENNEL | PLM | Java < v21 | Q3 2026 | Version Upgrade | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
52862 | DSR SERVICE | In Production | DSR | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 212 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Delear Service Record accessed via PTS / Motorcraft to enable technicians to view, record and maintain service history |  |  | YES | 3 | RKENNEL | PLM | Java Struts | Q3 2026 | Version Upgrade | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
52862 | DSR SERVICE | In Production | DSR | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 212 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Delear Service Record accessed via PTS / Motorcraft to enable technicians to view, record and maintain service history |  |  | YES | 3 | RKENNEL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
52528 | GDBP | In Production | GDBP | M&S TECH | OTHERS | NLAKSHMI | TCROCKF4 | TCROCKF4 | Silver | Non S-Ox | 211 | Yes | No | In-House | SJAGADE2 | NLAKSHMI | Marketing & Sales | - | BMIT tool providing capabilities for allocations, forecasting, vehicle mix and bulk order creation | 3 |  | YES | 2 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | 0% | 0% | 0% | 0% | 0% |  | GCP Migration | [5 empty] | No | VM
52120 | Driver Score | In Production | DSAPI | EVDD | RJOHN813 | GNANDURI | DSING103 | GNANDURI | Bronze | Non S-Ox | 211 | No | Yes | In-House | SSURYAN3 | GNANDURI | Integrated Services | 211 | Develop a consistent, reliable scoring methodology to rate a driver's performance based on telematics data |  | Springboot | YES | 3 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
52120 | Driver Score | In Production | DSAPI | EVDD | RJOHN813 | GNANDURI | DSING103 | GNANDURI | Bronze | Non S-Ox | 211 | No | Yes | In-House | SSURYAN3 | GNANDURI | Integrated Services | Enterprise Connectivity - PDO | Develop a consistent, reliable scoring methodology to rate a driver's performance based on telematics data |  |  | YES | 3 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
11296 | GCAT: Global Catalog | In Production | GCAT:11296 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 111 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | GCAT VB/OSP: Global Catalog VB/OSP Secondary outage impact 'Customer Complaint' | 11 |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
20184 | DRIVE - Dealer Reporting Incentives & Vehicle Elig | In Production | DRIVE | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Silver | Non S-Ox | 211 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Vehicle Division Contest & Incentive portal, accessible from FMCDealer, that displays a summary grid of incentives and program announcements. It also includes links to Smart VINCENT 2 as well as other resources and forms. |  |  | YES | 4 | NKANDULA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-11-27 | Complete | Blue | 2024-12-15 | 2024-11-27 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [6 empty] | As per PCF exit, team migrated to Springboot | No | Java < v21
20184 | DRIVE - Dealer Reporting Incentives & Vehicle Elig | In Production | DRIVE | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Silver | Non S-Ox | 211 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Vehicle Division Contest & Incentive portal, accessible from FMCDealer, that displays a summary grid of incentives and program announcements. It also includes links to Smart VINCENT 2 as well as other resources and forms. |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q4 2026 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
20184 | DRIVE - Dealer Reporting Incentives & Vehicle Elig | In Production | DRIVE | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Silver | Non S-Ox | 211 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Vehicle Division Contest & Incentive portal, accessible from FMCDealer, that displays a summary grid of incentives and program announcements. It also includes links to Smart VINCENT 2 as well as other resources and forms. |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
20184 | DRIVE - Dealer Reporting Incentives & Vehicle Elig | In Production | DRIVE | M&S TECH | VMUTHUPA | RANANDAL | CMICHALA | MPREETH6 | Silver | Non S-Ox | 211 | No | Yes | In-House | VMUTHUPA | RANANDAL | Marketing & Sales | Marketing, Sales and Service | Vehicle Division Contest & Incentive portal, accessible from FMCDealer, that displays a summary grid of incentives and program announcements. It also includes links to Smart VINCENT 2 as well as other resources and forms. |  |  | YES | 4 | NKANDULA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-11-27 | Complete | Blue | 2024-12-15 | 2024-11-27 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [6 empty] | As per PCF exit, team migrated to Springboot | No | Java < v21
21428 | FSA Government Incentive Program | In Production | FSA GIP | I-ERP | SFRANCI8 | KKOEHLER | GWAGNER9 | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This application is developed to support the government Incentive Program in South Africa called Automotive Production Development Program (APDP) effective 1st-Jan,2013, which benefits local Auto Manufacturers through Customs saving. The application will collect data as per Customs regulatory requirements and generate reports to support Quarterly Customs Accounts. It will also help to reduce duty payment due to compliance with the APDP. | 9 |  | YES | 4 | TSWEEN16 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 25% |  |  | 75% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | VM
11558 | DPES: Dealer Program Enrollment System | In Production | DPES | M&S TECH | NKANDULA | JLEWIS10 | KMICHALE | JHARPER2 | Bronze | S-Ox Out of Scope | 221 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | Dealer marketing program enrollments involve dealers mailing/faxing paper-based forms to program vendors. This takes much time for Ford/vendors/dealers to track enrollment status and reporting. DPES aims to provide a common approach to dealer enrollments. |  |  | YES | 2 | NKANDULA | PLM | Oracle | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-12 | 2025-03-12 | 2025-03-12 | Complete | Blue | 2025-03-12 | 2025-03-12 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | PDO Comment: new system on GCP (53012), and then migrated all the programs over from the old system to the new system. In the process of decomissioning right now. | No | Oracle
50074 | Ford Pro: NA Fleet Support Applications | In Production | NA-FSA | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Bronze | Non S-Ox | 221 | No | Yes | In-House | RSING163 | RKENNEL | Marketing & Sales | Ford Pro | A suite of web application supporting the NAFLRO business organization. Comprised of customer and Dealer facing website. | 9 |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q2 2025 | Partial Migration to GCP | Modernize | 2025-06-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 | 2025-03-12 | Planned |  | No | 75% | 25% | [6 empty] | Cloud Run | [5 empty] | No | VM
22137 | DPA 3 Data Manager | In Production | DPA3 | ISIT | JKOONS | MNOVAK1 | JANITA | GRAO3 | Copper | Non S-Ox | 211 | Yes | No | In-House | JKOONS | JKOONS | Advanced PD and Tech | - | Facilitates the management of DPA 3 related data. This is a tactical solution until DPA 3 will be handled within the Ford Engineering Design Environment FEDE. This application also goes under the name Variation Analysis Status Tracker or VAST. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
22137 | DPA 3 Data Manager | In Production | DPA3 | ISIT | JKOONS | MNOVAK1 | JANITA | GRAO3 | Copper | Non S-Ox | 211 | Yes | No | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | - | Facilitates the management of DPA 3 related data. This is a tactical solution until DPA 3 will be handled within the Ford Engineering Design Environment FEDE. This application also goes under the name Variation Analysis Status Tracker or VAST. |  |  | YES | 2 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
9826 | Domain Name Registration | In Production | DNR | OCETO | TVASU | KBALAS13 | MAMAREND | WJUSTICE | Bronze | Non S-Ox | 111 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | EPEO | Domain Name Registration Application allows users to request Domain Name Registrations outside of Ford, on the Public Internet, for Domain Names that do not end in ford.com |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | GCP Migration is completed for Database | No | SQL
22836 | Ford Pro Global Fleet Identification Number | In Production | GFIN | FORD PRO & FCSD TECH | RKENNEL | AKARTHI4 | AKARTHI4 | SHEMAMA2 | Silver | Non S-Ox | 221 | No | Yes | In-House | RSING163 | RKENNEL | Enterprise Technology | Ford Pro | Global FIN Identification database containing Fleet customer account information. Each FIN (Fleet Identification Number) will follow the new global standard, but a conversion table will be created to convert to local FIN standards during the migration period. The Welcome Package module is used to create a welcome letter & materials for new enrolled Fleet customers. | 4 |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q2 2025 | Partial Migration to GCP | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
9826 | Domain Name Registration | In Production | DNR | OCETO | TVASU | KBALAS13 | MAMAREND | WJUSTICE | Bronze | Non S-Ox | 111 | No | Yes | In-House |  |  | Enterprise Technology | EPEO | Domain Name Registration Application allows users to request Domain Name Registrations outside of Ford, on the Public Internet, for Domain Names that do not end in ford.com |  | Springboot | YES | 3 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
904 | Dollar Volume Reporting (DolVol) | In Production | DOLVOL | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Web application that provides Purchasing buyers ad-hoc reporting capabilities of FM&S total buy. Primary Users - FM&S Purchasing | 25 |  | YES | 4 | TSWEEN16 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
904 | Dollar Volume Reporting (DolVol) | In Production | DOLVOL | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | SARAUJO3 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Web application that provides Purchasing buyers ad-hoc reporting capabilities of FM&S total buy. Primary Users - FM&S Purchasing |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q2 2026 | Modernize to Cloud Databases | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Oracle
904 | Dollar Volume Reporting (DolVol) | In Production | DOLVOL | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Web application that provides Purchasing buyers ad-hoc reporting capabilities of FM&S total buy. Primary Users - FM&S Purchasing |  |  | YES | 4 | TSWEEN16 | PLM | Mainframe | Q2 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
51596 | Ford Identity Panel | In Production | FIdPanel | EPEO | NOKEEFE | MSNYDER5 | DDALKOVS | GSIENKIE | Silver | Non S-Ox | 232 | Yes | No | COTS | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Provides historical reporting for identity repositories. | 6 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
20461 | DNS, DHCP and IPAM (DDI) | In Production | DDI | EPEO | MCRNKOVI | SPANDRAN | MMIDDLET | MMIDDLET | Copper | Non S-Ox | 113 | No | Yes | Managed by 3rd Party Purchased Service | MCRNKOVI | MCRNKOVI | Enterprise Technology | EPEO | DNS (Domain Name System) is a standard Internet protocol that provides name-to-address resolution of servers and applications, allowing a user to connect to an easily remembered name like myapp.ford.com, rather than an esoteric IP address like 19.9.9.9. DHCP (Dynamic Host Configuration Protocol) is a standard Internet protocol that automatically configures workstation network information such as IP address, default router, DNS server, etc., eliminating the need to manually administer this information on each machine. IP Address Management (IPAM) software tracks IP Address allocation and manages distributed enterprise DNS and DHCP services. Use of an IPAM generates consistent and syntactically correct configuration files, reducing DNS and DHCP errors, and allowing delegation of day-to-day data administration to Level-1 site administrators. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50279 | FORD CREDIT PROCESS AUTOMATION | In Production | FCPA | FORD CREDIT | IPANKAJ | VM56 | RVIGNE24 | RPARAME4 | Silver | Non S-Ox | 332 | No | Yes | In-House | IPANKAJ | VNAVEEN1 | Ford Credit Services | Ford Credit (FMCC) | Development and Technical support for Automation owned by Ford Credit. Its primary aim is to keep automating based on baseline design document provided by the business. This record was used for UI path and now it is being used for Pega automations. | 29 |  | YES | 3 | SRAISIN1 | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
11889 | DMS - Drawing Management System | In Production | DMS | ISIT | SKING68 | JLYNN1 | JRICH264 | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | KCHRIST2 | KCHRIST2 | Manufacturing Engineering | Industrial System IT | Global Document Management System (DMS) provides plant and central staff personnel with electronic storage/retrieval and management of all engineering drawings (machine, tool, gage, controls, and so on) in use at Ford Powertrain facilities. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Oracle
22051 | Ford Credit Communication Messaging Services-NA | In Production | FCCMS | FORD CREDIT | IPANKAJ | DSINACOL | SVYSYARA | RPARAME4 | Silver | Non S-Ox | 321 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit Communication Messaging Services - North America provides the technical resources for triggering text (SMS) and e-mail notifications to Ford Credit customers. | 3 |  | YES | 3 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
9924 | Distribution Reporting | In Production | DR | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 112 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Batch system that creates the PREP file containing vehicle orders for the last 2-3 years from initial input through vehicle sold. Also included are the online systems DRIN/DROP that display order status. SLA 1, CIA 1,1,2 |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
9924 | Distribution Reporting | In Production | DR | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 112 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Batch system that creates the PREP file containing vehicle orders for the last 2-3 years from initial input through vehicle sold. Also included are the online systems DRIN/DROP that display order status. SLA 1, CIA 1,1,2 |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
11838 | Disputed Excess Transportation Charges | In Production | DETC | ISIT | VVIJAY55 | RADAM10 | PYORK | SSENTH15 | Copper | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | The DETC system uses data from Cass Premium processing and user input to assist the MP&L personnel with resolving supplier disputes regarding premium freight charges. Outside suppliers have limited access to read-only functions of the system. Application is build in Unix , Perl , Shell scripting & Oracle |  |  | YES | 4 | BWUNNAVA | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11838 | Disputed Excess Transportation Charges | In Production | DETC | ISIT | VVIJAY55 | RADAM10 | PYORK | SSENTH15 | Copper | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | SROYCHOU | Manufacturing Staffs | Industrial System IT | The DETC system uses data from Cass Premium processing and user input to assist the MP&L personnel with resolving supplier disputes regarding premium freight charges. Outside suppliers have limited access to read-only functions of the system. Application is build in Unix , Perl , Shell scripting & Oracle |  |  | YES | 4 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
11838 | Disputed Excess Transportation Charges | In Production | DETC | ISIT | VVIJAY55 | RADAM10 | PYORK | SSENTH15 | Copper | Non S-Ox | 211 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | The DETC system uses data from Cass Premium processing and user input to assist the MP&L personnel with resolving supplier disputes regarding premium freight charges. Outside suppliers have limited access to read-only functions of the system. Application is build in Unix , Perl , Shell scripting & Oracle | 26 |  | YES | 4 | BWUNNAVA | PLM | WebFocus | Q1 2025 | Migrate to QlikSense | Modernize | 2025-03-31 | 2025-04-11 |  | In-Progress | Green | 2025-07-10 |  | Planned |  | No | 100% | 100% | 75% | 75% | 75% | 75% | 75% |  | QlikSense | [5 empty] | No | DA
16096 | FFLA Brazil Ford Credit Web Site (TLK) | In Production | TLK | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Credit Services | - | The purpose of this system is to have available in the public internet, the Ford Credit Brazil Web Site, to provide information to FCB customers, non customers, dealers Ford and non Ford. FCB employees assigned to provide data maintenance have grants in the intranet. Customers can access personal data of their operation with FCB accessing the web through a password. Part of this application is based on Intranet application, such as: CRM backoffice, Payment Slip(wholesale and retail) and Parameters to Ford Credit Brazil Web Site (finance rates, programs, etc.) This application has others functions available to the Dealers in B2B process, such as the Input in an on-line transaction of the Used Vehicle to finance under FVU program and fill up a form to request authorization to move units from one sales point to another. | 8 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
12754 | Direct Sales System | In Production | DrctSales | M&S TECH | RAHMED33 | GDIAZ1 | ASYRAGAK | IKALUGIN | Gold | S-Ox Out of Scope | 232 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | Marketing, Sales and Service | Creates invoices for Direct Bill dealer codes, records payment and produces the accounting transactions for journal JV100. It also maintains a history database for all paid invoices. |  |  | YES | 1 | NKANDULA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11992 | Direct Order Entry System | In Production | DOESII | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | Provides dealerships with the ability to enter parts orders to FCSD. It also allows them to check on part inventories and track order status. | 4 |  | YES | 5 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11992 | Direct Order Entry System | In Production | DOESII | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Provides dealerships with the ability to enter parts orders to FCSD. It also allows them to check on part inventories and track order status. |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | Java Struts | Q3 2027 | Version Upgrade | Modernize | 2027-09-15 | 2027-09-15 |  | In-Progress |  | 2027-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
11992 | Direct Order Entry System | In Production | DOESII | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | Provides dealerships with the ability to enter parts orders to FCSD. It also allows them to check on part inventories and track order status. |  |  | YES | 5 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | On DB~ DB is moved to Exaadata(Cloud) in Q1, Postgress will go to Q4. On VM ~ PDO confirmed that a new application is being developed, Decom is planned in 1Q 2026. | No | Mainframe - DB2
11992 | Direct Order Entry System | In Production | DOESII | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | NBAECKER | NBAECKER | Ford Customer Service | FCSD Tech | Provides dealerships with the ability to enter parts orders to FCSD. It also allows them to check on part inventories and track order status. |  |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | Oracle | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-12-31 |  | In-Progress | Green | 2026-03-31 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL |  |  |  |  | On DB~ DB is moved to Exaadata(Cloud) in Q1, Postgress will go to Q4. On VM ~ PDO confirmed that a new application is being developed, Decom is planned in 1Q 2026. | No | Oracle
16101 | FFLA Brazil Accounting Reconciliation-CBB | In Production | CBB | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NMORALE7 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | The system performs the automatic banking and accounting reconciliation. There are two modules for Reconciliation: Account and Bank, also there is a module to Manual Repair Reconciliation. There is an Inquiry Module and a Report Module to extract files and Reports. There is a Module for inquiry General Ledger records from 1996 to 2003 which are initially loaded at once and no longer will be updated. | 2 |  | YES | 3 | TSWEEN16 | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
6293 | Direct Debit | In Production | EuAS-DDebi | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Gold | S-Ox Out of Scope | 222 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Vehicle Direct Debiting to dealers and Fordbank wholesale interface for Germany. Direct Debit also provides assumed payment records to Peoplesoft AR. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
54846 | Dimensional Planning & Validation | Planned | DPV | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | - | Yes | No | COTS | OTHERS | #N/A | Advanced PD and Tech | - | Tecnomatix Dimensional Planning and Validation (DPV) helps to collect, manage, dimensionally analyze, and report the quality measurement information. It is a quality management solution that can integrate into Teamcenter environment. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51250 | FCNA Dealer API Service Layer | In Production | FCDLRAPI | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | NVARADA2 | Gold | Non S-Ox | 332 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | Ford Credit Dealer Services API provides Restful-based service to provide dealer audit information to Dealer Risk (GLAS). | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
51164 | HnC - North American Compliance Suite | In Production | NACS | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 231 | No | Yes | In-House | #N/A | #N/A | Policy | 231 | NACS IS A NORTH AMERICAN COMPLIANCE SUITE OF CAPABILITIES SUPPORTING NORTH AMERICAN VEHICLES FE LABEL CERTIFICATION VIA EVALUATION, REPORTING OF FUEL ECONOMY VALUES FOR LABELS AND SUBMITTING THIS TO NORTH AMERICAN REGULATORY AGENCIES (EPA,CARB,NTSHA & EC). THIS SUPPORTS TO CONSOLIDATION OF CORPORATE AVERAGE AND FUEL ECONOMY (CAFE) AND GREEN HOUSE GAS (GHG) SUBMISSION TO EPA,CARB & EC TO AVAIL YEARLY EMISSION CREDITS FOR FORD. THIS HELPS TO OBTAINING VEHICLE HOMOLOGATION CERTIFICATION BY SUBMITTING TEST VEHICLES, TEST RESULTS, TEST GROUP, EVAP & EMISSION INFORMATION TO EPA & CARB FOR LIGHT AND HEAVY DUTY VEHICLE LINES TO START MASS PRODUCTION AND SALE VEHICLES IN NORTH AMERICA & CANADA. EPA: ENVIRONMENTAL PROTECTION AGENCY CARB: CALIFORNIA AIR RESOURCE BOARD NITHSA: NATIONAL HIGHWAY TRAFFIC SAFETY ADMINISTRATION EC: ENVIRONMENT CANADA |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-12-15 | 2024-12-15 |  | Complete | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | Java 17 | [5 empty] | No | Java < v21
51091 | FCE Vehicle Configuration Service | In Production | VCS | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | Data repository that holds vehicle entity and factory fitted options data plus pricing, residual values and finance plans data. Also acts as a service to feed this data to other relevant systems within Ford Credit | 12 |  | YES | 3 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
51854 | Digital Zone Board | In Production | DZB | ISIT | SKING68 | DCLEME13 | MIVES6 | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Manufacturing Plants | 111 | DIGITIZATION OF THE FORD PRODUCTION SYSTEM (FPS) PROCESS THE OPERATING PILLARS SQDCPME, USED BY PROCESS COACHES, FPS TEAM AND MANAGEMENT TO RUN THE OPERATIONS. PROVIDES ABILITY TO MAINTAIN A REPOSITORY OF COLLECTED AND HISTORICAL DATA. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
53891 | Digital Thread Platform | In Production | DTP | ISIT | JKOONS | NLAKSHMA | CCHADA | BAESCHLI | Silver | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | 311 | Digital Thread is a complete Digitalization and Integration across the work streams: Product Design, Suppliers, Plants, and Vehicle, and Customers, with single authoritative source of truth for all content in any given program. |  | Springboot | YES | 2 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
51104 | FCE Risk Service | In Production | FCE-RISK | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 321 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Set of microservices to handle risk score evaluation for marketplace, store risk data, integrate with PCO and share exposure value and evaluation result to marketplace underwriting system | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q2 2025 | EDC New Hypervisor | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
50374 | DIGITAL PROCESS AUTOMATION - PEGA | Active | DPA | EPEO | LFULCHER | EREYNOL3 | RGANESH7 | SDHANAS2 | Gold | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 3 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50582 | FCE Renewals | In Production | FCERN | FORD CREDIT | JBENITO | JCOCKWIL | CWILL663 | AGALLAG9 | Bronze | Non S-Ox | 332 | No | Yes | In-House | JBENITO | PLABROSS | Ford Credit Services | Ford Credit (FMCC) | The FCE Renewals platform is used to collate, validate and transform Core FCE data in order for it to be processed by parallel capability to generate Renewals Leads. This platform then collects the leads generated and provides them to various downstream systems. | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
51211 | FCE Proposal Service | In Production | FCE-PROP | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Set of microservices to handle proposal data management for marketplace, validate customer input, enrich customer IP & Dealer data, manage proposal state and send state update notification to marketplace orchestrator | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q2 2025 | EDC New Hypervisor | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
50374 | DIGITAL PROCESS AUTOMATION - PEGA | Active | DPA | EPEO | LFULCHER | EREYNOL3 | RGANESH7 | SDHANAS2 | Gold | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | #N/A | ITO | #N/A |  |  | YES | 3 | SWALIMBE | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
53259 | FCE On Line Document Enterprise Repository | In Production | FOLDER | FORD CREDIT | JBENITO | MLOPEZ31 | MSIMON12 | AGALLAG9 | Silver | Non S-Ox | 322 | No | Yes | In-House | JBENITO | MLOPEZ31 | Ford Credit Services | Ford Credit (FMCC) | Document Sharing Tool (mostly for documents from FC to dealers and vice versa) where documents are transient. | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
53001 | Diagnostics Data Management | In Production | DDM | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | 211 | Repository and product to process, store, and share Diagnostics data for the purposes of analysis, support and monitoring |  | Springboot | YES | 2 | RKENNEL | PLM | Java < v21 | Q3 2026 | Version Upgrade | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
53001 | Diagnostics Data Management | In Production | DDM | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 211 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Repository and product to process, store, and share Diagnostics data for the purposes of analysis, support and monitoring |  |  | YES | 2 | RKENNEL | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
16441 | Diagnostic Services File Manager Application | In Production | DSFM App | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 122 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Diagnostics, Service and Part information integrated into a hardware-independent single-point solution. DSFM/DWI supports the WebFlash product which is critical to meeting EPA legislation Objectives- Strategic - High |  |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | Modernization to DB is completed and SQL Server decom is planned for next quarter. | No | SQL
51018 | FCE Ford Credit Originations Back Office Services | In Production | FOBOS | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Silver | Non S-Ox | 332 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Ford credit Originations Back Office Services (FOBOS) for underwriting, pre-purchase checks and purchase of credit proposals | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
16441 | Diagnostic Services File Manager Application | In Production | DSFM App | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 122 | No | Yes | In-House | RKENNEL |  | Ford Customer Service | FCSD Tech | Diagnostics, Service and Part information integrated into a hardware-independent single-point solution. DSFM/DWI supports the WebFlash product which is critical to meeting EPA legislation Objectives- Strategic - High |  | Springboot | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | 100% | 50% | [6 empty] | Java 21 | [5 empty] | No | Java < v21
54713 | DevSecOps Test application | Planned | DevSecOps | OCETO | PMILLIGA | PMILLIGA | SNAMBIVE | JSTOLIKE | Bronze | Non S-Ox | - | No | Yes | In-House | PMILLIGA | MCHRIS38 | Enterprise Technology | - | THIS IS THE TEST APPLICATION CREATED TO EXPLORE THE DEVSECOPS TOOLS AND PIPELINE CREATION |  | Springboot | YES | 1 | PMILLIGA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
51140 | DevOps Command Center | In Production | DCC | EVDD | JREYN149 | NFAGEN | TARUNAC1 | STANIKEL | Copper | Non S-Ox | 111 | No | Yes | In-House | JREYN149 | TCARMEAN | Advanced PD and Tech | Enterprise Connectivity - PDO | Portal For System Tool Access |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
22573 | FCE Account Manager | In Production | FCE-AM | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 331 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Provides customer account self-servicing functionality for Ford Credit Europe customers. Application is currently available in UK, DE, ES, IT, FR & MX markets. | 10 |  | YES | 4 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
51140 | DevOps Command Center | In Production | DCC | EVDD | JREYN149 | NFAGEN | TARUNAC1 | STANIKEL | Copper | Non S-Ox | 111 | No | Yes | In-House |  |  | Advanced PD and Tech | Enterprise Connectivity - PDO | Portal For System Tool Access |  | Springboot | YES | 3 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50927 | FC Integration Abstraction Layer | In Production | FC-IAL | FORD CREDIT | IPANKAJ | PSRIKIR1 | MSRIRAM5 | AGALLAG9 | Gold | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | PSRIKIR1 | Ford Credit Services | Ford Credit (FMCC) | Integration abstraction layer for Ford Credit applications, exposed as API | 4 |  | YES | 3 | SRAISIN1 | PLM | VM | Q2 2025 | EDC New Hypervisor | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
53273 | Developer Marketplace | In Production | DMARK | EVDD | JWASNIC1 | RBUITEWE | ABIANC15 | SKHARE5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 211 | OPEN THE DOORS TO THE AUTOMOTIVE INDUSTRYS END-TO-END DEVELOPER ECOSYSTEM, WE ARE INVITING DEVELOPERS FROM ALL ACROSS THE GLOBE TO INNOVATE WITH FORD. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50547 | Dev Central Station | In Production | DCS | EVDD | RJOHN813 | RHAMMO57 | JGREE156 | JGREE156 | Silver | Non S-Ox | 221 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 221 | SOFTWARE ENGINEERING ENABLEMENT PLATFORM |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
57002 | Detailed Risk Assessment Report Application | Planned | DRA Report | OCETO | PMILLIGA | FWANG38 | DWEITZMO | DWEITZMO | Copper | Non S-Ox | - | Yes | No | In-House | PMILLIGA | FWANG38 | Enterprise Technology | Technology & Enterprise Services (TES) | This application is used to create visualizations from Enterprise Archer GRC Detailed Risk Assessment. In order to support Management awareness and approval process for Detailed Risk Assessments. |  |  | YES | 2 | PMILLIGA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
11459 | ePayables | In Production | ePay | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Provides suppliers with the capability to view and download 'remittance advices'. also provides functionality to view payment status and details. | 7 |  | YES | 4 | TSWEEN16 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 50% | 75% |  | 75% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | VM
18728 | Enterprise Document Print Service | In Production | EDPS | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | 212 | No | Yes | In-House | TVASU | NSENTHI1 | Finance | Technology & Enterprise Services (TES) | The EDPS project covers centralized mass printing of PDF documents archived by the US EDMS project in Documentum docbase. EDPS will be implemented and run as a J2EE web-application on a Linux box. The EDPS project is intended to be started with replacement of the current M/Archive printing. 2015 usage added for South Africa (EUROVAC Vehicle Invoices); also India and Thailand. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q2 2025 | Partial Migration to GCP | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
14484 | Design Verification Plan and Report | In Production | e-DVP&R | ISIT | JKOONS | MNOVAK1 | MGERMAN | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | JKOONS | JKOONS | PD Operations and Quality | Industrial System IT | e-DVP&R is a powerful engineering tool which allows engineers to maintain engine and component DVP&Rs online. All DVP&Rs are maintained in one centralized database thus enabling communication efficiences. Management concurrence is contained within the e-DVP&R application.The Engine Program Engineer/Development Engineers initiate the process that assigns responsibilities. Component Engineers then enter the Engine & Vehicle Test sample sizes. The Engine Program Engineer then enters a proposed test sample based on the engine and test facilities budget. A reconciled sample size is entered which creates both the engine and all identified component DVP&Rs. The DVP&R is a standardized planning and tracking document that, when completed, validates the design. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
21328 | Employee vehicle sales portal (CDV - Arg/Brazil) | In Production | CDV | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Web Internet application to sell vehicles to employees, agency, family, friends, retired and partnership. Those vehicles have the tendency to have lower price than regular market. | 5 |  | YES | 4 | TSWEEN16 | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-04-30 |  | In-Progress | Green | 2025-04-30 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
52970 | Design Studio Web Platform | Planned | DSWP | ISIT | SBONNICI | KRAMMOHA | IWEITZER | IWEITZER | Bronze | Non S-Ox | - | Yes | No | - | SBONNICI | KRAMMOHA | Advanced PD and Tech | - | A platform for a collection of web-based applications developed by and used within Design |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-04-14 |  | Planned |  | No | 100% | 50% | 25% |  |  |  | 25% |  | Cloud SQL PostgreSQL | Ramesh | 2025-03-11 |  |  | PCF BMIT app in Flight. There is a Possible spill over to Q2 due to Design change. Revised timeline & approval for the date change pending | No | SQL
53416 | eCommerce Payment Integration | In Production | EPI | FORD CREDIT | IPANKAJ | VNAVEEN1 | PMATHIV3 | ROBRIEN3 | Platinum | Non S-Ox | 312 | No | Yes | In-House | IPANKAJ | VNAVEEN1 | Ford Credit Services | Ford Credit (FMCC) | Capabilities Supporting the Payment Integration layer between GUX, SAP and Payment Vendors | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
22480 | Design Benchmarking Application | In Development | DESBEN | ISIT | SBONNICI | KRAMMOHA | RHARIKR2 | GRAO3 | Copper | Non S-Ox | 212 | Yes | No | In-House | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | This a data management tool used to facilitate the Design Benchmarking role which is currently Excel based, with the vision of converting to a database system that would expand use of existing and future competitive data sets and improve productivity by eliminating manual data management. The purpose of this application is to Convert from an Excel based data management system to a Database structure to enable automated data management, Convert existing Excel based data management tools to integrate with database structure creating a user friendly data management interface, Convert existing competitive vehicle audit excel data into formats compatible with database structure, Incorporate the database enabled environment on touch screen capable tablet devices for preforming critical job functions in the field (requires purchase of new touch screen capable tablet devices) |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize | 2024-07-30 | 2025-01-15 | 2025-01-03 | Complete | Blue | 2025-01-18 | 2025-01-20 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Priya | 2025-03-06 |  |  | Application moved to GCP (App tier to cloud run & DB to GCP PostgreSQL)in 2024 & Decommission complete in Q1 2025 | No | SQL
56911 | eCommerce Marketplace Portal - EU | In Production | EMP-EU | FORD PRO & FCSD TECH | TJUNIPER | GDRAGAZI | SMOHAM32 | JCOY3 | Bronze | Non S-Ox | 222 | No | Yes | In-House |  |  | Marketing & Sales | - | eCommerce Marketplace Portal supports Ford's eCommerce program by faciliating dealer onboarding and eCommerce order management | 4 |  | YES | 2 | RKENNEL | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
13581 | eCCO UK | In Production | EuHR-eCCO | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Bronze | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | NGIRISH | Marketing & Sales | Marketing, Sales and Service | Intranet hosted company car ordering application for Ford Motor Company UK. This enables authorised employees to order company cars, job cars and pool cars on-line. | 6 |  | YES | 2 | NKANDULA | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | Planned Q2 2025 for decommission. Running in ITO servers using .Net technology | No | VM
54932 | Delivery Day Tool | In Production | DDT | M&S TECH | RKLEINSM | MMILBOC1 | EGRIFF38 | SRUDENK2 | Gold | Non S-Ox | 211 | No | Yes | In-House | RKLEINSM | MMILBOC1 | Enterprise Technology | - | Mobile application to manage vehicle delivery for model e |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
15539 | Delegate+ | In Production | EuHR-Deleg | OCETO | TSWEEN16 | KADOMKAI | MMUPPITA | ESTILESK | Bronze | Non S-Ox | 111 | No | Yes | COTS | DDESAI | KADOMKAI | Ford Land | Staffs IT | Delegate is a system that manages information on canteen materials currently in stock and estimate future demand of such materials. It is also used to manage orders of food stock for the Cantines in Niehl. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
904 | Dollar Volume Reporting (DolVol) | In Production | DOLVOL | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Web application that provides Purchasing buyers ad-hoc reporting capabilities of FM&S total buy. Primary Users - FM&S Purchasing | 2 |  | YES | 4 | TSWEEN16 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
15399 | Debt Manager | In Production | DM | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | Non S-Ox | 312 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Vended collection software application for entire portfolio for early collections. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
15399 | Debt Manager | In Production | DM | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | RPARAME4 | Silver | Non S-Ox | 312 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Vended collection software application for entire portfolio for early collections. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
9072 | DEALIS: Distribution and Logistics Inf Sys | In Production | DEALIS | FORD PRO & FCSD TECH | CHURLEY3 | AHOFFM15 | IKAMLAH | MMEHTA5 | Silver | Non S-Ox | 212 | No | Yes | In-House | NBAECKER | NBAECKER | Ford Customer Service | FCSD Tech | DEALIS is an e-business application connecting order data with part picking, shipping and freight billing information. The system is able to track the movements of parts along the outbound distribution chain and then share this information with suppliers, internal Ford users, carriers, DFS suppliers, external Warehouses and dealers via the internet or intranet. Additionally freight billing information are provided for incoming and outgoing shipments. Dealis provides the management of durable modules. This DEALIS app is being replaced by SAP-TM app (54703). For France location, the replacement is completed. the replacement for remaining EU locations are planned in year 2024. |  |  | YES | 2 | RKENNEL | PLM | Oracle | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-30 |  | In-Progress | Green | 2025-12-29 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | No VMs found, As per EAMS 8/31 Decom date planned | No | Oracle
9072 | DEALIS: Distribution and Logistics Inf Sys | In Production | DEALIS | FORD PRO & FCSD TECH | CHURLEY3 | AHOFFM15 | IKAMLAH | MMEHTA5 | Silver | Non S-Ox | 212 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | FCSD Tech | DEALIS is an e-business application connecting order data with part picking, shipping and freight billing information. The system is able to track the movements of parts along the outbound distribution chain and then share this information with suppliers, internal Ford users, carriers, DFS suppliers, external Warehouses and dealers via the internet or intranet. Additionally freight billing information are provided for incoming and outgoing shipments. Dealis provides the management of durable modules. This DEALIS app is being replaced by SAP-TM app (54703). For France location, the replacement is completed. the replacement for remaining EU locations are planned in year 2024. |  |  | YES | 2 | RKENNEL | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
22414 | Dealership and User Profiles | In Production | Dlr UPrfle | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 111 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | Marketing, Sales and Service | Online source of comprehensive information about all Canadian dealerships (including Dealership name, code, sales territory, region etc.) and all user profiles information within it. Also, includes EADAM, Directory Search and Suppplier access review functions. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q1 2026 | Modernize to Cloud Databases | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | SQL
52970 | Design Studio Web Platform | Planned | DSWP | ISIT | SBONNICI | KRAMMOHA | IWEITZER | IWEITZER | Bronze | Non S-Ox | - | Yes | No | - | SBONNICI | KRAMMOHA | Advanced PD and Tech | - | A platform for a collection of web-based applications developed by and used within Design | 6 |  | YES | 2 | BWUNNAVA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-04-14 |  | Planned |  | No | 100% | 50% | 25% |  |  |  | 25% |  | GCP Migration | Ramesh | 2025-03-11 |  |  | PCF BMIT app in Flight. There is a Possible spill over to Q2 due to Design change. Revised timeline & approval for the date change pending | No | VM
22414 | Dealership and User Profiles | In Production | Dlr UPrfle | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 111 | No | Yes | In-House |  |  | Enterprise Technology | Marketing, Sales and Service | Online source of comprehensive information about all Canadian dealerships (including Dealership name, code, sales territory, region etc.) and all user profiles information within it. Also, includes EADAM, Directory Search and Suppplier access review functions. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
23844 | Dealers Objectives and Incentives Solution | In Production | DOIS | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | Dealers Objectives and Incentives is a solution used to: - Track Dealers annual Objectives - Easy incentive parameterization - Compare actual x Planned - Propose dealers incentive accordingly, Currently in development to be applied in Brazil and, later on, in Ford South America |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | Database servers & EAMS Status decommissioned | No | SQL
54932 | Delivery Day Tool | In Production | DDT | M&S TECH | RKLEINSM | MMILBOC1 | EGRIFF38 | SRUDENK2 | Gold | Non S-Ox | 211 | No | Yes | In-House | RKLEINSM | MMILBOC1 | Enterprise Technology | - | Mobile application to manage vehicle delivery for model e | 8 |  | YES | 2 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 100% | 25% | 0% | 0% | 0% | 0% | 0% |  | GCP Migration | [5 empty] | No | VM
23844 | Dealers Objectives and Incentives Solution | In Production | DOIS | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | Dealers Objectives and Incentives is a solution used to: - Track Dealers annual Objectives - Easy incentive parameterization - Compare actual x Planned - Propose dealers incentive accordingly, Currently in development to be applied in Brazil and, later on, in Ford South America |  |  | YES | 3 | TSWEEN16 | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
17715 | Dealers File Exchange Management (e-Datadif) | In Production | DTF | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | Data exchange Information(Dealers and Ford), download commom files and request from Ford to resend files to dealers regarding business information. This application informs details of file exchanged via EMVIA. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
12584 | Customer Knowledge Services File Upload Tool | In Production | CKSU | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 221 | No | Yes | In-House | DNANDAN | DWIERZBI | Marketing & Sales | Marketing, Sales and Service | Ford of Canada Customer Relationship Management (CRM) uses CKS Upload Tool, to upload Canadian Customer details captured thru various campaigns. The data is validated by the application and once it is successfully uploaded, it is then sent to the corporate Customer Knowledge System (CKS) repository via FTP. | 12 |  | YES | 1 | NKANDULA | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | 75% | 25% | [6 empty] | GCP Migration |  |  |  |  | Application (Web layer) will be decommissioned in Q1 2025. Decom planned Q2 | No | VM
50846 | Dealer Web Service (China). | In Production | fafctrns | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Bronze | Non S-Ox | 121 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | Dealer Web Service API provides dealer's demographic information for china dealers. |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
21538 | Dealer Vehicle Calculation Engine | In Production | DeViCE | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Silver | Non S-Ox | 12 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 12 | FCE DEALER VEHICLE CALCULATION ENGINE (DEVICE) IS A SYSTEM THAT PROVIDES A CENTRAL HUB FOR FORD BANK RETAIL FINANCE, LEASING AND MOTOR INSURANCE CALCULATIONS. IT DOES SO BY PROVIDING A SOAP INTERFACE TO THIRD PARTY POINT-OF-SALE (POS) AND/OR DEALER MANAGEMENT SYSTEMS (DMS). VIA THIS INTERFACE IT IS POSSIBLE TO OBTAIN REAL TIME VEHICLE FINANCE AND LEASING CALCULATIONS ACCORDING TO THE FINANCE PLANS, RESIDUAL VALUES, VEHICLE CONFIGURATIONS ETC. CURRENTLY VALID FOR SUPPORTED MARKETS DE THE CALCULATIONS ARE NOT VALID PROPOSALS OR OFFERS BUT NEED TO BE IMPORTED INTO FBA (ACR: 2000-589) AND TURNED INTO PROPOSALS THERE. THE POS SYSTEM NEEDS TO IMPLEMENT AN INTERFACE TO FBA TO DO SO. IN ORDER TO PROVIDE ACCURATE FINANCE CALCULATIONS DEVICE STORES THE FOLLOWING DATA: -VEHICLE ENTITY CONFIGURATION DATA -VEHICLE OPTIONS -FINANCE PLANS -VEHICLE RESIDUAL VALUES -PPP FACTORS DEVICE OFFERS A WEB INTERFACE TO ALLOW AUTHORIZED FORD CREDIT PERSONNEL TO MAINTAIN THIS DATA. DEVICE ALSO OFFERS A BATCH INTERFACES TO |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
21539 | Dealer Service Agenda System | In Production | Agenda | OCETO | DBRIGHEN | NMORALE7 | PDELMOND | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | Electronic Agenda System to allow customers to schedule services at Dealers (regular warranty check point, vehicle breaks, etc) in such a way that customers will be able to get online availability to book services at the Dealership, So that a common process for booking services at dealership is achieved. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q3 2025 | Rewrite | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
21539 | Dealer Service Agenda System | In Production | Agenda | OCETO | DBRIGHEN | NMORALE7 | PDELMOND | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | Electronic Agenda System to allow customers to schedule services at Dealers (regular warranty check point, vehicle breaks, etc) in such a way that customers will be able to get online availability to book services at the Dealership, So that a common process for booking services at dealership is achieved. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer | [5 empty] | No | SQL
50448 | Connected Vehicle Wholesale Audit | In Production | FCCVWA | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | VPOTTIBO | Gold | Non S-Ox | 222 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | Connected Vehicle Wholesale Audit(CvWA) formerly known as VIS, Leverages Modem technology from Ford Vehicles to abstract data from connected vehicle cloud to provide real-time wholesale unit locations for enhanced wholesale monitoring and real-time audit capabilities and trigger early warnings/alerts. The goal is to reduce the number of units to be physically inspected on Wholesale Audits YOY and provide data to assist risk mitigation metrics that will proactively prevent credit losses. Reduction in credit losses resulting from sold out of trust conditions. Potential savings in units that are audited: 70-75% of 1.4M / year. Avoid reputation risk in public marketplace. Risk avoidance resulting from improved line of sight on missing units. | 12 |  | YES | 2 | SRAISIN1 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
21539 | Dealer Service Agenda System | In Production | Agenda | OCETO | DBRIGHEN | NMORALE7 | PDELMOND | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Ford Customer Service | - | Electronic Agenda System to allow customers to schedule services at Dealers (regular warranty check point, vehicle breaks, etc) in such a way that customers will be able to get online availability to book services at the Dealership, So that a common process for booking services at dealership is achieved. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q3 2025 | Rewrite | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
24549 | DEALER REPORTING APPLICATION | In Production | DRA | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Silver | Non S-Ox | 211 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | The Dealer Reporting App is an application to save and index document information and its templates providing document generation and information lookup functionalities. Currently is being used to generate the Daily Summary Remittance Advice and Payment Advice documents as part of the eContracting project. |  |  | YES | 3 | SRAISIN1 | PLM | SQL | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | SQL
12880 | Commodity Strategy System | In Production | CSS | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Bronze | Non S-Ox | 221 | No | Yes | In-House |  |  | Supply Chain | - | Commodity Strategy System, based on VerticalNet (formerly B2eMarkets) software, used by purchasing worldwide to develop and store Commodity Strategies. | 3 |  | YES | 4 | TSWEEN16 | PLM | VM | Q2 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 50% | 75% |  | 75% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | VM
24549 | DEALER REPORTING APPLICATION | In Production | DRA | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Silver | Non S-Ox | 211 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | The Dealer Reporting App is an application to save and index document information and its templates providing document generation and information lookup functionalities. Currently is being used to generate the Daily Summary Remittance Advice and Payment Advice documents as part of the eContracting project. |  |  | YES | 3 | SRAISIN1 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
18814 | Dealer profile and performance reporting (DlrPls) | In Production | DealerPlus | EPEO | ARAJKUMA | LEHLERS1 | JBRETT1 | LRODR205 | Bronze | Non S-Ox | - | Yes | No | Managed by 3rd Party Purchased Service | ARAJKUMA | IKOVALEV | Marketing & Sales | - | Dealer profile and performance reporting. Provide a central repository of dealer data, collected from numerous sources, in order to decrease the time for end users to access dealer profile data. Data is updated monthly by Sylke Dickes, the application administrator. One record per year per dealer is archived to enable year on year comparisons. Dealer Profile Database covering a wider range of dealer data than DID. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53729 | Celonis | In Production | Celonis | OCETO | TVASU | SANANTH | VSRIRAMA | WJUSTICE | Bronze | Non S-Ox | 311 | No | Yes | Managed by 3rd Party Purchased Service | TVASU | SANANTH | Enterprise Technology | Technology & Enterprise Services (TES) | A Process Mining capability within enterprise to identify process automation opportunities and accelerate the ERP transition | 2 |  | YES | 1 | TSWEEN16 | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
14599 | Dealer Payment System | In Production | DPS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | KHEMANT | RANANDAL | Finance | - | Calculates payments and chargebacks to qualified dealers and special accounts made on the release/sale of the vehicle. |  |  | YES | 3 | NKANDULA | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
14599 | Dealer Payment System | In Production | DPS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | KHEMANT | RANANDAL | Finance | - | Calculates payments and chargebacks to qualified dealers and special accounts made on the release/sale of the vehicle. |  |  | YES | 3 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
14599 | Dealer Payment System | In Production | DPS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | KHEMANT | RANANDAL | Finance | - | Calculates payments and chargebacks to qualified dealers and special accounts made on the release/sale of the vehicle. |  |  | YES | 3 | NKANDULA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-11-01 | Complete | Blue | 2024-12-15 | 2025-02-02 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [6 empty] | As part of PCF exit, team migrated WAS to Springboot | No | Java < v21
23931 | Dealer Marketing Platform (ex-UACE) | In Production | DMP | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | COTS | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | New campaign engine for unified customer contacts in FCSD and potential REACT replacement. The application uses the Adobe Marketing cloud, specifically Adobe Campaign and Adobe Analytics premium. |  |  | YES | 4 | NKANDULA | PLM | Java Struts | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
23931 | Dealer Marketing Platform (ex-UACE) | In Production | DMP | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | COTS | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | New campaign engine for unified customer contacts in FCSD and potential REACT replacement. The application uses the Adobe Marketing cloud, specifically Adobe Campaign and Adobe Analytics premium. |  |  | YES | 4 | NKANDULA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
24523 | Billing Platform | In Production | BP | FORD CREDIT | DTAURO | SLYNCH11 | MSULLANO | ROBRIEN3 | Silver | Non S-Ox | 332 | No | Yes | In-House | DTAURO | LCARVA11 | Ford Credit Services | Ford Credit (FMCC) | The Billing Platform creates a unified billing experience by compiling data from multiple sources and generating reoccurring, consistent invoice templates for customers and downstream systems that includes itemized details of payments due and received as well as product/service information as applicable. The Billing Platform will support both Ford and Ford Credit globally including Ford Smart Mobility (FSM), Ford Pro, and Electric Vehicle initiatives. | 4 |  | YES | 4 | SRAISIN1 | PLM | VM | Q2 2025 | EDC New Hypervisor | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
23931 | Dealer Marketing Platform (ex-UACE) | In Production | DMP | M&S TECH | NKANDULA | LEHLERS1 | GHASENBE | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | COTS | SBAILE17 | TBRYANS1 | Marketing & Sales | Marketing, Sales and Service | New campaign engine for unified customer contacts in FCSD and potential REACT replacement. The application uses the Adobe Marketing cloud, specifically Adobe Campaign and Adobe Analytics premium. |  |  | YES | 4 | NKANDULA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
18813 | Dealer margin (BONI) | In Production | BONI | EPEO | ARAJKUMA | LEHLERS1 | JBRETT1 | LRODR205 | Bronze | Non S-Ox | - | Yes | No | Managed by 3rd Party Purchased Service | ARAJKUMA | IKOVALEV | Marketing & Sales | - | Stores and processes data related to some elements of the Dealer Margin calculation. Year end process calculates next years Dealer margin and downloads to DID. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
52948 | Automated OS Installation | In Development | AOS | EPEO | LFULCHER | KMAHAJAN | OSHVARTS | CDOSHI | Gold | S-Ox Out of Scope | - | No | Yes | In-House | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | Infrastructure for automated deployment of operating systems for virtual and physical servers. | 14 |  | YES | 1 | SWALIMBE | PLM | VM | Q2 2025 | EDC New Hypervisor | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
13362 | Dealer Information Systems Net Enabled | In Production | DISNE | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | DISNE (Dealer Information System InterNet Enabled) is the database of record for Dealer, Commercial and Specialty Product information. Information stored in DISNE is used by various Ford Credit applications, Ford Motor Company systems and vended applications primarily to facilitate processing of wholesale, retail, lease, dealer loan business and Commercial Line Of Credit. There are also numerous downstream systems that use DISNE data for a variety of reasons including risk analysis, marketing programs, Salesforce and MAPS reporting. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
17923 | Arg. Special Sales Management (VE) | In Production | ARVE | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | The system manages all special sales chanels. Includes the following operations: . Standard / Special Quotation Generation . Electronic Folder Generation. Tracking and administration. . Proforma Generation to down pay units. Taxing Approval. . RioServ debt publication (Proformas and Invoices) . Collection. Debit note emission for Down payments. . Price Release based invoicing. . Friendly process and operation. . Web Solutions oriented process. | 8 |  | YES | 4 | TSWEEN16 | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
13362 | Dealer Information Systems Net Enabled | In Production | DISNE | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 311 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | DISNE (Dealer Information System InterNet Enabled) is the database of record for Dealer, Commercial and Specialty Product information. Information stored in DISNE is used by various Ford Credit applications, Ford Motor Company systems and vended applications primarily to facilitate processing of wholesale, retail, lease, dealer loan business and Commercial Line Of Credit. There are also numerous downstream systems that use DISNE data for a variety of reasons including risk analysis, marketing programs, Salesforce and MAPS reporting. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
12649 | Dealer Information Database | In Production | DID | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Silver | S-Ox Out of Scope | 332 | No | Yes | In-House | FHIRSH | JLEWIS10 | Enterprise Technology | Marketing, Sales and Service | DID is the master database and system of record for official electronic dealer records for Ford of Europe. DID is also used for vehicle Order to Delivery in Asia Pacific region. DN@F is the web online interface to the DID for data entry and retrieval. Provision of DID data to more than 40 downstream applications and processes is supported by a batch suite, DN@F report writer, and direct access by program call. DID supports key processes in European Marketing, Sales, FCSD and Ford Financial. Key DID data is Dealer code & market, name and address/contact details, contracts and operating locations, dealer groups, dealer related accounting / invoicing data, financial status, delivery channels, and EDI data. DID application is coordinated by Ford of Europe Dealer Operations head office |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12649 | Dealer Information Database | In Production | DID | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Silver | S-Ox Out of Scope | 332 | No | Yes | In-House | FHIRSH | JLEWIS10 | Enterprise Technology | Marketing, Sales and Service | DID is the master database and system of record for official electronic dealer records for Ford of Europe. DID is also used for vehicle Order to Delivery in Asia Pacific region. DN@F is the web online interface to the DID for data entry and retrieval. Provision of DID data to more than 40 downstream applications and processes is supported by a batch suite, DN@F report writer, and direct access by program call. DID supports key processes in European Marketing, Sales, FCSD and Ford Financial. Key DID data is Dealer code & market, name and address/contact details, contracts and operating locations, dealer groups, dealer related accounting / invoicing data, financial status, delivery channels, and EDI data. DID application is coordinated by Ford of Europe Dealer Operations head office |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
12649 | Dealer Information Database | In Production | DID | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Silver | S-Ox Out of Scope | 332 | No | Yes | In-House | FHIRSH | JLEWIS10 | Enterprise Technology | Marketing, Sales and Service | DID is the master database and system of record for official electronic dealer records for Ford of Europe. DID is also used for vehicle Order to Delivery in Asia Pacific region. DN@F is the web online interface to the DID for data entry and retrieval. Provision of DID data to more than 40 downstream applications and processes is supported by a batch suite, DN@F report writer, and direct access by program call. DID supports key processes in European Marketing, Sales, FCSD and Ford Financial. Key DID data is Dealer code & market, name and address/contact details, contracts and operating locations, dealer groups, dealer related accounting / invoicing data, financial status, delivery channels, and EDI data. DID application is coordinated by Ford of Europe Dealer Operations head office |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q2 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
12649 | Dealer Information Database | In Production | DID | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Silver | S-Ox Out of Scope | 332 | No | Yes | In-House | FHIRSH | JLEWIS10 | Enterprise Technology | Marketing, Sales and Service | DID is the master database and system of record for official electronic dealer records for Ford of Europe. DID is also used for vehicle Order to Delivery in Asia Pacific region. DN@F is the web online interface to the DID for data entry and retrieval. Provision of DID data to more than 40 downstream applications and processes is supported by a batch suite, DN@F report writer, and direct access by program call. DID supports key processes in European Marketing, Sales, FCSD and Ford Financial. Key DID data is Dealer code & market, name and address/contact details, contracts and operating locations, dealer groups, dealer related accounting / invoicing data, financial status, delivery channels, and EDI data. DID application is coordinated by Ford of Europe Dealer Operations head office |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
53359 | Dealer Franchising Portal | In Development | DFP | M&S TECH | NKANDULA | JLEWIS10 | CVOGLER1 | JHARPER2 | Silver | Non S-Ox | 333 | No | Yes | COTS | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | DFP is used by the US Market Representation Team, including the regional and market area teams, franchising, representation planning, business management and retail operations to receive and process dealer change requests (aka transactions), manage/create/update dealer contracts, and track the progress of those requests through the different approval and signature chains. The final contract documents produced by the system will be stored and available internally in a document repository within the application. The application will allow Dealers to engage with Ford, upload necessary documentation, and sign the contracts electronically within the application. The system tracks all changes and it allows the team to monitor obligations and standards compliance, and provides metrics to support reporting and planning. The platform is a no code platform that allows custom configurations and scalability to other teams and processes to provide an holistic view of Dealer Information. |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
20189 | AccuRev | In Production | AccuRev | EA | RRISS | SHE1 | LKESHRI | SGURU8 | Silver | Non S-Ox | 221 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | - | The Ford IT Software Configuration Management tool for the distributed environment. | 1 |  | YES | 1 | GBRAIL | PLM | VM | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
51780 | Dealer Digital Service | In Production | DDS | I-ERP | HHUANGJI | JZHOU42 | JWANG187 | YXU116 | Silver | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Enterprise Technology | 211 | DEALER DIGITAL SERVICE IS A MID-END SERVICE LAYER PROVIDING MS&S LEADER SERVICE & DEALER MANAGEMENT FUNCTIONALITY. IT SUPPORTS LINCOLN CHINA & COMPANY C |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
24201 | Dealer Connectivity & Data Services | In Production | DCDS(GUDB) | M&S TECH | KPINNU | KHILLERT | GBONUTTI | JHARPER2 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | 222 | Previous ITMS is 107. This new ITMS entry is to reflect next generation technology upgrades. Global Unified Database is a data warehouse for customer pay and warranty repair data from Ford and Lincoln Mercury dealers. It provide one globally standardized POS database to provide POS performance metrics, global dashboards and reports, and standardized data extracts that support downstream applications and programs. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
24201 | Dealer Connectivity & Data Services | In Production | DCDS(GUDB) | M&S TECH | KPINNU | KHILLERT | GBONUTTI | JHARPER2 | Silver | S-Ox In Scope | 222 | No | Yes | In-House | KPINNU | KHILLERT | Marketing & Sales | Marketing, Sales and Service | Previous ITMS is 107. This new ITMS entry is to reflect next generation technology upgrades. Global Unified Database is a data warehouse for customer pay and warranty repair data from Ford and Lincoln Mercury dealers. It provide one globally standardized POS database to provide POS performance metrics, global dashboards and reports, and standardized data extracts that support downstream applications and programs. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
22331 | ACCOUNT MANAGER - NORTH AMERICA | In Production | AM - NA | FORD CREDIT | NJOSHI21 | SFRAGAL1 | KUHL1 | ASAXENA8 | Silver | Non S-Ox | 322 | No | Yes | In-House | NJOSHI21 | ABARNA10 | Ford Credit Services | Ford Credit (FMCC) | Customer-facing web site that allows customers to view and update their Ford Credit and Lincoln-AFS accounts. Functionality includes viewing account details, scheduling payments, and exchanging documents electronically with Ford Credit. | 4 |  | YES | 4 | SRAISIN1 | PLM | VM | Q2 2025 | EDC New Hypervisor | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | VM
23329 | Dealer Communication | In Production | DlrComm | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | Marketing, Sales and Service | An online tool for Ford of Canada Dealers and In-house users to manage the creation, editing, reviewing, approving and publishing process for bulletins and surveys with their dealership. The application also allows the dealers to target the audience for each bulletin/survey. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
23329 | Dealer Communication | In Production | DlrComm | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | Marketing, Sales and Service | An online tool for Ford of Canada Dealers and In-house users to manage the creation, editing, reviewing, approving and publishing process for bulletins and surveys with their dealership. The application also allows the dealers to target the audience for each bulletin/survey. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q1 2027 | Modernize to Cloud Databases | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [14 empty] | No | SQL
22235 | Wholesale Securitization | In Production | GSWS | FORD CREDIT | DTAURO | SKHAN29 | APAUL31 | VPOTTIBO | Silver | S-Ox In Scope | 232 | No | Yes | COTS | DTAURO | SKHAN29 | Ford Credit Services | Ford Credit (FMCC) | Moody's ABS System provides the processing needed to track wholesale asset-based information and translate that asset-based information to produce investor reporting, and accounting and manage Cash Wires of the deals. This application relies on Wholesale Securitization backend processing. It is a vended application, hosted and supported by Ford Credit IT. It also includes My Friend which is a Windows based functionality developed in house to monitor ABS modules like Process Groups, Cash Management, Journal Entry, Calendar, User Roles, and New Deal Setup. | 13 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2027 | Complete Migration to SaaS | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
23329 | Dealer Communication | In Production | DlrComm | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | Marketing, Sales and Service | An online tool for Ford of Canada Dealers and In-house users to manage the creation, editing, reviewing, approving and publishing process for bulletins and surveys with their dealership. The application also allows the dealers to target the audience for each bulletin/survey. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
9818 | Dealer Billing | In Production | DLR Bill | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Finance | FCSD Tech | The Dealer Billing System bills dealers via their parts statements for their use of software, hardware and communication expenses. Pricing is updated annually for billing for Fordstar Communications Services. The purpose of the system is to collect money from the dealers for their use of Ford Motor Company's software, hardware and communications systems (e.g, Fordstar). The system runs through a complete cycle once per month to collect charges from the prior month. Reports are created showing all inputs entering the system, highlighting the transactions that fail the edits. The final process is to create a file of all the month's charges and forward this file to ARMIS for inclusion in the dealers' parts statements. Billing of dealers for Ford Motor Company internal functions (Fordstar, FCSD, e.g.) as well as outside suppliers (Dealer e-Store, OE Connection, DealerConnection, e.g.). | 28 |  | YES | 2 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
9818 | Dealer Billing | In Production | DLR Bill | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Finance | FCSD Tech | The Dealer Billing System bills dealers via their parts statements for their use of software, hardware and communication expenses. Pricing is updated annually for billing for Fordstar Communications Services. The purpose of the system is to collect money from the dealers for their use of Ford Motor Company's software, hardware and communications systems (e.g, Fordstar). The system runs through a complete cycle once per month to collect charges from the prior month. Reports are created showing all inputs entering the system, highlighting the transactions that fail the edits. The final process is to create a file of all the month's charges and forward this file to ARMIS for inclusion in the dealers' parts statements. Billing of dealers for Ford Motor Company internal functions (Fordstar, FCSD, e.g.) as well as outside suppliers (Dealer e-Store, OE Connection, DealerConnection, e.g.). |  |  | YES | 2 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
52022 | Dealer Accounting Management System | In Production | DAMS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Make available to dealers information regarding their Account within Ford. The dealers can also ask for transfer between units of their group(filiais). |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
50191 | Verint Call Recording India | In Production | VCR | FORD CREDIT | KDELTA | PBINGI | RGUTOWS3 | SMOCK6 | Bronze | Non S-Ox | 311 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | Application to record contact agent calls with customers | 16 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
21504 | DDVPM Data Management | In Production | DDVPM-DM | ISIT | SBONNICI | SBONNICI | ABANSA15 | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SBONNICI | SBONNICI | Enterprise Technology | Industrial System IT | Application to store and manage digital appearance assets captured from physical materials using appearance capture devices. Also has provision to capture metadata about the verification status of the captured material . Acronym meaning: Design Digital Validation of Physical Material. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
13904 | Time and Attendance | In Production | SAL PAYROL | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 222 | No | Yes | In-House | DNANDAN | DWIERZBI | Finance | Marketing, Sales and Service | A web based Intranet application used by Canadian employees to record Time & Attendance. | 12 |  | YES | 1 | NKANDULA | PLM | VM | Q1 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
21504 | DDVPM Data Management | In Production | DDVPM-DM | ISIT | SBONNICI | SBONNICI | ABANSA15 | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SBONNICI | SBONNICI | Enterprise Technology | Industrial System IT | Application to store and manage digital appearance assets captured from physical materials using appearance capture devices. Also has provision to capture metadata about the verification status of the captured material . Acronym meaning: Design Digital Validation of Physical Material. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
19598 | DCW: Dealer Contracts Worksite | In Production | DCW | M&S TECH | NKANDULA | JLEWIS10 | CVOGLER1 | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | DCW is a SharePoint online application used by U.S. Market Rep to track dealer contract progress using InfoPath forms. The site houses training and other documents required throughout the contract lifecycle. The application is a subsite to Market Rep which is the main landing page for the Market Representation group to post content related to Rep Planning. DCW relies on GOLDD views to ETL dealer data into the DCW SQL database and the Ford Business and PDO team are actively working on a replacement for this application. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
16544 | SOF Releases | In Production | SOFRELS | M&S TECH | FHIRSH | JEISIMIN | SPAMULA1 | CKEMPSKI | Gold | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Single Order Filter will combine three major areas of functionality and six legacy systems to create a single application that selects and schedules orders. SOF will streamline, simplify, and enhance the scheduling business processes and supporting systems within the Marketing & Sales and Material Planning & Logistics organizations. | 5 |  | YES | 6 | NKANDULA | PLM | VM | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
16721 | DCRS (Dimensional Control Request System) | In Production | DCRS | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Copper | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Dimensional Control Request System (DCRS)/(formerly WLRR)- web based application to submit and requests changes to engineering data related to Vehicle Operation, Dimension Control groups. DCRS includes several subsystems: 1.WLRR (Web locator Revision Request) allows engineer to request change to fixture & gage locators, while it tracks and records requests. 2. WTRR (Web Template Revision Request) allows for requests to change templates that are populated from measurements of locator points on fixtures & gages. 3. WSS allow for fixture and gage information transfer from vendor to Ford facility /plant. 4. DCD Standards - allows for requests to change VO DCD standards for global manufacturing processes. 5. DVA Study Request (Dimensional Variation Analysis) allows for a list of DVA Study requests sorted by vehicle programs. Requested studies are used to calculate ability to achieve fit and finish relative to completive vehicle set. 6. Paint Study Requests - used to request, track and house studies for paint en |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
16721 | DCRS (Dimensional Control Request System) | In Production | DCRS | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Copper | Non S-Ox | 211 | No | Yes | In-House | SKING68 | SKING68 | Manufacturing Engineering | Industrial System IT | Dimensional Control Request System (DCRS)/(formerly WLRR)- web based application to submit and requests changes to engineering data related to Vehicle Operation, Dimension Control groups. DCRS includes several subsystems: 1.WLRR (Web locator Revision Request) allows engineer to request change to fixture & gage locators, while it tracks and records requests. 2. WTRR (Web Template Revision Request) allows for requests to change templates that are populated from measurements of locator points on fixtures & gages. 3. WSS allow for fixture and gage information transfer from vendor to Ford facility /plant. 4. DCD Standards - allows for requests to change VO DCD standards for global manufacturing processes. 5. DVA Study Request (Dimensional Variation Analysis) allows for a list of DVA Study requests sorted by vehicle programs. Requested studies are used to calculate ability to achieve fit and finish relative to completive vehicle set. 6. Paint Study Requests - used to request, track and house studies for paint en |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
16721 | DCRS (Dimensional Control Request System) | In Production | DCRS | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Copper | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Dimensional Control Request System (DCRS)/(formerly WLRR)- web based application to submit and requests changes to engineering data related to Vehicle Operation, Dimension Control groups. DCRS includes several subsystems: 1.WLRR (Web locator Revision Request) allows engineer to request change to fixture & gage locators, while it tracks and records requests. 2. WTRR (Web Template Revision Request) allows for requests to change templates that are populated from measurements of locator points on fixtures & gages. 3. WSS allow for fixture and gage information transfer from vendor to Ford facility /plant. 4. DCD Standards - allows for requests to change VO DCD standards for global manufacturing processes. 5. DVA Study Request (Dimensional Variation Analysis) allows for a list of DVA Study requests sorted by vehicle programs. Requested studies are used to calculate ability to achieve fit and finish relative to completive vehicle set. 6. Paint Study Requests - used to request, track and house studies for paint en |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
15288 | QRM - Quantitative Risk Management | In Production | QRM | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | S-Ox In Scope | 231 | No | Yes | COTS | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | The QRM application is a vended application that Ford Treasury Risk Management analysts use to assess Ford Credit's risk exposure. Risk Management analysts use QRM to assess the Company's interest rate risk, profit volatility and to calculate market values for all on- and off-balance sheet instruments. In Ford Treasury and Ford Credit Finance use QRM to forecast the Company's borrowing cost. | 32 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2027 | EDC New Hypervisor | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
53971 | Database Strategy | Active | DBStrategy | EPEO | SKULKA52 | NSHAH43 | BCAPATIN | BCAPATIN | Copper | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | ENTERPRISE TECHNOLOGY | - | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
13041 | OEM Pool Accounts Web Site | In Production | POOLACCTS | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Marketing & Sales | Marketing, Sales and Service | The Commercial Sales (Pool Accounts) website manages Pool Accounts for Canadian Business Partners. It is used by modifiers of Ford vehicles. Modifiers are companies that build special use vehicles such as school buses and ambulances. | 13 |  | YES | 1 | NKANDULA | PLM | VM | Q1 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53660 | Database Migration Service | Active | dbmig | EPEO | SKULKA52 | NSHAH43 | HLIN13 | HLIN13 | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53671 | Nuance Security Suite | In Production | VoiceID | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Silver | Non S-Ox | 321 | No | Yes | COTS | KDELTA | PBINGI | Ford Credit Services | - | Voice Identification tool that uses Phone number, Background Noise, SIP Header, connected infrastructure and voice audio to provide probabilities that identify a caller for authentication. | 38 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2027 | Complete Migration to SaaS | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
19947 | Database Activity Monitoring | Active | DAM | EPEO | SKULKA52 | NSHAH43 | AVELMURU | AVELMURU | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | NSHAH43 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50371 | MAPS Manual Adjustment / Adhoc System | In Production | MAPS - MAA | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The primary use of this SQL Server and its data is to facilitate end-user, ad-hoc queries of account-level MAPS data. The data are used to provide more granular (tactical) breakdowns of the MAPS operational reports on a case-by-case, ad-hoc basis. Also, the data are used to identify deficiencies in the source systems' feeds to MAPS and prototype workarounds and ultimate resolutions to the deficiencies. Was AMPO 2648 MAPS EUC with a launch date of 5/31/2006. | 3 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2027 | EDC New Hypervisor | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
19338 | MAPS Budget | In Production | MAPSBudget | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The MAPS Budget reports provide a budget and actual for key measures relating to the business of Ford Credit. There are 18 reports for MAPS Budget. | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2027 | EDC New Hypervisor | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
23132 | Data Supply Chain | In Production | DSC | GDIA | MLYONS23 | ARAMAKR4 | NSANKAR4 | RPOLLO13 | Silver | Non S-Ox | 311 | No | Yes | In-House | DTERPST1 | ARAMAKR4 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | GDIA Data Supply Chain Analytical repository of all enterprise data. |  |  | YES | 3 | FRANBELL | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
23132 | Data Supply Chain | In Production | DSC | GDIA | MLYONS23 | ARAMAKR4 | NSANKAR4 | RPOLLO13 | Silver | Non S-Ox | 311 | No | Yes | In-House | DTERPST1 | ARAMAKR4 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | GDIA Data Supply Chain Analytical repository of all enterprise data. |  |  | YES | 3 | FRANBELL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-02-28 | 2024-11-30 | 2025-01-01 | Complete | Blue | 2025-02-28 |  | Planned |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | SQL
15860 | Management, Analysis and Planning-MAPS MF | In Production | MAPS - MF | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 221 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | MAPS MF is a cobol mainframe system (facility A) which takes in 20+ data feeds from receivable systems and Op Cost. The system runs at month-end. It processes the data and buckets it according to a g-number definition (EG; Average net receivables = g2004)which represents either a dollar value or a tranaction count. The data is passed to a Teradata repository. The data in the Teradata repository is pulled by the MAPS Presentation System which provides OLAP reports (another system). | 8 |  | YES | 3 | SRAISIN1 | PLM | VM | Q1 2027 | EDC New Hypervisor | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
21822 | Data Loss Prevention | In Production | DLP | EPEO | NOKEEFE | VNACHIMU | WMAGGETT | WJUSTICE | Silver | Non S-Ox | 311 | No | Yes | - | NOKEEFE | NOKEEFE | Enterprise Technology | EPEO | Symantec Tool to monitor data in an effort to prevent loss. |  |  | YES | 3 | SWALIMBE | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
21822 | Data Loss Prevention | In Production | DLP | EPEO | NOKEEFE | VNACHIMU | WMAGGETT | WJUSTICE | Silver | Non S-Ox | 311 | No | Yes | - | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | Symantec Tool to monitor data in an effort to prevent loss. |  |  | YES | 3 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
22721 | Integrated Management & Profit Reporting System | In Production | IMPRS | I-ERP | SFRANCI8 | AKANSKI | CDERUITE | LWU14 | Silver | S-Ox In Scope | 331 | No | Yes | COTS | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | This is a corporate system which consolidates and produces internal as well as external-facing views of corporate financials. Specifically, it address the business plan (5 year plan), next year calendarized budget, and present year actuals, forecast, and variance analysis. | 31 |  | YES | 3 | TSWEEN16 | PLM | VM | Q1 2027 | EDC New Hypervisor | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [14 empty] | No | VM
50884 | Data Fulfillment Application | In Production | DFA | GDIA | AFRADKIN | PBOSCO3 | KNAWAZ | RPOLLO13 | Silver | Non S-Ox | 311 | No | Yes | COTS | AFRADKIN | PBOSCO3 | Enterprise Technology | 311 | Fulfill revenue generating Data Products per business requirements at market speed by enabling an environment with necessary tools and access to internal/external data sources |  | Springboot | NO | 3 | FRANBELL | PLM | Java < v21 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50884 | Data Fulfillment Application | In Production | DFA | GDIA | AFRADKIN | PBOSCO3 | KNAWAZ | RPOLLO13 | Silver | Non S-Ox | 311 | No | Yes | COTS | AFRADKIN | PBOSCO3 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Fulfill revenue generating Data Products per business requirements at market speed by enabling an environment with necessary tools and access to internal/external data sources |  |  | NO | 3 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
56364 | IMG Parts and Logistics Systems | In Production | IPLS | FORD PRO & FCSD TECH | DNANDAN | MAMUDHA | MAMUDHA | MMEHTA5 | Gold | S-Ox Out of Scope | 233 | No | Yes | COTS | RSING163 | DNANDAN | Enterprise Technology | - | IPLS is the Integrated Parts management system used for aftermarket service parts management across IMG markets. | 1 |  | YES | 2 | RKENNEL | PLM | VM | Q1 2027 | Complete Migration to SaaS | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [14 empty] | No | VM
53019 | Data Factory | In Production | DF | GDIA | CPELTZE1 | SS348 | NSEGUIN3 | RPOLLO13 | Bronze | S-Ox In Scope | 311 | No | Yes | COTS | DTERPST1 | MLYONS23 | Enterprise Technology | 311 | Streamline IT processes using correct patterns and use cases |  | Springboot | YES | 1 | FRANBELL | PLM | Java < v21 | Q1 2026 | Version Upgrade | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
50701 | Data Aggregator | In Production | DataAg | FORD CREDIT | DTAURO | JJACK348 | VKHANNA1 | NVARADA2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | Data Aggregator is a Java batch application and it updates Salesforce.com with DISNE and EDW data on a daily basis. |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
24175 | Ford of Canada Cognos | In Production | FocCognos | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | Marketing, Sales and Service | Cognos is a web-based integrated Business Intelligence suite by IBM. It provides a toolset for reporting, analysis, scorecarding, and monitoring of events and metrics. The software consists of several components to meet different information requirements in a company. | 8 |  | YES | 2 | NKANDULA | PLM | VM | Q1 2027 | EDC New Hypervisor | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [14 empty] | No | VM
52687 | Data Activation Portal | In Production | DG - DAP | GDIA | CPELTZE1 | NSEGUIN3 | NSHAMSI1 | RPOLLO13 | Bronze | Non S-Ox | 221 | No | Yes | In-House | LDANGELO | MGARRET2 | Enterprise Technology | 221 | Allow automation of access approval and provisioning |  | Springboot | YES | 3 | FRANBELL | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2025-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
52687 | Data Activation Portal | In Production | DG - DAP | GDIA | CPELTZE1 | NSEGUIN3 | NSHAMSI1 | RPOLLO13 | Bronze | Non S-Ox | 221 | No | Yes | In-House | LDANGELO | MGARRET2 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Allow automation of access approval and provisioning |  |  | YES | 3 | FRANBELL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2024-12-20 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% | [7 empty] | No | SQL
21243 | Ford Credit Treasury Insurance Risk System - TIRS | In Production | FCTIRS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Bronze | Non S-Ox | 231 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | Ford Treasurys Corporate Insurance Department will use the Treasury Insurance Risk System, known as TIRS, to assess risk and conduct insurance risk management. The application will automate Corporate Insurances process for collecting data and provide industry-standard reporting to facilitate risk management analysis and to manage internal risk related to insurance matters, support insurance claims, and the purchasing of insurance. | 6 |  | YES | 4 | SRAISIN1 | PLM | VM | Q1 2027 | EDC New Hypervisor | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
600 | Daily Production Reporting | In Production | DPR | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | FHIRSH | Manufacturing Staffs | Marketing, Sales and Service | DPR provides management with manufacturing and assembly plant production data from the previous day (close of business). It is a global application used by ford plants globally, both assembly and powertrain. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
600 | Daily Production Reporting | In Production | DPR | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | DPR provides management with manufacturing and assembly plant production data from the previous day (close of business). It is a global application used by ford plants globally, both assembly and powertrain. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
51697 | Ford Credit Smart Secure Documents | In Production | FCSSD | FORD CREDIT | DTAURO | DTAURO | EGOMATH1 | ASAXENA8 | Copper | Non S-Ox | 311 | No | Yes | In-House | DTAURO | EGOMATH1 | Ford Credit Services | Ford Credit (FMCC) | Ford Credit Smart Secure Document Management utilizing Adobe Forms connected to Customer and Account Data Feeds to create customer letters and forms. | 23 |  | YES | 3 | SRAISIN1 | PLM | VM | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
600 | Daily Production Reporting | In Production | DPR | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Bronze | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JEISIMIN | Manufacturing Staffs | Marketing, Sales and Service | DPR provides management with manufacturing and assembly plant production data from the previous day (close of business). It is a global application used by ford plants globally, both assembly and powertrain. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
18815 | Daily download from DID database into local DB | In Production | SQL DID | EPEO | ARAJKUMA | LEHLERS1 | JBRETT1 | LRODR205 | Bronze | Non S-Ox | - | Yes | No | Managed by 3rd Party Purchased Service | ARAJKUMA | IKOVALEV | Marketing & Sales | - | Daily download from DID database. The data is loaded into a local database, and used by various Business Managed Apps for Dealer Info. This application referes only to the Database portion. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
18119 | Ford Credit Finance Analytical System-FCFAS | In Production | FCFAS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | Non S-Ox | 222 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The objective of the Forecast project is to improve Ford Credit's borrowing cost forecasting capability using: 1 - An integrated system for assets and liabilities. 2 - Revised organizational roles and responsibilities. 3 - Common inputs and assumptions. 4 - A new analytical capability - through the creation of an analytical data base to provide 'historical' asset/liability measures via Excel based Olap reporting | 8 |  | YES | 3 | SRAISIN1 | PLM | VM | Q1 2027 | EDC New Hypervisor | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
50588 | Cycletool | In Production | Cycletool | ISIT | JKOONS | MNOVAK1 | HLIN11 | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | Cycletool is application to populate and screen data and displays report for vehicle energy management engineering. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
22713 | Ford Credit AEM Infrastructure | In Production | FCAEM | FORD CREDIT | NJOSHI21 | NJOSHI21 | NKOMMERA | ASAXENA8 | Silver | Non S-Ox | 11 | No | Yes | In-House | NJOSHI21 | ABARNA10 | Ford Credit Services | Ford Credit (FMCC) | This Adobe Experience Manager (AEM) platform has an authoring node which publishes content to publisher nodes. General Usage Clause: It is intented for AEM-based solutions used in the B2C space globally for varying sized systems, with multi-JVM vertical scaling, enabling the dedicated use at the JVM within a shared VM | 18 |  | YES | 1 | SRAISIN1 | PLM | VM | Q1 2027 | EDC New Hypervisor | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
56575 | Cycle Time Health | In Production | iiot-cth | ISIT | SKING68 | JLYNN1 | KKISIEL | AELANGO | Bronze | Non S-Ox | 111 | No | Yes | - | SKING68 | JLYNN1 | Manufacturing Engineering | - | Shows Cycle Time Health per hour per shift. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
11585 | FCSD Imaging and Workflow | In Production | Warranty | FORD PRO & FCSD TECH | RKENNEL | PPRASAN2 | SDEENAD1 | SDHANAS2 | Silver | Non S-Ox | 211 | No | Yes | Managed by 3rd Party Purchased Service | RKENNEL | PPRASAN2 | Ford Customer Service | FCSD Tech | This application provides document storage and management services to Ford Global Warranty claims processing. Warranty Imaging FileNet | 3 |  | YES | 2 | RKENNEL | PLM | VM | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
22431 | Electronic Parts Claims (EPC) | In Production | PART CLAIM | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | Marketing, Sales and Service | Application that allows Ford of Canada Dealers to submit claims for parts that are damaged, mis-shipped, missing, etc. | 13 |  | YES | 1 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q1 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50140 | Duck Creek | In Production | AMROClaims | FORD CREDIT | DTAURO | DSHARM61 | SGABLE | VPOTTIBO | Silver | S-Ox In Scope | 331 | No | Yes | COTS | DTAURO | DSHARM61 | Ford Credit Services | Ford Credit (FMCC) | Duck Creek manages the entire Ford Credit AMRO claim management lifecycle from First Notice of Loss (FNOL) to investigation, payments, negotiations, reporting, and closure in an integrated solution. | 14 |  | YES | 5 | SRAISIN1 | PLM | VM | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
23650 | CVPODS - Connected Vehicle Payload Orchestration a | In Production | CVPODS | EVDD | JWASNIC1 | MBOMMANA | SPRADHAN | SPRADHAN | Platinum | Non S-Ox | 212 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 212 | CONNECTED VEHICLE PAYLOAD ORCHESTRATION AND DELIVERY SERVICES |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
50575 | CVNG - Connected Vehicle Notification Gateway | In Production | CVNG | EVDD | JWASNIC1 | JWASNIC1 | HPAPANAS | HPIERC10 | Gold | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Integrated Services | 111 | CVNG - CV NOTIFICATION GATEWAY TRIGGERS THE APP NOTIFICATIONS LEVERAGING CSDN NOTIFICATION SERVICES. IT SUPPORTS THE FOLLOWING NOTIFICATION METHODS: 1) EMAIL 2) PUSH NOTIFICATIONS 3) MESSAGE CENTER 4) SMS |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
6287 | CVMS | In Production | CVMS | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | CVMS - Company Vehicle Management System (US Only). Manages the company vehicle asset from order through disposal. Tightly integrated with MFV application. | 32 |  | YES | 4 | NKANDULA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
6287 | CVMS | In Production | CVMS | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | CVMS - Company Vehicle Management System (US Only). Manages the company vehicle asset from order through disposal. Tightly integrated with MFV application. |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
6287 | CVMS | In Production | CVMS | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Silver | S-Ox In Scope | 333 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | CVMS - Company Vehicle Management System (US Only). Manages the company vehicle asset from order through disposal. Tightly integrated with MFV application. |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
23329 | Dealer Communication | In Production | DlrComm | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | Marketing, Sales and Service | An online tool for Ford of Canada Dealers and In-house users to manage the creation, editing, reviewing, approving and publishing process for bulletins and surveys with their dealership. The application also allows the dealers to target the audience for each bulletin/survey. | 3 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q1 2027 | Complete Migration to GCP (Both App & DB) | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50453 | CV Integration Data and Device Management | In Production | CVDDM | EVDD | NDIMMITT | DCHAMB77 | SCUNNIN8 | SCUNNIN8 | Copper | Non S-Ox | 111 | No | Yes | In-House | NDIMMITT | DCHAMB77 | Advanced PD and Tech | - | This system provides Data Management service, Device Management service, Data Validation Service and Health Checkup for Test Data Setup Core systems in lower environment |  |  | YES | 3 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
21415 | Business Objects - Shared | Active | BusObj-SE | EPEO | SKULKA52 | MWILLI20 | TCULLER | RMODI2 | Silver | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | ITO | *NO NEW BO APPS ALLOWED* The Business Objects Shared Environment provides the enterprise a shared platform capable of hosting multiple discrete Business Objects reporting applications. The business criticality rating cannot be easily calculated. It is assumed to be A since the sum of the hosted applications BCA ratings would likely result in an A rating. | 23 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2027 | Will be Decommissioned | Decommission | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned | [17 empty] | VM
50453 | CV Integration Data and Device Management | In Production | CVDDM | EVDD | NDIMMITT | DCHAMB77 | SCUNNIN8 | SCUNNIN8 | Copper | Non S-Ox | 111 | No | Yes | In-House | NDIMMITT | DCHAMB77 | Advanced PD and Tech | - | This system provides Data Management service, Device Management service, Data Validation Service and Health Checkup for Test Data Setup Core systems in lower environment |  |  | YES | 3 | MJONE308 | PLM | WAS | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
23474 | CV Business and Operations Portal | In Production | CVBOP | EVDD | JWASNIC1 | ACHRIS39 | VMARIUCC | JBENNER6 | Gold | Non S-Ox | 322 | No | Yes | In-House | JWASNIC1 | ACHRIS39 | Advanced PD and Tech | 322 | Connected Vehicle Portal and Dashboard will act as a common platform to configure vehicles (via RDR, CARMON, PARSED, FOTA Etc.) for vehicle diagnostic/rich vehicle data collection at vehicle and individual module level via common APIs. view Data and Reports / Dashboard / Feature KPIs / advanced analytics. Querying any vehicle record to address vehicle operations issues. |  | Springboot | YES | 3 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
23474 | CV Business and Operations Portal | In Production | CVBOP | EVDD | JWASNIC1 | ACHRIS39 | VMARIUCC | JBENNER6 | Gold | Non S-Ox | 322 | No | Yes | In-House | JWASNIC1 | ACHRIS39 | Advanced PD and Tech | - | Connected Vehicle Portal and Dashboard will act as a common platform to configure vehicles (via RDR, CARMON, PARSED, FOTA Etc.) for vehicle diagnostic/rich vehicle data collection at vehicle and individual module level via common APIs. view Data and Reports / Dashboard / Feature KPIs / advanced analytics. Querying any vehicle record to address vehicle operations issues. |  |  | YES | 3 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50332 | AEM Europe (Adobe Experience Manager) | In Production | AEMEU | FORD PRO & FCSD TECH | TJUNIPER | AMEIKLE | SPEGG2 | JCOY3 | Gold | Non S-Ox | 223 | No | Yes | COTS | TJUNIPER | AMEIKLE | Enterprise Technology | Marketing, Sales and Service | Adobe Experience Manager is the Web Content Management standard for B2C websites replacing Oracle WebCenter Sites/FatWire. | 72 |  | YES | 1 | RKENNEL | PLM | VM | Q1 2027 | Complete Migration to SaaS | Modernize | 2027-03-15 | 2027-03-15 |  | Not Started |  | 2027-06-13 |  | Planned |  | No | [14 empty] | No | VM
50321 | CV Authorization Service | In Production | CVAS | EVDD | JWASNIC1 | JWASNIC1 | STHOTTE1 | NPAPANAS | Gold | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 322 | CV AUTHORIZATION SERVICES TO ENABLE USER VEHICLE AUTHORIZATION ON TMC TO OFFER VEHICLE CONNECTIVITY FOR RETAIL, FLEET & FORD BACKEND APPLICATIONS. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
51393 | X-Carline Chart | In Production | XCC | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Current technical solution is a SQL-database providing one single data source for all global programs. Future development of the next generation of the X-Carline Chart targets at increased efficiency with further data | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
51417 | Vehicle Cybersecurity Access | In Production | ECUKG | ISIT | MNOWICK1 | PBORGAO1 | SBELSAR1 | GRAO3 | Silver | Non S-Ox | 221 | No | Yes | In-House | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | Industrial System IT | Tool and processes for ECU Key Generation requests, approvals, and distribution. | 5 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
56103 | Customer Value Demonstrator | In Production | CVD | FORD PRO & FCSD TECH | DNANDAN | CFORSYT1 | CFORSYT1 | SDHANAS2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | ZKOUL | General Management | - | Web App to support the FORDLiive Business team to demonstrate the value of FORDLiive+ to a Liive+ Customer |  | Springboot | YES | 1 | RKENNEL | PLM | Java < v21 | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-30 |  | In-Progress | Green | 2026-03-30 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | No VM found | No | Java < v21
50080 | Customer Service Forecast Consolidation Essbase | In Production | CSFC | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 321 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Standardize and improve Asia Pacific FCSD Financial planning & analysis activities specific to Budget and Forecast and improvement of the Financial Planning & Analysis on FCSD Forecast Reporting which cannot be supported by IMPRS. | 35 |  | YES | 3 | TSWEEN16 | PLM | Datastage | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | DA
50080 | Customer Service Forecast Consolidation Essbase | In Production | CSFC | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 321 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Standardize and improve Asia Pacific FCSD Financial planning & analysis activities specific to Budget and Forecast and improvement of the Financial Planning & Analysis on FCSD Forecast Reporting which cannot be supported by IMPRS. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
51013 | Workflow II FAFC | In Production | WFIIFAFC | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | Non S-Ox | 222 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | - | Provides initiate and routing activities related to Account Service Request, Charge Off, Direct Debit, Financial Change Notice (FCN), New Document Follow-up (NDF), Print Lien Release, Admin and Role Change that are utilized by Shanghai Business Center in China. Includes Server Components and Mainframe compents. | 3 |  | YES | 3 | SRAISIN1 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2025-06-15 |  | Planned | [17 empty] | VM
23328 | Customer Loyalty and Retention | In Production | CusLoylRet | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Customer Experience | Marketing, Sales and Service | The Customer Loyalty and Retention application supports Ford of Canada Dealers in enhancing customer satisfaction and loyalty by assisting dealership personnel in selecting the right Loaner program for a specific repair, helping customers with partial payment of cost of repair once their warranty has expired, and providing their customers with alternate transportation (loaner or shuttle vehicles), while their vehicles are being serviced. |  |  | YES | 4 | NKANDULA | PLM | Java Struts |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
23328 | Customer Loyalty and Retention | In Production | CusLoylRet | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Customer Experience | Marketing, Sales and Service | The Customer Loyalty and Retention application supports Ford of Canada Dealers in enhancing customer satisfaction and loyalty by assisting dealership personnel in selecting the right Loaner program for a specific repair, helping customers with partial payment of cost of repair once their warranty has expired, and providing their customers with alternate transportation (loaner or shuttle vehicles), while their vehicles are being serviced. |  |  | YES | 4 | NKANDULA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-08-31 | Complete | Blue | 2024-12-15 | 2024-10-21 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | migrated to PostgreSQL | No | SQL
22002 | WebFOCUS - Shared | Active | WFOCUS-SE | EPEO | SKULKA52 | MWILLI20 | TCULLER | RMODI2 | Silver | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | ITO | WebFOCUS shared environment for Ford Motor. Built on TIBCO WebFOCUS. | 28 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
23328 | Customer Loyalty and Retention | In Production | CusLoylRet | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Customer Experience | Marketing, Sales and Service | The Customer Loyalty and Retention application supports Ford of Canada Dealers in enhancing customer satisfaction and loyalty by assisting dealership personnel in selecting the right Loaner program for a specific repair, helping customers with partial payment of cost of repair once their warranty has expired, and providing their customers with alternate transportation (loaner or shuttle vehicles), while their vehicles are being serviced. |  |  | YES | 4 | NKANDULA | PLM | WAS |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | Need to check if there was a WAS? | No | Java < v21
50444 | WebEx Teams BOTs and Integrations | In Production | WebExBOTS | EPEO | SRUNSON | PWILL357 | NRAMJI | GSIENKIE | Copper | Non S-Ox | 312 | No | Yes | In-House | SRUNSON | PWILL357 | Enterprise Technology | EPEO | This application is to host the BOTs and Integrations developed for WebEx teams. | 3 |  | YES | 3 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
52081 | Customer Experience | In Production | CX | FORD CREDIT | RMINHAS3 | SSINGH14 | CARNOLD9 | VBHUPATH | Silver | Non S-Ox | 211 | No | Yes | In-House | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | Provide surveys and interactive analytics of our Ford Credit customer feedback |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
52850 | CRM for Third Party Enablement | In Production | TPE CRM | EVDD | JWASNIC1 | RBUITEWE | ABIANC15 | WESTES6 | Silver | Non S-Ox | 111 | No | Yes | COTS | JWASNIC1 | RBUITEWE | Advanced PD and Tech | - | The Developer Marketplace team in Model e use MS Dynamics 365 solutions to manage the activities related to User management, Marketing, Sales (Lead and Account) management and Case management. This application as global CRM system helps to coordinate customer partnerships, people, processes and technologies to render the ultimate mobility customer experience. |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
12096 | W2 Online | In Production | W2 | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | Display W2 online for salaried employees. | 7 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12336 | CRM Core -CuPID | In Production | Core-CuPID | GDIA | EBLOCH | LDESHPAN | RROBI177 | AJOGIYAT | Silver | Non S-Ox | 311 | No | Yes | - | EBLOCH | LDESHPAN | Enterprise Technology | - | Customer and Prospect Information Database for Marketing. Covers Ford brand in the European region with 27 active Markets at various levels of maturity; some use full CRM services and some do not. For a further 12 markets, infrastructure is in place and data capture was previously enabled but then switched off as no business owner identified. 7 other markets have infrastructure in place but no significant data captured. 5 markets have no infrastructure in place but still have a tiny volume of dummy customers |  |  | NO | 1 | FRANBELL | PLM | Mainframe |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
51473 | Stamping Die Buy-off | In Production | SDBO | ISIT | SKING68 | JLYNN1 | GKESAVAR | AELANGO | Silver | Non S-Ox | 211 | Yes | No | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | - | Stamping Die Buy-off is a web app that manages die checksheets for validation before buy off |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | SQL
51473 | Stamping Die Buy-off | In Production | SDBO | ISIT | SKING68 | JLYNN1 | GKESAVAR | AELANGO | Silver | Non S-Ox | 211 | Yes | No | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | - | Stamping Die Buy-off is a web app that manages die checksheets for validation before buy off | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50241 | Vehicle Environmental Engineering | In Production | VEE | ISIT | OTHERS | MFUHER | MGUENTHE | TTOBOLSK | Copper | Non S-Ox | 311 | Yes | No | In-House | PHARDIGA | MFUHER | Policy | - | Vehicle Environmental Engineering Data system for preparing information for regulatory compliance. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
16968 | Credit Bureau Report-CBR | In Production | CBR | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Bronze | Non S-Ox | 332 | No | Yes | In-House | JMALETZ | SGATTI | Ford Credit Services | Ford Credit (FMCC) | Allows end user to request a stand-alone commercial or consumer credit bureau report. A second function is to retrieve contact information on a company. |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q3 2027 | Will be Decommissioned | Decommission | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
53257 | Credit Application Processing Engine (formerly Off | In Production | CAPE | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 322 | THIS IS A CREDIT APPLICATION ORCHESTRATOR WITH AN API TO HANDLE ALL THE OFFER TRANSACTIONS FROM ROUTEONE AND DEAL OPTIMIZER. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q3 2027 | Version Upgrade | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
22161 | Crash Designer 2.9.1 | In Production | CLCD | ISIT | JPITTERL | MZIRWES1 | RKAREN | JLUCAS1 | Bronze | Non S-Ox | 211 | Yes | No | In-House | CBOHN | MZIRWES1 | PD Operations and Quality | Industrial System IT | Crash Designer is a software application for data acquisition purpose in crash testing from vendor Kistler. It is separated in two parts. The first part is management of test equipment (sensors and measurement devices) and preparation of test sequences. The second part manages the execution of tests and provides measurement results in various formats. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
52678 | TrueSight Orchestration | In Production | TSO | EPEO | RHAMMO57 | JGIES | AMANI1 | GSIENKIE | Silver | Non S-Ox | 223 | No | Yes | COTS | RHAMMO57 | JGIES | Enterprise Technology | EPEO | True Sight Orchestration (TSO) is a BMC Business Process Automation tool. We plan to use this to automate manual/routine ITSM processes. | 13 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
56590 | Trend Micro Workload Security | In Production | TMWS | EPEO | NOKEEFE | VNACHIMU | PFREILE | WJUSTICE | Silver | Non S-Ox | 332 | No | Yes | COTS | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | Trend Micro Workload Security will be responsible for protecting Ford Motor Company's critical infrastrustructure through the use of Intrusion Preventation and Detection System. | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to SaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
11001 | CPR II | In Production | EuAS-CPRII | ISIT | VVIJAY55 | RADAM10 | SMAHES11 | SSENTH15 | Gold | S-Ox In Scope | 231 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | The Carrier Payment Routine is an Automated Freight Payment System for Vehicle Transportation and Handling Services that pays the Carrier for the transport or handling after the event and books this payment automatically under the FORD account previously defined for this segment. The two processes featured in CPR are (1) Self Billing Invoice Process (SBI) and (2) Invoice Checking Process (ICP). |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q4 2026 | Move Capabilities to SaaS Solution | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
21145 | CPMD - Central Product Marketing Data | In Production | CPMD | M&S TECH | FHIRSH | GVIJI | STHANGAV | JCOY3 | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | - | Product marketing solution for FoE Configurator, based on Adobe AEM. CPMD is a central repository for ALL customer-facing (marketing) descriptions. 1) System allows users to assign marketing descriptions to WERS codes. 2) System enables these descriptions to be re-used across models, model years or markets, without re-keying. 3) System facilitates workflow to enable translations/approvals/both. 4) Descriptions are distributed via GForce application (ITMS21144) and can be consumed by any UI that has a GForce applicationID (Web, Mobile, internal, external etc) 5) CPMD enables CV's to be sold as PV's, Vignale to be offered as a brand (if req), selling of global vehicles into EU, Accessories to be integrated into configurator; 'series as a brand' (e.g ST), used vehicle specifications for eUsed and much more. CPMD is a replacement for CDMWEPT application in Europe |  |  | YES | 4 | NKANDULA | PLM | Java Struts | TBD | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-23 | 2024-12-23 | Complete | Blue | 2024-12-23 | 2024-12-23 | Complete |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
21145 | CPMD - Central Product Marketing Data | In Production | CPMD | M&S TECH | FHIRSH | GVIJI | STHANGAV | JCOY3 | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | - | Product marketing solution for FoE Configurator, based on Adobe AEM. CPMD is a central repository for ALL customer-facing (marketing) descriptions. 1) System allows users to assign marketing descriptions to WERS codes. 2) System enables these descriptions to be re-used across models, model years or markets, without re-keying. 3) System facilitates workflow to enable translations/approvals/both. 4) Descriptions are distributed via GForce application (ITMS21144) and can be consumed by any UI that has a GForce applicationID (Web, Mobile, internal, external etc) 5) CPMD enables CV's to be sold as PV's, Vignale to be offered as a brand (if req), selling of global vehicles into EU, Accessories to be integrated into configurator; 'series as a brand' (e.g ST), used vehicle specifications for eUsed and much more. CPMD is a replacement for CDMWEPT application in Europe |  |  | YES | 4 | NKANDULA | PLM | SQL | TBD | Already decommissioned(Q4 2024) | Decommission | 2024-12-15 | 2024-12-23 | 2024-12-23 | Complete | Blue | 2024-12-23 | 2024-12-23 | Complete |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
23175 | ThreatConnect On-Premises | In Production | TIP | EPEO | NOKEEFE | NOKEEFE | VVENKA40 | GSIENKIE | Silver | Non S-Ox | 222 | No | Yes | COTS | UARJUNAN | NOKEEFE | Enterprise Technology | EPEO | The ThreatConnect application is used by Cyber Defense Center (CDC) for Threat Management. | 20 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
21145 | CPMD - Central Product Marketing Data | In Production | CPMD | M&S TECH | FHIRSH | GVIJI | STHANGAV | JCOY3 | Silver | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | GVIJI | Marketing & Sales | - | Product marketing solution for FoE Configurator, based on Adobe AEM. CPMD is a central repository for ALL customer-facing (marketing) descriptions. 1) System allows users to assign marketing descriptions to WERS codes. 2) System enables these descriptions to be re-used across models, model years or markets, without re-keying. 3) System facilitates workflow to enable translations/approvals/both. 4) Descriptions are distributed via GForce application (ITMS21144) and can be consumed by any UI that has a GForce applicationID (Web, Mobile, internal, external etc) 5) CPMD enables CV's to be sold as PV's, Vignale to be offered as a brand (if req), selling of global vehicles into EU, Accessories to be integrated into configurator; 'series as a brand' (e.g ST), used vehicle specifications for eUsed and much more. CPMD is a replacement for CDMWEPT application in Europe |  |  | YES | 4 | NKANDULA | PLM | WAS | TBD | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-23 | 2024-12-23 | Complete | Blue | 2024-12-23 | 2024-12-23 | Complete |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
20162 | Cost Reduction Idea Database 2 | In Production | CRID2 | ISIT | MNOWICK1 | LSRINIVA | RSTOCKTO | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | A system for managing cost-reducing ideas for current model vehicles. First version will target design ideas on current-model vehicles (0-18 months) |  |  | YES | 4 | BWUNNAVA | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
20162 | Cost Reduction Idea Database 2 | In Production | CRID2 | ISIT | MNOWICK1 | LSRINIVA | RSTOCKTO | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | A system for managing cost-reducing ideas for current model vehicles. First version will target design ideas on current-model vehicles (0-18 months) |  |  | YES | 4 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
20501 | Teradata DBMS | Active | Teradata | EPEO | SKULKA52 | MWILLI20 | SYERASI | GARUNAC1 | Bronze | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | ITO | It covers all software as part of the Teradata DBMS purchase - this includes the DBMS, the Teradata utilities (x86, mainframe and desktop client), and Viewpoint. | 8 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
20162 | Cost Reduction Idea Database 2 | In Production | CRID2 | ISIT | MNOWICK1 | LSRINIVA | RSTOCKTO | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | A system for managing cost-reducing ideas for current model vehicles. First version will target design ideas on current-model vehicles (0-18 months) |  |  | YES | 4 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
53250 | Cost Ideas Authority | In Production | CIA | GDIA | AMADDULA | RVISWAN1 | TMAHALAK | GCARLSO2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KLIDDLE | RVISWAN1 | Enterprise Technology | 211 | . The proposed Cost Savings Warehouse tool will allow the user to start with a cost savings idea, assess it for applicability to forward model and existing production, replicate it broadly, and deploy it to usage. |  | Springboot | YES | 2 | FRANBELL | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-02-28 | 2025-02-28 | 2025-02-28 | Complete | Blue | 2025-03-15 | 2025-03-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | [5 empty] | No | Java < v21
53250 | Cost Ideas Authority | In Production | CIA | GDIA | AMADDULA | RVISWAN1 | TMAHALAK | GCARLSO2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KLIDDLE | RVISWAN1 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | . The proposed Cost Savings Warehouse tool will allow the user to start with a cost savings idea, assess it for applicability to forward model and existing production, replicate it broadly, and deploy it to usage. |  |  | YES | 2 | FRANBELL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-02-28 | 2025-02-28 | 2025-02-28 | Complete | Blue | 2025-03-15 | 2025-03-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
53463 | Cost Analysis | In Production | COSTSCAN | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | RSRINI38 | Bronze | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | - | DPA project to perform parts price comparison |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
20539 | System Center Operations Manager (SCOM) for SCCM | In Production | SCOMSMS | EPEO | SRUNSON | ASTONE31 | CHOSSEIN | BNABOZNY | Bronze | Non S-Ox | 111 | Yes | No | COTS | SRUNSON | ASTONE31 | Enterprise Technology | - | System Center Operations Manager is a Microsoft tool set used for monitoring several enterprise Microsoft products. In this particular situation it is monitoring the global System Center Configuration Manager environment. | 6 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
51722 | Mfg Digital Twin | In Production | MFGDigTwin | ISIT | SKING68 | JLYNN1 | KKISIEL | AELANGO | Copper | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Digital Twin for Manufacturing Process | 2 |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-09-30 | 2024-09-30 | 2024-09-23 | Complete | Blue | 2024-10-25 | 2024-10-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Ramesh | 2025-03-17 |  |  |  | No | VM
20693 | Symantec Anti-Malware (SEP) | Planned | AntiMalwar | EPEO | NOKEEFE | VNACHIMU | PFREILE | WJUSTICE | Silver | Non S-Ox | 211 | No | Yes | - | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | Corporate Anti-Malware (Virus and Spyware Protection) Solution - Symantec. | 11 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
11409 | Corporate Procurement and Receiving System (CPARS) | In Production | CPARS | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | CPARS - Corp Procurement & Receiving System - Manages requisitioning, sourcing, purchasing, and receiving of non-prod materials. Includes 2 Subsystems - Boss90 for Blanket Orders and Part Spec for Inventory Items. | 2 |  | YES | 4 | TSWEEN16 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11409 | Corporate Procurement and Receiving System (CPARS) | In Production | CPARS | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | CPARS - Corp Procurement & Receiving System - Manages requisitioning, sourcing, purchasing, and receiving of non-prod materials. Includes 2 Subsystems - Boss90 for Blanket Orders and Part Spec for Inventory Items. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
11409 | Corporate Procurement and Receiving System (CPARS) | In Production | CPARS | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | CPARS - Corp Procurement & Receiving System - Manages requisitioning, sourcing, purchasing, and receiving of non-prod materials. Includes 2 Subsystems - Boss90 for Blanket Orders and Part Spec for Inventory Items. |  |  | YES | 4 | TSWEEN16 | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11409 | Corporate Procurement and Receiving System (CPARS) | In Production | CPARS | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | CPARS - Corp Procurement & Receiving System - Manages requisitioning, sourcing, purchasing, and receiving of non-prod materials. Includes 2 Subsystems - Boss90 for Blanket Orders and Part Spec for Inventory Items. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
21555 | Corporate knowledge Wiki | In Production | CKW | ISIT | JKOONS | NLAKSHMA | MMAHIMA | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JKOONS | NLAKSHMA | Quality | Industrial System IT | Wiki based on Confluence-(Atlassian-vendor). Designed to store corporate knowledge using the power of Wiki. Initially to store Quality Procedures and allow organic growth across the company. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50623 | Symantec Advanced Threat Protection | In Production | ATP | EPEO | NOKEEFE | VNACHIMU | PFREILE | WJUSTICE | Silver | Non S-Ox | 211 | No | Yes | - | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | Gathers external security threat information | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
19934 | CORL replacement | In Production | CORL REPL | ISIT | JKOONS | MNOVAK1 | JSURESHR | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | COTS | JKOONS | JKOONS | PD Operations and Quality | Industrial System IT | This project will provide a vendor-supplied, web-based data archive, retrieval, reporting, and plotting system that will provide the following benefits for Road Load Durability Engineering: -improve search capability -enhance search results reports -improve customer satisfaction -reduce IT support burden |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
19934 | CORL replacement | In Production | CORL REPL | ISIT | JKOONS | MNOVAK1 | JSURESHR | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | COTS | JKOONS | MNOVAK1 | PD Operations and Quality | Industrial System IT | This project will provide a vendor-supplied, web-based data archive, retrieval, reporting, and plotting system that will provide the following benefits for Road Load Durability Engineering: -improve search capability -enhance search results reports -improve customer satisfaction -reduce IT support burden |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
53666 | STORAGE DATA PROTECTION SERVICE | Active | DPAAS | EPEO | LFULCHER | RMANNING | ACHALME4 | RCLAFFEY | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | RMANNING | Enterprise Technology | ITO | Data Protection Services (Backup & Restore) delivered to consumers via Storage as a Service ITO offering. Entry defines the technologies that are used to support this service offering to support global infrastructure deployments. | 101 |  | YES | 3 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
52834 | Core Content Storage Services | In Production | CCSS | FORD CREDIT | DTAURO | JJACK348 | NBHALWAN | ROBRIEN3 | Silver | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 322 | CCSS PROVIDES APIS(APPLICATION PROGRAMMING INTERFACE) TO STORE AND RETRIEVE DOCUMENTS FROM OBJECT STORAGE. THE STORED DOCUMENTS WILL BE ACCESSED VIA APIS BY CONSUMING APPLICATIONS AND SERVICES FOR THE PURPOSE OF SERVICING CUSTOMERS AND DEALERS AT FORD AND FORD CREDIT. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
50791 | South America Customs API | In Production | CustomsAPI | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | Provide communication between legacy applications and OneSource Global Trade solution (50790). It manages data transformation to attend all requirements related to customs data need for Ford applications and for OneSource controls. | 12 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
899 | Control Of Requisitions and Approvals | In Production | CORA | I-ERP | SARAUJO3 | VANURAD2 | AATHILAK | SNAG1 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Provides mechanised processes for raising Purchase Notices, blanket order releases, and revision notices for facilities, services and non production materials for expense and project requisitions. The line manager and financial approval processes |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
53217 | Contract API | In Production | ContracAPI | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Silver | Non S-Ox | 223 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 223 | PROCESS ALL CONTRACT TRANSACTIONS FROM ROUTEONE TO PINNACLE |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q3 2027 | Version Upgrade | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned | [17 empty] | Java < v21
11973 | ConTrack - European Container Tracking Sys | In Production | EuMP-CONTR | FORD PRO & FCSD TECH | CHURLEY3 | AHOFFM15 | DJOHN675 | DJOHN675 | Copper | Non S-Ox | 111 | No | Yes | In-House | NBAECKER | AHOFFM15 | Manufacturing Staffs | Industrial System IT | Container Tracking (ConTrack) was initiated by the European Ford Material Planning & Logistics (MP&L) department. The primary function of the application is to retrieve shipment data from the global Ford MP&L system CMMS3(DataMart) for specific container types and reporting of current and historic container balances at plant and supplier sites. |  | WAS | YES | 2 | RKENNEL | PLM | Java < v21 | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
11973 | ConTrack - European Container Tracking Sys | In Production | EuMP-CONTR | FORD PRO & FCSD TECH | CHURLEY3 | AHOFFM15 | DJOHN675 | DJOHN675 | Copper | Non S-Ox | 111 | No | Yes | In-House | NBAECKER | AHOFFM15 | Manufacturing Staffs | Industrial System IT | Container Tracking (ConTrack) was initiated by the European Ford Material Planning & Logistics (MP&L) department. The primary function of the application is to retrieve shipment data from the global Ford MP&L system CMMS3(DataMart) for specific container types and reporting of current and historic container balances at plant and supplier sites. |  |  | YES | 2 | RKENNEL | PLM | Oracle | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
52517 | Contest and Incentives Systems | In Production | CIS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TBABU | SDHANAS2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | - | Effective implementation of ESB Vehicle Management programs by having system capabilities 1) To define the Program Targets 2) Measure the dealer performance 3) Insights to dealers on performance & standing 4) Payment to dealer and their staff |  |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
11952 | Shipping Instructions | In Production | ShipInst | ISIT | VVIJAY55 | RADAM10 | KARUNKU4 | SSENTH15 | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Staffs | Industrial System IT | Shipping Instructions is the Global Logistics shipping instructions website to develop and distribute shipping instructions to internal and external users. Logistics providers send data to SI, which in turn sends route information to CMMS3 (HMRSII, WIP6, Supplier Performance), Cass freight payment and premium, and OFM Data Warehouse. | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52517 | Contest and Incentives Systems | In Production | CIS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TBABU | RKADAM1 | Bronze | Non S-Ox | 211 | No | Yes | In-House |  |  | Ford Customer Service | - | Effective implementation of ESB Vehicle Management programs by having system capabilities 1) To define the Program Targets 2) Measure the dealer performance 3) Insights to dealers on performance & standing 4) Payment to dealer and their staff |  | Springboot | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | Q3 2026 | Version Upgrade | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
14892 | Contest and Incentive Wizard (CIW) | In Production | CIW | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Silver | Non S-Ox | 221 | No | Yes | In-House | VMUTHUPA | RANANDAL | Ford Customer Service | - | This application supports FCSD Contests and Incentive programs internally within Ford by providing a configurable tool that puts much of the website set up in the hands of the business owners. |  |  | YES | 4 | NKANDULA | PLM | Java Struts | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-11-01 | Complete | Blue | 2024-12-15 | 2025-02-28 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | As per PCF exit, team migrated to Springboot | No | Java < v21
14892 | Contest and Incentive Wizard (CIW) | In Production | CIW | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Silver | Non S-Ox | 221 | No | Yes | In-House | KHEMANT | RANANDAL | Ford Customer Service | - | This application supports FCSD Contests and Incentive programs internally within Ford by providing a configurable tool that puts much of the website set up in the hands of the business owners. |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q4 2024 | Rewrite apps to GCP | Modernize |  |  |  | In-Progress |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
14892 | Contest and Incentive Wizard (CIW) | In Production | CIW | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Silver | Non S-Ox | 221 | No | Yes | In-House | KHEMANT | RANANDAL | Ford Customer Service | - | This application supports FCSD Contests and Incentive programs internally within Ford by providing a configurable tool that puts much of the website set up in the hands of the business owners. |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
14892 | Contest and Incentive Wizard (CIW) | In Production | CIW | M&S TECH | VMUTHUPA | RANANDAL | PP5 | JHARPER2 | Silver | Non S-Ox | 221 | No | Yes | In-House | KHEMANT | RANANDAL | Ford Customer Service | - | This application supports FCSD Contests and Incentive programs internally within Ford by providing a configurable tool that puts much of the website set up in the hands of the business owners. |  |  | YES | 4 | NKANDULA | PLM | WAS | Q4 2024 | Rewrite | Modernize | 2024-12-15 | 2024-12-15 | 2024-11-01 | Complete | Blue | 2024-12-15 | 2025-02-28 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | As per PCF exit, team migrated to Springboot | No | Java < v21
53322 | Consumer Incident Vehicle Information Questionnair | In Production | CIVIQ | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 11 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | New application namely CIVIQ (Consumer Incident Vehicle Information Questionnaire), to be created to replace VOQ (Vehicle Owner Questionnaire). VOQ system is supporting English language currently and in future system must support other languages such as Chinese, Taiwan, Spanish etc., Users exists globally. It helps to identify potential vehicle safety issues at the early stage and reduction of warranty costs. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2024-09-30 | 2024-09-30 | 2024-09-16 | Complete | Blue | 2025-01-13 | 2025-01-13 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Priya | 2025-03-05 |  |  | App migrated in 3Q 2024 & Infra Decommission complete in Q1 2025 | No | SQL
54387 | Service Asset and Configuration Management | In Production | SACM | EPEO | RHAMMO57 | JGIES | PSTRICK3 | GSIENKIE | Silver | Non S-Ox | 211 | No | Yes | Managed by 3rd Party Purchased Service | RHAMMO57 | JGIES | Enterprise Technology | EPEO | This application consists of Micro Focus AMX (Asset Management X) SaaS product and all the ETL required to populate data into the AMX or federate to a trusted data source. UD is an MicroFocus discovery tool focused on discovery CI relationships and storing that data in UCMDB. It is also used for inventory discovery. | 24 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
51724 | eFPS | In Production | eFPS | ISIT | SKING68 | JLYNN1 | JRICH264 | AELANGO | Copper | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Manufacturing Staffs | 111 | ELECTRONIC DIGITAL PROCESS SHEETS |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-09-30 | 2024-12-13 | 2024-12-13 | Complete | Blue | 2025-03-31 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 21 | Ramesh | 2025-03-17 |  |  |  | No | Java < v21
159 | Consignee Reconciliation | In Production | conrec | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 221 | No | Yes | In-House |  |  | Finance | FCSD Tech | Comparison between consignee month-end inventory and what Ford has identified as the consignee inventory. |  |  | YES | 1 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
50448 | Connected Vehicle Wholesale Audit | In Production | FCCVWA | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | VPOTTIBO | Gold | Non S-Ox | 222 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | Connected Vehicle Wholesale Audit(CvWA) formerly known as VIS, Leverages Modem technology from Ford Vehicles to abstract data from connected vehicle cloud to provide real-time wholesale unit locations for enhanced wholesale monitoring and real-time audit capabilities and trigger early warnings/alerts. The goal is to reduce the number of units to be physically inspected on Wholesale Audits YOY and provide data to assist risk mitigation metrics that will proactively prevent credit losses. Reduction in credit losses resulting from sold out of trust conditions. Potential savings in units that are audited: 70-75% of 1.4M / year. Avoid reputation risk in public marketplace. Risk avoidance resulting from improved line of sight on missing units. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned | [17 empty] | SQL
50694 | Secure Email | In Production | SECEMAIL | EPEO | NOKEEFE | VNACHIMU | BSARAV20 | ADOREZA | Silver | Non S-Ox | 111 | No | Yes | COTS | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | Secure Email (S/MIME) allows users to send S/MIME encrypted email. | 4 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
50448 | Connected Vehicle Wholesale Audit | In Production | FCCVWA | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | VPOTTIBO | Gold | Non S-Ox | 222 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Connected Vehicle Wholesale Audit(CvWA) formerly known as VIS, Leverages Modem technology from Ford Vehicles to abstract data from connected vehicle cloud to provide real-time wholesale unit locations for enhanced wholesale monitoring and real-time audit capabilities and trigger early warnings/alerts. The goal is to reduce the number of units to be physically inspected on Wholesale Audits YOY and provide data to assist risk mitigation metrics that will proactively prevent credit losses. Reduction in credit losses resulting from sold out of trust conditions. Potential savings in units that are audited: 70-75% of 1.4M / year. Avoid reputation risk in public marketplace. Risk avoidance resulting from improved line of sight on missing units. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
23399 | Connected Vehicle Feature Management Application | In Production | CVFMA | EVDD | JWASNIC1 | STHOTTE1 | CHOWEL12 | FSYED11 | Bronze | Non S-Ox | 212 | No | Yes | In-House | #N/A | #N/A | Integrated Services | 212 | CONNECTED VEHICLE FEATURE MANAGEMENT APPLICATION TO SUPPORT CAPABILITY, ENROLLMENTS, UNENROLLMENTS, FEATURES, FEATURE PACKAGE, VEHICLE PROFILE, EVENTS, AND PUSH ENROLLMENTS/CCS SETTINGS. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
52731 | Connected Vehicle Enrollment | In Production | CVFE | EVDD | JWASNIC1 | STHOTTE1 | CHOWEL12 | VJOYSON | Gold | Non S-Ox | 212 | No | Yes | In-House | #N/A | #N/A | Integrated Services | 212 | CORE ENROLLMENT COMPONENT OF CONNECTED VEHICLE ECOSYSTEM TO MANAGE AND GOVERN CV FEATURES OFFERED ACROSS BRANDS, REGIONS, AND RETAIL/FLEET CUSTOMERS. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
53975 | Connected Vehicle Data Base (China) | Planned | CVDB | EVDD | HHUANGJI | YZHOU159 | JSHAN | WJIN12 | Silver | Non S-Ox | - | No | Yes | In-House | HHUANGJI | YZHOU159 | Advanced PD and Tech | - | CVDB (Connected Vehicle Data Base) is a backend system that collects China Vehicle Data |  |  | YES | 1 | MJONE308 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
23636 | Connected Testing | In Production | ConTest | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Copper | S-Ox Out of Scope | 311 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | Connected Testing is a tool to support the VEV Operating System including short & long term planning. It offers efficiencies and savings in many facets of the Business and it links Data Management of Program DVPs with Facility Plans. |  |  | YES | 1 | BWUNNAVA | PLM | SQL | Q4 2027 | Modernize to Cloud Databases | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | SQL
23636 | Connected Testing | In Production | ConTest | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Copper | S-Ox Out of Scope | 311 | No | Yes | In-House |  |  | PD Operations and Quality | Industrial System IT | Connected Testing is a tool to support the VEV Operating System including short & long term planning. It offers efficiencies and savings in many facets of the Business and it links Data Management of Program DVPs with Facility Plans. |  | Springboot | YES | 2 | BWUNNAVA | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
50726 | Connected BlueZone | In Production | CBZ | EVDD | AGARBY | ACHRIS39 | SHOWE | RKRISH61 | Silver | Non S-Ox | 222 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 222 | THE CONNECTED BLUE ZONE (CBZ) PROJECT INTENDS TO LEVERAGE THE POWER OF CROWDSOURCED DATA FOR CREATING BLUEZONE ATTRIBUTES. CONNECTED BLUEZONE CLOUD APPLICATION PROVIDES A METHOD TO DELIVER A CONNECTED BLUEZONE MAP TO SUPPORT HIGHWAY ASSIST FEATURES. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
24129 | Confluence (EESEWiki) | In Production | EESEWiki | EVDD | JREYN149 | JREYN149 | MCHATTE1 | VVEINOTT | Copper | Non S-Ox | 311 | Yes | No | COTS | MJONE308 | JREYN149 | Advanced PD and Tech | - | Confluence is the current tool used for collaboration for EC projects. It is a rich wiki environment that supports creating pages, blog posts, questions, diagrams etc. |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
23063 | SCA-Customer | In Production | SCA-C | GDIA | CBUCKL19 | SPATIBAN | NTHAYANI | MPATEL20 | Silver | S-Ox In Scope | 322 | No | Yes | Managed by 3rd Party Purchased Service | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | It provides the ability to understand the interaction between enterprise actions (inc. Ford & Partners) and the customer lifecycle, determine which actions maximize the benefit to the customer and the enterprise and then track the actions through completion in a closed loop. | 41 |  | YES | 5 | FRANBELL | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-01-15 | 2027-06-29 |  | Not Started | Green | 2027-06-29 |  | Planned |  | No | [14 empty] | No | VM
9955 | CONCEPS Sales Entry | In Production | CSE | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Silver | Non S-Ox | 322 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | The online CONCEPS Sales Entry (CSE) application provides the entry point for all new vehicle sales, transfers, customer name and address changes, etc. for Ford and Lincoln Mercury Divisions, Ford of Canada and Ford of Mexico. |  |  | YES | 1 | NKANDULA | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
204 | Conceps | In Production | CN204 | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Online order entry system that allows dealers/fleets to immedidately and accurately configure, edit, and price out vehicle orders, and submit orders. New orders, alterations (spec. changes), and cancellations are supported. NOTE: also included within application is VSPS table maintenance; SERL and CPM / Old Acronym : CN SLA 1, CIA 2,3,3 |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q3 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
204 | Conceps | In Production | CN204 | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Online order entry system that allows dealers/fleets to immedidately and accurately configure, edit, and price out vehicle orders, and submit orders. New orders, alterations (spec. changes), and cancellations are supported. NOTE: also included within application is VSPS table maintenance; SERL and CPM / Old Acronym : CN SLA 1, CIA 2,3,3 |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
12627 | Computer Mgmt Interface | In Production | CMI | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Interface for Dealer Facing Web Based Training. https://web.cmi.dealerconnection.com/servlet/cmi2.ExternalAccessServlet?SA=USA&studentLangPref=en&requestTo=HomePageServlet |  |  | YES | 4 | NKANDULA | PLM | Java Struts | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
12627 | Computer Mgmt Interface | In Production | CMI | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | FHIRSH | FHIRSH | Customer Experience | Marketing, Sales and Service | Interface for Dealer Facing Web Based Training. https://web.cmi.dealerconnection.com/servlet/cmi2.ExternalAccessServlet?SA=USA&studentLangPref=en&requestTo=HomePageServlet |  |  | YES | 4 | NKANDULA | PLM | Oracle | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
52489 | Sales Exchanging Information System | In Production | SEIS | OCETO | DBRIGHEN | NMORALE7 | DFELTRI1 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | NMORALE7 | Marketing & Sales | - | SEIS receives from dealers all information related to retail and delivery vehicle information. Brazil knows it as CVVG information (Carta de venda varejo e garantia) and, Argentina, Chile, Peru and Colombia as TAE. | 4 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12627 | Computer Mgmt Interface | In Production | CMI | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Bronze | Non S-Ox | 111 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Interface for Dealer Facing Web Based Training. https://web.cmi.dealerconnection.com/servlet/cmi2.ExternalAccessServlet?SA=USA&studentLangPref=en&requestTo=HomePageServlet |  |  | YES | 4 | NKANDULA | PLM | WAS | Q2 2026 | Will be Decommissioned | Decommission | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-06-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
251 | Component Data Collection II (Traceability) | In Production | CDC-II | ISIT | SKING68 | KBARTHO1 | LMEENAKS | RPRASA22 | Copper | Non S-Ox | 121 | No | Yes | In-House | SKING68 | SKING68 | Enterprise Technology | Industrial System IT | Traceability of component serial numbers and the VIN of the vehicle in which the components were installed. Current components traced include front and side air bags, engines, transmissions, keycodes, fuel tanks, and tires. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
53676 | Sainapse | In Production | Sainapse | FORD PRO & FCSD TECH | DNANDAN | MAMUDHA | PVIVEKAN | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | - | DNANDAN | MAMUDHA | Enterprise Technology | - | Sainapse (COTS product) is an AI ML tool which has the below functionality 1. Creation and classification of tickets from incoming mails 2. Predict fields for creation of ticket from free text of ticket/request based on information available in ticketing system 3. Recommendation for resolution of tickets based on the past historical tickets and Knowledge Base Articles | 3 |  | YES | 1 | RKENNEL | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
52177 | Environmental Mass Properties Service | In Production | EMPS | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Silver | Non S-Ox | 222 | No | Yes | In-House | DKAVITHA | UVIJAYAL | PD Operations and Quality | Industrial System IT | Environmental view of vehicle weight data | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-10-01 | 2024-10-01 | 2024-05-22 | Complete | Blue | 2024-07-31 | 2024-07-30 | Complete |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52407 | Global Recall Implementation Database | In Production | GRID | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Silver | Non S-Ox | 231 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | GRID (Global Recall Implementation Database) is a fully integrated system to manage the analysis, preparation, approval, and launch of Field Service Actions. |  | Springboot | YES | 1 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-11-30 | 2024-11-30 | 2024-11-28 | Complete | Blue | 2024-12-20 | 2024-12-16 | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Priya | 2025-03-13 |  |  |  | No | Java < v21
52594 | Cortona 3D Training | In Production | C3DT | ISIT | SKING68 | JLYNN1 | KKISIEL | AELANGO | Bronze | Non S-Ox | 311 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | Deploy training material created by Cortona 3D application so that users on the plant floor can access it and get trained. |  |  | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | SQL
23330 | SA Fleet Control System | In Production | Fleec | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Ford Customer Service | - | Manage company fleet vehicle processes : order placement and tracking, documentation, release, maintenance, fines and rental payment, fuel consumption, incidents and sale. | 4 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
50092 | Compliance Accounting and Reporting Environment | In Production | CARE | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Bronze | Non S-Ox | 232 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | - | ICS, RAPS, PS GL GAPS and ERES delivers monthly data feeds to this tool. CARE was developed during an external German customs audit and is part of the GDIA database. This project is to transform the existing CARE tool to have automated feeds from source applications, create Data integration layer, IT compliant and scalable solution, which could be launched to GDIA Production environment and will be supported by IT team |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
23174 | RSA Archer GRC Platform | In Production | ArcherGRC | EPEO | NOKEEFE | NOKEEFE | VVENKA40 | WJUSTICE | Silver | Non S-Ox | 322 | No | Yes | COTS | UARJUNAN | NOKEEFE | Enterprise Technology | EPEO | The RSA Archer GRC application for Cyber Defense Center (CDC) for Case Management. | 16 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
53488 | Complexity Scorecard | In Production | CS | GDIA | KLIDDLE | MBURZLAF | MJADE2 | GGREEN5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KLIDDLE | MNOEL2 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | The goal of this tool to provide teams metrics on progress towards Complexity Targets |  |  | NO | 1 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
53710 | PYTHON SERVICE | Active | Python | EPEO | SKULKA52 | MWILLI20 | SBATHISH | GARUNAC1 | Bronze | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | ITO | The Python Service delivers (1) An internal repository of Python packages approved for Ford internal use, (2) Python package request service, and (3) Python clients for client & server-side use across multiple platforms (Windows & Linux). Service offering details, including repositories and clients in scope, can be found at: https://azureford.sharepoint.com/sites/analytics-service-customers/SitePages/Home.aspx | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
23948 | Common Vehicle Data Access Application | In Production | CVDA | EVDD | MMISHR12 | JVEDANAY | CRAMESH5 | JVEDANAY | Gold | Non S-Ox | 212 | No | Yes | In-House | MMISHR12 | JVEDANAY | Advanced PD and Tech | - | Defines configurations and delivers to vehicles. |  |  | YES | 1 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
565 | Common Security Interface | In Production | CSI | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 222 | No | Yes | In-House | SKING68 | SKING68 | Manufacturing Staffs | - | Common Security Interface (CSI)- for Plant Floor Systems. Provides for a single User ID & Password to use all plant applications integrated into utilizing CSI Authentication and Authorization APIs and screens. Allows the plant security administrator one User Profile administration application for all applications integrated into utilizing CSI User Ids. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned | [16 empty] | No | Oracle
22823 | Pinnacle - Global Loan Origination | In Production | PinGLO | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | Pinnacle Global Loan Origination contains functionality that is used for Credit Analysis and Discounting. Initially this application will only be used in China. | 1 |  | YES | 4 | SRAISIN1 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
12880 | Commodity Strategy System | In Production | CSS | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Bronze | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | - | Commodity Strategy System, based on VerticalNet (formerly B2eMarkets) software, used by purchasing worldwide to develop and store Commodity Strategies. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 50% | 75% |  | 75% |  | Cloud Run | Praveen | 2025-03-06 |  |  |  | No | Java < v21
12880 | Commodity Strategy System | In Production | CSS | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Bronze | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | SARAUJO3 | Supply Chain | - | Commodity Strategy System, based on VerticalNet (formerly B2eMarkets) software, used by purchasing worldwide to develop and store Commodity Strategies. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 50% | 75% |  | 75% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-06 |  |  |  | No | Oracle
21175 | Performance Management Tools | In Production | PerfMgnt | EPEO | MCRNKOVI | SSOLTANI | CCRAIG39 | CCRAIG39 | Copper | Non S-Ox | 111 | No | Yes | In-House | MCRNKOVI | SSOLTANI | Enterprise Technology | EPEO | Performance Management Tools is a set of custom tools used by ITO Network Operations to integrate and manage network performance assets. In-house developed WeatherMap and IP SLA Manager Apps part of this Application ID. | 5 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
12880 | Commodity Strategy System | In Production | CSS | I-ERP | SARAUJO3 | CBISWADI | CPARTHIB | SNAG1 | Bronze | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | - | Commodity Strategy System, based on VerticalNet (formerly B2eMarkets) software, used by purchasing worldwide to develop and store Commodity Strategies. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q2 2025 | Rewrite | Modernize | 2025-06-15 | 2025-05-15 |  | In-Progress | Green | 2025-08-13 |  | Planned |  | No | 100% | 100% | 75% | 50% | 75% |  | 75% |  | GCP Migration | Praveen | 2025-03-06 |  |  |  | No | Java < v21
52875 | Command Abstraction Layer | In Production | CAL | EVDD | JWASNIC1 | JVEDANAY | PPANDYA1 | CHOWEL12 | Gold | Non S-Ox | 222 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 222 | COMMAND ABSTRACTION LAYER IS A SERVICE THAT IS DEVELOPED WITH AN OBJECTIVE TO COMMUNICATE BETWEEN CLOUD APPLICATION LAYER AND TMC API LAYER. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
9080 | COMBAT | In Production | COMBAT | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Silver | Non S-Ox | 212 | No | Yes | In-House | KPINNU | KHILLERT | Ford Customer Service | Marketing, Sales and Service | COMBAT is the communications system used for unattended batch file transfer to and from dealerships in North America. It is also used to transfer files between Ford and Export locations around the world. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q2 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Mainframe
9080 | COMBAT | In Production | COMBAT | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Silver | Non S-Ox | 212 | No | Yes | In-House | KPINNU | KHILLERT | Ford Customer Service | Marketing, Sales and Service | COMBAT is the communications system used for unattended batch file transfer to and from dealerships in North America. It is also used to transfer files between Ford and Export locations around the world. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
52732 | Collision Assistance (FNOL) Event Data Manager | In Production | CA | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | SPINNADH | PVENKA21 | Silver | Non S-Ox | 322 | No | Yes | In-House | #N/A | #N/A | Ford Customer Service | 322 | THE COLLISION ASSISTANCE (FNOL) EVENT DATA MANAGER USES VEHICLE CRASH DATA WHICH PLACES FORD UNDER LEGAL OBLIGATION TO PROTECT AND PROVIDE THIS DATA TO APPROVED EXTERNAL AGENCIES ON REQUEST. THIS SOLUTION WILL PROVIDE FORD AND LINCOLN OWNERS SUPPORT AND GUIDANCE DURING A HIGHLY STRESSFUL ACCIDENT EVENT WHICH WILL INCREASE CUSTOMER SATISFACTION AND BUILD BRAND LOYALTY. |  | Springboot | YES | 1 | RKENNEL | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-30 |  | Not Started |  | 2026-03-30 |  | Planned |  | No | 100% | [12 empty] | Resource On-boarding Pending. | No | Java < v21
6313 | COLETTE - Travel Expense Administration System | In Production | EuAS-COLET | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Gold | S-Ox Out of Scope | 331 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | Concur Interface to Accounting Systems. It enables payment to individual bank accounts and or citibank bank accounts. It also interfaces the accounting to general ledger |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
52757 | Vehicle Environmental Attribute Tracking | In Production | VEAT | ISIT | DKAVITHA | DKAVITHA | BMCCALL1 | TTOBOLSK | Gold | Non S-Ox | 222 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Tracking of agreed environmental attributes against orders and vehicles |  |  | YES | 1 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | SQL
12095 | Paystub Online | In Production | payonline | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | Displays employee pay stubs online. | 5 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
52868 | Supplier Part Data Quality System | In Production | SPDQS | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | In-House | SKING68 | JLYNN1 | Quality | Industrial System IT | SPDQS is Web application that provides Quality engineers with functionalities to manage/ visualize the different Supplier data feed formats, PD nominal data availability/ status and SPC Quality reports . | 1 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
53052 | Manufacturing Innovation Project Tracker | In Production | MIPT | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Bronze | Non S-Ox | 211 | Yes | No | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | - | Ford internally developing web based application for tracking Manufacturing innovation project list |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | SQL
53052 | Manufacturing Innovation Project Tracker | In Production | MIPT | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Bronze | Non S-Ox | 211 | Yes | No | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | - | Ford internally developing web based application for tracking Manufacturing innovation project list | 2 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | VM
12785 | CMMS3 Empress - Commodity Audit | In Production | CMMS EMP | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Empress is a suite of Web based audit tools that validates the CMMS assembly bills of material (BOM) identifies differences with the WERS engineering BOM and provides the infrastructure/mechanism to manage the resolution of the differences. An extensive set of web screens Excel downloads and reports are provided to the users to enable them to determine the cause of the errors. |  |  | YES | 3 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
14874 | CMMS3 Datamart | In Production | CMMS DMR | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SROYCHOU | SROYCHOU | Manufacturing Staffs | Industrial System IT | Datamart for CMMS that is refreshed daily from selected CMMS3 tables. Users/applications connect directly to Datamart to obtain data/generate reports. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
17146 | Parts Management System (PANDA) | In Production | PANDA | FORD PRO & FCSD TECH | DNANDAN | MAMUDHA | PVIVEKAN | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | MAMUDHA | Enterprise Technology | FCSD Tech | PANDA is the integrated parts management system used by Asia Pacific and Africa. For the warehouse, it manages all aspects of material control (receiving, storage, order processing, claims, intra-company shipments, packaging, junking and cyclic inventory). For Supply, it performs forecasting, procurement and expediting. For Marketing & Sales, it measures Work in Progress, Activity and dealer performance. For Finance, it supports Standard Costing, Accounting, Pricing and Billing through to Statements and Receivables. | 20 |  | YES | 4 | RKENNEL | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
13588 | CMMS3 Bridges/PACO&ILVS | In Production | EuMP-ILVS | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | CMMS3 Bridges transfers the various bridge files information between CMMS3 and European applications. ILVS (IN LINE VEHICLE SEQUECING) receives plant wise bridges files from CMMS3 and delivers supplier wise part number info (vehicle Bill of Material) to the Supplier to enable the subsequent match with the actual vehicle sequence from PVS. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
53211 | Weld Quality Monitoring | In Development | WQM | ISIT | DKAVITHA | ELIM9 | SSATHEE2 | AELANGO | Copper | Non S-Ox | 111 | No | Yes | - | #N/A | #N/A | Manufacturing Engineering | 111 | THIS APPLICATION IS USED TO MONITOR THE KEY PARAMETERS OF THE WELD TIMERS CONNECTED IN THE BODY SHOP. THE SYSTEM SUPPORTS INVESTIGATION & SYNERGIES WITH DATA ACCESSIBILITY ACROSS PLANTS ACROSS PLATFORMS |  | Springboot | YES | 1 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
53322 | Consumer Incident Vehicle Information Questionnair | In Production | CIVIQ | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 11 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | New application namely CIVIQ (Consumer Incident Vehicle Information Questionnaire), to be created to replace VOQ (Vehicle Owner Questionnaire). VOQ system is supporting English language currently and in future system must support other languages such as Chinese, Taiwan, Spanish etc., Users exists globally. It helps to identify potential vehicle safety issues at the early stage and reduction of warranty costs. | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-09-30 | 2024-09-30 | 2024-09-16 | Complete | Blue | 2025-01-13 | 2025-01-13 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Priya | 2025-03-05 |  |  | App migrated in 3Q 2024 & Infra Decommission complete in Q1 2025 | No | VM
11539 | CMMS Web-Enabled Direct Data Link | In Production | CMMS eDDL | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | eDDL is a web front-end to the CMMS system and is used by the suppliers to update information needed by Ford analysts to properly manage inventory levels. |  |  | YES | 3 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11863 | CMMS Supplier Releasing and Packaging | In Production | CMMS MSR | ISIT | VVIJAY55 | BGANESH | MHOPKINS | PKOTILA | Gold | S-Ox In Scope | 133 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | CMMS Supplier Release. Tool supporting the weekly material scheduling for suppliers. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
53322 | Consumer Incident Vehicle Information Questionnair | In Production | CIVIQ | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 111 | No | Yes | In-House |  |  | Policy | Industrial System IT | New application namely CIVIQ (Consumer Incident Vehicle Information Questionnaire), to be created to replace VOQ (Vehicle Owner Questionnaire). VOQ system is supporting English language currently and in future system must support other languages such as Chinese, Taiwan, Spanish etc., Users exists globally. It helps to identify potential vehicle safety issues at the early stage and reduction of warranty costs. |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-09-30 | 2024-09-30 | 2024-09-16 | Complete | Blue | 2025-01-13 | 2025-01-13 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Priya | 2025-03-06 |  |  | App migrated in 3Q 2024 & Infra Decommission complete in Q1 2025 | No | Java < v21
53398 | Next-gen Global Packaging Portal | In Production | NGGPP | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 211 | No | Yes | In-House | GHERMAN | ADURSO | Enterprise Technology | Industrial System IT | NGGPP is Next-gen Global Packaging Portal | 0 |  | YES | 4 | BWUNNAVA | PLM | Datastage | Q4 2024 | Already Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | Saran | 2025-03-06 |  |  | Confirmed with PDO (Balaji) and updated the status to 'Complete'. | No | DA
12836 | CMMS Security Authorization Service | In Production | CMMS SAS | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | Non S-Ox | 113 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | The Security Authorization Service (SAS) provides a self-contained package that is designed to authorize the web security needs of all Material Planning and Logistics applications. Act as common reusable security framework which applications use as a plug and play module to secure their applications. Functionality of this application is to set up security policies, make authorization decisions based on security policies, authorization decisions of used applications. |  |  | YES | 3 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11955 | CMMS Receiving | In Production | CMMS RCV | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | S-Ox In Scope | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | RCV is the receiving module within CMMS. Part of the CMMS application portfolio. |  |  | YES | 2 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11955 | CMMS Receiving | In Production | CMMS RCV | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | S-Ox In Scope | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | RCV is the receiving module within CMMS. Part of the CMMS application portfolio. |  |  | YES | 2 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11433 | CMMS Preproduction BOM | In Production | CMMS PRP | ISIT | VVIJAY55 | BGANESH | MHOPKINS | PKOTILA | Gold | Non S-Ox | 332 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Preproduction Bill of Material System. Part of the CMMS3 Proproduction application portfolio. The Pre-production function gathers, analyzes, and disseminates Engineering product release and change information to all affected areas of the plant and Company |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
53609 | Digital zone board-IMG | Planned | DZB-IMG | ISIT | SKING68 | JLYNN1 | GKESAVAR | AELANGO | Bronze | Non S-Ox | 211 | Yes | No | In-House | SKING68 | JLYNN1 | PD Operations and Quality | Industrial System IT | Ford internally developing web based application to tracking zone board status for IMG plants. | 1 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | VM
53609 | Digital zone board-IMG | Planned | DZB-IMG | ISIT | SKING68 | JLYNN1 | GKESAVAR | AELANGO | Bronze | Non S-Ox | 211 | Yes | No | In-House | SKING68 | JLYNN1 | PD Operations and Quality | Industrial System IT | Ford internally developing web based application to tracking zone board status for IMG plants. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | SQL
17770 | CMMS Open-To-Go Reporting | In Production | CMMS OTG | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Silver | Non S-Ox | 333 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Open To Go (OTG) is a global reporting application for vehicle and manufacturing parts progress that allows Launch Team and Preproduction Analyst to quickly gather metrics on part availability issues so that they can prove-out launch readiness. The OTG reports are the mechanism by which all parts new to a vehicle line/engine/transmission and required for launch are tracked. It indicates the part status relative to Production Part Approval Process (PPAP), sample promise date, part identification, supplier name/GSDB code, engineering release level, part approval status, etc. The report is used to determine launch readiness, provide an early indication of the health of a program and to create status projections into the future. The application is used as the primary tool for a series of on-going OTG meetings held with launch management. |  |  | YES | 3 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [9 empty] | Priya | 2025-03-06 |  |  |  | No | Mainframe
53810 | Part Pedigree Tool | In Production | PPT | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | The Part Pedigree Tool is a common global tool for Test Engineers to view the as-built BOM for Prototype vehicles and any Part changes made to them after their initial build |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-08-29 | 2024-08-29 | 2024-08-29 | Complete | Blue | 2024-09-30 | 2024-09-30 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Ramesh | 2025-03-10 |  |  |  | No | SQL
53810 | Part Pedigree Tool | In Production | PPT | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Silver | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | The Part Pedigree Tool is a common global tool for Test Engineers to view the as-built BOM for Prototype vehicles and any Part changes made to them after their initial build | 4 |  | YES | 2 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-08-29 | 2024-08-29 | 2024-08-29 | Complete | Blue | 2024-09-30 | 2024-09-30 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Ramesh | 2025-03-10 |  |  |  | No | VM
12833 | CMMS Obsolescence | In Production | CMMS OBSO | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | S-Ox In Scope | 131 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Application allows claims from DDL suppliers and mechanical canvassing plant obsolete parts. For qualified obsolete parts disposition directions will be provided by obsolete ananlysts and settlements will be issued to suppliers. Accounting information is created and sent to affected accounting systems. Rejections are sent to suppliers for incomplete/erroneous claims. |  |  | YES | 3 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
21300 | CMMS NG-Web | In Production | CMMS NG | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | S-Ox In Scope | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Web hosted front end for CMMS. This enables existing CMMS3 mainframe screens to be accessible via a web browser. |  |  | YES | 2 | BWUNNAVA | PLM | Java Struts | Q3 2025 | Rewrite | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started | Green | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
21300 | CMMS NG-Web | In Production | CMMS NG | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | S-Ox In Scope | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Web hosted front end for CMMS. This enables existing CMMS3 mainframe screens to be accessible via a web browser. |  |  | YES | 2 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11864 | CMMS Material Cost Accounting | In Production | CMMS MCA | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | S-Ox In Scope | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | CMMS Cost Accounting to support F@ST plants and non-F@ST plants (Visteon, Getrag, Nemac and Rest-of-World locations) |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
13479 | CMMS Manufacturing Vehicle Part Repository | In Production | CMMS MVP | ISIT | VVIJAY55 | BGANESH | MHOPKINS | PKOTILA | Gold | Non S-Ox | 132 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Operational data base containing historical vehicle bills of material, Contents of Assembly for manufactured parts, and part/supplier information. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11445 | CMMS Hourly Material Requirements | In Production | CMMS HMRS | ISIT | VVIJAY55 | BGANESH | MHOPKINS | PKOTILA | Gold | S-Ox In Scope | 133 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Common Manufacturing Mgmt System. HMRS I-Vin BOM Create. Breaks engineering changes, calculates usage, performs part requirement calculations, provides feeds to numerous systems, HMRS II-provides tools to organize the requirements into Delivery Windows. ILVS - Supports commodity definition & generation of ILVS 866 shipping transactions. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11911 | CMMS Inventory | In Production | CMMS INV | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | S-Ox In Scope | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | CMMS Inventory Module. Part of the CMMS Application Portfolio. Note: eSRS Scrap and Reject System is part of CMMS INV module. Quality Reject system (listed as ITMS 20720) is part of the CMMS NV Module. |  |  | YES | 2 | BWUNNAVA | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11911 | CMMS Inventory | In Production | CMMS INV | ISIT | VVIJAY55 | BGANESH | SMERCYAN | PKOTILA | Gold | S-Ox In Scope | 233 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | CMMS Inventory Module. Part of the CMMS Application Portfolio. Note: eSRS Scrap and Reject System is part of CMMS INV module. Quality Reject system (listed as ITMS 20720) is part of the CMMS NV Module. | 1 |  | YES | 2 | BWUNNAVA | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
16720 | CM4D | In Production | CM4D | ISIT | SKING68 | JLYNN1 | GCHIDAMB | AELANGO | Silver | Non S-Ox | 211 | No | Yes | COTS | SKING68 | JLYNN1 | Manufacturing Engineering | Industrial System IT | CM4D (Coordinate Measurement Machine Management Mechanism for Data) Plant Process(es) Quality Reporting Tool. Produces Variables Charts and basic Attrbute Charts. Data is fed from Measuring Devices such as CMMs, Perceptrons, DataMytes etc. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
50896 | Partner Identity Management - SPS & MCS | In Production | PartnerIAM | EPEO | NOKEEFE | MSNYDER5 | SRAJEN26 | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Partner Identity Management is responsible for Managing B2B (Dealers, Suppliers & Other) Accounts lifecycle events. Dealer user personal accounts for their dealerships with Delegated Administration Model. Other external users such as Ford PRO, Marketingcomm,B2BSP and Tier2/3 supplier accounts. Supplier FSN accounts and their access to FORD FSP registered Applications. | 4 |  | YES | 5 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
53114 | Cloud App Optimizer | In Production | CAO | EA | RRISS | THALL6 | SDESHP16 | SDESHP16 | Copper | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Enterprise Technology | 111 | APP IS USED TO HELP OPTIMIZE USAGE OF CLOUD APPS IN PCF |  | Springboot | YES | 1 | GBRAIL | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
24107 | Cloud Adventure Builder | In Development | CAB | EA | RRISS | THALL6 | SDESHP16 | SGURU8 | Copper | Non S-Ox | 111 | No | Yes | - | RRISS | THALL6 | Enterprise Technology | - | The intent of the Cloud Native Adventure Builder is to describe a default set of patterns and practices for building cloud native applications or modern distributed systems at Ford. The codebase focuses on Java development with Pivotal Cloud Foundry, Spring, and Spring Cloud Services. The is a reference application, and not a real application that will be deployed to a production environment. |  |  | YES | 1 | GBRAIL | PLM | WAS | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
19643 | Clipsheet | In Production | Clipsheet | OCETO | TSWEEN16 | KADOMKAI | GWHOLIHA | MBALAN2 | Silver | Non S-Ox | 111 | Yes | No | Managed by 3rd Party Purchased Service | DDESAI | DDESAI | Communications | - | www.clipsheet.ford.com provides employees links to articles related to Ford Motor Company. |  |  | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q1 2025 | Will be Decommissioned | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | SaaS |  |  |  |  | Clipsheet is hosted externally and PCF Component has already decommissioned | No | Java < v21
50907 | Clam Antivirus | In Production | ClamAV | EPEO | NOKEEFE | VNACHIMU | PFREILE | KSAYEE | Gold | Non S-Ox | 11 | No | Yes | Open Source | #N/A | #N/A | Enterprise Technology | 11 | ANTIVIRUS FOR LINUX SERVER SYSTEMS |  | Springboot | YES | 1 | SWALIMBE | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
24934 | Citrix XenApp 7.15 Infrastructure | Active | XA 7.15 | EPEO | LFULCHER | LFULCHER | EREYNOL3 | GSIENKIE | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
50621 | PARMS China | In Production | PARMSChina | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | PARMS is an application to maintain rates and marketing plans for Ford Credit China retail products during Offer submission and discounting. | 1 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
13834 | CiTiS: Customs & International Trading Information | In Production | EuAS-CITIS | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Silver | Non S-Ox | 222 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | CiTiS (Customs & International Trading Information)System is a pan-European Ford Customs system that embraces all data and processes necessary to operate a cost-efficient, compliant Customs operation, capable of handling the diverse business under the Ford Motor Company trust mark. |  |  | YES | 2 | BWUNNAVA | PLM | Mainframe | Q3 2027 | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
13834 | CiTiS: Customs & International Trading Information | In Production | EuAS-CITIS | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Silver | Non S-Ox | 222 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | CiTiS (Customs & International Trading Information)System is a pan-European Ford Customs system that embraces all data and processes necessary to operate a cost-efficient, compliant Customs operation, capable of handling the diverse business under the Ford Motor Company trust mark. |  |  | YES | 2 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11772 | Paint Emissions Reporting System | In Production | PERS | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Bronze | Non S-Ox | 111 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Formerly Volatile Organic Compounds | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | Q1 2026 | Partial Migration to GCP | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22408 | ORACLE SOLARIS SERVER OS | Active | Solaris | EPEO | LFULCHER | KMAHAJAN | TKLEMER | CMORAN2 | Silver | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | Enterprise Technology | ITO | Oracle Solaris is a Unix operating system originally developed by Sun Microsystems. Solaris is known for its scalability, especially on SPARC systems, and for originating many innovative features such as DTrace, ZFS, and Zones. Solaris is registered as compliant with the Single Unix Specification. | 6 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
24071 | OneSumX FS | In Production | OneSumX FS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | OneSumX FS IFRS9 is a financial application provided by Wolters Kluwer that uses contract data to calculate Expected Credit Loss amounts over contract lifetime. IFRS9/CECL is an accounting standard that addresses the treatment of Expected Credit Losses (ECL). These ECL amounts are then aggregated by the particular market and posted to the General Ledger. This information will be publicly available as part of the balance sheet for Ford Credit, thus making it a SOX application. 10 markets are currently in scope - FCE, US, Canada, Mexico and China. The contract scope is for the retail markets. The ECL for wholesale contracts is out of scope and will be calculated manually. OneSumX will start to generate EAD/ECL calculations from take on date (TOD). The contractual outstanding principal that FORD CREDIT is required to deliver should be the principal outstanding amount at TOD. FORD CREDIT is also required to deliver the contractual accrued interest from the contractual last repayment date to TOD. | 15 |  | YES | 3 | SRAISIN1 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
23849 | China VAT (Value Added Tax) | In Production | HVAT | FORD CREDIT | JCHEN11 | CYANG63 | YFU33 | YZHU86 | Silver | S-Ox Out of Scope | 211 | No | Yes | COTS | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | China VAT (HVAT) is a vended application that assists in calculating and reporting on the Value Added Tax required in China for Ford Credit. VAT vendor is HAND. This process also uses Aisino (Golden Tax) for the invoicing piece of the requirement.These applications are applicable for both FAFC and FAFL. |  |  | YES | 1 | SRAISIN1 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
53338 | China Subscription Adaptor | In Production | CSA | EVDD | DHE14 | QJI4 | YGONG6 | WJIN12 | Bronze | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 211 | THIS APPLICATION IS TO SUPPORT CHINA SUBSCRIPTION PLATFORM LAUNCH. MAKE SURE GLOBAL SUBSCRIPTION PLATFORM'S COMMON CAPABILITY IS RE-USED AND WHILE PROVIDE FLEXIBIITY FOR CHINA SUBSCRIPTION BUSINESS. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
54779 | China Prognostic Services Application | Planned | CPAE | EVDD | HHUANGJI | YZHOU159 | YZHOU159 | WJIN12 | Silver | Non S-Ox | - | No | Yes | - | TSWEEN16 | HHUANGJI | Marketing & Sales | - | This is application to provide the prognostic service for business , such as OIL LIFE, TSL , etc. |  |  | YES | 1 | MJONE308 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
51599 | China IVI Service Layer | In Production | CN IVISL | EVDD | DHE14 | QJI4 | YGONG6 | WJIN12 | Silver | Non S-Ox | 311 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 311 | CHINA IVI SERVICE LAYER PROVIDES COMMUNICATION CHANNEL BETWEEN IVI APPS AND FORD BACKEND OR THIRD-PARTY SYSTEMS. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
52241 | China IVI Operation Portal | In Production | IVIOP | EVDD | DHE14 | QJI4 | YGONG6 | WJIN12 | Bronze | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 211 | CHINA IVI OPERATION PORTAL PROVIDES SYNC+ IVI RELATED DATA/STATUS TO SUPPORT IVI OPERATION TEAM |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
57339 | China Export Data Application Aggregator | In Production | CEDAA | EVDD | DHE14 | QJI4 | YGONG6 | WJIN12 | Silver | Non S-Ox | 211 | No | Yes | In-House | DHE14 | QJI4 | Advanced PD and Tech | - | For China export data aggregate, and transfer the data to the national platform. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
53399 | China Enablement Systems - CES | In Production | CES | FORD CREDIT | IPANKAJ | VNAVEEN1 | GKAMAL | ROBRIEN3 | Copper | Non S-Ox | 112 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 112 | SUITE OF CHINA ENCAPSULATED API'S SUPPORTING CUSTOMER, ACCOUNT AND VEHICLE USING LA AND DB2 INFORMATION TO SUPPORT CHINA APPLICATIONS. |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
50640 | China digital service | In Production | CNDSL | I-ERP | HHUANGJI | JZHOU42 | CGU7 | HYANG80 | Silver | Non S-Ox | 212 | No | Yes | In-House | #N/A | #N/A | Marketing & Sales | 212 | CHINA DIGITIAL SERVICE APPLICATION PROVIDES LIST OF WEBSERVICES AND DATA THAT ENABLES FUNCTIONALITY FOR FORD AND LINCOLN CUSTOMER FACING DIGITAL CHANNELS IN CHINA |  | Springboot | YES | 1 | TSWEEN16 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
53920 | China Devops | In Production | CNDEVOPS | EVDD | DHE14 | QJI4 | YGONG6 | WJIN12 | Copper | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 211 | CHINA DEVOPS ORGNIZATION |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
53418 | China Customer Feedback Service | In Production | CNCFS | EVDD | DHE14 | QJI4 | TGUO9 | WJIN12 | Silver | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 211 | CHINA CUSTOMER FEEDBACK SERVICE PROVIDES THE CAPABILITY TO COLLECT CUSTOMER FEEDBACK FROM VARIOUS CHANNELS, AND PROVIDES A PORTAL TO OPERATION TEAM TO VIEW AND PROCESS FEEDBACK DATA. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
23138 | China Benefit Platform | In Production | CBP | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | Implement a one-stop shop portal for employee benefit self-service and HR Shared Service to process the benefit administration on numerous benefit programs. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
18635 | NetOps Tools | In Production | NETOPSTOOL | EPEO | MCRNKOVI | SPANDRAN | NVIDICAN | NVIDICAN | Platinum | Non S-Ox | 221 | No | Yes | In-House | MCRNKOVI | MCRNKOVI | Enterprise Technology | - | Automation and Tooling to support ITI Operations - Network Operations and Network Management Systems (NMS). As of 5/19/2015, merging this ITMS Application with ITMS App 19547 and decomming that app to consolidate portfolio. | 8 |  | YES | 3 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
23138 | China Benefit Platform | In Production | CBP | OCETO | TSWEEN16 | NMUTHUK2 | MVAIRAM1 | MBALAN2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DDESAI | NMUTHUK2 | Human Resources | Staffs IT | Implement a one-stop shop portal for employee benefit self-service and HR Shared Service to process the benefit administration on numerous benefit programs. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud Run | [5 empty] | No | Java < v21
23685 | China Account Manager | In Production | CAM | FORD CREDIT | JCHEN11 | CYANG63 | YSUN74 | YZHU86 | Copper | Non S-Ox | 311 | No | Yes | - | JCHEN11 | CYANG63 | Ford Credit Services | 311 | China Account Manager is an Account Management application embedded on the WeChat, FordPass and LincolnWay containers. This mobile application includes features like allowing the customer to view Account details (payment statement), FAQ etc. |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned | [17 empty] | Java < v21
23685 | China Account Manager | In Production | CAM | FORD CREDIT | JCHEN11 | CYANG63 | YSUN74 | YZHU86 | Copper | Non S-Ox | 311 | No | Yes | - | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | China Account Manager is an Account Management application embedded on the WeChat, FordPass and LincolnWay containers. This mobile application includes features like allowing the customer to view Account details (payment statement), FAQ etc. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
23685 | China Account Manager | In Production | CAM | FORD CREDIT | JCHEN11 | CYANG63 | YSUN74 | YZHU86 | Copper | Non S-Ox | 311 | No | Yes | - | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | China Account Manager is an Account Management application embedded on the WeChat, FordPass and LincolnWay containers. This mobile application includes features like allowing the customer to view Account details (payment statement), FAQ etc. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
23346 | NETCOOL OPERATIONS INSIGHT | Active | NOI | EPEO | MCRNKOVI | SSOLTANI | CCRAIG39 | SSOLTANI | Silver | Non S-Ox | - | No | Yes | - | MCRNKOVI | MCRNKOVI | Enterprise Technology | - | Netcool Operations Insight is an upgrade of the IBM Netcool suite of event management and monitor applications. This application includes the former applications known as Precision IP, Omnibus, and Impact. IBM is now bundling these applications under the NOI name. Precision is a fault monitor for networks. It allows for the collection and distribution of layers 2-3 network data and thereby build and maintain knowledge about physical and logical network connectivity. With accurate network visibility you can efficiently and effectively visualize and manage complex networks. OMNIbus delivers real-time, centralized monitoring of complex networks and IT domains. Netcool-OMNIbus offers around-the-clock management and automation to help deliver continuous uptime of business services and applications, optimize operations costs and efficiency. Impact provides event enrichment and business logic for handling the events. It automates incident creation. | 43 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
51939 | China - Pinnacle Account Servicing Batch | In Production | FAFC-PASMF | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CXUE7 | Ford Credit Services | Ford Credit (FMCC) | The China Pinnacle Account Servicing Mainframe Suite is a S-OX classified suite of programs responsible for passing Pinnacle DB2 Data to/from the Pinnacle Account Servicing application and for Account Servicing batch processes. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20167 | MPS - Web Jet Admin | In Production | MPS - WJA | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Copper | Non S-Ox | 11 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | PSIMONTE | Enterprise Technology | EPEO | HP Web Jet Admin is freely distributed software that provides the ability to install, configure, manage and troubleshoot TCP/IP printers. The software monitors network printers and detects error states. [TM to follow up & identify what action software takes when error state [event] occurs.] | 13 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
22821 | Chef | Active | Chef | EPEO | LFULCHER | KMAHAJAN | TKLEMER | TKLEMER | Copper | Non S-Ox | - | No | - | - | LFULCHER | KMAHAJAN | Information Technology | ITO | Chef Enterprise is an IT automation framework that helps make rapid, repeatable changes to help manage various stages of the IT infrastructure lifecycle, including the provisioning, patching, configuration, and management of operating system and application components across enterprise data centers. | 507 |  | YES | 3 | SWALIMBE | PLM | WebFocus | Q4 2025 | Migrate to Webfocus 9 | Modernize | 2025-12-15 | 2025-12-15 |  | In-Progress | Green | 2026-01-31 |  | Planned | [10 empty] | Webfocus 9 | [6 empty] | DA
22821 | Chef | Active | Chef | EPEO | LFULCHER | KMAHAJAN | TKLEMER | TKLEMER | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 3 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
24133 | MPS - Jet Advantage Security Manager (printer secu | In Production | MPS -JA SM | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Bronze | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | PSIMONTE | Enterprise Technology | EPEO | JA SM is an application from HP to provide real time security for printers installed under the MPS (Managed Print Services) program. | 9 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
52968 | Checksheets Service | In Production | Checksheet | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | 111 | Service accessed via PTS to enable users including dealer technicians to access vehicle servicing checksheets |  | Springboot | YES | 3 | RKENNEL | PLM | Java < v21 | Q3 2026 | Version Upgrade | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
52968 | Checksheets Service | In Production | Checksheet | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Service accessed via PTS to enable users including dealer technicians to access vehicle servicing checksheets |  |  | YES | 3 | RKENNEL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | [5 empty] | No | SQL
22096 | MPS - HP Digital Sending Server | In Production | MPS HP DSS | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Copper | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | PSIMONTE | Enterprise Technology | EPEO | Digital Sending Software is the server side software which controls the Scan to Email and Scan to Folder functions on the HP Managed Print Services multifunction devices. | 18 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
50188 | Checkmarx CxSAST | In Production | CHKMX | OCETO | PMILLIGA | SNAMBIVE | SHEMALAT | WJUSTICE | Silver | Non S-Ox | 221 | Yes | No | COTS | MCHRIS38 | SNAMBIVE | Enterprise Technology | - | A static application testing tool used to identify vulnerabilities in application code. |  |  | YES | 2 | PMILLIGA | PLM | SQL | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
50421 | MPS - HP Device Connect | In Production | MPS HP DC | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Bronze | Non S-Ox | 11 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | PSIMONTE | Enterprise Technology | EPEO | The software collects page counts information for all MPS printers which are connected to the Ford network and sends the information back to HP. The information is used by HP to generate the monthly Ford billing. | 4 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
54943 | Channel Foundation Client Service Proxy Layer | Active | CSPL | M&S TECH | RAHMED33 | DPOOVATH | TBALOGH5 | MSCHOLT3 | Copper | Non S-Ox | - | No | Yes | - | OTHERS | OTHERS | Not in EAMS | - |  |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
24939 | MPS - HP CAPTURE & ROUTE | In Production | MPS -HP CR | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Copper | Non S-Ox | 222 | No | Yes | Managed by 3rd Party Purchased Service |  |  | Enterprise Technology | EPEO | HP CR is an application to support scan to folder and scan to 'myfile' | 16 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
54271 | Critical Supply Chain Enablement | In Production | SCE | ISIT | VVIJAY55 | SDESHPA5 | JGAINADI | SNAIR16 | Silver | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | SDESHPA5 | Supply Chain | Industrial System IT | The application collects, organizes and reports on the data related to IC chips in short supply, and which daily production plan s they are likely to affect, based on supplier-promised weekly deliveries. Also called: SmashDB, N-Tier Interim View | 4 |  | YES | 3 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-10-31 | 2024-12-13 | 2024-12-13 | Complete | Blue | 2025-01-31 | 2025-01-20 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Ramesh | 2025-03-17 |  |  |  | No | VM
755 | Certificate of Conformity | In Production | COC | ISIT | DKAVITHA | UVIJAYAL | NSENTHI7 | TTOBOLSK | Bronze | Non S-Ox | 211 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | Creation of Certificate of Conformity (CoC) in the National Sales Companies. Used within Ford EU and Ford Otosan. A mainframe Telon Cobol facility that generates CoC VIN data for specific vehicles in line with EU legislative requirements together with feed to central client server application which prints the Certificate of conformity (CoC) in the National Sales Companies. The data held on the system is also used to aid the registration systems. Being enhanced during 2015 to enable Digital Transmission of data via Registration Applications. Cross functionally managed - Business Owner MP&L; Consumption Funding EMS&S; BIT SESE; Project funding dependant on which skill team requests the change and what the change consists of. |  |  | YES | 4 | BWUNNAVA | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  | 2027-12-15 |  | Not Started | Green | 2028-03-14 |  | Planned |  | No | [9 empty] | Priya | 2025-03-06 |  |  |  | No | Mainframe
23297 | MPS - HP AC (Secure Pull Print) | Planned | MPS SPP | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Silver | Non S-Ox | 22 | No | Yes | - | SRUNSON | PSIMONTE | Enterprise Technology | - | Secure Pull Print - HP software managed by the Global Managed Print Service team. | 21 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
54271 | Critical Supply Chain Enablement | In Production | SCE | ISIT | VVIJAY55 | SDESHPA5 | JGAINADI | SNAIR16 | Silver | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | SDESHPA5 | Supply Chain | Industrial System IT | The application collects, organizes and reports on the data related to IC chips in short supply, and which daily production plan s they are likely to affect, based on supplier-promised weekly deliveries. Also called: SmashDB, N-Tier Interim View |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-10-31 | 2024-12-13 | 2024-12-13 | Complete | Blue | 2025-01-31 | 2025-01-20 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Ramesh | 2025-03-17 |  |  |  | No | Java < v21
15745 | MIS Reporting | In Production | MIS | FORD CREDIT | IPANKAJ | VGA | BSENTHI1 | VBHUPATH | Bronze | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | VGA | Ford Credit Services | Ford Credit (FMCC) | MIS Reporting provides a centralized integrated management reporting function for Ford Credit. It allows for reduced data storage and processing needs through the elimination of redundant and obsolete reports, and resources spent on data reconciliation between reports. With CIG as the business customer, MIS Reporting utilizes a centralized process and leverages the Ford Credit Enterprise Data Warehouse (EDW). WebFOCUS is the core technology for all new reports with a few reports still on Business Objects. | 8 |  | YES | 3 | SRAISIN1 | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
21655 | Ceridian Salaried/Temporary Payroll | In Production | CeridianSP | I-ERP | SFRANCI8 | FFIORINO | KDELACY | CDEMERIN | Copper | Non S-Ox | 322 | Yes | No | Open Source | DDUDLEY3 | FFIORINO | Finance | - | Ford of Canada's Salaried and Temporary employee payroll system is outsourced to Ceridian. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2024 | On-Prem | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | Microsoft SQL on Azure | [5 empty] | No | SQL
53450 | MAINFRAME CONSOLE OPERATIONS | Active | MCOS | EPEO | SKULKA52 | CGIACOBB | KKRISH33 | KKRISH33 | Gold | Non S-Ox | - | No | Yes | - |  |  |  | Not in EAMS |  | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
18008 | CEPS User Access Review (TVS) | In Production | TVS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Supply Chain | - | O sistema TVS eh um sistema utilizado para fazer a revisao de acesso de outros sistemas (mainframe, web ou clientserver). Ele possui a facilidade dos coordenadores de sistemas e executivos utilizarem a propria intranet para fazer o processo de revisao de acesso. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
57204 | LAN Management Automation Tools | In Production | LANTOOLS | EPEO | MCRNKOVI | SSOLTANI | SSASINOW | ASALOWI1 | Silver | Non S-Ox | 211 | No | Yes | In-House | MCRNKOVI | SSOLTANI | Enterprise Technology | EPEO | Tools Supporting Automation with Wifi, Cisco Wireless, Identity Services Engine (ISE), and Manufacturing LAN | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
14971 | CEPS - Purchasing System (Non Production) | In Production | CEPS Non P | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Supply Chain | - | System controls the non production purchasing process for Argentina and Brazil, including purchase request, suppliers selection, quotation, negotiation and PO Placement. The application acronyms for CEPS non productive are: DA, DB, DC, DE, DR, DS, DU and DV. |  | MF - WAS Liberty | YES | 1 | TSWEEN16 | PLM | Java < v21 | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
21068 | Centralized Vehicle Order Services | In Production | CVOS | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Centralized services and globally common interface specifications for vehicle order configuration, pricing, submission, retrieval, amendment, contracting, transfer and supporting analytics. |  |  | YES | 5 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
21068 | Centralized Vehicle Order Services | In Production | CVOS | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Centralized services and globally common interface specifications for vehicle order configuration, pricing, submission, retrieval, amendment, contracting, transfer and supporting analytics. |  |  | YES | 5 | NKANDULA | PLM | Java Struts | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
21068 | Centralized Vehicle Order Services | In Production | CVOS | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Centralized services and globally common interface specifications for vehicle order configuration, pricing, submission, retrieval, amendment, contracting, transfer and supporting analytics. |  |  | YES | 5 | NKANDULA | PLM | SQL | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
24772 | Knowledge Based Systems China | In Production | KBS China | FORD CREDIT | JCHEN11 | CYANG63 | WWANG153 | YZHU86 | Silver | Non S-Ox | 333 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | Ford Credit (FMCC) | The Knowledge Based System (KBS) China is comprised of one application, chKBS the Scoring Knowledge Base System. chKBS provides a set of predictive characteristics that are input into scorecards used in determining a customer's credit worthiness. | 1 |  | YES | 1 | SRAISIN1 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
21068 | Centralized Vehicle Order Services | In Production | CVOS | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Centralized services and globally common interface specifications for vehicle order configuration, pricing, submission, retrieval, amendment, contracting, transfer and supporting analytics. |  |  | YES | 5 | NKANDULA | PLM | WAS | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
11449 | Central Outbound Payment and Control | In Production | COPAC | ISIT | VVIJAY55 | RADAM10 | VDODDAMR | SSENTH15 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Plants | Industrial System IT | COPAC authorizes freight payments to rail and convoy carriers for the movement of finished vehicles from plants to dealers in North America. |  |  | YES | 2 | BWUNNAVA | PLM | Mainframe | Q4 2026 | Move Capabilities to SaaS Solution | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11449 | Central Outbound Payment and Control | In Production | COPAC | ISIT | VVIJAY55 | RADAM10 | VDODDAMR | SSENTH15 | Gold | S-Ox In Scope | 232 | No | Yes | In-House | SROYCHOU | RADAM10 | Manufacturing Plants | Industrial System IT | COPAC authorizes freight payments to rail and convoy carriers for the movement of finished vehicles from plants to dealers in North America. |  |  | YES | 2 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
24049 | KCF Technologies Vibration Monitoring | In Production | KCFVIB | ISIT | SKING68 | KRAMESH | MKRAWCZA | AELANGO | Copper | Non S-Ox | 111 | Yes | No | - | SKING68 | KRAMESH | Manufacturing Staffs | - | The KCF SmartDiagnostics is a turnkey predictive maintenance wireless tool for monitoring excessive vibration and temperature for motors, gearboxes, pumps on production equipment. The predictive tool allows reading of vibration and temperature data that can be trended such that a warning or an alarm can be triggered automatically to Ford Maintenance Personnel so that maintenance action can be taken to prevent unplanned downtime. Furthermore, the vibration data can be analyzed with Physics based models to recommend a cause of the failure. The predictive maintenance sensors are wireless battery powered nodes which are attached to production equipment and transmit vibration and temperature data through a base station to AWS cloud via cellular connection. The vibration/temperature data is accessed through a web-based application. | 2 |  | YES | 1 | BWUNNAVA | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
51074 | Jenkins for Unix Operations | In Production | Jenkins-UX | EPEO | LFULCHER | KMAHAJAN | TKLEMER | LLIANG2 | Copper | Non S-Ox | 133 | No | Yes | In-House | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | Automation tool used for managing DCoF Unix servers with Jenkins | 26 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
20434 | CENTRAL ADMIN FRAMEWORK | In Production | CAF | EPEO | LFULCHER | LFULCHER | NGILLIKI | NGILLIKI | Bronze | Non S-Ox | 111 | Yes | No | In-House | CMIRABIT | LFULCHER | Enterprise Technology | EPEO | A centralized framework providing a suite of commonized tools that can be executed across multiple systems and platforms. |  |  | YES | 2 | SWALIMBE | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
21742 | ITO-ORACLE-UTILITY-SHARED | Active | ITOOUS | EPEO | LFULCHER | KMAHAJAN | TKLEMER | SGABLE | Silver | Non S-Ox | 0 | No | Yes | - |  |  | Enterprise Technology | EPEO | Oracle Utility Shared Farm | 6 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
12700 | CDS CUPID - CDS Customer Module (VISTA) | In Production | CDSCUPID | M&S TECH | FHIRSH | NSIVASA1 | BRAMA3 | PSATISH2 | Gold | Non S-Ox | 311 | No | Yes | In-House | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | CDS CUPID is the CDS front end to the CUPID mainframe system. It enables dealers to search and maintain customers for the other CDS platform applications. |  |  | YES | 2 | NKANDULA | PLM | Oracle | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
53611 | InTP UEBA | In Production | UEBA | EPEO | NOKEEFE | VNACHIMU | WMAGGETT | WJUSTICE | Silver | Non S-Ox | 311 | Yes | No | COTS | NOKEEFE | VNACHIMU | Enterprise Technology | Technology & Enterprise Services (TES) | User & Entity Behavioral Analytics (UEBA) to support Insider Threat Program | 5 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to SaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
52983 | CDR Platform | In Production | fwbx | EVDD | JWOOD38 | RDEBSHAL | SSHAILAJ | LJ5 | Silver | Non S-Ox | 212 | No | Yes | In-House | MJONE308 | JWOOD38 | Advanced PD and Tech | 212 | FLEET CHARGING SOLUTION USED FOR CDR CONSOLIDATION |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
51628 | CCOT | In Production | CCOT | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KDELTA | PBINGI | Ford Credit Services | Ford Credit (FMCC) | The Contact Center Optimization Tool (CCOT) is a web based application which allows Ford contact center employees to interact with the configuration files which control call flow within the Cisco UCCE. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | SQL
53147 | Informatica PCDQ - Shared | Active | Infa-PCDQ | EPEO | SKULKA52 | MWILLI20 | MMAES | RPOLLO13 | Gold | S-Ox In Scope | - | No | Yes | - | CMIRABIT | MWILLI20 | Enterprise Technology | Ford Credit (FMCC) | This is a PLACEHOLDER EAMS entry, per the 'IT Application Portfolio Management' guidelines. Customers of this service are required to raise their own EAMS entries, complete GRC App Assessments, etc. as required. ITO Shared environment featuring Informatica's Power Center and Data Quality product suites. | 17 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
51628 | CCOT | In Production | CCOT | FORD CREDIT | KDELTA | PBINGI | MFORMOSA | SMOCK6 | Bronze | Non S-Ox | 111 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | The Contact Center Optimization Tool (CCOT) is a web based application which allows Ford contact center employees to interact with the configuration files which control call flow within the Cisco UCCE. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q1 2026 | Version Upgrade | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | Java < v21
17716 | CCD - User Profile Management South America | In Production | CCD | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | CCD System is a Ford and dealership user profile management for B2B (Dealer) applications. Also there is a module to view old brazilian dealer communications. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
19418 | IMS INTEGRATION APP | In Production | IMS-IA | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Bronze | Non S-Ox | 222 | No | Yes | In-House | TVASU | NSENTHI1 | Enterprise Technology | Technology & Enterprise Services (TES) | IMS Integration App provides web interface to access Ford IMS regions through XML, via https post method. Windows or Non-Windows platform based applications use this interface to connect with IMS region to access their IMS Transaction Program. | 2 |  | YES | 4 | TSWEEN16 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
11463 | CCAPS-NA Corporate Accounts Payables | In Production | CCAPS | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | S-Ox In Scope | 332 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Corporate Centralized Accounts Payable System (CCAPS) is a North American Accounts Payable system fully sourced to ADS AP. Corporate Centralized Accounts Payable System is use for processing payments for parts received into North American plants.CCAPS accepts on-line input for payment requests from remote sites as an alternative to the submission of hard-copy check requests to the servicing Accounting location. | 20 |  | YES | 2 | TSWEEN16 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
11463 | CCAPS-NA Corporate Accounts Payables | In Production | CCAPS | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | S-Ox In Scope | 332 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Corporate Centralized Accounts Payable System (CCAPS) is a North American Accounts Payable system fully sourced to ADS AP. Corporate Centralized Accounts Payable System is use for processing payments for parts received into North American plants.CCAPS accepts on-line input for payment requests from remote sites as an alternative to the submission of hard-copy check requests to the servicing Accounting location. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q3 2025 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
158 | CBS: Customer Billing System | In Production | CBS158 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | DNANDAN | DWIERZBI | Finance | FCSD Tech | Used by Ford Customer Service Division to bill its customers (dealers). It includes modules for transaction editing, billing correction, price testing, ledger accounting, invoicing, and monthly statement production. Old Acronym : CBS | 7 |  | YES | 3 | RKENNEL | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
158 | CBS: Customer Billing System | In Production | CBS158 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | NBAECKER | DWIERZBI | Finance | FCSD Tech | Used by Ford Customer Service Division to bill its customers (dealers). It includes modules for transaction editing, billing correction, price testing, ledger accounting, invoicing, and monthly statement production. Old Acronym : CBS |  |  | YES | 3 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
158 | CBS: Customer Billing System | In Production | CBS158 | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | NBAECKER | DWIERZBI | Finance | FCSD Tech | Used by Ford Customer Service Division to bill its customers (dealers). It includes modules for transaction editing, billing correction, price testing, ledger accounting, invoicing, and monthly statement production. Old Acronym : CBS |  |  | YES | 3 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
24226 | IBM TIVOLI MONITORING - MAINFRAME | Active | ITMM | EPEO | SKULKA52 | CGIACOBB | DMUCKLIN | DMUCKLIN | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | CGIACOBB | Enterprise Technology | - | This product will be used enterprise wide for monitoring Mainframe environments. | 7 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
22033 | HPC HADOOP ENVIRONMENT | Active | Hadoop | EPEO | SKULKA52 | CPENNEY | JMART256 | CPENNEY | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | CPENNEY | Enterprise Technology | ITO | Hadoop is a analytics tool used for solving big data problems. | 3 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
52901 | Capacity Management Dashboard Tool | In Development | Capacity D | OCETO | TSWEEN16 | VSIVAKU5 | AMARIA13 | AMARIA13 | Copper | Non S-Ox | - | No | Yes | In-House | JMENDOL1 | VSIVAKU5 | Ford Land | - | In order to track capacity utilization more efficiently a cross functional team including GDIA, IT, FBS Transition team, Finance & Ford Land team has developed a capacity management dashboard tool |  |  | YES | 1 | TSWEEN16 | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
51474 | Capacity Analysis Report | In Production | eCAR | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | eCAR enables the suppliers to demonstrate their ability to satisfy Ford volume requirements (Average Production Weekly and Maximum Production Weekly) and report them as part of the Global Product Development System (GPDS). Ford utilizes Overall Equipment Effectiveness (OEE) to assess the risk associated with the suppliers plan to demonstrate capacity requirements, as it incorporates three key manufacturing performance elements (Equipment Availability, Performance Efficiency, and Quality Rate). |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-02-01 | 2025-02-01 | Complete | Blue | 2025-02-16 | 2025-02-16 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-05 |  |  | Migration completed. Decom in progress. | No
21346 | HOST ON DEMAND | In Production | HOD | EPEO | SKULKA52 | CGIACOBB | COLIVE34 | COLIVE34 | Silver | Non S-Ox | 112 | Yes | No | COTS | CMIRABIT | CGIACOBB | Enterprise Technology | EPEO | Host On Demand (HOD) is a thin client terminal emulation solution. Thin client being a java applet rather than the traditional, fat client, operating system specific executable file,ie (Windows EXE file). HOD is a solution for communicating with servers using a terminal interface commonly called Green Screen Emulation. This method of communication is non-graphical and consists of purely standard ASCII characters. HOD sessions are pre-configured java applets that are deployed to any standard web server. The java applet is accessed through a web page link that, in turn, will run inside the client's web browser. The java applet connects to a specified host based on the pre-configuration data and produces a Green Screen session within the client's browser. | 6 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
51474 | Capacity Analysis Report | In Production | eCAR | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House |  |  | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | eCAR enables the suppliers to demonstrate their ability to satisfy Ford volume requirements (Average Production Weekly and Maximum Production Weekly) and report them as part of the Global Product Development System (GPDS). Ford utilizes Overall Equipment Effectiveness (OEE) to assess the risk associated with the suppliers plan to demonstrate capacity requirements, as it incorporates three key manufacturing performance elements (Equipment Availability, Performance Efficiency, and Quality Rate). |  | Springboot | YES | 3 | TSWEEN16 | PLM | Java < v21 | Q1 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-03-01 | 2025-03-01 | Complete | Blue | 2025-03-01 | 2025-03-01 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Praveen | 2025-03-05 |  |  |  | No | Java < v21
24816 | Canadian Dealer Facilities Website | In Production | CFW | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | Marketing, Sales and Service | Web application to manage Canadian dealer facilities information. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
24816 | Canadian Dealer Facilities Website | In Production | CFW | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | Marketing, Sales and Service | Web application to manage Canadian dealer facilities information. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
21819 | GOTD - Transitional Data Interface | In Production | GOTD-TDI | M&S TECH | FHIRSH | SBINO | VSRINI23 | PSATISH2 | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | SBINO | Marketing & Sales | Marketing, Sales and Service | Global Service Interfaces (GOTD-Service Interfaces) is a service module of Global -OTD, which abstracts all the interfaces of Global - OTD Applications with multiple Data sources (e.g. dealer, customer, sales & contracting, vehicle & commodity allocations), in order to provide information, which are gathered and collected from multiple applications from Ford Motor Company at any time across the Globe. | 5 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
24816 | Canadian Dealer Facilities Website | In Production | CFW | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | Marketing, Sales and Service | Web application to manage Canadian dealer facilities information. |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
12552 | Campaign Administration and Microsites | In Production | CA&Msites | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 221 | No | Yes | In-House | KBERCH | GDIAZ1 | Marketing & Sales | Marketing, Sales and Service | The primary goal of the Campaign Administration Tool is to create a generic, reusable version of a contest entry form that allows the business to quickly generate and publish contests and campaigns. This application is hosted on Ford B2B server and the microsites are created on the Ford B2C servers. Campaign Administration Tool complies with Federal Canadian Anti-Spam Legislation (CASL) requirements which requires Ford of Canada to communicate electronically only with individuals, who have provided explicit permission to communicate with them. |  |  | YES | 2 | NKANDULA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
25047 | GOTD - Order Integration Services | In Production | GOTD - OIS | M&S TECH | FHIRSH | VDONTHY | JKHARE | CKEMPSKI | Silver | Non S-Ox | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | This application is to bring data into the Global Order Bank (GOB) and provide data to all consumers including GOTD. Previously known as SICON. | 8 |  | YES | 5 | NKANDULA | PLM | VM | Q1 2026 | Partial Migration to GCP | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration |  |  |  |  | Its planned for 2026 | No | VM
12552 | Campaign Administration and Microsites | In Production | CA&Msites | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 221 | No | Yes | In-House |  |  | Marketing & Sales | Marketing, Sales and Service | The primary goal of the Campaign Administration Tool is to create a generic, reusable version of a contest entry form that allows the business to quickly generate and publish contests and campaigns. This application is hosted on Ford B2B server and the microsites are created on the Ford B2C servers. Campaign Administration Tool complies with Federal Canadian Anti-Spam Legislation (CASL) requirements which requires Ford of Canada to communicate electronically only with individuals, who have provided explicit permission to communicate with them. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
54271 | Critical Supply Chain Enablement | In Production | SCE | ISIT | VVIJAY55 | SDESHPA5 | JGAINADI | SNAIR16 | Silver | Non S-Ox | 221 | No | Yes | In-House | SROYCHOU | SDESHPA5 | Supply Chain | Industrial System IT | The application collects, organizes and reports on the data related to IC chips in short supply, and which daily production plan s they are likely to affect, based on supplier-promised weekly deliveries. Also called: SmashDB, N-Tier Interim View |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-10-31 | 2024-12-13 | 2024-12-13 | Complete | Blue | 2025-01-31 | 2025-01-20 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL SQLServer | Ramesh | 2025-03-17 |  |  |  | No | SQL
54352 | Letters of Interpretation and Opinion from NHTSA | In Production | LION | ISIT | DKAVITHA | UVIJAYAL | VNEELIMA | TTOBOLSK | Bronze | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Policy | 111 | NEW APPLICATION NAMELY LION (LETTERS OF INTERPRETATION AND OPINION FROM NHTSA), TO BE CREATED TO STORE THE INTERPRETATIONS FROM NHTSA WEBSITE. THIS APPLIACTION ALLOWS TO PERFORM SEARCHES BASED ON A PARAMETERS LIKE FMVSS, CPSC WITH SELECTIVE KEYWORDS. LION APPLICATION DASHBOARD ALLOWS USERS TO SEARCH THE DATA EFFICIENTLY. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-08-30 | 2024-08-30 | 2024-07-22 | Complete | Green | 2024-08-02 | 2024-08-05 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Priya | 2025-03-13 |  |  |  | No | Java < v21
21336 | GOTD - Global Order Bank | In Production | GOTD - GOB | M&S TECH | FHIRSH | VDONTHY | JKHARE | CKEMPSKI | Silver | S-Ox In Scope | 233 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | GOTD Order Bank Management provides a central view of orders further enabling Cross-CBG OTD Build Anywhere, Sell Anywhere processes. Global Order Bank is the common repository of all new vehicle order information for all vehicles built or sold by Ford mapped to the single codification language with a common aligned representation supported by global information retention standards. | 6 |  | YES | 5 | NKANDULA | PLM | VM | Q1 2026 | Partial Migration to GCP | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
12025 | CA-IDMS Facility D | Active | IDMS D | M&S TECH | RAHMED33 | GDIAZ1 | ASYRAGAK | IKALUGIN | Gold | Non S-Ox | - | No | - | - | KBERCH | GDIAZ1 | Information Technology | Marketing, Sales and Service | Mainframe charges for Facility D. Includes IDMS-DB/DC Central Version for online 3270 applications. |  |  | YES | 1 | NKANDULA | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
17689 | Global Emissions Manager | In Production | GEM | ISIT | DKAVITHA | UVIJAYAL | ARADHA11 | TTOBOLSK | Bronze | Non S-Ox | 211 | No | Yes | COTS | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | The GEM database is a global environmental compliance tool that supports Environmental Operating System (EOS) implementation and the tracking of waste, water, CO2, and environmental scorecard metrics consistent with Manufacturing Business Plans. (GEM was formerly known as GHG - Green House Gases) | 4 |  | YES | 5 | BWUNNAVA | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
52964 | CAE Gives and Gets & X-Functional Data Management | In Development | CAE GGXFDM | ISIT | JKOONS | MNOVAK1 | BTHOMA47 | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | 211 | Delivers Disciplined CAE Gives & Gets process platform based on standard SIPOC model for efficient CAE workflow Program milestone support. Establishes a Cross-Functional CAE Data Base as source of truth platform for Digital Traceability and automating model builds.Includes CAE process Dashboard for program/workflow health and drilldowns for issue control. |  | Springboot | YES | 2 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
52964 | CAE Gives and Gets & X-Functional Data Management | In Development | CAE GGXFDM | ISIT | JKOONS | MNOVAK1 | BTHOMA47 | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | Delivers Disciplined CAE Gives & Gets process platform based on standard SIPOC model for efficient CAE workflow Program milestone support. Establishes a Cross-Functional CAE Data Base as source of truth platform for Digital Traceability and automating model builds.Includes CAE process Dashboard for program/workflow health and drilldowns for issue control. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
56984 | Cadence Orcad PCB | In Development | Cadence | ISIT | MNOWICK1 | PBORGAO1 | IAKLEH | GRAO3 | Bronze | Non S-Ox | 211 | No | Yes | COTS | MNOWICK1 | PBORGAO1 | Advanced PD and Tech | - | Design and build Printed Circuit Boards (PCBs) used by the Global eDrive Systems team. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50484 | Global DEFT | In Production | GEFT | FORD CREDIT | JCHEN11 | CYANG63 | YFU33 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CYANG63 | Ford Credit Services | - | China - Electronically moves funds between Dealers bank accounts and Ford/Ford Credit bank accounts. | 1 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
23002 | CAD Release Information System | In Production | CADRIS | ISIT | MNOWICK1 | LSRINIVA | HKUMAR7 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | CAD Release Information System would store Parts claim data which would be used by other applications to view, update Part information during its release progression. In the context of a vehicle program CAD Supervisors, CAD Lead, CAD Designers would have the capability to claim parts, update claimed parts, transfer claimed parts , update Causal Factors , CAD Remarks along with other comments related to release statuses which would be stored in the CAD Release Information System. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
19544 | GIM Accutrac | In Production | Accutrac | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Silver | Non S-Ox | 221 | No | Yes | COTS | DDESAI | KADOMKAI | Policy | Staffs IT | Ford's implementation of Iron Mountain's Accutrac software provides a total records management solution, one that manages active and inactive records wherever they reside, from a single interface. Accutrac software supports a full range of capabilities required for physical records management. Manage records through their entire lifecycle Reduce overall storage costs Mitigate legal, regulatory and compliance risks and provide clear audit trails. Streamline records retrieval onsite or offsite. Create standard and customized reports. Extend enterprise content management or document management investments Accutrac software helps companies apply a consistent and compliant records management program in line with documented policies. As a DoD 5015.2 certified application, it offers enterprise-scale, configurable workflows for the classification and indexing of records to support robust retention management, legal holds, and final disposition. Replaced GARMS application, ITMS 12076. | 8 |  | YES | 2 | TSWEEN16 | PLM | VM | Q1 2026 | EDC CaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
23002 | CAD Release Information System | In Production | CADRIS | ISIT | MNOWICK1 | LSRINIVA | HKUMAR7 | LPATIL | Silver | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | Advanced PD and Tech | Industrial System IT | CAD Release Information System would store Parts claim data which would be used by other applications to view, update Part information during its release progression. In the context of a vehicle program CAD Supervisors, CAD Lead, CAD Designers would have the capability to claim parts, update claimed parts, transfer claimed parts , update Causal Factors , CAD Remarks along with other comments related to release statuses which would be stored in the CAD Release Information System. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
23159 | FORD+ VIRTUAL DESKTOP INFRASTRUCTURE | Active | Ford+ VDI | EPEO | LFULCHER | LFULCHER | EREYNOL3 | GSIENKIE | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | Enterprise Technology | ITO | Ford+ Virtual Desktop Infrastructure is a XenDesktop installation that is completely managed and supported by Ford infrastructure teams to cater to Ford internal customers | 1 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to SaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
19552 | Cacti | In Production | CACTI | EPEO | MCRNKOVI | SSOLTANI | CCRAIG39 | CCRAIG39 | Silver | Non S-Ox | 122 | No | Yes | Open Source | MCRNKOVI | SSOLTANI | Enterprise Technology | EPEO | Cacti is a network performance analysis tool. It has the ability to identify trends in the network, by hour, day, week, month and even year to year. It also allows the ability to drill down from yearly to daily, and even hourly displays of data, simply by clicking the mouse. Cacti is used by Network Operations for network devices and Server Hosting for a limited number of servers |  |  | YES | 2 | SWALIMBE | PLM | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
53589 | CaaS Cloud App Optimizer | In Production | CCAO | EA | RRISS | THALL6 | CASTLEY2 | CASTLEY2 | Copper | Non S-Ox | 111 | No | Yes | In-House | RRISS | THALL6 | Enterprise Technology | Industrial System IT | App is used to help optimize usage of Cloud Apps in CaaS |  |  | YES | 1 | GBRAIL | PLM | WAS | Q2 2025 | Version Upgrade | Modernize | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned | [17 empty] | Java < v21
11756 | C3P-NG(NG) | Active | NG | ISIT | JKOONS | NLAKSHMA | CCHADA | GRAO3 | Silver | Non S-Ox | - | No | - | - | SBONNICI | SBONNICI | Product Development | - | C3P NG is a program that delivers the next level of digital product capabilities for all brand partners in Ford Motor Company, to effectively conduct enterprise-wide vehicle and technology product creation. Ford moved to C3P NG to achieve efficiencies in Product Creation that will enable it to bring products to market faster by (a)Moving to a central CAD solution (b)Negotiating Not to Exceed pricing for C3P NG tools (c)Providing Visualization access. This ITMS is used as a financial holding for operating expenses of a variety of applications in the C3P suite |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
50194 | Ford Pro: Commercial Specialty Vehicle Accounts | In Production | CSVA | FORD PRO & FCSD TECH | RKENNEL | JBULSARA | JBULSARA | AHULL19 | Copper | Non S-Ox | 221 | No | Yes | In-House | AKARTHI4 | MMATEEN2 | General Management | Ford Pro | Commercial Speciality Vehicle forecasting website, used by region 86 accounts to forecast the production allocation needed for future months. | 8 |  | YES | 3 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q1 2026 | Partial Migration to GCP | Modernize | 2026-03-15 | 2026-03-30 |  | Not Started |  | 2026-06-28 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | VM
13868 | C3P Central Authentication System | In Production | CCAS | ISIT | JKOONS | NLAKSHMA | MMAHIMA | GRAO3 | Silver | Non S-Ox | 111 | No | Yes | In-House | JKOONS | NLAKSHMA | Advanced PD and Tech | Industrial System IT | C3P Central Authentication System is the user authentication wrapper aroud TcEng. CCAS forces login to TcEng to go through the WSL authentication before access to TcEng is allowed. CCAS is developed as a generic function to be used for future C3P tools that do not meet Ford password strength requirements. |  |  | YES | 2 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
53280 | Ford Credit Residual Equipment Tool | In Production | FC RET | FORD CREDIT | RMINHAS3 | ASAPEHIA | PHUTCHI8 | JMANI | Bronze | Non S-Ox | 112 | No | Yes | In-House | RMINHAS3 | PBALUSU | Ford Credit Services | Ford Credit (FMCC) | RET provides dealers with the ability to configure, price and residualize vehicle accessories during the financing process | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2026 | Partial Migration to GCP | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
21415 | Business Objects - Shared | Active | BusObj-SE | EPEO | SKULKA52 | MWILLI20 | TCULLER | RMODI2 | Silver | Non S-Ox | - | No | Yes | - | CMIRABIT | MWILLI20 | ENTERPRISE TECHNOLOGY | ITO | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
22631 | Ford Credit InfoSphere (IBM) Annex (DataStage) | In Production | FCInfoSpA | FORD CREDIT | IPANKAJ | VGA | BSENTHI1 | VBHUPATH | Bronze | Non S-Ox | 323 | No | Yes | COTS | IPANKAJ | VGA | Ford Credit Services | Ford Credit (FMCC) | Shared Extract-Transform-Load (ETL) infrastructure environment utilizing DataStage to support multiple discrete applications. | 18 |  | YES | 3 | SRAISIN1 | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
51597 | Business Intelligence for Global Cost | Planned | BIGC | ISIT | OTHERS | MSTOECKL | MFRANIA1 | MQAZI1 | Bronze | Non S-Ox | - | Yes | No | In-House | BGUBING | MSTOECKL | Manufacturing Engineering | - | BMIT Database for BI data around the Global Cost processes. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50761 | FNA Foundation | In Production | FNA | M&S TECH | RKLEINSM | KPONNUSW | JSUGAMOS | JPOTTE60 | Platinum | Non S-Ox | 323 | No | Yes | In-House | RKLEINSM | KPONNUSW | Enterprise Technology | - | A platform for the B2C consumer experience. This system will support mult services and apps. This documents the data center controls for the foundation app supplied by Adobe. | 90 |  | YES | 1 | NKANDULA | PLM | VM | Q1 2026 | Complete Migration to SaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
20891 | Business Intelligence for Digital Innovation App | In Development | BIDI | ISIT | MNOWICK1 | LSRINIVA | RSTOCKTO | JMATHEWS | Copper | Non S-Ox | 211 | Yes | No | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | - | Not really an application. A placeholder for non-Prod data studies supporting Business Intelligence for DI |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
13040 | Fleet Deal Maker - Variable Marketing | In Production | DEAL MAKER | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | DNANDAN | DWIERZBI | Marketing & Sales | Marketing, Sales and Service | The Fleet Deal Maker system is a Ford of Canada Intranet web based application. The system is designed for use by Ford of Canada Controller's Office and Fleet Sales to administer Government Price Concessions (GPC) and Competive Price Allowance (CPA) Fleet deals. There are four business entities in the application: Vehicle Groups, Vehicle Financials, Deal Financials and Approval Request. | 12 |  | YES | 1 | NKANDULA | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
17368 | Bulk Mail | Active | BULKMAIL | EPEO | SKULKA52 | CGIACOBB | VMANDELL | VMANDELL | Copper | Non S-Ox | - | No | - | - | CMIRABIT | CGIACOBB | Information Technology | ITO | Create mass mailing lists from based on selection criteria supplied by list owners or subscription lists. Send emails to those lists |  |  | YES | 1 | SWALIMBE | PLM | Mainframe | Q4 2025 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
20216 | Broadcom Data Center Security (Symantec Critical S | In Production | DCS (SCSP) | EPEO | NOKEEFE | VNACHIMU | PFREILE | GSIENKIE | Copper | Non S-Ox | 221 | Yes | No | COTS | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | DCS (Formerly known as SCSP) is deployed on servers to act as a host-based firewall to protect against interna/external threats. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
21805 | FIREEYE HX | Active | FireEye HX | EPEO | NOKEEFE | VNACHIMU | PFREILE | WJUSTICE | Copper | Non S-Ox | - | No | Yes | - | NOKEEFE | VNACHIMU | Enterprise Technology | ITO | FireEye HX is a client-server platform for the detection, analysis and management of security incidents on Windows based platforms. | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
50991 | Broadcast Web Services | In Production | BCWS | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Silver | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | 121 | Broadcast Web Services is a service allowing downstream subscribers internal to assembly plants to receive various types of vehicle build data |  | Springboot | YES | 3 | BWUNNAVA | PLM | Java < v21 | Q2 2025 | Version Upgrade | Modernize | 2025-09-30 | 2025-09-30 |  | Not Started | Green | 2025-09-30 |  | Planned |  | No | [8 empty] | Java 17 | Priya | 2025-03-11 |  |  | Upgrade to Java version 17 estimated completion by end of Q3 2025 | No | Java < v21
50991 | Broadcast Web Services | In Production | BCWS | ISIT | AMEHER1 | ADURSO | RVOSS5 | RPRASA22 | Silver | Non S-Ox | 121 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Broadcast Web Services is a service allowing downstream subscribers internal to assembly plants to receive various types of vehicle build data |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [8 empty] | SQL | Priya |  |  |  | Requires SQL AlwaysOn. Database VM will be migrated to OSV AS-IS. No changes will be made to the application. Timeline depends on OSV availability | No | SQL
50322 | File & Print | In Production | F&P | EPEO | SRUNSON | PSIMONTE | RGOMEZ40 | AGUTIE95 | Copper | Non S-Ox | 12 | No | Yes | In-House | SRUNSON | PSIMONTE | Enterprise Technology | EPEO | Identification and discovery of distributed File, Print, and SCCM DP servers. | 2 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
340 | Broadcast | In Production | VBC | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Gold | Non S-Ox | 133 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Part of VSC suite.The Broadcast System expands the basic order data into build information for the assembly plant trim and chassis operations. Generates the 8502 for the Plant Floor systems. |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q3 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
340 | Broadcast | In Production | VBC | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Gold | Non S-Ox | 133 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Part of VSC suite.The Broadcast System expands the basic order data into build information for the assembly plant trim and chassis operations. Generates the 8502 for the Plant Floor systems. |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
51592 | BrakeLab Connect | In Production | BLC | ISIT | OTHERS | KESTIEV1 | HOBERKIR | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | In-House | MMAILE1 | KESTIEV1 | PD Operations and Quality | Industrial System IT | The system manages Brake Lab Processes i.e. Warehousing test parts, Dynometer Configuration File Management, Reporting. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
13488 | FGTI-Internal Website | In Production | FGTI Web | OCETO | TSWEEN16 | BLALLY | VCHEA | MBALAN2 | Copper | Non S-Ox | 111 | Yes | No | In-House | SCROLEY | JSTEC1 | Policy | Staffs IT | Internal website for the Ford Global Technologies, LLC business activity. | 9 |  | YES | 2 | TSWEEN16 | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22265 | Brake Analysis and Calculation Info System | In Production | BASIC | ISIT | OTHERS | BAESCHLI | GRAO3 | GRAO3 | Bronze | Non S-Ox | 122 | Yes | No | In-House | LLANE10 | BAESCHLI | Advanced PD and Tech | Industrial System IT | Chassis Engineering has developed a new Matlab based application to replace the currently in use Excel sheets with Makros to simulate, calculate and analyse new break systems. NAS Site: \\FMC9040181\ola2_beamng_prod8337 Group: ESA\USWF-NAS-ola2_beamng_prod8337 |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
15182 | FCLA Brazil Wholesale Operations Controls (WAP) | In Production | WAP | OCETO | DBRIGHEN | RCORDEI1 | RSCHIEVE | NVARADA2 | Silver | Non S-Ox | 312 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Marketing & Sales | - | Improve Systems and Controls to support Wholesale Operations in Brazil to avoid losses or frauds and to migrate mandatory controls from manual to automatic. Business Issue and / or Opportunity 1.There are many manual controls over all the steps of the Wholesale process. 2.The Wholesale charge off routine (USA GAAP) has manual adjustments to be in compliance with the Global Policy. 3.All collection activities are done manually without a system support. 4.There is no management tool to allow operational analysis over the daily operation. 5.Part of the COI collection process has no system to support it. 6.The COIs need be within a structured system to avoid controls problems, including the control of the properties received as payment-in-kind. 7.The collaterals appraisals and environment risk assessment needs to be controlled through a system. 8.There is an opportunity to build an automatic interface by downloading the Dealer Financial Statement data to ADCP to avoid data transfer bugs and speed up the | 4 |  | YES | 4 | TSWEEN16 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
11915 | Border Crossing System | In Production | BCS | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Gold | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | BCS is designed to capture the Corporate Material Release information from (CMMS,FCSD ) concerning any part that is expected to cross an international border between the current date and 9 weeks into the future. |  |  | YES | 1 | BWUNNAVA | PLM | Mainframe | Q3 2027 | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
6260 | BOPS: Business Operating Plan System | In Production | EuFA-BOPS | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | The cycle plan, budget, actuals and performance reporting system used by Product Development (PD) in Ford of Europe. |  |  | YES | 1 | TSWEEN16 | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Oracle
6260 | BOPS: Business Operating Plan System | In Production | EuFA-BOPS | I-ERP | SFRANCI8 | AKANSKI | BPRAKAS4 | LWU14 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Finance | Integrated Enterprise Resource Planning (I-ERP) | The cycle plan, budget, actuals and performance reporting system used by Product Development (PD) in Ford of Europe. |  | Springboot | YES | 2 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
53317 | BookitLab | In Production | bookitlab | OCETO | PMILLIGA | TYOUNG91 | RDOLLETE | WJUSTICE | Bronze | Non S-Ox | 211 | No | Yes | COTS | TGEIGER | TYOUNG91 | Enterprise Technology | - | Bookit-Lab is a comprehensive and easy to use Lab & Asset Management tool to manage and maintain software and hardware assets, reservations and storage of test results. |  |  | YES | 2 | PMILLIGA | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | Database servers & EAMS Status decommissioned | No | SQL
22394 | FCE Svenson Suite (Austria) | In Production | Svenson | FORD CREDIT | RMINHAS3 | PSRIKIR1 | RMRINAL2 | NKALE | Silver | Non S-Ox | 321 | No | Yes | COTS | RMINHAS3 | SSINGH14 | Ford Credit Services | Ford Credit (FMCC) | Software package for administration and registration/reporting of the required data (statistic bank data) due to the Austria Banking Act which clearly specify the laws for banking business in Austria. One part of this law is the regular reporting of statistic data to the Austian Central Bank. | 3 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
21253 | BOM Validation ICA | In Production | BOMval_ICA | ISIT | JKOONS | TBROWN99 | EMARTI32 | JLUCAS1 | Bronze | Non S-Ox | 211 | No | Yes | In-House | JKOONS | TBROWN99 | Manufacturing Staffs | Industrial System IT | Excel/VBA tool originally developed by PD Business consist of an Excel/VBA file stored in SharePoint and with a SQL database on the backend. It is used by MP&L PPM and D&R Engineers to confirm the Parts listed in the GPIRS BOM are accurate for a specific Build before ordering them for that Build. The tool contains Part numbers and usages retrieved from GPIRS and provides a point-in-time copy of the GPIRS BOM for an upcoming Prototype Build event. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
54357 | Ford Visualization Pipeline | In Production | FrdVisPipe | ISIT | SBONNICI | KRAMMOHA | RHARIKR2 | GRAO3 | Bronze | Non S-Ox | 122 | No | Yes | In-House | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | The Ford Visualization Pipeline is a web enabled application that is a hub for various visualization data inputs to be processed into refined downstream assets that can be consumed in downstream applications, such as the XR Hub. It consists of the Connector Tool, Asset Wizard, and 3D viewer | 3 |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
19630 | FCE SAP-Greece | In Production | FCESAPGRE | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | Non S-Ox | 11 | No | Yes | Managed by 3rd Party Purchased Service | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | The local accounting system used by FC Greece. The system provides accounting functionality that is fully compliant with Greek Tax Legislation and supports local reporting requirements, Greek Chart of Accounts for Banks, the Greek code of Books & Records, Accounts Receivables and Payables. It takes feeds from BLESS Wholesale and Receivables and passes data to the corporate GL system PSGL. | 1 |  | YES | 1 | SRAISIN1 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
20481 | Body-Shop Information System | In Production | BIS | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Engineering | Industrial System IT | Electronic Maintenance Manuals. Replaces Paper Manuals. Contains documentation for Ford assembly and stamping plant welding assembly automation. Users are plant skilled trades personnel. Access through Ford Intranet. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23477 | FCE Retail Deposits - Core Capability | In Production | FCERD Core | FORD CREDIT | JBENITO | JCOCKWIL | CWILL663 | AGALLAG9 | Bronze | S-Ox In Scope | 332 | No | Yes | Managed by 3rd Party Purchased Service | JBENITO | PLABROSS | Ford Credit Services | Ford Credit (FMCC) | This application supports the FCE required process to deliver the Retail Deposits Business capability to both the FCE UK Market and FBG DE market. The operational processing is all performed by an outsource partner (NSSSL for UK, FIS for FBG), who send us a daily overnight feed of information. This information (for both markets: UK & DE), is updated within an FCE owned database for processing and then management reporting and transmission of data to other FCE and FMC systems. | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
20481 | Body-Shop Information System | In Production | BIS | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Engineering | Industrial System IT | Electronic Maintenance Manuals. Replaces Paper Manuals. Contains documentation for Ford assembly and stamping plant welding assembly automation. Users are plant skilled trades personnel. Access through Ford Intranet. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
21747 | BodyEngg Web Site | In Production | BdyEngWeb | ISIT | OTHERS | KPAPENDI | PVANAST | GRAO3 | Copper | Non S-Ox | 311 | Yes | No | In-House | PFRANTZE | KPAPENDI | Advanced PD and Tech | Industrial System IT | This is the Test Data Management (TDM) solution of Body Engineering called Body Engineering Safety Web Site. The application provides a very powerful search engine based on meta data and compressed video clips. Engineers can identify and retrieve crash data, digital stills and high speed crash videos. |  |  | YES | 1 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
50594 | FCE Italy Local Applications | In Production | FCEITALA | FORD CREDIT | JBENITO | SHODGSO9 | VFERRARO | AGALLAG9 | Gold | Non S-Ox | 332 | Yes | No | In-House | JBENITO | SHODGSO9 | Ford Credit Services | - | The following MS Access DB have been migrated onto a Web Based solution hosted in US in DCoF. FCEClient/FCELocalApp.import/CASH/GEIS/IFK/BOI(Finco)/CSCUtenti/CFSUtenti/DocFIliali/Lettere/DB Dealer/ControlloGrandiRischi/Ordini di Acquisto FCE/IVASS/FollowUpIF/IdeaFord/ManutFrog/OperationReport/LogDlrService/SitGiorn/AUI-BRIDGE/ImmFOI/INBIX/JIF/API CSCUtenti/SSIS/Master DB su SQL/ScorMarketing Francia/FCELocalApp.import_France/ScorMarketing Italia/Ordini di Acquisto FOI/Credit Bureau/FCELocalApp.import_Spain | 8 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2026 | EDC CaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
12698 | ESBOL - Extended Service Business Online | In Production | ESBOL | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TBABU | RKADAM1 | Silver | Non S-Ox | 211 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | ESB Online (ESBOL) enables European Ford dealer users and internal Admin users to register Optional Vehicle Service (loyalty) Contract coverage online for new and used Ford vehicles. In ESB Online, dealers can inquire for existing contracts, retrieve price information, look up customer information via an interface to SCA-C, and submit new contracts for registration. The registration process completes when ESB Online generates a PDF contract form to be printed and signed. | 1 |  | YES | 5 | RKENNEL | PLM | VM | Q1 2026 | EDC CaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
23125 | Blueprint (formerly Storyteller) | In Production | Blueprint | EA | RRISS | SHE1 | SLOSEY | SGURU8 | Bronze | Non S-Ox | 321 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | Technology & Enterprise Services (TES) | Blueprint is a requirements management solution to replace Requisite Pro |  |  | YES | 2 | GBRAIL | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
51567 | ERPAAS - SHARED TECHNOLOGY SERVICE (STS) | Active | ERPaaS | EPEO | LFULCHER | EREYNOL3 | ALATIF | MSING120 | Gold | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | Enterprise Technology | - | Strategic and shared hosting infrastructure for Enterprise Resource Planning and SAP landscapes which will be offered as a robust, secure, scalable and supportable service - ERPaaS. The infrastructure will be hosted in Ford EDCs and initially designed, built, managed and supported by HPE. The hosting infrastructure will serve product teams who will be leveraging SAP modules, applications and in-memory HANA database to meet future enterprise resource planning initiatives. | 50 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to SaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
23753 | BlueOvalNow | In Production | BON | OCETO | TSWEEN16 | KADOMKAI | GWHOLIHA | MBALAN2 | Copper | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | TSWEEN16 | DDESAI | Communications | Staffs IT | BlueOvalNow (SocialChorus) is a mobile app that connects employees to a daily digest of work news and content. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
20722 | EPIC. Odette File Transfer Protocol | In Production | EPIC/OFTP2 | EPEO | MCRNKOVI | BBOGEDIN | JMEZQUIT | RMODI2 | Silver | Non S-Ox | 322 | Yes | No | COTS | MCRNKOVI | MCRNKOVI | Enterprise Technology | - | EPIC is an EDI software used to transfer files between Ford apps and Trading Partners. It uses the EDI Protocols OFTP2, SFTP and AS2 | 3 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
24523 | Billing Platform | In Production | BP | FORD CREDIT | DTAURO | SLYNCH11 | MSULLANO | ROBRIEN3 | Silver | Non S-Ox | 332 | No | Yes | In-House | DTAURO | LCARVA11 | Ford Credit Services | 332 | The Billing Platform creates a unified billing experience by compiling data from multiple sources and generating reoccurring, consistent invoice templates for customers and downstream systems that includes itemized details of payments due and received as well as product/service information as applicable. The Billing Platform will support both Ford and Ford Credit globally including Ford Smart Mobility (FSM), Ford Pro, and Electric Vehicle initiatives. |  | Springboot | YES | 4 | SRAISIN1 | PLM | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned | [17 empty] | Java < v21
24523 | Billing Platform | In Production | BP | FORD CREDIT | DTAURO | SLYNCH11 | MSULLANO | ROBRIEN3 | Silver | Non S-Ox | 332 | No | Yes | In-House | DTAURO | LCARVA11 | Ford Credit Services | Ford Credit (FMCC) | The Billing Platform creates a unified billing experience by compiling data from multiple sources and generating reoccurring, consistent invoice templates for customers and downstream systems that includes itemized details of payments due and received as well as product/service information as applicable. The Billing Platform will support both Ford and Ford Credit globally including Ford Smart Mobility (FSM), Ford Pro, and Electric Vehicle initiatives. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
24523 | Billing Platform | In Production | BP | FORD CREDIT | DTAURO | SLYNCH11 | MSULLANO | ROBRIEN3 | Silver | Non S-Ox | 332 | No | Yes | In-House | DTAURO | LCARVA11 | Ford Credit Services | Ford Credit (FMCC) | The Billing Platform creates a unified billing experience by compiling data from multiple sources and generating reoccurring, consistent invoice templates for customers and downstream systems that includes itemized details of payments due and received as well as product/service information as applicable. The Billing Platform will support both Ford and Ford Credit globally including Ford Smart Mobility (FSM), Ford Pro, and Electric Vehicle initiatives. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
15918 | Enterprise Data Warehouse-EDW | In Production | EDW | FORD CREDIT | IPANKAJ | VGA | BSENTHI1 | VBHUPATH | Bronze | Non S-Ox | 323 | No | Yes | In-House | IPANKAJ | VGA | Ford Credit Services | Ford Credit (FMCC) | The Ford Credit Enterprise Data Warehouse is an integrated repository of data sourced from various operational applications intended for analytical and reporting purposes. | 1 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
19836 | Bill of Material Foundation | In Production | BOMF | ISIT | MNOWICK1 | LSRINIVA | VATMAKUR | LPATIL | Silver | Non S-Ox | 211 | No | Yes | - | MNOWICK1 | MNOWICK1 | Advanced PD and Tech | - | This application is expected to become the BOM Foundation database within Ford Motor Company; it is part of the BOM Convergence & Transformaton project. It is initially expected to replace AVBOM starting in 2009 and serve as the kernel for a BOM Foundation platform. BOM Foundation is a repository for BOM & Part data and includes a set of web services to the Process Driven BOM (PDB) tool in a way that allows the AVBOM application to no longer be necessary. BOM Foundation establishes a robust, scalable platform that will enable future unification of BOM and Parts databases from other Ford applications (e.g., WERS, CMMS3). |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
51175 | EDDMS | In Production | EDDMS | EPEO | ARAJKUMA | MSAGNIA | SPATIL9 | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | In-House | ARAJKUMA | MSAGNIA | Advanced PD and Tech | - | department database | 2 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
23598 | BCTDM | In Production | BCTDM | ISIT | JKOONS | MNOVAK1 | BTHOMA47 | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | Need to separate BCTDM from eInspection. Detail to follow. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java Struts | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Saran | 2025-03-11 |  |  |  | No | Java < v21
23598 | BCTDM | In Production | BCTDM | ISIT | JKOONS | MNOVAK1 | BTHOMA47 | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | In-House | JKOONS | JKOONS | Advanced PD and Tech | Industrial System IT | Need to separate BCTDM from eInspection. Detail to follow. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Saran | 2025-03-11 |  |  |  | No | Oracle
23598 | BCTDM | In Production | BCTDM | ISIT | JKOONS | MNOVAK1 | BTHOMA47 | GRAO3 | Copper | Non S-Ox | 111 | No | Yes | In-House | JKOONS | MNOVAK1 | Advanced PD and Tech | Industrial System IT | Need to separate BCTDM from eInspection. Detail to follow. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Saran | 2025-03-11 |  |  |  | No | Java < v21
21040 | Battery Cell Innovation Lab | In Production | BCIL | ISIT | KCHRIST2 | KCHRIST2 | JCICOTTE | JLUCAS1 | Silver | Non S-Ox | 211 | Yes | No | COTS | GHERMAN | GHERMAN | PD Operations and Quality | Industrial System IT | Provide a comprehensive test environment for battery cell technology. Arrays of Battery Cycling Instruments and Test Cells have been installed to accommodate testing battery cell packaging ranging from single cells to multi-cell pack configurations. These testing instruments are capable of performing thermally controlled and automated test procedures, defined by test engineers. Test configuration, data capture, and data storage/data management is being supplied by a comprehensive AVL software solution. This software solution employs a client-server model architecture, where the client side will be a supplied and configured by AVL, and the server side component will be provisioned and managed by Ford IT residing in the corporate data center. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
50374 | DIGITAL PROCESS AUTOMATION - PEGA | Active | DPA | EPEO | LFULCHER | EREYNOL3 | RGANESH7 | SDHANAS2 | Gold | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | Enterprise Technology | ITO | Pega is an RPA/DPA tool that can be utilized to generate workflows that automates human actions in a desktop environment. RPA/DPA works best in automating standard, repetitive, rule based actions that a business user performs in their desktop environment. This tool allows us to write rules for business processes requiring efficient execution. | 53 |  | YES | 3 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to SaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
52962 | Banking Enablement Systems | In Production | BES | FORD CREDIT | IPANKAJ | VNAVEEN1 | VRUKMANG | ROBRIEN3 | Silver | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | VNAVEEN1 | Ford Credit Services | Ford Credit (FMCC) | Suite of APIs to support customer banking details. |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
52962 | Banking Enablement Systems | In Production | BES | FORD CREDIT | IPANKAJ | VNAVEEN1 | VRUKMANG | ROBRIEN3 | Silver | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | VRUKMANG | Ford Credit Services | Ford Credit (FMCC) | Suite of APIs to support customer banking details. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | SQL
22590 | Bank Accounts Reconciliation System (BARS) | In Production | BARS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Bank Accounts Reconciliation. The purpose of BARS application is performing bank accounts reconciliation of Accounting items (PeopleSoft GL) and bank statement. |  |  | YES | 3 | TSWEEN16 | PLM | SQL | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
56891 | DIGITAL PROCESS AUTOMATION - PEGA | In Production | DPA | EPEO | LFULCHER | EREYNOL3 | RGANESH7 | SDHANAS2 | Gold | Non S-Ox | 313 | No | Yes | COTS |  |  | Enterprise Technology | EPEO | Pega is an RPA/DPA tool that can be utilized to generate workflows that automates human actions in a desktop environment. RPA/DPA works best in automating standard, repetitive, rule based actions that a business user performs in their desktop environment. This tool allows us to write rules for business processes requiring efficient execution. | 8 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to SaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
22590 | Bank Accounts Reconciliation System (BARS) | In Production | BARS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Bank Accounts Reconciliation. The purpose of BARS application is performing bank accounts reconciliation of Accounting items (PeopleSoft GL) and bank statement. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
12101 | Balanced Single Agenda for Quality | In Production | BSAQ | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Bronze | Non S-Ox | 212 | No | Yes | In-House | JDEGUZMA | JDEGUZMA | Quality | Industrial System IT | The BSAQ employs 9 objective metrics, selected low and high time in service indicators, to form the basis for creating a prioritized list of issues to drive and track actions and provide timely metrics reports. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
12101 | Balanced Single Agenda for Quality | In Production | BSAQ | ISIT | JDEGUZMA | RMEHTA3 | MDUNFIEL | ISIDDIQ6 | Bronze | Non S-Ox | 212 | No | Yes | In-House | JDEGUZMA | RMEHTA3 | Quality | Industrial System IT | The BSAQ employs 9 objective metrics, selected low and high time in service indicators, to form the basis for creating a prioritized list of issues to drive and track actions and provide timely metrics reports. |  |  | YES | 2 | BWUNNAVA | PLM | Java Struts | Q4 2025 | Rewrite | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
50335 | Baidu Experience Service Layer | In Production | BESL | EVDD | DHE14 | QJI4 | YGONG6 | WJIN12 | Silver | Non S-Ox | 211 | No | Yes | In-House | #N/A | #N/A | Advanced PD and Tech | 211 | BAIDU EXPERIENCE SERVICE LAYER IS THE KEY ENABLER FOR BAIDU/FORD INTEGRATION. THIS SERVICE LAYER WILL PROVIDE SECURITY AND BUSINESS LOGIC TO COMMUNICATE WITH FORD BACKEND SERVICES FOR BAIDU. |  | Springboot | YES | 1 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
11996 | Back Order | In Production | PS&L BO | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ALOYA | MMEHTA5 | Silver | Non S-Ox | 222 | No | Yes | In-House | DNANDAN | DWIERZBI | Ford Customer Service | FCSD Tech | Orders where all PDCs are out of stock. |  |  | YES | 1 | RKENNEL | PLM | Mainframe | Q3 2027 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
50385 | B2D-CMS-Foundation | In Production | B2DCMS | M&S TECH | NKANDULA | JLEWIS10 | KDAILY | JHARPER2 | Platinum | Non S-Ox | 213 | No | Yes | COTS | FHIRSH | JLEWIS10 | Marketing & Sales | 213 | Foundation infrastructure for CMS implementations used for Business-to-Dealer, providing components common to all tenants. Tenant dealer CMS applications will reference this as their foundation. Content will reside in those tenants. |  | Springboot | YES | 2 | NKANDULA | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
23960 | DeviceWise | In Production | devicewise | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Copper | Non S-Ox | 23 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Device Wise is a PC based communications gateway to enable plant floor PLC communications to upper level manufacturing and plant floor systems. The application allows for native communications to Rockwell, Siemens, Mitsubishi and all major PLC manufacturers. | 5 |  | YES | 1 | BWUNNAVA | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
22414 | Dealership and User Profiles | In Production | Dlr UPrfle | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 111 | No | Yes | In-House | KBERCH | GDIAZ1 | Enterprise Technology | Marketing, Sales and Service | Online source of comprehensive information about all Canadian dealerships (including Dealership name, code, sales territory, region etc.) and all user profiles information within it. Also, includes EADAM, Directory Search and Suppplier access review functions. | 13 |  | YES | 2 | NKANDULA | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
22811 | B2C Services Layer | In Production | B2CSL | M&S TECH | VMUTHUPA | AMEIKLE | LCURRAN1 | JCOY3 | Silver | Non S-Ox | 213 | No | Yes | In-House | TJUNIPER | AMEIKLE | Marketing & Sales | Marketing, Sales and Service | This application provides web services and data that enables functionality on consumer digital channels, such as the National Web Portals (Consumer Websites) |  |  | YES | 3 | NKANDULA | PLM | Java Struts | Q3 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-09-15 |  | In-Progress | Green | 2025-12-14 |  | Planned |  | No | 100% | 0% | 0% | 0% | 0% | 0% | 0% |  | Java 21 |  |  |  |  | They are already on 17. Need to verify if they have plan to upgrade to 21 | No | Java < v21
22811 | B2C Services Layer | In Production | B2CSL | M&S TECH | VMUTHUPA | AMEIKLE | LCURRAN1 | JCOY3 | Silver | Non S-Ox | 213 | No | Yes | In-House | TJUNIPER | AMEIKLE | Marketing & Sales | Marketing, Sales and Service | This application provides web services and data that enables functionality on consumer digital channels, such as the National Web Portals (Consumer Websites) |  |  | YES | 3 | NKANDULA | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-30 | Complete | Blue | 2025-06-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | MongoDB Atlas |  |  |  |  | This app has mongoDB Atlas in GCP which is a final state so no action in PLM. | Yes | SQL
22811 | B2C Services Layer | In Production | B2CSL | M&S TECH | VMUTHUPA | AMEIKLE | LCURRAN1 | JCOY3 | Silver | Non S-Ox | 213 | No | Yes | In-House | TJUNIPER | AMEIKLE | Marketing & Sales | Marketing, Sales and Service | This application provides web services and data that enables functionality on consumer digital channels, such as the National Web Portals (Consumer Websites) |  |  | YES | 3 | NKANDULA | PLM | WAS | Q3 2025 | Version Upgrade | Modernize | 2025-03-15 | 2025-01-30 | 2025-01-30 | Complete | Blue | 2025-04-30 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | This app does not have WAS. It should be deleted | No | Java < v21
18813 | Dealer margin (BONI) | In Production | BONI | EPEO | ARAJKUMA | LEHLERS1 | JBRETT1 | LRODR205 | Bronze | Non S-Ox | - | Yes | No | Managed by 3rd Party Purchased Service | ARAJKUMA | IKOVALEV | Marketing & Sales | - | Stores and processes data related to some elements of the Dealer Margin calculation. Year end process calculates next years Dealer margin and downloads to DID. | 4 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
23854 | Azure AD Connect | In Production | AAC | EPEO | NOKEEFE | MSNYDER5 | CQI | GSIENKIE | Silver | Non S-Ox | 213 | Yes | No | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Strategic implementation to support existing Azure AD Accounts in AZUREFORD. CHINAFORD to remain as tactical solution and will not be part of this HA implemented solution. Enterprise Systems Management Description - This project will provide one way synchronization of internal Ford Active Directory user accounts to existing Azure AD accounts in such a way that all internal Ford users for an Azure Tenant will be managed by an internal Ford Active Directory system so that there is a single identity source for all existing Azure AD accounts which have been issued to users who existing within Fords internal Active Directory. BCE Rating E OLA2. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
53576 | Cyber Security Vulnerability Scanning and Manageme | In Production | CSVSM | EPEO | NOKEEFE | NOKEEFE | VVENKA40 | WJUSTICE | Bronze | Non S-Ox | 331 | No | Yes | COTS | UARJUNAN | NOKEEFE | Enterprise Technology | EPEO | Cyber Security Vulnerability Scanning and Management | 13 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
24934 | Citrix XenApp 7.15 Infrastructure | Active | XA 7.15 | EPEO | LFULCHER | LFULCHER | EREYNOL3 | GSIENKIE | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | Enterprise Technology | ITO | Citrix XenApp is a MS Terminal Services based technology that allows remote users to connect to applications that are actually installed on a remote server. It uses a mix of technology that results in that remote applications looking and behaving though it was installed on a local desktop. Within Ford Citrix is cerfied to enable Unix workstation based customers to make use of MS Office, to virtualize LOB fat clients applications on centrally managed servers, solve network latency issues with client/server applications etc. This ITMS entry represents a global Citrix XenApp farm infrastructure which delivers XenApp functionaliy and management. | 18 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to SaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
11060 | AXZ Plan System Mainframe | In Production | AXZ | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Silver | Non S-Ox | 313 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | AXZ Employee Vehicle Purchase Plans |  |  | YES | 2 | NKANDULA | PLM | Mainframe | Q4 2027 | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11060 | AXZ Plan System Mainframe | In Production | AXZ | M&S TECH | FHIRSH | NGIRISH | VBALAMU2 | CKEMPSKI | Silver | Non S-Ox | 313 | No | Yes | In-House | FHIRSH | NGIRISH | Human Resources | Marketing, Sales and Service | AXZ Employee Vehicle Purchase Plans |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
54148 | AW and Indexing | In Production | AWINDEX | ISIT | JKOONS | NLAKSHMA | KRAJES33 | GRAO3 | Silver | Non S-Ox | 311 | No | Yes | COTS | JKOONS | NLAKSHMA | Advanced PD and Tech | - | Active Workspace is an user interface for an improved Teamcenter user experience. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51939 | China - Pinnacle Account Servicing Batch | In Production | FAFC-PASMF | FORD CREDIT | JCHEN11 | CYANG63 | CXUE7 | YZHU86 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | JCHEN11 | CXUE7 | Ford Credit Services | Ford Credit (FMCC) | The China Pinnacle Account Servicing Mainframe Suite is a S-OX classified suite of programs responsible for passing Pinnacle DB2 Data to/from the Pinnacle Account Servicing application and for Account Servicing batch processes. | 1 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
23359 | AVL Creta | In Production | AVL-C | ISIT | JKOONS | TBROWN99 | GKIRANKU | JLUCAS1 | Copper | Non S-Ox | - | Yes | No | COTS | JKOONS | TBROWN99 | PD Operations and Quality | Industrial System IT | AVL Creta is software supplied by AVL that manages the development lifecycle of engine calibrations and facilitates the managed sharing of engine calibrations across different vehicle programs and software calibrators. Initially being used as a pilot on V408 in Europe with a view to evaluating as the global strategic solution. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started | Green | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
20434 | CENTRAL ADMIN FRAMEWORK | In Production | CAF | EPEO | LFULCHER | LFULCHER | NGILLIKI | NGILLIKI | Bronze | Non S-Ox | 111 | Yes | No | In-House | CMIRABIT | LFULCHER | Enterprise Technology | EPEO | A centralized framework providing a suite of commonized tools that can be executed across multiple systems and platforms. | 13 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
19552 | Cacti | In Production | CACTI | EPEO | MCRNKOVI | SSOLTANI | CCRAIG39 | CCRAIG39 | Silver | Non S-Ox | 122 | No | Yes | Open Source | MCRNKOVI | SSOLTANI | Enterprise Technology | EPEO | Cacti is a network performance analysis tool. It has the ability to identify trends in the network, by hour, day, week, month and even year to year. It also allows the ability to drill down from yearly to daily, and even hourly displays of data, simply by clicking the mouse. Cacti is used by Network Operations for network devices and Server Hosting for a limited number of servers | 14 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
54071 | AV Partner Integration | Planned | AVPI | M&S TECH | KHEMANT | MVAIRAP1 | VNANDURU | MPARTHI3 | Gold | Non S-Ox | - | No | Yes | In-House | NKANDULA | GCHOUKAI | Model E Customer | - | PARTNER INTEGRATION SERVICES |  | Springboot | YES | 1 | NKANDULA | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
20059 | Autosys | Active | Autosys | EPEO | LFULCHER | LFULCHER | BMORAN20 | BMORAN20 | Gold | Non S-Ox | - | No | - | - | CMIRABIT | CMIRABIT | Information Technology | ITO | Enterprise scheduling system for UNIX, Linux and Windows servers. Accounting Systems Renewal uses a local implementation of Autosys. |  |  | YES | 3 | SWALIMBE | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
20216 | Broadcom Data Center Security (Symantec Critical S | In Production | DCS (SCSP) | EPEO | NOKEEFE | VNACHIMU | PFREILE | GSIENKIE | Copper | Non S-Ox | 221 | Yes | No | COTS | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | DCS (Formerly known as SCSP) is deployed on servers to act as a host-based firewall to protect against interna/external threats. | 25 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
20059 | Autosys | Active | Autosys | EPEO | LFULCHER | LFULCHER | BMORAN20 | BMORAN20 | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | LFULCHER | #N/A | ITO | #N/A |  |  | YES | 3 | SWALIMBE | PLM | WAS | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned | [17 empty] | Java < v21
50304 | B2C GLOBAL 2 FOUNDATION | In Production | B2CGLOBAL2 | M&S TECH | RKLEINSM | RKLEINSM | KPONNUSW | JPOTTE60 | Silver | Non S-Ox | 222 | No | Yes | COTS |  |  | Enterprise Technology | Marketing, Sales and Service | AEM 6.5 Foundation is the platform for the B2C Consumer experience. The Foundation will support multiple tenants like CLIMS, Performance, Quicklane, etc. | 27 |  | YES | 1 | NKANDULA | PLM | VM | Q1 2026 | Complete Migration to SaaS | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
236 | Automated Vehicle Scheduling | Inactive | AVS | ISIT | AMEHER1 | ADURSO | RHOPKIN4 | - | Copper | Non S-Ox | - | No | Yes | - | GHERMAN | ADURSO | Manufacturing Staffs | - | Multiple Vehicle Scheduling applications which control the Plant build process. There are applications which run in the Plant Data Center and on the Plant Floor which provide vehicle build information to operators and automation in all areas of the plant; Body, Paint, Trim, Chassis, Final, Predelivery, Yard. This ITMS entry is used to reference the entire suite of AVS applications. The Tehcnical Manifest for this application is not detailed in this ITMS record. Instead each component of AVS (listed below in Data Interfaces) reflects it's own detail as part of the individual ITMS records. |  |  | YES | 1 | BWUNNAVA | PLM | ESB |  |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
20486 | Automated Knowledge Acquisition - AKATT | In Production | AKATT | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | ASARKA14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | AKATT is used for reviewing archived Pinnacle Loan Origination offerings. The analyst uses it to investigate and/or validate offerings. There is no SPII or identifiable PII data in AKATT. | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
23256 | Application Performance Monitoring | In Production | APM | EPEO | RHAMMO57 | MBRUM | APOE3 | GSIENKIE | Bronze | Non S-Ox | 211 | No | Yes | COTS | RHAMMO57 | SHAYDEN5 | Enterprise Technology | EPEO | APM solution will allow the enterprise to monitor business applications in a holistic, end-to-end manner using a comprehensive integrated tool set with clearly defined processes. APM includes: End-user experience monitoring Runtime application architecture discovery Business transaction tracing Component deep-dive monitoring Reporting and analytics | 54 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
20486 | Automated Knowledge Acquisition - AKATT | In Production | AKATT | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | ASARKA14 | Bronze | Non S-Ox | 111 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | AKATT is used for reviewing archived Pinnacle Loan Origination offerings. The analyst uses it to investigate and/or validate offerings. There is no SPII or identifiable PII data in AKATT. |  |  | YES | 2 | SRAISIN1 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
19357 | APA TW DPI (Taiwan) | In Production | TWN DPI | FORD PRO & FCSD TECH | OTHERS | OTHERS | THUANG2 | THUNG | Bronze | Non S-Ox | 211 | No | Yes | In-House | WCHEN130 | VWEN | Ford Customer Service | - | The purpose of the DPI system is not just to help FLH ACSG collect all dealer order data efficiently and manage the analysis of dealer parts & sales data, but also to provide a systematic and automatic process for Dealer parts warehouse business in order to reduce FLH business workload and personal oversight. The DPI system is also able to automatically check, control and receive the dealer orders. Based on the dealer orders, FLH ACSD can schedule the shipping time to dealers. System is supported by local Taiwan IT team and hosted in Dearborn. | 4 |  | YES | 1 | RKENNEL | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
20486 | Automated Knowledge Acquisition - AKATT | In Production | AKATT | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | ASARKA14 | Bronze | Non S-Ox | 111 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | AKATT is used for reviewing archived Pinnacle Loan Origination offerings. The analyst uses it to investigate and/or validate offerings. There is no SPII or identifiable PII data in AKATT. |  | Springboot | YES | 3 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned | [17 empty] | Java < v21
53602 | Automated Infrastructure Delivery Engineering Plus | Planned | AIDE | EPEO | LFULCHER | KMAHAJAN | MBRYAN66 | MPEKARSK | - | Non S-Ox | - | No | Yes | In-House | LFULCHER | KMAHAJAN | Enterprise Technology | EPEO | Automated service tool for Infrastructure Delivery Engineering (IDE) team members |  |  | YES | 1 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned | [17 empty] | SQL
19179 | Automated Image Management System-AIMS | In Production | AIMS | FORD CREDIT | DTAURO | JJACK348 | NBHALWAN | ROBRIEN3 | Silver | Non S-Ox | 223 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | The application streamlines incoming faxes to a business unit by eliminating paper faxes and converting incoming faxes to images, tagging incoming images with index information based on bar codes, and storing them in an application for viewing, routing, processing, and archiving. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Mainframe
19179 | Automated Image Management System-AIMS | In Production | AIMS | FORD CREDIT | DTAURO | JJACK348 | NBHALWAN | ROBRIEN3 | Silver | Non S-Ox | 223 | No | Yes | In-House | DTAURO | DTAURO | Ford Credit Services | Ford Credit (FMCC) | The application streamlines incoming faxes to a business unit by eliminating paper faxes and converting incoming faxes to images, tagging incoming images with index information based on bar codes, and storing them in an application for viewing, routing, processing, and archiving. |  |  | YES | 4 | SRAISIN1 | PLM | Oracle | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
19359 | APA TW ASN-P&S (TAIWAN) | In Production | TWN ASN-PS | FORD PRO & FCSD TECH | OTHERS | OTHERS | THUANG2 | THUNG | Bronze | Non S-Ox | 211 | No | Yes | In-House |  |  | Ford Customer Service | - | At the first working night in every month PANDA system produces the suggest order of local parts in next month. On next day the merchandiser in parts division at Ford Lio Ho would review suggest order which would be consquently purified (concurred) by the supervisor and the formal order & A.S.N. download file would be produced during the time of overnight job at every night . Until Cycle I the completely produced A.S.N. Data File would be transmitted to A.S.N. server through TCP/IP meanwhile the data would be transmitted to A.S.N. database through program. System is supported by local Taiwan IT team and hosted in Taiwan. | 4 |  | YES | 1 | RKENNEL | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | VM
19179 | Automated Image Management System-AIMS | In Production | AIMS | FORD CREDIT | DTAURO | JJACK348 | NBHALWAN | ROBRIEN3 | Silver | Non S-Ox | 223 | No | Yes | In-House | DTAURO | JJACK348 | Ford Credit Services | Ford Credit (FMCC) | The application streamlines incoming faxes to a business unit by eliminating paper faxes and converting incoming faxes to images, tagging incoming images with index information based on bar codes, and storing them in an application for viewing, routing, processing, and archiving. |  |  | YES | 4 | SRAISIN1 | PLM | WAS | Q2 2026 | Rewrite | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started |  | 2026-09-13 |  | Planned | [17 empty] | Java < v21
19319 | APA AU/NZL PANDA2 Data Warehouse | In Production | PANDA2_DW | ISIT | SBONNICI | KTONG1 | JAGATI | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SBONNICI | KTONG1 | Ford Customer Service | - | The PANDA Data Warehouse is a SQL server database which provides reporting and ad hoc analytical capabilities to Ford Customer Service Division (Australia/New Zealand)personnel. The PANDA Data Warehouse provides business information to the FCSD warehouses Supply Finance and Marketing and Sales groups. The data warehouse is populated from data extracts sourced from the PANDA appliation. Overnight batch jobs create extract files which are subsequently used to populate the SQL tables via DTS packages and stored procedures which run overnight on the SQL server. Users access data via a Business Objects front end. | 8 |  | YES | 3 | BWUNNAVA | PLM | VM | Q1 2026 | Will be Decommissioned | Decommission | 2026-03-15 | 2026-03-15 |  | Not Started | Green | 2026-06-13 |  | Planned |  | No | [14 empty] | No | VM
54513 | AutoHitch_DAT_AIML_Pipeline | In Development | AH_DAT_PL | EVDD | OTHERS | DROGAN4 | SSHAR137 | VKOSURI | - | Non S-Ox | - | No | Yes | In-House |  |  | Advanced PD and Tech | - | An MLOps pipeline to automate AI/ML model development and training |  | Springboot | YES | 2 | MJONE308 | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Java < v21
51948 | AutoDraw | In Production | AutoDraw | ISIT | SKING68 | JLYNN1 | KKISIEL | AELANGO | Copper | Non S-Ox | 111 | Yes | No | In-House | SKING68 | JLYNN1 | Manufacturing Engineering | - | AutoDraw is a toolset that provides the Layout Engineer a way to place Material and Power Tools into the correct station. It also provides tools to compare the content to the Allocation Planning Tool report and Plan for Every Part report to make updates as needed. |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | Q2 2025 | Version Upgrade | Modernize | 2025-01-27 | 2025-01-27 | 2025-01-27 | Complete | Blue | 2025-01-27 | 2025-01-27 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Java 17 | Priya | 2025-03-04 |  |  | App already on Java 17, planning for an upgrade to JAVA 21 | No | Java < v21
20897 | Autodesk Vault | In Production | Vault/DMS | ISIT | SKING68 | JLYNN1 | JRICH264 | AELANGO | Bronze | Non S-Ox | 211 | No | Yes | COTS | KCHRIST2 | GECHOLS | Manufacturing Engineering | Industrial System IT | Multi-user DWG data base for Ford Land, PTO, and VO. Mutiple users work collaboratively without overwriting other data including version controls. Includes Vault Enterprise Add-On function for clients. Includes Vault Auto-Naming Utility (add-on). |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
20181 | APA AU Dealer Service Bureau 2 (DSB2) | In Production | DSB2 | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KPINNU | KHILLERT | Ford Customer Service | Marketing, Sales and Service | Dealer Service Bureau consolidates financial data from applications such as RMS, PSAR, etcssxaxd | 6 |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration |  |  |  |  | This is going to decommission completely in 2026 and funtionality will get merged in DCDS Hub | No | VM
53534 | Auth Agent | In Production | A2 | FORD PRO & FCSD TECH | TJUNIPER | AMEIKLE | LCURRAN1 | JCOY3 | Platinum | Non S-Ox | 213 | No | Yes | - | #N/A | #N/A | Marketing & Sales | 213 | A ROBUST, LIGHT-WEIGHT ZERO-TRUST SECURITY, GLOBAL FRAMEWORK THAT PROVIDES SECURITY TO MULTIPLE PLATFORMS USING ADFS. KEY USES: ADFS PROTECTION FOR SERVICES IN NON-PROD & PROD AND EMBARGO CONTENT BEFORE GOING LIVE |  | Springboot | YES | 1 | RKENNEL | PLM | Java < v21 | Q4 2024 | Version Upgrade | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
24856 | Aurora Foundational Data | In Production | AFD | I-ERP | SARAUJO3 | VANURAD2 | PCHITIYA | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Purchasing Foundational Data to support Aurora- A Global cloud-based tool (Ariba/SAP) that manages requisitioning, sourcing, purchasing, and receiving of non-production materials. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q1 2025 | Modernize to Cloud Databases | Modernize | 2025-03-15 | 2025-02-01 | 2025-02-01 | Complete | Blue | 2025-02-16 | 2025-02-16 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Praveen | 2025-03-05 |  |  |  | No | SQL
20643 | AP Capitalised Vehicle System Version 2 | In Production | CAVES2 | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | System to manage the vehicle processing of Ford company capitalised vehicles. | 8 |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24856 | Aurora Foundational Data | In Production | AFD | I-ERP | SARAUJO3 | VANURAD2 | PCHITIYA | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Purchasing Foundational Data to support Aurora- A Global cloud-based tool (Ariba/SAP) that manages requisitioning, sourcing, purchasing, and receiving of non-production materials. |  | Springboot | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q3 2025 | Version Upgrade | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
23643 | Attunity Replicate | Active | RATTUNIT | EPEO | SKULKA52 | NSHAH43 | NVAIDYAN | RPOLLO13 | Silver | Non S-Ox | - | No | - | - | CMIRABIT | CMIRABIT | Information Technology | - | Attunity Replicate is a Data Ingestion tool (software) that replicates data from source systems (SQL Server, Oracle, DB2 z/OS, Teradata, and unstructured formats) to target Hadoop and Greenplum infrastructure |  |  | YES | 2 | SWALIMBE | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned | [17 empty] | Oracle
50897 | AMA - Access Governance and Administration | In Production | APS - AGA | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | AMA(aka APS) provides a standard solution for managing user access policies within an application, in addition to a work flow tool to manage user-id maintenance | 5 |  | YES | 4 | SWALIMBE | PLM | VM | Q1 2026 | Complete Migration to GCP (Both App & DB) | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
24460 | Attribute Based Access Control | In Production | ABAC | GDIA | CPELTZE1 | ARAMAKR4 | KNAMDEV | RPOLLO13 | Copper | Non S-Ox | 111 | No | Yes | In-House | CPELTZE1 | SS348 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Application Policy Services (APS) application will continue to be used to manage access requests and approvals, and some roles will have additional information to drive policies in ABAC by user by requested attribute. New attributes represent Source (data table or data file), Country (data row), and PII-level (data column). This enables the user to have access to specific data. The ABAC application will generate the necessary Policies for those users for the role and selected attribute. |  |  | NO | 2 | FRANBELL | PLM | SQL |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
22747 | AEM PRODUCT ENGINEERING | Active | AEM-PE | EPEO | LFULCHER | EREYNOL3 | JKADAKIA | MPINRED1 | Copper | Non S-Ox | - | No | Yes | - | MPATIL1 | MPATIL1 | Enterprise Technology | ITO | This ITMS entry is required to support the engineering of Adobe Experience Manager at Ford. This engineering effort meets the definition of a service application. The effort is self-contained, the resources are closely related, all working to support a particular business process. There is an OLA behind the engineering and support team. This entry is a Service, ACR/ICR, Business Criticality & Function Points are not applicable. | 48 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2026 | EDC New Hypervisor | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned | [17 empty] | VM
13096 | ATS - Automated Test System | In Production | ATS App | M&S TECH | OTHERS | JSTRIEGE | KSHRABLE | JHARPER2 | Bronze | Non S-Ox | 111 | Yes | No | Managed by 3rd Party Purchased Service | AVIETOR | JJACO146 | Marketing & Sales | Marketing, Sales and Service | A purchased package for storing and distributing test modules. |  |  | YES | 2 | NKANDULA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
52840 | WLTP Service | In Production | WLTP | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 212 | No | Yes | In-House | RKENNEL | JCHAUSSE | General Management | FCSD Tech | Service accessed via Motorcract to enable EU legislative requirement for vehicel converters to obtain certificate confirming revised C02 and fuel economy data when converting Ford commercial vehicles. | 1 |  | YES | 2 | RKENNEL | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-15 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
18231 | ATNPC Website | In Production | ATNPC | ISIT | SKING68 | JLYNN1 | RTHIRUV1 | AELANGO | Copper | Non S-Ox | 222 | Yes | No | In-House | SKING68 | SKING68 | New Model Programs | Industrial System IT | Automatic Transmission New Product Center Website |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | Q4 2025 | On-Prem | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
20005 | WEBSPHERE APPLICATION SERVER | Active | WAS | EPEO | LFULCHER | EREYNOL3 | JKADAKIA | JKADAKIA | Copper | Non S-Ox | - | No | Yes | - | LFULCHER | EREYNOL3 | Enterprise Technology | ITO | Java Enterprise Edition (Java EE) Application server software which runs the strategic, Java-based Ford application portfolio. Deployed on several hundred physical devices and over 2,000 licenses. This is an umbrella applying to all WAS versions (6.1, 7.0 and 8.0) and all WAS components (WAS, IHS and WAS Plug-in). | 10 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2025 | EDC New Hypervisor | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | VM
53008 | ATLAS Load Frame System | In Production | ALFS | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | The Humanetics ATLAS (Advanced Testing, Laboratory Acquisition System) is a state of the art Load Cell Test and Calibration equipment with unique capabilities of minimizing human effort and maximizing product quality. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q4 2027 | On-Prem | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started | Green | 2027-12-15 |  | Planned |  | No | [14 empty] | No | SQL
18033 | WAR - Warranty Datawarehouse | In Production | WAR | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Database with warranty information that is used by Service staff to get information and compose some business report. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-07 | Complete | Blue | 2025-06-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | The server is shared with other applications, so decommissioning it will impact the other apps., Team in process of reassigning it to depenedent app # | No | VM
21216 | System Center Configuration Manager | In Production | SCCM 2012 | EPEO | SRUNSON | ASTONE31 | CHOSSEIN | BNABOZNY | Copper | Non S-Ox | 212 | No | Yes | COTS | SRUNSON | ASTONE31 | Enterprise Technology | EPEO | SCCM 2012 is the replacement version for System Management Server 2007 (SCCM 2007) which is the strategic direction for software delivery solutions. This applicaiton suite replaces all legacy software delivery tools globally for Windows clients and servers. | 80 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2025 | EDC New Hypervisor | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | VM
53816 | STA Competency eScorecard | In Production | eSTACS | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Manage & assess the competencies for the STA personnel. | 4 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-14 | Complete | Blue | 2025-04-14 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Praveen | 2025-03-04 |  |  |  | No | VM
12877 | ASR Systems & Infrastructure | In Production | ASR | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | CWADE | Gold | Non S-Ox | 11 | No | Yes | COTS | SFRANCI8 | DSHAH1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Systems and Infrastructure required for maintaining PeopleSoft suite of applications for Finance & Accounting functions. This includes feeder systems as well. |  |  | YES | 3 | TSWEEN16 | PLM | Mainframe | Q4 2026 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
12877 | ASR Systems & Infrastructure | In Production | ASR | I-ERP | SFRANCI8 | DSHAH1 | HPADMANA | CWADE | Gold | Non S-Ox | 11 | No | Yes | COTS | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Systems and Infrastructure required for maintaining PeopleSoft suite of applications for Finance & Accounting functions. This includes feeder systems as well. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Oracle
53331 | SQL SERVER FREE TRIALS | In Production | SQLFT | EPEO | SKULKA52 | NSHAH43 | NVAIDYAN | DPATEL43 | Copper | Non S-Ox | 111 | Yes | No | - |  |  | Enterprise Technology | - | SQL Server Free Trials Servers are 1) 120 day free trials for the FORD Customers provisioned through Ford Cloud Portal (FCP) at this time of the offering. 2) Testing Servers for DB Automation | 5 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [17 empty] | VM
9751 | As Built: As Built | In Production | ASBUILT | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 11 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | This application helps retrieve module configuration of a vin. |  |  | YES | 2 | RKENNEL | PLM | Mainframe | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
9751 | As Built: As Built | In Production | ASBUILT | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 11 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | This application helps retrieve module configuration of a vin. |  |  | YES | 2 | RKENNEL | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
17927 | South America Free of Charge (ARPW) | In Production | ARPW | OCETO | DBRIGHEN | AMACHAD3 | WBIANCHI | NMORALE7 | Silver | S-Ox Out of Scope | 211 | No | Yes | - | DBRIGHEN | AMACHAD3 | Ford Customer Service | - | This system controls the delivery of parts free of charge to the Dealer when the vehicle repaired is in warranty period. Also controls that these parts are involved in a warranty claim submitted by the Dealer after the repair. | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-10 | Complete | Blue | 2025-06-13 |  | Planned | RITM0140743/REQ0140385 | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | DB VMs - decommission request raised | No | VM
50326 | Arrow | In Production | Arrow | ISIT | MNOWICK1 | LSRINIVA | GPIOT1 | LPATIL | Bronze | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | Team of four interfaces to supplement supplier provided BoBQuote data with right hand walk, cost categories etc. | 5 |  | YES | 2 | BWUNNAVA | PLM | Datastage | Q2 2026 | No Datastage | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | DA
50326 | Arrow | In Production | Arrow | ISIT | MNOWICK1 | LSRINIVA | GPIOT1 | LPATIL | Bronze | Non S-Ox | 211 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | 211 | Team of four interfaces to supplement supplier provided BoBQuote data with right hand walk, cost categories etc. |  | Springboot | YES | 2 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
154 | ARMIS: Account Receivable Misc. Invoicing System | In Production | ARMIS | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Gold | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | ARMIS is used to bill dealers for non-part marketing programs. Invoice amounts are posted to the dealer's monthly billing statement. |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
24041 | Ariba Indirect | In Production | Aurora | I-ERP | SARAUJO3 | VANURAD2 | PCHITIYA | SNAG1 | Silver | S-Ox In Scope | 231 | No | Yes | Managed by 3rd Party Purchased Service | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Aurora- A Global cloud-based tool (Ariba/SAP) that manages requisitioning, sourcing, purchasing, and receiving of non-production materials. |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | SQL
22796 | SonarQube | In Production | SonarQube | EA | RRISS | SHE1 | LKESHRI | SGURU8 | Bronze | Non S-Ox | 211 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | - | SonarQube is an open source quality management platform, dedicated to continuously analyze and measure technical quality, from project portfolio to method. | 11 |  | YES | 2 | GBRAIL | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
24799 | Ariba Direct Sourcing | In Production | ADS | I-ERP | SARAUJO3 | KSYROCKI | PBUKKAPA | SNAG1 | Copper | Non S-Ox | 221 | No | Yes | Managed by 3rd Party Purchased Service | #N/A | #N/A | Supply Chain | 221 | SAP ARIBA CLOUD-BASED SAAS SOLUTION FOR NEXT GENERATION SUPPLIER SOURCING AND CONTRACTING TO SUPPORT THE DIRECT SOURCING PROCESS. IMPROVEMENTS IN DIRECT SOURCING PROCESSES WILL POSITION FORD TO TAKE ADVANTAGE OF BEST IN CLASS OFFERING: 1. ALIGN WITH MATURE INDUSTRY OFFERINGS THAT PROVIDE SOLUTIONS AT MARKET SPEED 2. ENABLE FORD TO EXPLORE SUPPLIERS BEYOND THE TRADITIONAL AUTOMOTIVE SUPPLY CHAIN. |  | Springboot | YES | 2 | TSWEEN16 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
22496 | SCA-Vehicle | In Production | SCA-V | GDIA | MLYONS23 | CDEBASHI | JJOHN998 | KMARATH1 | Bronze | Non S-Ox | 321 | No | Yes | In-House | DTERPST1 | JFERNSLE | Enterprise Technology | Global Data Insight and Analytics (GDIA) | SCA-V is a back end application that collects, receives and stores vehicle data from all sources so that it can be made available to enterprise teams for analytical purposes. Project also encompasses data discovery environment for analytic purposes. | 2 |  | YES | 3 | FRANBELL | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-01-15 | 2025-01-15 | 2025-01-15 | Complete | Blue | 2025-01-15 | 2025-01-15 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
17928 | Arg. VAT Recovery (VR) | In Production | ARVR | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | The application does the assignment of the fiscal credit to be recovered that is related to the vehicles, parts and accessories that are exported during a month. This assignment is based in the fiscal credit that the company pays in their purchases. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
104 | SBOM: Service Bill of Material | In Production | SBOM | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Web based software tool designed to help engineering community manage the service part release business in WERS | 2 |  | YES | 4 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-29 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | 4 VMs are pending , QA and PROD , Ticket submitted. Possible delay , Considering huge chunk of data as per PDO. | No | VM
17928 | Arg. VAT Recovery (VR) | In Production | ARVR | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | The application does the assignment of the fiscal credit to be recovered that is related to the vehicles, parts and accessories that are exported during a month. This assignment is based in the fiscal credit that the company pays in their purchases. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17828 | Arg. Transport Documentation (MK) | In Production | ARMK | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Manufacturing Plants | - | Manages Bailment process to control parts delivered to Suppliers and their return with new features. Supports all legal requirements of Argentina Customs regime in factories. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL PostgreSQL | [5 empty] | No | Oracle
52967 | SBDO Service | In Production | SBDO | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | - | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Service accessed via PTS to enable symptom based diagnostics and repair of vehicles | 8 |  | YES | 3 | RKENNEL | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-29 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | Decom Completed | No | VM
17828 | Arg. Transport Documentation (MK) | In Production | ARMK | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Plants | - | Manages Bailment process to control parts delivered to Suppliers and their return with new features. Supports all legal requirements of Argentina Customs regime in factories. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
16025 | Arg. Traffic & Customs (T&C) | In Production | ARTC | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Manufacturing Staffs | - | Manages Ford Argentina Import & Export Operations. Sends information to Custom Brokers with the material to be imported/exported and receives the information from the custom office with the imports and exports declared. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
22326 | SAS RDM Middleware | In Production | SASRDMMID | FORD CREDIT | RMINHAS3 | PBALUSU | SILANGOV | TSAILESH | Silver | Non S-Ox | 333 | No | Yes | In-House | RMINHAS3 | NJERRYDE | Ford Credit Services | Ford Credit (FMCC) | SAS RDM Middleware is a web service app used to convert mainframe to web service to pass Pinnacle Loan Originations transactions to SAS RDM. | 2 |  | YES | 3 | SRAISIN1 | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned | [10 empty] | GCP Migration | [6 empty] | VM
16025 | Arg. Traffic & Customs (T&C) | In Production | ARTC | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | - | Manages Ford Argentina Import & Export Operations. Sends information to Custom Brokers with the material to be imported/exported and receives the information from the custom office with the imports and exports declared. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17923 | Arg. Special Sales Management (VE) | In Production | ARVE | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | The system manages all special sales chanels. Includes the following operations: . Standard / Special Quotation Generation . Electronic Folder Generation. Tracking and administration. . Proforma Generation to down pay units. Taxing Approval. . RioServ debt publication (Proformas and Invoices) . Collection. Debit note emission for Down payments. . Price Release based invoicing. . Friendly process and operation. . Web Solutions oriented process. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
17923 | Arg. Special Sales Management (VE) | In Production | ARVE | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | The system manages all special sales chanels. Includes the following operations: . Standard / Special Quotation Generation . Electronic Folder Generation. Tracking and administration. . Proforma Generation to down pay units. Taxing Approval. . RioServ debt publication (Proformas and Invoices) . Collection. Debit note emission for Down payments. . Price Release based invoicing. . Friendly process and operation. . Web Solutions oriented process. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Oracle
51857 | SA Vehicle Subscription | In Production | SAVS | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | South America Vehicle Subscription Platform | 4 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | Fully modernized to GCP. No servers shown in SNOW | No | VM
17923 | Arg. Special Sales Management (VE) | In Production | ARVE | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Bronze | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | The system manages all special sales chanels. Includes the following operations: . Standard / Special Quotation Generation . Electronic Folder Generation. Tracking and administration. . Proforma Generation to down pay units. Taxing Approval. . RioServ debt publication (Proformas and Invoices) . Collection. Debit note emission for Down payments. . Price Release based invoicing. . Friendly process and operation. . Web Solutions oriented process. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
20379 | ARG. PLANT ACCESS REPORT (AR) | In Production | ARAR | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Land | Staffs IT | System that receives feed from the corporate card access system and other HR interfaces in order to be able to get reports online of: - Badge Audit trails - Presence of personel in an area - Cafeteria control - Monitor Fleet usage - Gas consumption control |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-06 | Complete | Blue | 2025-06-13 | 2025-01-06 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is already decommissioned | No | Java < v21
20379 | ARG. PLANT ACCESS REPORT (AR) | In Production | ARAR | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Land | Staffs IT | System that receives feed from the corporate card access system and other HR interfaces in order to be able to get reports online of: - Badge Audit trails - Presence of personel in an area - Cafeteria control - Monitor Fleet usage - Gas consumption control |  |  | YES | 4 | TSWEEN16 | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | Database servers & EAMS Status decommissioned | No | SQL
24155 | SA Smart Mobility Data Hub | In Production | SMDH | OCETO | DBRIGHEN | DBRIGHEN | AMACHAD3 | NMORALE7 | Copper | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Integrated Services | - | Cloud Hub to capture Data from Smart Mobility experiments. The clients would be IOT, Mobile applications, or other sources sending data to support Fleet Management, Active Call and Enterprise Values development | 3 |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 |  | Planned | REQ0084386, REQ0084388 | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | VM Decom ticket raised - Decomm server ito13301:Request Number : REQ0084386 Decomm server ito13302 Request Number : REQ0084388 | No | VM
20379 | ARG. PLANT ACCESS REPORT (AR) | In Production | ARAR | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Ford Land | Staffs IT | System that receives feed from the corporate card access system and other HR interfaces in order to be able to get reports online of: - Badge Audit trails - Presence of personel in an area - Cafeteria control - Monitor Fleet usage - Gas consumption control |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-06 | Complete | Blue | 2025-06-13 | 2025-01-06 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is already decommissioned | No | Java < v21
17850 | Arg. Parts Document Recording (PDR) | In Production | ARPD | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | This system allocates the purchasing documents (suppliers invoices and Import dispatches) to the produced vehicles. Allows to Financial inventory control and production FIFO by documents. This is the baseline to take advantage of the RAF import regime and the VAT Recovery process. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
51037 | RET AEM Foundation | In Production | RET STACK | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Copper | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Foundation infrastructure for RET AEM application, providing components common to all tenants. Tenant applications(RET esourcebook & CEM) will reference this as their foundation. Content will reside in those tenants. | 23 |  | YES | 1 | NKANDULA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
17850 | Arg. Parts Document Recording (PDR) | In Production | ARPD | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | This system allocates the purchasing documents (suppliers invoices and Import dispatches) to the produced vehicles. Allows to Financial inventory control and production FIFO by documents. This is the baseline to take advantage of the RAF import regime and the VAT Recovery process. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17847 | Arg. Foreign Payment (Pagos al Exterior) (PE) | In Production | ARPE | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | This system prepares all documentation requested by Argentinian Banco Central to perform a Payment to a foreign supplier. Receives information of all Ford Argentina Imports and, based on suppliers payment condition and Banco Central Regulations, determines payment dates and prepare information to send to the Banks for payments. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17847 | Arg. Foreign Payment (Pagos al Exterior) (PE) | In Production | ARPE | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | This system prepares all documentation requested by Argentinian Banco Central to perform a Payment to a foreign supplier. Receives information of all Ford Argentina Imports and, based on suppliers payment condition and Banco Central Regulations, determines payment dates and prepare information to send to the Banks for payments. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
51553 | Recall Investigative VIN Attribute tool | In Production | RIVAT | FORD PRO & FCSD TECH | RKENNEL | RRAJKIR2 | KAMIT4 | SDHANAS2 | Gold | Non S-Ox | 221 | No | Yes | In-House | RKENNEL | RRAJKIR2 | Ford Customer Service | FCSD Tech | RIVAT is an accounting (Tracking and Monitoring) database and Information Review Tool for the accounting and completion of Takata Airbag recalls as per NHTSA guidelines. The tool will be used to identify, control and maintain supplemental vehicle and owner data obtained from designated internal and external sources and vendors. Application has integration like smtp | 12 |  | YES | 4 | RKENNEL | PLM | VM | Q1 2025 | Complete Migration to SaaS | Modernize | 2025-03-31 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-29 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | SaaS |  |  |  |  | Already decommisioned due to migration on SaaS | No | VM
17847 | Arg. Foreign Payment (Pagos al Exterior) (PE) | In Production | ARPE | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | This system prepares all documentation requested by Argentinian Banco Central to perform a Payment to a foreign supplier. Receives information of all Ford Argentina Imports and, based on suppliers payment condition and Banco Central Regulations, determines payment dates and prepare information to send to the Banks for payments. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17855 | Arg. Export invoice hub to PS AR (Black Box) (BB) | In Production | ARBB | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This system receives billing data from the argentinian billing systems (Popims, VH and T&C) and creates an outbound file for PeopleSoft Accounts Receivable known as Open Items interface. This systems also maintains conversion tables in order to translate different values from one system to another. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17855 | Arg. Export invoice hub to PS AR (Black Box) (BB) | In Production | ARBB | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | Integrated Enterprise Resource Planning (I-ERP) | This system receives billing data from the argentinian billing systems (Popims, VH and T&C) and creates an outbound file for PeopleSoft Accounts Receivable known as Open Items interface. This systems also maintains conversion tables in order to translate different values from one system to another. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
51052 | RE&T Ford Lincoln Dealer Product Info AEM Tenant | In Production | eSB Tenant | M&S TECH | NKANDULA | JLEWIS10 | PSARADHA | JHARPER2 | Copper | Non S-Ox | 211 | No | Yes | In-House | FHIRSH | JLEWIS10 | Customer Experience | Marketing, Sales and Service | Product information repository and workflow validation tool. The application will also enable publishing of product information to Ford and Lincoln sales consultants, sales managers, etc. The 'Next Gen' platform will replace the current Ford eSourceBook and Lincoln Mercury ProductPortfolio websites. | 6 |  | YES | 3 | NKANDULA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-03-12 | Complete | Blue | 2025-06-13 | 2025-03-12 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
17855 | Arg. Export invoice hub to PS AR (Black Box) (BB) | In Production | ARBB | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | This system receives billing data from the argentinian billing systems (Popims, VH and T&C) and creates an outbound file for PeopleSoft Accounts Receivable known as Open Items interface. This systems also maintains conversion tables in order to translate different values from one system to another. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17831 | Arg. End-User File Upload Control (Consola) | In Production | ARCO | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Enterprise Technology | - | This system was developed to process all manual file input to accomplish all acr interfaces requirements. Users can send files (in pre defined formats) to a system, and CO makes the transference after a manager approval. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Modernize to Cloud Databases | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
52956 | Payment Enablement Systems | In Production | PES | FORD CREDIT | IPANKAJ | VNAVEEN1 | VRUKMANG | ROBRIEN3 | Silver | Non S-Ox | 322 | No | Yes | In-House | IPANKAJ | VRUKMANG | Ford Credit Services | Ford Credit (FMCC) | Suite of services to enable payment across Ford & Ford Credit. | 4 |  | YES | 2 | SRAISIN1 | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [6 empty] | VM
17874 | Arg. EDI-FIS Supplier (FIS Prove) (IS) | In Production | ARIS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Supply Chain | - | Creacion del Site para la Transferencias de Datos entre Ford Argentina y su Red de Proveedores, Despachantes, Transportistas y Socios para mantener y Continuar las Operaciones Comerciales con Ford. |  |  | YES | 3 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17874 | Arg. EDI-FIS Supplier (FIS Prove) (IS) | In Production | ARIS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Supply Chain | - | Creacion del Site para la Transferencias de Datos entre Ford Argentina y su Red de Proveedores, Despachantes, Transportistas y Socios para mantener y Continuar las Operaciones Comerciales con Ford. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
17874 | Arg. EDI-FIS Supplier (FIS Prove) (IS) | In Production | ARIS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Supply Chain | - | Creacion del Site para la Transferencias de Datos entre Ford Argentina y su Red de Proveedores, Despachantes, Transportistas y Socios para mantener y Continuar las Operaciones Comerciales con Ford. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17873 | ARG. EDI-FIS DEALER (FD) | In Production | ARFD | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Information sent to Dealers, Suppliers, Carriers, Browkers & Partners. Files generated by Mainframe and Others Ford Systems. Information received from Dealers Suppliers Carriers Browkers & Partners Files generated IN House PC to be processed in Mainframe systems in Ford. |  |  | YES | 4 | TSWEEN16 | PLM | Java Struts | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2025-03-30 |  | Not Started |  | 2025-06-28 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
17873 | ARG. EDI-FIS DEALER (FD) | In Production | ARFD | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Information sent to Dealers, Suppliers, Carriers, Browkers & Partners. Files generated by Mainframe and Others Ford Systems. Information received from Dealers Suppliers Carriers Browkers & Partners Files generated IN House PC to be processed in Mainframe systems in Ford. |  |  | YES | 4 | TSWEEN16 | PLM | SQL | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
16427 | Password Expiration Notification | In Production | PEN | EPEO | SKULKA52 | SKRISH30 | MMUTHUK1 | GSIENKIE | Copper | Non S-Ox | 111 | Yes | No | In-House | CMIRABIT | SKRISH30 | Enterprise Technology | - | The Password Expiration Notification System will provide email notifications to individual and application owners when their Oracle passwords are due to expire within a 15-30 day window. | 6 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2025 | EDC New Hypervisor | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
17873 | ARG. EDI-FIS DEALER (FD) | In Production | ARFD | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Information sent to Dealers, Suppliers, Carriers, Browkers & Partners. Files generated by Mainframe and Others Ford Systems. Information received from Dealers Suppliers Carriers Browkers & Partners Files generated IN House PC to be processed in Mainframe systems in Ford. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2025-03-30 |  | Not Started |  | 2025-06-28 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
17860 | Arg. Dealer Retail Data Collection (DR) | In Production | ARDR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Copper | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | This system contains information about: - Vehicle orders submitted - Tracking of vehicles: . From Assembly to Delivery to Dealer . Transportation to Dealer Arrivals/Delivery to Customers at Dealer Location - Wholesale Invoicing - Ford Credit financing status - Retail Invoicing - Vehicle patents at R.N.P.A. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
14893 | PackMan | In Production | PACKMAN | ISIT | AMEHER1 | ADURSO | NKARTH32 | RPRASA22 | Bronze | Non S-Ox | 111 | No | Yes | In-House | GHERMAN | ADURSO | Manufacturing Staffs | Industrial System IT | Packaging data collection and maintenance system used within Vehicle and Powertrain Operation plants within Europe. | 3 |  | YES | 4 | BWUNNAVA | Modernize Components (Backlog-2024) | VM | Q1 2025 | Partial Migration to GCP | Decommission | 2025-03-15 | 2025-03-10 | 2025-03-10 | Complete | Blue | 2025-03-10 | 2025-03-10 | Complete | Ticket # REQ0151002 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Saran | 2025-03-05 | 2025-03-10 |  | Decommissioned VM | No | VM
17860 | Arg. Dealer Retail Data Collection (DR) | In Production | ARDR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Copper | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | This system contains information about: - Vehicle orders submitted - Tracking of vehicles: . From Assembly to Delivery to Dealer . Transportation to Dealer Arrivals/Delivery to Customers at Dealer Location - Wholesale Invoicing - Ford Credit financing status - Retail Invoicing - Vehicle patents at R.N.P.A. |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
17832 | Arg. Customs Vehicle BoM Classification (CTC) | In Production | ARCT | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Bronze | Non S-Ox | 11 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | - | Manages classification of the BoM of each vehicle built in Argentina. For that, it uses harmonized codes for all trading goods. Finally, it creates all the legally required documents to be presented to the Government (Secretaria de Industria y Comercio). The documentation created by this system is required to be able to use RAF customs benefits in Argentina. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
17832 | Arg. Customs Vehicle BoM Classification (CTC) | In Production | ARCT | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Bronze | Non S-Ox | 11 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Manufacturing Staffs | - | Manages classification of the BoM of each vehicle built in Argentina. For that, it uses harmonized codes for all trading goods. Finally, it creates all the legally required documents to be presented to the Government (Secretaria de Industria y Comercio). The documentation created by this system is required to be able to use RAF customs benefits in Argentina. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q3 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
23097 | Order and Pricing Guides | In Production | OrdPrcGuid | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Bronze | Non S-Ox | 111 | No | Yes | In-House | KBERCH | GDIAZ1 | Finance | Marketing, Sales and Service | Order and Pricing Guides is an online source for comprehensive information for FoC Dealers on Ford's new lineup of cars and trucks. Each vehicle's complete order and pricing guide pages are available on-line for quick reference. | 4 |  | YES | 4 | NKANDULA | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-04 | Complete | Blue | 2025-06-13 | 2025-03-04 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
17832 | Arg. Customs Vehicle BoM Classification (CTC) | In Production | ARCT | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Bronze | Non S-Ox | 11 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | - | Manages classification of the BoM of each vehicle built in Argentina. For that, it uses harmonized codes for all trading goods. Finally, it creates all the legally required documents to be presented to the Government (Secretaria de Industria y Comercio). The documentation created by this system is required to be able to use RAF customs benefits in Argentina. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
17834 | Arg. Custom In House Regime (RAF) | In Production | ARFA | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Manufacturing Staffs | - | Manages Custom in House Imports & Exports. This Regime suspends duties and import fees payment for import parts used in production until the invoicing date. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
20655 | Online Supplier Rating Control | In Production | OSRC | ISIT | VVIJAY55 | BGANESH | TKRISHN8 | PKOTILA | Copper | Non S-Ox | 111 | No | Yes | In-House | SROYCHOU | BGANESH | Quality | Industrial System IT | The OSRC application is used to register and follow up IMRR, PSW and incoming parts; as well as it allows the user to evaluate the supplier rating. This application was originally designed for the Valencia Engine Plant and REDESIGNED to be used by all PTO plants within Europe. | 4 |  | YES | 4 | BWUNNAVA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-01-09 | 2025-01-09 | 2025-01-09 | Complete | Blue | 2025-01-09 | 2025-01-09 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | Ramesh | 2025-03-04 |  |  | App is Decommissioned | No | VM
17834 | Arg. Custom In House Regime (RAF) | In Production | ARFA | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | - | Manages Custom in House Imports & Exports. This Regime suspends duties and import fees payment for import parts used in production until the invoicing date. |  |  | YES | 3 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
17913 | Arg. Consortium Online Sales (VOPA) | In Production | ARWC | OCETO | DBRIGHEN | RCORDEI1 | EGARCI98 | NMORALE7 | Silver | Non S-Ox | 311 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | The Web Page contains information about products their features and Dealers availability. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2027 | Modernize to Cloud Databases | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Oracle
13360 | Online Credit Application | In Production | OCA | FORD CREDIT | NJOSHI21 | ASAPEHIA | RMANDE | ASAXENA8 | Silver | Non S-Ox | 321 | No | Yes | In-House | NJOSHI21 | ASAPEHIA | Enterprise Technology | Ford Credit (FMCC) | Ford Credit online credit application that supports customers and dealers to finance vehicle purchases. | 2 |  | YES | 4 | SRAISIN1 | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [6 empty] | VM
17917 | Arg. CMMS3 Local Data Hub (BM) | In Production | ARBM | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Manufacturing Staffs | - | This local process supports all the following tasks: - Receive information from CMMS3 - Validate and receive all valid Purchase Requests (from CEPS system) for parts received through CMMS3 - Productive Parts lifecycle from Pre-Production process to Logistics and finishing in Purchasing. - Provide Suppliers with information to support parts lifecycle - Hub for delivering information to local systems and end users - Update of local databases through Batch processes with Local, Regional and Global systems |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
17917 | Arg. CMMS3 Local Data Hub (BM) | In Production | ARBM | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | - | This local process supports all the following tasks: - Receive information from CMMS3 - Validate and receive all valid Purchase Requests (from CEPS system) for parts received through CMMS3 - Productive Parts lifecycle from Pre-Production process to Logistics and finishing in Purchasing. - Provide Suppliers with information to support parts lifecycle - Hub for delivering information to local systems and end users - Update of local databases through Batch processes with Local, Regional and Global systems |  |  | YES | 2 | TSWEEN16 | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
18586 | Arg. Catalog Administration System (CAS) | In Production | ARAC | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Copper | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | Industrial System IT | This application is used to define and generate the different catalogs of the produced models. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-05 | Complete | Blue | 2025-06-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP CaaS |  |  |  |  | Modernized Struts to Java Angular and Springboot | No | Java < v21
18586 | Arg. Catalog Administration System (CAS) | In Production | ARAC | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Copper | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Manufacturing Staffs | Industrial System IT | This application is used to define and generate the different catalogs of the produced models. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
24397 | New Vehicle Orientation Application | In Production | NVO | M&S TECH | RKLEINSM | BMUNIE | DCHITRA1 | JPOTTE60 | Gold | Non S-Ox | 222 | No | Yes | In-House | RKLEINSM | BMUNIE | Enterprise Technology | - | Provide a simple to use, device agnostic, interactive resource center that provides customer focused vehicle feature education and engages the customer throughout the delivery/orientation and initial ownership experience. Provide Delivery guides & feature education resources conveniently avail from FMCDealer, Fordowner, Lincolnowner and also accessible online, throught the Dealer Showcase App (iPad) tablets and smart phones. The Delivery guides will be available to dealership employees, corp users and customers. | 6 |  | YES | 3 | NKANDULA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-01-24 | Complete | Blue | 2025-06-13 | 2025-01-24 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
18586 | Arg. Catalog Administration System (CAS) | In Production | ARAC | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Copper | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Manufacturing Staffs | Industrial System IT | This application is used to define and generate the different catalogs of the produced models. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q1 2025 | Rewrite | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-05 | Complete | Blue | 2025-06-13 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run |  |  |  |  | Modernized Struts to Java Angular and Springboot | No | Java < v21
17838 | Arg. Application Access Profile Sytem (MS) | In Production | ARMS | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Copper | Non S-Ox | 111 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Enterprise Technology | - | Local Profile administration security system developed to manage access of users to each application and job in Ford Argentina. |  |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
50549 | New Parts Setup | In Production | NPS | FORD PRO & FCSD TECH | CHURLEY3 | DWIERZBI | TOBERHOF | MMEHTA5 | Silver | Non S-Ox | 211 | No | Yes | In-House | NBAECKER | AHOFFM15 | Ford Customer Service | - | New Parts Setup will support parts data collection prior to job 1#. | 10 |  | YES | 3 | RKENNEL | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Decom Only .Followed up with PDO. 10 VMs are pending. | No | VM
16021 | Arg. & Chile Vehicle Invoicing (VH) | In Production | ARVH | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | S-Ox In Scope | 211 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | - | Ford Argentina&Chile Invoicing System. Manages the following tasks: Domestic &Export Dispatching / Invoicing Ford-Mazda-PAG Units Operations. Dealers Limits Credit affectation Floor & No-Floor. Taxing registration according Gov regulations. Accounting recording Domestic & Export operations. Models & Customer (Dealers included)Master Files. Built Certificate generation. Units Price Lists administration. Freight quotation and Payment to Carriers. Domestic Operations involved: Dealers Fleet Consignment Consortium Harvest Plan Employees Used others. Export Operations involved: Ford Locs Non-affiliates. Miscelaneous DB-CR notes generation regarding: Incentives Pricing adjm Consortium others. ACR 2004-3709. |  |  | YES | 4 | TSWEEN16 | PLM | Oracle | Q2 2027 | Will be Decommissioned | Decommission | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
16021 | Arg. & Chile Vehicle Invoicing (VH) | In Production | ARVH | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | S-Ox In Scope | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Ford Argentina&Chile Invoicing System. Manages the following tasks: Domestic &Export Dispatching / Invoicing Ford-Mazda-PAG Units Operations. Dealers Limits Credit affectation Floor & No-Floor. Taxing registration according Gov regulations. Accounting recording Domestic & Export operations. Models & Customer (Dealers included)Master Files. Built Certificate generation. Units Price Lists administration. Freight quotation and Payment to Carriers. Domestic Operations involved: Dealers Fleet Consignment Consortium Harvest Plan Employees Used others. Export Operations involved: Ford Locs Non-affiliates. Miscelaneous DB-CR notes generation regarding: Incentives Pricing adjm Consortium others. ACR 2004-3709. |  |  | YES | 4 | TSWEEN16 | PLM | SQL | Q2 2027 | Will be Decommissioned | Decommission | 2027-06-15 | 2027-06-15 |  | Not Started |  | 2027-09-13 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
23793 | NAC-Global Server Operations Utilities | Active | GSOU | EPEO | LFULCHER | KMAHAJAN | AKHALI11 | SPOYNTE4 | Silver | Non S-Ox | - | No | Yes | - | LFULCHER | KMAHAJAN | Enterprise Technology | - | This is a tool set used by system administrators for performing their day to day operations | 33 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2025 | EDC New Hypervisor | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
16021 | Arg. & Chile Vehicle Invoicing (VH) | In Production | ARVH | OCETO | DBRIGHEN | RCORDEI1 | HMONTANO | NMORALE7 | Silver | S-Ox In Scope | 211 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | Ford Argentina&Chile Invoicing System. Manages the following tasks: Domestic &Export Dispatching / Invoicing Ford-Mazda-PAG Units Operations. Dealers Limits Credit affectation Floor & No-Floor. Taxing registration according Gov regulations. Accounting recording Domestic & Export operations. Models & Customer (Dealers included)Master Files. Built Certificate generation. Units Price Lists administration. Freight quotation and Payment to Carriers. Domestic Operations involved: Dealers Fleet Consignment Consortium Harvest Plan Employees Used others. Export Operations involved: Ford Locs Non-affiliates. Miscelaneous DB-CR notes generation regarding: Incentives Pricing adjm Consortium others. ACR 2004-3709. |  |  | YES | 4 | TSWEEN16 | PLM | WAS | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
51944 | MKT Advocacy tool | In Production | Advocacy | M&S TECH | VMUTHUPA | DSHANKA1 | RPURUSH3 | MPREETH6 | Bronze | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | VMUTHUPA | DSHANKA1 | Marketing & Sales | - | Advocacy program is the tool allowing Ford owner to recommend Ranger through theirs own peer to peer social media contact. | 2 |  | YES | 3 | NKANDULA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-05 | 2025-03-05 | Complete | Blue | 2025-03-05 | 2025-03-05 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | EAMS status - Decommissioned | No | VM
24297 | MEA ZA SVD Archiving SQL Reporting Services | In Production | MEA ZA SVD | EPEO | ARAJKUMA | SSURES35 | EVANVUU1 | SKANIMO2 | Copper | Non S-Ox | 211 | No | Yes | Managed by 3rd Party Purchased Service | ARAJKUMA | SSURES35 | Marketing & Sales | EPEO | Archiving and reporting solution to support the decommissioning of the South Africa legacy Sales & Vehicle Distribution mainframe solution. | 2 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2025 | EDC New Hypervisor | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
23673 | Appspace | Active | ADSS | EPEO | SRUNSON | PWILL357 | SKENNE67 | HLEVINE | Bronze | Non S-Ox | - | No | Yes | - | SRUNSON | PWILL357 | ENTERPRISE TECHNOLOGY | - | #N/A |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | SQL
11131 | Market Offering Complexity Analysis (MOCA) | In Production | MOCA | M&S TECH | FHIRSH | VDONTHY | LRAMPRA3 | CKEMPSKI | Copper | Non S-Ox | 221 | No | Yes | In-House | FHIRSH | VDONTHY | Marketing & Sales | Marketing, Sales and Service | MOCA - Market Offering Complexity Analysis is a Web-based application that allows Brand Teams to analyze historical vehicle order information and supports their efforts to develop more customer-focused vehicles. MOCA provides four core reports: Canned reports, Ad Hoc Queries, Models and Scenarios Reporting and Market Offering Health Reports (Mohr). | 8 |  | YES | 4 | NKANDULA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-03-03 | Complete | Blue | 2025-06-13 | 2025-03-03 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | EAMS status - App is Decommissioned . PDO team confirmed on the status | No | VM
19111 | Applus (Inc@Web) | In Production | Applus | ISIT | JDEGUZMA | RMEHTA3 | RJAMBUNA | ISIDDIQ6 | Bronze | Non S-Ox | 211 | No | Yes | COTS | JDEGUZMA | RMEHTA3 | PD Operations and Quality | Industrial System IT | Applus is a modified off the shelf package provided by www.novosoft.es The application is used to record and store internal audit data for the whole of Ford of Europe, MEA, Ford Sollers & Ford Otosan. This data is required in support of ISO 9001 Compliance for Ford of Europe etc. The application provides the ability for all contributing functions / organisations to submit internal audit data to one central data base for Ford of Europe etc. The application has analysis tools within it to allow the centralised/Regional Quality OCM's to analyse the internal audit results and provide direction for Quality Operating System improvements. This is a purchased application from a company called Novotec (www.novatec.es) and is also known as Inc@Web |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q2 2027 | Modernize to Cloud Databases | Modernize | 2027-06-15 | 2027-06-15 |  | Not Started | Green | 2027-09-13 |  | Planned |  | No | [14 empty] | No | SQL
51794 | Jacobs Test SLATE | In Production | TestSLATE | ISIT | KCHRIST2 | KCHRIST2 | BNASSER | JLUCAS1 | Bronze | Non S-Ox | 111 | Yes | No | COTS | GHERMAN | KCHRIST2 | PD Operations and Quality | Industrial System IT | Test SLATE is Jacobs' comprehensive, easy-to-use test control and measurement process management application, ideal for testing virtually any product under a variety of environmental and product conditions. W | 3 |  | YES | 2 | BWUNNAVA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-03-31 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 3 | Decommission | Priya | 2025-03-03 |  |  | Decommission complete, Validation in progress | No | VM
20943 | Applink Remote Management and Reporting | In Production | ARMR | EVDD | MJAMWAL | VVINOD3 | RDAS9 | TANBUCHE | Platinum | Non S-Ox | 122 | No | Yes | In-House | MJAMWAL | VVINOD3 | Advanced PD and Tech | - | Provide means of communication between Applink-enabled mobile applications and SYNC IT ecosystem (Ford backend systems) |  |  | YES | 2 | MJONE308 | PLM | Java Struts | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Java < v21
20943 | Applink Remote Management and Reporting | In Production | ARMR | EVDD | MJAMWAL | VVINOD3 | RDAS9 | TANBUCHE | Platinum | Non S-Ox | 122 | No | Yes | In-House | MJAMWAL | VVINOD3 | Advanced PD and Tech | - | Provide means of communication between Applink-enabled mobile applications and SYNC IT ecosystem (Ford backend systems) |  |  | YES | 2 | MJONE308 | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | SQL
50713 | Intune | In Production | Intune | EPEO | SRUNSON | ASTONE31 | MEDWA173 | AWROBEL2 | Gold | Non S-Ox | 111 | No | Yes | Managed by 3rd Party Purchased Service | SRUNSON | ASTONE31 | Enterprise Technology | EPEO | Microsoft Intune is an application used to manage mobile devices as well as deploy mobile apps to managed and unmanaged devices. Intune is part of Microsoft Azure, which is a public cloud-computing platform, developed, maintained, hosted, and managed by Microsoft Corporation. | 6 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2025 | EDC New Hypervisor | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
16411 | Application Management System | In Production | AppMgmtSys | FORD CREDIT | JBRADB21 | JBRADB21 | DSINACOL | DSINACOL | Bronze | Non S-Ox | 222 | No | Yes | In-House | SRAISIN1 | SRAISIN1 | Ford Credit Services | - | Global repository of Ford Credit applications. AMS is a J2EE application used by multiple processes. The System integrates EAA Architecture Review for both Ford and Ford Credit, EUC for Ford Credit, Application Profile for Ford Credit, TM for both Ford and Ford Credit, North American Change Control, North American Command Center support information, North American SDS information. (A.W) |  |  | YES | 2 | SRAISIN1 | PLM | Oracle | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | [15 empty] | Oracle
16411 | Application Management System | In Production | AppMgmtSys | FORD CREDIT | JBRADB21 | JBRADB21 | DSINACOL | DSINACOL | Bronze | Non S-Ox | 222 | No | Yes | In-House | JBRADB21 | JBRADB21 | Finance | - | Global repository of Ford Credit applications. AMS is a J2EE application used by multiple processes. The System integrates EAA Architecture Review for both Ford and Ford Credit, EUC for Ford Credit, Application Profile for Ford Credit, TM for both Ford and Ford Credit, North American Change Control, North American Command Center support information, North American SDS information. (A.W) |  |  | YES | 2 | SRAISIN1 | PLM | WAS | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | Java < v21
24154 | Application Database Management and Services | Active | ADM&S | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | ROBRIEN3 | Copper | Non S-Ox | - | No | - | - | DTAURO | JJACK348 | Ford Credit Services | - | FORD Credit Service Team that will execute Adhoc SQL (SPUFIs), perform Data Propagation requests and provide DBMS services for the Ford Credit Applications |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
1668 | App 1668 Not in EAMS | Not In EAMS |  | OTHERS | OTHERS | [5 empty] | - | No | Yes | - | OTHERS | OTHERS | Not in EAMS | - |  |  | Springboot | YES | 1 | OTHERS | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Java < v21
136 | App 136 Not in EAMS | Not In EAMS |  | OTHERS | OTHERS | OTHERS | OTHERS |  |  |  | - | No | Yes | - | OTHERS | OTHERS | Not in EAMS | - |  |  | Springboot | YES | 1 | OTHERS | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Java < v21
22523 | APMEA Statutory Interface & Registration Database | In Production | APMEA SIRD | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | The APMEA Statutory Interface and Registration Database (APMEA SIRD) supports the registration of vehicles with local governments and external interfaces in the AP and MEA regions |  |  | YES | 3 | NKANDULA | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete | Blue | 2024-12-15 | 2024-12-15 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL |  |  |  |  | As per PCF exit, team migrated to Postgres | No | SQL
53129 | Intel EndPoint Management Assistant | Planned | EMA | EPEO | SRUNSON | ASTONE31 | JJAFANO | JJAFANO | Gold | Non S-Ox | - | Yes | No | - | SRUNSON | ASTONE31 | Enterprise Technology | - | Application and server needed to manage remote control of Ford owned PC's and Laptops | 9 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2025 | EDC New Hypervisor | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
22523 | APMEA Statutory Interface & Registration Database | In Production | APMEA SIRD | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 211 | No | Yes | - | NSIVASA1 | JSARAVA5 | Marketing & Sales | Marketing, Sales and Service | The APMEA Statutory Interface and Registration Database (APMEA SIRD) supports the registration of vehicles with local governments and external interfaces in the AP and MEA regions |  | WAS | YES | 3 | NKANDULA | PLM | WAS | Q4 2027 | Rewrite | Modernize | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [14 empty] | No | Java < v21
50480 | API Platform | In Production | API | EPEO | SJOHN172 | SJOHN172 | KMURRA13 | ECHURCHM | Silver | Non S-Ox | 211 | No | Yes | - | RRISS | RRISS | Enterprise Technology | - | API Platform Tooling describes the suite of products that support API lifecycle management. The API Catalog enables discovery and documentation, the API Publisher deploys APIs to enterprise gateways and the Access Management product automates API consumption by providing app id's and provisioning access to registered APIs. API Platform Tooling products support teams across the Ford enterprise. |  |  | YES | 1 | SWALIMBE | PLM | SQL | Q4 2024 | Modernize to Cloud Databases | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [15 empty] | SQL
50480 | API Platform | In Production | API | EPEO | SJOHN172 | SJOHN172 | KMURRA13 | ECHURCHM | Silver | Non S-Ox | 211 | No | Yes | - |  |  | Enterprise Technology | - | API Platform Tooling describes the suite of products that support API lifecycle management. The API Catalog enables discovery and documentation, the API Publisher deploys APIs to enterprise gateways and the Access Management product automates API consumption by providing app id's and provisioning access to registered APIs. API Platform Tooling products support teams across the Ford enterprise. |  | Springboot | YES | 2 | SWALIMBE | PLM | Java < v21 | Q4 2026 | Version Upgrade | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [15 empty] | Java < v21
18130 | API FOCUS Production Systems | In Production | APIPROD | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Batch system for finance reporting and journals to PeopleSoft. THe API FOCUS Productions sytems are jobs that run in CA7 for Business Expense, Cost Accounting, and other finance systems. | 130 |  | YES | 2 | TSWEEN16 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
18130 | API FOCUS Production Systems | In Production | APIPROD | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Batch system for finance reporting and journals to PeopleSoft. THe API FOCUS Productions sytems are jobs that run in CA7 for Business Expense, Cost Accounting, and other finance systems. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q3 2025 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
18220 | API FOCUS Pre-Paid Rent System | In Production | APIRENT | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | - | Creates prepaid rental feed to CCAPS and related reports from FOCUS database |  |  | YES | 1 | TSWEEN16 | PLM | Mainframe | Q1 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
18129 | API FOCUS Menu (APIMENU) Reporting System | In Production | APIMENU | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Creates finance reports based on data pulled from the FPC (Finance Productivity Center) and CCAPS. The APIMENU is an easy to use interface that uses FOCUS to build reports so that the customer doesn't need to know how to program in FOCUS. | 2 |  | YES | 2 | TSWEEN16 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | DA
18129 | API FOCUS Menu (APIMENU) Reporting System | In Production | APIMENU | I-ERP | SFRANCI8 | RJAYAKU2 | SSRINI47 | LWU14 | Gold | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | RJAYAKU2 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Creates finance reports based on data pulled from the FPC (Finance Productivity Center) and CCAPS. The APIMENU is an easy to use interface that uses FOCUS to build reports so that the customer doesn't need to know how to program in FOCUS. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q3 2025 | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Mainframe
18131 | API FOCUS Cost Accounting | In Production | APICOST | I-ERP | SFRANCI8 | AKANSKI | CDERUITE | LWU14 | Gold | S-Ox In Scope | 221 | No | Yes | In-House | SFRANCI8 | AKANSKI | Finance | Integrated Enterprise Resource Planning (I-ERP) | Provides reporting and creates journal entries for PeopleSoft for CPARS Non-Produciton inventory. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q1 2025 | Rewrite apps to GCP | Modernize |  |  |  | In-Progress |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
18131 | API FOCUS Cost Accounting | In Production | APICOST | I-ERP | SFRANCI8 | AKANSKI | CDERUITE | LWU14 | Gold | S-Ox In Scope | 221 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Provides reporting and creates journal entries for PeopleSoft for CPARS Non-Produciton inventory. |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
14875 | APFEAD | In Production | APFEAD | ISIT | JKOONS | MNOVAK1 | BTHOMA47 | GRAO3 | Bronze | Non S-Ox | 111 | No | Yes | COTS | JKOONS | JKOONS | PD Operations and Quality | Industrial System IT | This software is used for the FEAD / READ engine sub-system design APFEAD is an internal tool developed by subsystem's engineering C dept in VEE APFEAD Creates and analyzes accessory drive subsystems for: System geometry belt length. Slip threshold. Hub loads. Model and forced vibrations. Belt span vibrations. Transient events. Belt and bearing life. |  |  | YES | 1 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
14080 | APDM - Analytical Powertrain Data Manager | In Production | APDM | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | JKOONS | TBROWN99 | PD Operations and Quality | 311 | APDM is a data management system that stores non-geometric Powertrain and PD engineering data. |  | Springboot | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
14080 | APDM - Analytical Powertrain Data Manager | In Production | APDM | ISIT | JKOONS | TBROWN99 | RMOHAME4 | JLUCAS1 | Silver | Non S-Ox | 311 | No | Yes | In-House | JKOONS | JKOONS | PD Operations and Quality | Industrial System IT | APDM is a data management system that stores non-geometric Powertrain and PD engineering data. |  |  | YES | 3 | BWUNNAVA | Modernize Components (Backlog-2024) | Oracle | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started | Green | 2026-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
21473 | INTEGRATED TICKETING SUBMISSION SYSTEMB1708 | Active | ITSS | EPEO | LFULCHER | KMAHAJAN | MBRYAN66 | MPEKARSK | Copper | Non S-Ox | - | No | Yes | - |  |  |  | Not in EAMS |  | 3 |  | YES | 1 | SWALIMBE | PLM | VM | Q1 2025 | EDC New Hypervisor | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
56030 | I-ERP Purchasing Reporting | In Production | IERPPURRP | I-ERP | SARAUJO3 | CBISWADI | JBAJI | SNAG1 | Bronze | Non S-Ox | 221 | No | Yes | In-House |  |  | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Its a data warehouse for global Purchasing data in IERP state. It is the repository for all historical data, facilitating analytical queries and reporting needs. The system is to consolidate functionality and data of many disparate strategic solutions into one place. Goals, 1. Provide analytical capabilities and reporting across all Purchasing functions 2. Support interfaces where appropriate to reduce transactional load on source systems 3. Interconnect with other enterprise-wide analytical layers 4. Provide security and controls in line with ITPM and GIS 5. Provide framework to allow for expansion in line with the ability of the source systems 6. Promote reusable nature for extracting, manipulating, loading information to analytical and reporting environment 7. Use the Purchasing Logical Object Model. | 6 |  | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green |  |  | Planned |  | No | [8 empty] | GCP Migration |  |  |  |  | Initially, PDO thought VMs mentioned in this sheet are Hadoop machines. But realized these are IICS VMs. And need to migrate. Hence timing changed from Q1 2025 to TBD | No | VM
18215 | IDS Feedback | In Production | IDSFDBCK | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | JGOODPAS | LWANG319 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Ford Customer Service | FCSD Tech | Feedback server - capture/storage and reporting on diagnostic field data collected from in-dealership IDS units. | 1 |  | YES | 5 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Only one VM is pending , Being followed up. PDO has acknowledged | No | VM
54648 | IBM License Management Tool | In Production | ILMT | EPEO | RHAMMO57 | JGIES | PSTRICK3 | GSIENKIE | Copper | Non S-Ox | 211 | No | Yes | COTS | RHAMMO57 | JGIES | Enterprise Technology | - | This tool allows the counting of IBM licenses utilized in our compute environment | 13 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2025 | EDC New Hypervisor | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
18604 | APA SAP CRM | In Production | CRM SAP | M&S TECH | NKANDULA | SSAURAV1 | PTHAMILA | RFERMAN1 | Gold | Non S-Ox | 312 | No | Yes | COTS | SBAILE17 | TBRYANS1 | Ford Customer Service | Marketing, Sales and Service | SAP based CRM solution used by Asia Pacific and Africa. CRM Next supports the business by providing a single view of the customers and a suite of analytics and reporting tools. With these tools, the business is able to increase sales volume and loyalty through precision marketing in order to utilize the budget to increase profits. SAP CRM replaced the legacy CKS CRM system used by Australia, New Zealand, India, China, South Africa and ASEAN markets. SAP CRM is hosted in Dearborn. Also supports Fleet (AU), VISTA retail reporting, leads distribution to Dealers and Predictive service marketing for IN, AU & NZ | 1223 |  | YES | 3 | NKANDULA | PLM | Datastage | Q3 2026 |  | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
18604 | APA SAP CRM | In Production | CRM SAP | M&S TECH | NKANDULA | SSAURAV1 | PTHAMILA | RFERMAN1 | Gold | Non S-Ox | 312 | No | Yes | COTS | SBAILE17 | TBRYANS1 | Ford Customer Service | Marketing, Sales and Service | SAP based CRM solution used by Asia Pacific and Africa. CRM Next supports the business by providing a single view of the customers and a suite of analytics and reporting tools. With these tools, the business is able to increase sales volume and loyalty through precision marketing in order to utilize the budget to increase profits. SAP CRM replaced the legacy CKS CRM system used by Australia, New Zealand, India, China, South Africa and ASEAN markets. SAP CRM is hosted in Dearborn. Also supports Fleet (AU), VISTA retail reporting, leads distribution to Dealers and Predictive service marketing for IN, AU & NZ |  |  | YES | 3 | NKANDULA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [14 empty] | No | SQL
13492 | Global Hardware Database | In Production | GHD | EPEO | SRUNSON | ASTONE31 | JJAFANO | SBARFKNE | Copper | Non S-Ox | 111 | No | Yes | In-House | SRUNSON | ASTONE31 | Enterprise Technology | EPEO | Global PC desktop and mobile computing hardware platforms web site. | 4 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [8 empty] | GCP Migration | [6 empty] | VM
18604 | APA SAP CRM | In Production | CRM SAP | M&S TECH | NKANDULA | SSAURAV1 | PTHAMILA | RFERMAN1 | Gold | Non S-Ox | 312 | No | Yes | COTS |  |  | Ford Customer Service | Marketing, Sales and Service | SAP based CRM solution used by Asia Pacific and Africa. CRM Next supports the business by providing a single view of the customers and a suite of analytics and reporting tools. With these tools, the business is able to increase sales volume and loyalty through precision marketing in order to utilize the budget to increase profits. SAP CRM replaced the legacy CKS CRM system used by Australia, New Zealand, India, China, South Africa and ASEAN markets. SAP CRM is hosted in Dearborn. Also supports Fleet (AU), VISTA retail reporting, leads distribution to Dealers and Predictive service marketing for IN, AU & NZ |  | Springboot | YES | 4 | NKANDULA | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
19319 | APA AU/NZL PANDA2 Data Warehouse | In Production | PANDA2_DW | ISIT | SBONNICI | KTONG1 | JAGATI | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SBONNICI | KTONG1 | Ford Customer Service | - | The PANDA Data Warehouse is a SQL server database which provides reporting and ad hoc analytical capabilities to Ford Customer Service Division (Australia/New Zealand)personnel. The PANDA Data Warehouse provides business information to the FCSD warehouses Supply Finance and Marketing and Sales groups. The data warehouse is populated from data extracts sourced from the PANDA appliation. Overnight batch jobs create extract files which are subsequently used to populate the SQL tables via DTS packages and stored procedures which run overnight on the SQL server. Users access data via a Business Objects front end. | 78 |  | YES | 3 | BWUNNAVA | PLM | BO | Q1 2026 | Migrate to SAP4/Hana | Modernize | 2026-03-31 | 2026-03-31 |  | In-Progress | Green | 2026-06-30 |  | Planned |  | No | [13 empty] | The SAP for PS&L launch in Australia has moved from November 2025 to February 2026. There will be no SAP launch for Australia in 2025. Allowed for launch + 1 quarter for decommission activities based on previous timing | No | DA
19319 | APA AU/NZL PANDA2 Data Warehouse | In Production | PANDA2_DW | ISIT | SBONNICI | KTONG1 | JAGATI | MMEHTA5 | Bronze | Non S-Ox | 211 | No | Yes | COTS | SBONNICI | KTONG1 | Ford Customer Service | - | The PANDA Data Warehouse is a SQL server database which provides reporting and ad hoc analytical capabilities to Ford Customer Service Division (Australia/New Zealand)personnel. The PANDA Data Warehouse provides business information to the FCSD warehouses Supply Finance and Marketing and Sales groups. The data warehouse is populated from data extracts sourced from the PANDA appliation. Overnight batch jobs create extract files which are subsequently used to populate the SQL tables via DTS packages and stored procedures which run overnight on the SQL server. Users access data via a Business Objects front end. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
51716 | GDIA Discovery Zone - NAS & SQL Storage | In Production | GDIANASSQL | GDIA | AFRADKIN | PKHARE2 | JROSS119 | GARUNAC1 | Bronze | Non S-Ox | 312 | No | Yes | In-House | EBLOCH | PKHARE2 | Enterprise Technology | - | This represents the Inputs and Outputs (Files and Data Tables) as well as the development artifacts (Workflows and Dashboards) that GDIA teams and Democratized users use for the Alteryx (23288) workflows and Qlik dashboards they create. | 3 |  | YES | 2 | FRANBELL | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-09-15 | 2025-09-15 | 2025-02-20 | Complete | Blue | 2025-03-31 |  | Planned |  | No | [14 empty] | No | VM
12926 | APA AU Total Vehicle Database (TVDB) | In Production | TVDB | ISIT | SBONNICI | KTONG1 | JAGATI | PSATISH2 | Copper | Non S-Ox | 211 | Yes | No | In-House | SBONNICI | KTONG1 | Marketing & Sales | - | SQL database containing retail history and vehicle orders for Ford Australia, used to drive reporting within M&S and Finance functional areas. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
14996 | FSAO BR SA-Timekeeping | In Production | TKP | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 321 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | - | WEB system with the feature of planning process and accounting worked days and hours to generate the base data for month-end payroll calculation. | 6 |  | YES | 3 | TSWEEN16 | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is already decommissioned | No | VM
20181 | APA AU Dealer Service Bureau 2 (DSB2) | In Production | DSB2 | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KPINNU | KHILLERT | Ford Customer Service | Marketing, Sales and Service | Dealer Service Bureau consolidates financial data from applications such as RMS, PSAR, etcssxaxd |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | Java Struts | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [13 empty] | This is going to decommission completely in 2026 and funtionality will get merged in DCDS Hub | No | Java < v21
20181 | APA AU Dealer Service Bureau 2 (DSB2) | In Production | DSB2 | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KPINNU | KHILLERT | Ford Customer Service | Marketing, Sales and Service | Dealer Service Bureau consolidates financial data from applications such as RMS, PSAR, etcssxaxd |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Cloud SQL SQLServer |  |  |  |  | This is going to decommission completely in 2026 and funtionality will get merged in DCDS Hub | No | SQL
50275 | FordEcat-US | In Production | fordecatus | FORD PRO & FCSD TECH | DNANDAN | DWIERZBI | ASASIDHA | MMEHTA5 | Silver | Non S-Ox | 212 | No | Yes | COTS | NBAECKER | DWIERZBI | Ford Customer Service | FCSD Tech | Ford service part catalog developed jointly with OEConnection. Hosted and maintained by Ford IT with vendor support. Ford Europe runs a different version of this product on separate infrastructure, covered by 12659 | 4 |  | YES | 2 | RKENNEL | PLM | VM | Q1 2025 | EDC CaaS | Modernize | 2025-03-15 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | 100% | 75% | 75% | 75% |  | 0% | 75% |  | EDC CaaS |  |  |  |  | Possible delay due to Policy Change in Openshift, UK Supplier team OEC Team is working on it. | No | VM
20181 | APA AU Dealer Service Bureau 2 (DSB2) | In Production | DSB2 | M&S TECH | KPINNU | KHILLERT | VRAMAMU3 | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KPINNU | KHILLERT | Ford Customer Service | Marketing, Sales and Service | Dealer Service Bureau consolidates financial data from applications such as RMS, PSAR, etcssxaxd |  |  | YES | 4 | NKANDULA | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [13 empty] | This is going to decommission completely in 2026 and funtionality will get merged in DCDS Hub | No | Java < v21
21714 | AP Weights & Measures | In Production | AP W&M | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Copper | Non S-Ox | 121 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Tactical solution to manage vehicle weights and measures. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | Q4 2025 | Modernize to Cloud Databases | Modernize | 2024-12-06 | 2024-12-06 | 2024-12-06 | Complete | Blue | 2024-12-20 | 2024-12-23 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL PostgreSQL | Priya | 2025-03-10 |  |  | App tier & DB moved to GCP in 2024. This was a complete rewrite to GCP with DB migrated to GCP PostgreSQL | No | SQL
18020 | Ford Facil - Customer Relationship Management | In Production | CRR | OCETO | DBRIGHEN | AMACHAD3 | SSOUSA6 | NMORALE7 | Silver | Non S-Ox | 211 | No | Yes | In-House | DBRIGHEN | AMACHAD3 | Marketing & Sales | - | Internet system to support dealer sales process with an enhanced customer experience - integration with Ford customer database - lead management | 4 |  | YES | 4 | TSWEEN16 | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-02-28 | Complete | Blue | 2025-06-13 | 2025-02-28 | Complete |  | No | [8 empty] | Decommission |  |  |  |  | EAMS status is already decommissioned | No | VM
21714 | AP Weights & Measures | In Production | AP W&M | ISIT | VVIJAY55 | RADAM10 | SYARLAGA | SSENTH15 | Copper | Non S-Ox | 121 | No | Yes | In-House | SROYCHOU | BGANESH | Manufacturing Staffs | Industrial System IT | Tactical solution to manage vehicle weights and measures. |  |  | YES | 3 | BWUNNAVA | PLM | WAS | TBD | Rewrite | Modernize | 2024-12-06 | 2024-12-06 | 2024-12-06 | Complete | Blue | 2024-12-20 | 2024-12-23 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | Priya | 2025-03-10 |  |  | App tier & DB moved to GCP in 2024. This was a complete rewrite to GCP with DB migrated to GCP PostgreSQL | No | Java < v21
23318 | AP B2C Services Layer | In Production | APB2CSL | M&S TECH | VMUTHUPA | DSHANKA1 | RPURUSH3 | MPREETH6 | Silver | Non S-Ox | 212 | No | Yes | In-House | VMUTHUPA | DSHANKA1 | Marketing & Sales | 212 | AP B2C Service layer application provides list of webservices and data that enables functionality for Ford and Lincoln customer facing Digital channels. Ford including Brand websites in AP, Mex, MEA, and South America. Lincoln including Brand websites in China, South Korea, Middle East, Puerto Rico and Mexico. |  | Springboot | YES | 3 | NKANDULA | PLM | Java < v21 | Q2 2025 | Rewrite | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-09-13 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
23318 | AP B2C Services Layer | In Production | APB2CSL | M&S TECH | VMUTHUPA | DSHANKA1 | RPURUSH3 | MPREETH6 | Silver | Non S-Ox | 212 | No | Yes | In-House | VMUTHUPA | DSHANKA1 | Marketing & Sales | Marketing, Sales and Service | AP B2C Service layer application provides list of webservices and data that enables functionality for Ford and Lincoln customer facing Digital channels. Ford including Brand websites in AP, Mex, MEA, and South America. Lincoln including Brand websites in China, South Korea, Middle East, Puerto Rico and Mexico. |  |  | YES | 3 | NKANDULA | PLM | SQL | Q3 2025 | Modernize to Cloud Databases | Modernize | 2025-09-15 | 2025-09-15 |  | Not Started |  | 2025-12-14 |  | Planned |  | No | [14 empty] | No | SQL
12619 | Ford Direct Stock Exchange | In Production | FDSE | FORD PRO & FCSD TECH | TJUNIPER | RHOWEL46 | RRAKESH4 | JCOY3 | Silver | Non S-Ox | 211 | No | Yes | In-House | TJUNIPER | RHOWEL46 | Marketing & Sales | - | A B2B application (Company to Dealer), enabling Dealers to purchase premium used vehicles direct from Ford. | 3 |  | YES | 3 | RKENNEL | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP CaaS |  |  |  |  | 3 VMs are pending related NAS Server,only NAS servers pending due to Gechub dependencies. This will be removed by April 2025. Moved from M&S tech. Following up. | No | VM
20643 | AP Capitalised Vehicle System Version 2 | In Production | CAVES2 | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | System to manage the vehicle processing of Ford company capitalised vehicles. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | Java Struts | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
20643 | AP Capitalised Vehicle System Version 2 | In Production | CAVES2 | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | System to manage the vehicle processing of Ford company capitalised vehicles. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | SQL | Q2 2025 | Modernize to Cloud Databases | Modernize | 2025-06-15 | 2025-06-15 | 2025-01-25 | Complete | Blue | 2025-09-13 |  | Planned |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud SQL SQLServer |  |  |  |  | GCP Migration is completed for Database. DB VMs decommissioning in Progress | No | SQL
50222 | FoM Reporting Application for Dealers | In Production | FOMRAD | M&S TECH | RKLEINSM | BMUNIE | EGARRO | JHARPER2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | RKLEINSM | BMUNIE | Marketing & Sales | - | This is a smart, real time, mobile and device agnostic reporting platform for all Ford of Mexico Marketing, Sales and Service KPIs, that provides information to many business customers (Ford and Dealers) about performance metrics | 4 |  | YES | 3 | NKANDULA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-31 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
20643 | AP Capitalised Vehicle System Version 2 | In Production | CAVES2 | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DDESAI | PTOCCO | Finance | Staffs IT | System to manage the vehicle processing of Ford company capitalised vehicles. |  |  | YES | 4 | TSWEEN16 | Modernize Components (Backlog-2024) | WAS | Q1 2026 | Rewrite | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
21575 | FoA-Line Balancing ADP Interface | In Production | LBAI | OCETO | TSWEEN16 | PTOCCO | KVIJAYA7 | MBALAN2 | Silver | Non S-Ox | 211 | No | Yes | In-House | DDESAI | PTOCCO | Human Resources | Staffs IT | Line Balancing to ADP Interface application. This replaces existing Midnight Technologies interface to PeopleSoft Payroll. | 4 |  | YES | 4 | TSWEEN16 | PLM | VM | Q1 2025 | Complete Migration to SaaS | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-04 | Complete | Blue | 2025-06-13 |  | Planned | REQ0146552 & REQ0146556 | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | SaaS |  |  |  |  | VMs will be decommissioned | No | VM
16136 | Andina Dealer Website Portal | In Production | CONFORD | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Silver | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Marketing & Sales | - | Conford: CONcesionarios FORD. Andina Dealer Website Portal. Scope: Venezuela, Colombia, Ecuador Main system functionalities: - Submit FCSD part orders - Register retail vehicle sales - Warranty claims management - Payments control (FCSD Parts/Vehicles) - Inquiry financial statements - Issuance of Warranty certificate |  |  | YES | 2 | TSWEEN16 | PLM | Oracle | Q4 2026 | Modernize to Cloud Databases | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Oracle
50758 | FCE Residual Value Setting Tool | In Production | RVST | FORD CREDIT | JBENITO | CMUELLEN | PKRAHMER | AGALLAG9 | Bronze | Non S-Ox | 311 | No | Yes | In-House | JBENITO | CMUELLEN | Ford Credit Services | Ford Credit (FMCC) | This setting tool is used to aid facilitate the business setting Residual Values against defined vehicle configurations mileage bands and Optional Final Payments. | 3 |  | YES | 3 | SRAISIN1 | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
11044 | Anaqua | In Production | Anaqua | OCETO | TSWEEN16 | KADOMKAI | SAKASAPU | MBALAN2 | Silver | Non S-Ox | 331 | No | Yes | COTS | DDESAI | KADOMKAI | Policy | Staffs IT | The Anaqua application manages Ford's Intellectual Property (IP). Launched on commercial version 6.2 in December 2009. ANAQUA 8.5.5 upgrade went live in 4/2017 |  |  | YES | 2 | TSWEEN16 | PLM | SQL | Q1 2026 | On-Prem | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | SQL
12345 | eUsed (FDO2 and gebrauchtwagen)(Eur) | In Production | eUsed | FORD PRO & FCSD TECH | TJUNIPER | RHOWEL46 | RRAKESH4 | JCOY3 | Silver | Non S-Ox | 211 | No | Yes | In-House | TJUNIPER | RHOWEL46 | Marketing & Sales | - | eUsed is a B2C (Company to consumer) application provides the web-users with functionality to locate (search engine) the used vehicles owned by Ford and Ford Dealers. Vehicle data are obtained from different sources for each market. UK dealers also have the option to add any other Ford vehicle they wish to advertise, using the eUsed dealer admin site | 4 |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-31 | 2025-01-31 | Complete | Blue | 2025-06-29 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | Cloud Run | [5 empty] | No | VM
23928 | Analytics X Planning | In Development | AXP | EPEO | SKULKA52 | MWILLI20 | SBATHISH | SBATHISH | Copper | Non S-Ox | 111 | No | Yes | In-House | CMIRABIT | MWILLI20 | Enterprise Technology | EPEO | Application to track IT data and generate utilization reports |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | SQL
22508 | Environmental Handling Charge | In Production | EHC | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | S-Ox Out of Scope | 111 | No | Yes | In-House | DNANDAN | DWIERZBI | Finance | Marketing, Sales and Service | A web interface to govern the Mainframe System which is used to capture any sold parts that are applicable under environmental handling charges laws as dictated by the Provincial Government and to apply provincial charges to that part for being sold. | 12 |  | YES | 1 | NKANDULA | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-11 | Complete | Blue | 2025-06-13 | 2025-03-11 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | DB is mssing so add one more line Item. Both the VM and DB is completed as per PDO. | No | VM
13864 | AMA - Authorization | In Production | APS -AuthZ | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Gold | S-Ox In Scope | 233 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | 233 | AMA aka APS Authorization provides various run time authorization services and standard process for defining, administering access control policies. Powered by industry leading Authorization engine - PDP by Axiomatics. It is cloud native service and full supports Attribute Based Access Control (ABAC). Supports XACML Policy editor, Policy Auditing and Reporting tools, policy publishing lifecycle |  | Springboot | YES | 5 | SWALIMBE | PLM | Java < v21 | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Java < v21
13864 | AMA - Authorization | In Production | APS -AuthZ | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Gold | S-Ox In Scope | 233 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | AMA aka APS Authorization provides various run time authorization services and standard process for defining, administering access control policies. Powered by industry leading Authorization engine - PDP by Axiomatics. It is cloud native service and full supports Attribute Based Access Control (ABAC). Supports XACML Policy editor, Policy Auditing and Reporting tools, policy publishing lifecycle | 13 |  | YES | 5 | SWALIMBE | PLM | WebFocus | Q3 2025 | Migrate to Power BI | Modernize | 2025-09-15 | 2025-09-15 |  | In-Progress | Green | 2025-12-14 |  | Planned |  | No | [15 empty] | DA
13864 | AMA - Authorization | In Production | APS -AuthZ | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Gold | S-Ox In Scope | 233 | No | Yes | In-House | NOKEEFE | MSNYDER5 | EPEO | EPEO | AMA aka APS Authorization provides various run time authorization services and standard process for defining, administering access control policies. Powered by industry leading Authorization engine - PDP by Axiomatics. It is cloud native service and full supports Attribute Based Access Control (ABAC). Supports XACML Policy editor, Policy Auditing and Reporting tools, policy publishing lifecycle |  |  | YES | 5 | SWALIMBE | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | DA
13864 | AMA - Authorization | In Production | APS -AuthZ | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Gold | S-Ox In Scope | 233 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | AMA aka APS Authorization provides various run time authorization services and standard process for defining, administering access control policies. Powered by industry leading Authorization engine - PDP by Axiomatics. It is cloud native service and full supports Attribute Based Access Control (ABAC). Supports XACML Policy editor, Policy Auditing and Reporting tools, policy publishing lifecycle |  |  | YES | 5 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | SQL
13771 | EAA Services | In Production | EAA | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | WJUSTICE | Gold | S-Ox In Scope | 232 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | Repository / Server for EAA Services | 10 |  | YES | 2 | SWALIMBE | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
50897 | AMA - Access Governance and Administration | In Production | APS - AGA | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | AMA(aka APS) provides a standard solution for managing user access policies within an application, in addition to a work flow tool to manage user-id maintenance |  |  | YES | 4 | SWALIMBE | PLM | Java Struts | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Java < v21
50897 | AMA - Access Governance and Administration | In Production | APS - AGA | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | AMA(aka APS) provides a standard solution for managing user access policies within an application, in addition to a work flow tool to manage user-id maintenance |  |  | YES | 4 | SWALIMBE | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | SQL
52969 | DTA Service | In Production | DTA | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 222 | No | Yes | In-House | RKENNEL | JCHAUSSE | General Management | FCSD Tech | Service accessed via PTS for Downtime Alert functionality | 4 |  | YES | 2 | RKENNEL | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
50897 | AMA - Access Governance and Administration | In Production | APS - AGA | EPEO | NOKEEFE | MSNYDER5 | RSILVIYA | GSIENKIE | Gold | Non S-Ox | 223 | No | Yes | In-House | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | AMA(aka APS) provides a standard solution for managing user access policies within an application, in addition to a work flow tool to manage user-id maintenance |  |  | YES | 4 | SWALIMBE | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Java < v21
52862 | DSR SERVICE | In Production | DSR | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 212 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Delear Service Record accessed via PTS / Motorcraft to enable technicians to view, record and maintain service history | 4 |  | YES | 3 | RKENNEL | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
11346 | Allocation Optimization | In Production | ALLOPT | M&S TECH | FHIRSH | JEISIMIN | CSIVAKU3 | CKEMPSKI | Silver | Non S-Ox | 222 | No | Yes | In-House | FHIRSH | JEISIMIN | Marketing & Sales | Marketing, Sales and Service | Allocation Optimization takes the monthly Sales planning total vehicle and commodity allocations (for Markets, Reserve Accounts, Regions, and Dealers) and breaks those allocations into buildable weeks within the scheduling month based upon reasonable customer preference patterns. That weekly data is then electronically sent to the OSR, RTOM, COS and SRO systems so those processes use the same allocation data. |  |  | YES | 2 | NKANDULA | PLM | ESB |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | DA
11558 | DPES: Dealer Program Enrollment System | In Production | DPES | M&S TECH | NKANDULA | JLEWIS10 | KMICHALE | JHARPER2 | Bronze | S-Ox Out of Scope | 221 | No | Yes | In-House | FHIRSH | JLEWIS10 | Marketing & Sales | Marketing, Sales and Service | Dealer marketing program enrollments involve dealers mailing/faxing paper-based forms to program vendors. This takes much time for Ford/vendors/dealers to track enrollment status and reporting. DPES aims to provide a common approach to dealer enrollments. | 11 |  | YES | 2 | NKANDULA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-12 | 2025-03-12 | 2025-03-12 | Complete | Blue | 2025-03-12 | 2025-03-12 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | PDO Comment: DB data was just retained, and server decom tickets submitted and approved 9th February 2025. Expecting final decom by end of February 2025 at the latest. | No | VM
12334 | AIM on the WEB- | In Production | AIMWEB | ISIT | JKOONS | TBROWN99 | JBROSKI | ISIDDIQ6 | Silver | Non S-Ox | 312 | No | Yes | In-House | JKOONS | JKOONS | New Model Programs | Industrial System IT | The Automated Issues Management system is designed to provide structured management of issues, with proper enforcement of key business rules. The initial version of AIM on the Web was created to manage Vehicle Launch Team issues, which was the primary issue type managed by the Client/Server version of AIM. The primary business owner for the VLT module of AIM is A&ME/VO Global Quality New Model Programs. In 2011, AIM became the primary issues management tool for Powertrain launch programs. Integrated into AIM on the Web is the Drive Evaluation Management System (DEMS). This module is used to track Voice of the Customer fleet vehicles, drives, service actions and other data and to ensure proper capture and resolution of all engineering concerns for the drive fleets. The Durability Information System (DURIS) is used for Proving Ground test scheduling, program status, vehicle incident and concern reporting, driver assignment and test status. DURIS was added into AIMWEB in early 2013. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
16441 | Diagnostic Services File Manager Application | In Production | DSFM App | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | SSUBHANK | RANKAM1 | Silver | Non S-Ox | 122 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Diagnostics, Service and Part information integrated into a hardware-independent single-point solution. DSFM/DWI supports the WebFlash product which is critical to meeting EPA legislation Objectives- Strategic - High | 4 |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | Modernization is completed and VM decom is planned for next quarter. | No | VM
13618 | AGU Info | In Production | EuHR-AGU | OCETO | TSWEEN16 | KKOEHLER | WALBERS | MBALAN2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KKOEHLER | Human Resources | Staffs IT | Supports the distribution of worker instruction sheets (WIS, german: Betriebsanweisung) and allows all Ford employees with email account to view via a Web Interface all WIS. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | Q2 2025 | Will be Decommissioned | Decommission |  |  |  | In-Progress |  |  |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | No | Mainframe
13618 | AGU Info | In Production | EuHR-AGU | OCETO | TSWEEN16 | KKOEHLER | WALBERS | MBALAN2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | DDESAI | KKOEHLER | Human Resources | Staffs IT | Supports the distribution of worker instruction sheets (WIS, german: Betriebsanweisung) and allows all Ford employees with email account to view via a Web Interface all WIS. |  |  | YES | 2 | TSWEEN16 | PLM | WAS | Q2 2025 | Will be Decommissioned | Decommission | 2025-06-15 | 2025-06-15 |  | In-Progress | Green | 2025-06-15 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | Java < v21
11227 | AFRL - Registration & Licensing (UK) | In Production | AFRL | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 312 | No | Yes | - | FHIRSH | FHIRSH | Marketing & Sales | Marketing, Sales and Service | The Automated First Registration and Licensing System (AFRL) is used by Ford UK dealers to tax and register new vehicles online with direct real-time communication to UK government agency (DVLA). |  |  | YES | 4 | NKANDULA | PLM | Oracle | Q3 2026 | Will be Decommissioned | Decommission | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-09-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
11227 | AFRL - Registration & Licensing (UK) | In Production | AFRL | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 312 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | The Automated First Registration and Licensing System (AFRL) is used by Ford UK dealers to tax and register new vehicles online with direct real-time communication to UK government agency (DVLA). |  |  | YES | 4 | NKANDULA | PLM | Mainframe | Q2 2027 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
11227 | AFRL - Registration & Licensing (UK) | In Production | AFRL | M&S TECH | FHIRSH | NSIVASA1 | JSARAVA5 | PSATISH2 | Gold | Non S-Ox | 312 | No | Yes | - | FHIRSH | NSIVASA1 | Marketing & Sales | Marketing, Sales and Service | The Automated First Registration and Licensing System (AFRL) is used by Ford UK dealers to tax and register new vehicles online with direct real-time communication to UK government agency (DVLA). |  |  | YES | 4 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
52687 | Data Activation Portal | In Production | DG - DAP | GDIA | CPELTZE1 | NSEGUIN3 | NSHAMSI1 | RPOLLO13 | Bronze | Non S-Ox | 221 | No | Yes | In-House | LDANGELO | MGARRET2 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Allow automation of access approval and provisioning | 4 |  | YES | 3 | FRANBELL | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2024-12-20 | 2025-01-31 | Complete | Blue | 2025-01-31 | 2025-01-31 | Complete |  | No | [14 empty] | No | VM
51957 | AEP-MQTT | In Production | AEPMQTT | ISIT | SKING68 | CSHORTZ | BBURKLAN | AELANGO | Silver | Non S-Ox | 111 | No | Yes | COTS | #N/A | #N/A | Manufacturing Engineering | 111 | MQTT MESSAGING FOR THE AEP PLATFORM |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | 0 | Modernize |  |  |  | Not Started | Green | 1900-03-30 |  | Planned |  | No | [14 empty] | No | Java < v21
23328 | Customer Loyalty and Retention | In Production | CusLoylRet | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House | KBERCH | GDIAZ1 | Customer Experience | Marketing, Sales and Service | The Customer Loyalty and Retention application supports Ford of Canada Dealers in enhancing customer satisfaction and loyalty by assisting dealership personnel in selecting the right Loaner program for a specific repair, helping customers with partial payment of cost of repair once their warranty has expired, and providing their customers with alternate transportation (loaner or shuttle vehicles), while their vehicles are being serviced. | 4 |  | YES | 4 | NKANDULA | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-03-04 | Complete | Blue | 2025-06-13 | 2025-03-04 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
52517 | Contest and Incentives Systems | In Production | CIS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | TBABU | SDHANAS2 | Bronze | Non S-Ox | 211 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | - | Effective implementation of ESB Vehicle Management programs by having system capabilities 1) To define the Program Targets 2) Measure the dealer performance 3) Insights to dealers on performance & standing 4) Payment to dealer and their staff | 3 |  | YES | 2 | RKENNEL | Modernize Components (Backlog-2024) | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
50219 | Aegis | In Production | AEGIS | OCETO | PMILLIGA | MWESTRA | SBAUGHER | WJUSTICE | Bronze | Non S-Ox | 221 | No | Yes | In-House | TGEIGER | MWESTRA | Enterprise Technology | 221 | Aegis (formerly known as EVMS) is a broker service to receive vehicle module binaries from various Ford systems and request a security scanning from a third party on-prem application. |  | Springboot | YES | 2 | PMILLIGA | PLM | Java < v21 | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Java < v21
50219 | Aegis | In Production | AEGIS | OCETO | PMILLIGA | MWESTRA | SBAUGHER | WJUSTICE | Bronze | Non S-Ox | 221 | No | Yes | In-House | TGEIGER | MWESTRA | Enterprise Technology | - | Aegis (formerly known as EVMS) is a broker service to receive vehicle module binaries from various Ford systems and request a security scanning from a third party on-prem application. |  |  | YES | 2 | PMILLIGA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | SQL
52968 | Checksheets Service | In Production | Checksheet | FORD PRO & FCSD TECH | RKENNEL | JCHAUSSE | BRAMAMU3 | RANKAM1 | Gold | Non S-Ox | 111 | No | Yes | In-House | RKENNEL | JCHAUSSE | Ford Customer Service | FCSD Tech | Service accessed via PTS to enable users including dealer technicians to access vehicle servicing checksheets | 2 |  | YES | 3 | RKENNEL | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-15 | 2025-01-31 | Complete | Blue | 2025-06-13 | 2025-01-31 | Complete |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | [5 empty] | No | VM
51474 | Capacity Analysis Report | In Production | eCAR | I-ERP | SARAUJO3 | CBISWADI | HTAKAWAL | SNAG1 | Silver | Non S-Ox | 221 | No | Yes | In-House | SARAUJO3 | CBISWADI | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | eCAR enables the suppliers to demonstrate their ability to satisfy Ford volume requirements (Average Production Weekly and Maximum Production Weekly) and report them as part of the Global Product Development System (GPDS). Ford utilizes Overall Equipment Effectiveness (OEE) to assess the risk associated with the suppliers plan to demonstrate capacity requirements, as it incorporates three key manufacturing performance elements (Equipment Availability, Performance Efficiency, and Quality Rate). | 4 |  | YES | 2 | TSWEEN16 | PLM | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-02-15 | 2025-02-15 | Complete | Blue | 2025-04-01 |  | Planned |  | No | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration | Praveen | 2025-03-05 |  |  | Migration completed. Decom in progress. | No
22663 | Administrative Forecast Expenses | In Production | AFx | I-ERP | SFRANCI8 | AKANSKI | NTAMILMA | LWU14 | Silver | Non S-Ox | 211 | No | Yes | In-House | SFRANCI8 | SFRANCI8 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Administrative forecast expenses(Afx) provides data for every country, business unit, operation location, and department that is launched on PeopleSoft General Ledger System and non-Peoplesoft countries. Afx reports on both Actuals and Budgets.Actuals refers to the expenses and headcount data that are sent from the BPR and BOPS.Afx uses Essbase to interface with Excel for the collection and rollup of monthly Administrative, Selling & Marketing,Depot and Engineering actual expenses;Budget and Forecast are input using templates.AFx provides access to underlying transaction level detail thru Oracle tables. EXPLANATION Provides Ford management and financial analysts with headcount, actuals, budget and forecast data which can be viewed at various geographical, account and functional management levels in local currency as well as at budget and bookkeeping exchange rates. FUNCTION Financial reporting of actuals,budget and forecast expense for all Regions, Business units, Operation locations and Departments. BE |  |  | YES | 1 | TSWEEN16 | PLM | Oracle | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-01-15 | 2025-01-15 | Complete | Blue | 2025-01-30 | 2025-01-30 | Complete |  | No | [8 empty] | Decommission | Praveen | 2025-03-05 |  |  |  | No | Oracle
6249 | Administration of Marketing and Sales | In Production | EuAS-AIMS | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Administration of Stock Financing, Stock Protection, Price Protection, Dealer Bonus, Retroactive Invoicing and Employee Sales. Management of incentive payments. Vehicle information system. |  | WAS | YES | 2 | TSWEEN16 | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [13 empty] | JAVA (Lift and Shift -CaaS completed Jan 2024) WAS upgrade remains TBD in the future | No | Java < v21
6249 | Administration of Marketing and Sales | In Production | EuAS-AIMS | I-ERP | SFRANCI8 | SDHANAL3 | PDIVAKAR | LWU14 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Administration of Stock Financing, Stock Protection, Price Protection, Dealer Bonus, Retroactive Invoicing and Employee Sales. Management of incentive payments. Vehicle information system. |  |  | YES | 2 | TSWEEN16 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
23125 | Blueprint (formerly Storyteller) | In Production | Blueprint | EA | RRISS | SHE1 | SLOSEY | SGURU8 | Bronze | Non S-Ox | 321 | No | Yes | COTS | RRISS | SHE1 | Enterprise Technology | Technology & Enterprise Services (TES) | Blueprint is a requirements management solution to replace Requisite Pro | 7 |  | YES | 2 | GBRAIL | PLM | VM | Q1 2025 | Complete Migration to SaaS | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
15663 | Adaptive Control Systems | In Production | ACS | FORD CREDIT | IPANKAJ | RRAJESH8 | MRAMASW2 | JMANI | Bronze | Non S-Ox | 311 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | - | Implements collections strategies and probability of default models. EU ACS business owner: Steve Earle |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
12283 | B2C Site Search Service | In Production | B2CSearch | M&S TECH | RKLEINSM | KPONNUSW | TARNOLDI | MPINRED1 | Silver | Non S-Ox | 121 | No | Yes | Managed by 3rd Party Purchased Service | RKLEINSM | KPONNUSW | Enterprise Technology | Marketing, Sales and Service | B2C Search provides content search for customer facing web sites. It is used by Accessories, Fleet Web, Ford.com, Ford Corporate, Ford Credit US, Lincoln, Lincoln Credit, NG Ford/Lincoln Dealer Product Info Platform, Ford and Lincoln of Canada, Retail Ford and Lincoln, Accessories FoC, Fleet Canada and QuickLane. The application internally uses the Endeca product. | 4 |  | YES | 1 | NKANDULA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-15 | 2025-03-03 | Complete | Blue | 2025-06-13 | 2025-03-03 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission |  |  |  |  | EAMS status - decommissioned | No | VM
52709 | Activity Tracker | In Production | AT | FORD CREDIT | JMALETZ | RRAJESH8 | RSUDHIR | JMANI | Bronze | Non S-Ox | 111 | No | Yes | In-House | #N/A | #N/A | Ford Credit Services | 111 | TRACKS AND REPORTS ALL INCOMING AND OUTGOING TRANSACTIONS IN XNET AND ICE |  | Springboot | YES | 1 | SRAISIN1 | PLM | Java < v21 | Q3 2027 | Version Upgrade | Modernize | 2027-09-15 | 2027-09-15 |  | Not Started |  | 2027-12-14 |  | Planned |  | No | [15 empty] | Java < v21
20865 | Active Directory Federation Services | In Production | ADFS | EPEO | NOKEEFE | MSNYDER5 | ZZHAN106 | GSIENKIE | Gold | Non S-Ox | 211 | No | Yes | COTS | NOKEEFE | MSNYDER5 | Enterprise Technology | EPEO | The Active Directory Federation Service ADFS provides a Ford Motor Company centralized Multiple Domain Single-Sign-On solution for web based applications. ADFS uses the Security Assertion Markup Language SAML and the WS-Federation framework to securely and directly communicate information about application users between Ford Motor Company and trusted partners. ADFS acts as either an identity provider or a service provider depending on the needs of the partner application. The Identity Provider role is used to gather required user attributes - generate a Federated Response-Assertion Document, sign the document, encrypt the document, and redirect the browser with the Federated Response-Assertion Document to the federated partners server acting in the Service Provider Role. The Service Provider is used to decrypt the Federated Response-Assertion Document provided by the federated partners server acting in the Identity Provider Role, verify the signature of the Document, and pass the validated user |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | SQL
51893 | AV TaaS Analytics | Planned | AVTSAnlytc | FORD PRO & FCSD TECH | AAMBADIP | AAMBADIP | RTWUMASI | RANKAM1 | - | Non S-Ox | - | No | Yes | - | WKNAPP11 | AAMBADIP | Integrated Services | - | AV TaaS Analytics Product Line for Data and Analytics products and services | 1 |  | YES | 1 | RKENNEL | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-15 | 2025-03-31 |  | In-Progress | Green | 2025-06-29 |  | Planned |  | No | [8 empty] | Decommission |  |  |  |  | Only one VM is pending to decom, Following up with PDO | No | VM
20059 | Autosys | Active | Autosys | EPEO | LFULCHER | LFULCHER | BMORAN20 | BMORAN20 | Gold | Non S-Ox | - | No | Yes | - | CMIRABIT | LFULCHER | Enterprise Technology | ITO | Enterprise scheduling system for UNIX, Linux and Windows servers. Accounting Systems Renewal uses a local implementation of Autosys. | 19 |  | YES | 3 | SWALIMBE | PLM | VM | Q1 2025 | EDC New Hypervisor | Modernize | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | VM
18560 | Active Directory Certificate Services (ADCS) | In Production | CA | EPEO | NOKEEFE | VNACHIMU | BSARAV20 | GSIENKIE | Silver | Non S-Ox | 232 | No | Yes | COTS | NOKEEFE | VNACHIMU | Enterprise Technology | EPEO | Active Directory Certificate Services is the Windows OS-based software which issues digital certificates for use within the Ford computing environment. |  |  | YES | 2 | SWALIMBE | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | SQL
21081 | AUTOMATED RETIREMENT KIT | In Production | ARK | M&S TECH | RAHMED33 | GDIAZ1 | CDEMERIN | JGONZ486 | Silver | Non S-Ox | 211 | No | Yes | In-House |  |  | Human Resources | Marketing, Sales and Service | Web based application used by Ford of Canada employees to request retirement estimates and retirement application. | 12 |  | YES | 1 | NKANDULA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-03-25 | 2025-03-25 |  | In-Progress | Green | 2025-06-23 |  | Planned |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | Decommission | [5 empty] | No | VM
54358 | Theorem CAE CAD Compare Tool | In Production | CAECADCOMP | ISIT | SBONNICI | KRAMMOHA | RHARIKR2 | GRAO3 | Bronze | Non S-Ox | 122 | No | Yes | - | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | The Theorem CAE CAD Compare tool comprises of a web application where users can upload 3D data from various release milestones and allows the user to visually compare the data to note what has changed. There is a backend server that executes the comparison and output files, along with a database that stores the data. | 3 |  | YES | 1 | BWUNNAVA | PLM | VM | Q4 2024 | Complete Migration to GCP (Both App & DB) | Modernize | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [8 empty] | GCP Migration | [5 empty] | No | VM
24856 | Aurora Foundational Data | In Production | AFD | I-ERP | SARAUJO3 | VANURAD2 | PCHITIYA | SNAG1 | Silver | Non S-Ox | 211 | No | Yes | In-House | SARAUJO3 | VANURAD2 | Supply Chain | Integrated Enterprise Resource Planning (I-ERP) | Purchasing Foundational Data to support Aurora- A Global cloud-based tool (Ariba/SAP) that manages requisitioning, sourcing, purchasing, and receiving of non-production materials. | 4 |  | YES | 2 | TSWEEN16 | Modernize Components (Backlog-2024) | VM | Q1 2025 | Complete Migration to GCP (Both App & DB) | Modernize | 2025-03-15 | 2025-03-31 | 2025-01-10 | Complete | Blue | 2025-04-15 | 2025-01-10 | Complete |  | No |  | 100% | 100% | 100% | 100% | 100% | 100% |  | GCP Migration |  |  |  |  | Decommissioned VM and App is now in GCP fully | No | VM
21751 | Acronis Advanced Workstation | In Production | Acronis | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | SKING68 | Manufacturing Engineering | - | Acronis Advanced Workstation is the global standard Industrial PC Imaging and Backup software used throughout Manufacturing. |  |  | YES | 3 | BWUNNAVA | PLM | Oracle | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Oracle
21751 | Acronis Advanced Workstation | In Production | Acronis | ISIT | SKING68 | KRAMESH | VGARIMEL | SKANIMO2 | Copper | Non S-Ox | 111 | No | Yes | COTS | SKING68 | KRAMESH | Manufacturing Engineering | - | Acronis Advanced Workstation is the global standard Industrial PC Imaging and Backup software used throughout Manufacturing. |  |  | YES | 3 | BWUNNAVA | PLM | SQL | TBD | On-Prem | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
12482 | ACS: Automated Certification System | In Production | ACSPD | ISIT | DKAVITHA | UVIJAYAL | KDINESH4 | TTOBOLSK | Copper | Non S-Ox | 211 | No | Yes | In-House | DKAVITHA | UVIJAYAL | Policy | Industrial System IT | ACS allows users to process and maintain the necessary data to produce emission certification data for the EPA and the California Air Resources Board (CARB) and submit electronic transactions to both agencies. | 5 |  | YES | 2 | BWUNNAVA | PLM | VM | Q1 2025 | Will be Decommissioned | Decommission | 2025-01-21 | 2025-01-21 | 2025-01-21 | Complete | Blue | 2025-01-21 | 2025-01-21 | Complete |  | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 5 | Decommission | Priya | 2025-03-03 |  |  | App fully Decommissioned | No | VM
51067 | Transformation Enterprise Manager | In Production | TEM | GDIA | CPELTZE1 | MRAFFLE | WHAIDRI | RPOLLO13 | Gold | Non S-Ox | 11 | No | Yes | In-House | MLYONS23 | MJUHASZ | Enterprise Technology | - | Sql generator for Transformation and scheduler to run jobs in Hadoop Environment | 4 |  | NO | 3 | FRANBELL | PLM | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
16012 | Accounts Receivable | In Production | CXC | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Account Receivable Perfit system Scope: Venezuela, Colombia Main system functionalities: - Generates vehicle and parts e-collections client statements - Maintains a repository of all local automated and manual journals that are transmitted daily to PS GL. - Generates several VAT Tax Books of Sales for tax reporting purposes. - Generates dealer statement for Regional Publicity Fund from installments deducted from vehicle invoices. - Interfaces with vehicle/parts billing systems to automatically journalize sales - Calculates and journalizes different types of interest charges such as interests on vehicle financing and on overdue parts balances. - Receive and journalize interface file of installment payments - Backoffice for Planford Consortium Website Portal |  | WAS | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q4 2025 | Will be Decommissioned | Decommission | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Java < v21
16012 | Accounts Receivable | In Production | CXC | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | Integrated Enterprise Resource Planning (I-ERP) | Account Receivable Perfit system Scope: Venezuela, Colombia Main system functionalities: - Generates vehicle and parts e-collections client statements - Maintains a repository of all local automated and manual journals that are transmitted daily to PS GL. - Generates several VAT Tax Books of Sales for tax reporting purposes. - Generates dealer statement for Regional Publicity Fund from installments deducted from vehicle invoices. - Interfaces with vehicle/parts billing systems to automatically journalize sales - Calculates and journalizes different types of interest charges such as interests on vehicle financing and on overdue parts balances. - Receive and journalize interface file of installment payments - Backoffice for Planford Consortium Website Portal |  |  | YES | 3 | TSWEEN16 | Modernize Components (Backlog-2024) | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
23697 | SCA-C Consumer Account Profile | In Production | SCA-C CAP | GDIA | EBLOCH | KKB | PSIRISIN | SDUTTA9 | Gold | Non S-Ox | 322 | No | Yes | COTS | EBLOCH | KKB | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Provides access to Consumer Account Profile data on demand to consumers regardless of their geographic location and stores the data within the SCA-Customer environment.Note: Please see the Tech07 and CBID documents for the most current list of regions and interfaces. | 3 |  | NO | 3 | FRANBELL | PLM | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
16011 | Accounts Payable | In Production | CXP | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | RCORDEI1 | Finance | Integrated Enterprise Resource Planning (I-ERP) | Account Payable Perfit system Scope: Venezuela, Colombia Main system functionalities: - Payment disbursement for CCAPS (production material and Non-production payments). - Payment processing for spare parts billed by the P&A Parts and Accessories System. - Issues checks on preprinted check formats. - Generates tax adjustments and other tax reporting including VAT tax Book of Purchases. - Generates a withholding tax declaration file in Seniat format for electronic uploading. - Generates miscellaneous payments for items not handled by corporate systems. |  | WAS | YES | 3 | TSWEEN16 | PLM | Java < v21 | Q4 2026 | Will be Decommissioned | Decommission | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
16011 | Accounts Payable | In Production | CXP | OCETO | DBRIGHEN | RCORDEI1 | VMATHAVA | NMORALE7 | Bronze | Non S-Ox | 221 | No | Yes | In-House | DBRIGHEN | DBRIGHEN | Finance | Integrated Enterprise Resource Planning (I-ERP) | Account Payable Perfit system Scope: Venezuela, Colombia Main system functionalities: - Payment disbursement for CCAPS (production material and Non-production payments). - Payment processing for spare parts billed by the P&A Parts and Accessories System. - Issues checks on preprinted check formats. - Generates tax adjustments and other tax reporting including VAT tax Book of Purchases. - Generates a withholding tax declaration file in Seniat format for electronic uploading. - Generates miscellaneous payments for items not handled by corporate systems. |  |  | YES | 3 | TSWEEN16 | PLM | Oracle | Q4 2027 | Will be Decommissioned | Decommission | 2027-12-15 | 2027-12-15 |  | Not Started |  | 2027-12-15 |  | Planned |  | No | [8 empty] | Decommission | [5 empty] | No | Oracle
19420 | Oracle IMS Gateway | Active | OIG | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Copper | Non S-Ox | - | No | Yes | - | AFRADKIN | JLIDDLE1 | Enterprise Technology | Marketing, Sales and Service | The Oracle IMS Gateway is an infrastructure application developed by the ITI Ford Middleware Development Team that allows access to Fords IMS Mainframe systems from an Oracle DB environment. This infrastructure application provides the ability for any authorized Ford Oracle application to access IMS transactions. | 0 |  | NO | 2 | TSWEEN16 | PLM | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
15334 | Accounting - NAFO Account Recon | In Production | NAFORECON | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | Non S-Ox | 111 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | This application provides a mechanized means of reconciling five GL accounts: Receipts Clearing, Disbursement Clearing, Retail New Business Clearing, RCL New Business Clearing, and Cash Clearing. The reconciliation process takes place daily. There are five source systems from which data will be extracted. These are DCASH, CCW, UVIS, WSS and FMS. It uses WebFOCUS as the report generator. | 97 |  | YES | 3 | SRAISIN1 | PLM | WebFocus | Q2 2025 | Migrate to QlikSense | Modernize | 2025-06-30 | 2025-06-30 |  | In-Progress | Green | 2025-09-28 |  | Planned |  | No | [15 empty] | DA
15334 | Accounting - NAFO Account Recon | In Production | NAFORECON | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | Non S-Ox | 111 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | This application provides a mechanized means of reconciling five GL accounts: Receipts Clearing, Disbursement Clearing, Retail New Business Clearing, RCL New Business Clearing, and Cash Clearing. The reconciliation process takes place daily. There are five source systems from which data will be extracted. These are DCASH, CCW, UVIS, WSS and FMS. It uses WebFOCUS as the report generator. | 97 |  | YES | 3 | SRAISIN1 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [15 empty] | DA
15334 | Accounting - NAFO Account Recon | In Production | NAFORECON | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | Non S-Ox | 111 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | This application provides a mechanized means of reconciling five GL accounts: Receipts Clearing, Disbursement Clearing, Retail New Business Clearing, RCL New Business Clearing, and Cash Clearing. The reconciliation process takes place daily. There are five source systems from which data will be extracted. These are DCASH, CCW, UVIS, WSS and FMS. It uses WebFOCUS as the report generator. |  |  | YES | 3 | SRAISIN1 | PLM | Mainframe | TBD | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
15301 | Accounting - Misc 1099 | In Production | MISC1099 | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | Non S-Ox | 332 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | This application edits and accumulates the Misc 1099 information from all the disbursements issued by Ford Credit operations and any applicable transactions from the DEFT application. This information is then sent at yearend to E&Y for 1099 preparation. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
15879 | Accounting - Like Kind Exchange-CLIPS | In Production | CLIPS | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | Non S-Ox | 121 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | Tax reporting system. Mainframe data gathering, processing, formatting of transaction files to feed external vendor application that generates tax reports. Processing is done at PwC. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
15299 | Accounting - GL Summarization | In Production | GL-Summ | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | This application summarizes the general ledger transactions from a variety of Ford Credit sources and produces summarized journal entry transaction files for Peoplesoft GL. This application also verifies that the batches are valid for the month and in balance. | 1 |  | YES | 2 | SRAISIN1 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [15 empty] | DA
15299 | Accounting - GL Summarization | In Production | GL-Summ | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | This application summarizes the general ledger transactions from a variety of Ford Credit sources and produces summarized journal entry transaction files for Peoplesoft GL. This application also verifies that the batches are valid for the month and in balance. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
15327 | Accounting - Dealer EFT | In Production | DEFT | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | ROBRIEN3 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | KDELTA | MVENKA15 | Ford Credit Services | Ford Credit (FMCC) | US & Canada - Electronically moves funds between Dealers bank accounts and Ford/Ford Credit bank accounts. | 7 |  | YES | 5 | SRAISIN1 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [15 empty] | DA
15327 | Accounting - Dealer EFT | In Production | DEFT | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | ROBRIEN3 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | KDELTA | MVENKA15 | Ford Credit Services | Ford Credit (FMCC) | US & Canada - Electronically moves funds between Dealers bank accounts and Ford/Ford Credit bank accounts. |  |  | YES | 5 | SRAISIN1 | PLM | Mainframe | Q4 2027 | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
15327 | Accounting - Dealer EFT | In Production | DEFT | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | ROBRIEN3 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | KDELTA | MVENKA15 | Ford Credit Services | Ford Credit (FMCC) | US & Canada - Electronically moves funds between Dealers bank accounts and Ford/Ford Credit bank accounts. |  |  | YES | 5 | SRAISIN1 | PLM | SQL | Q4 2024 | Will be Decommissioned | Decommission | 2024-12-15 | 2024-12-15 |  | In-Progress | Green | 2024-12-15 |  | Planned |  | No | [15 empty] | SQL
53011 | NA Light Duty Near Term Compliance Command Center | In Production | NTC | GDIA | AFRADKIN | JLIDDLE1 | JBELZYT1 | GCARLSO2 | Bronze | Non S-Ox | 311 | No | Yes | In-House | AFRADKIN | JLIDDLE1 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | A DB + Dashboard application that helps EPLM Sustainability Planning team to display Near Term Compliance data for emission and environmental regulations. | 0 |  | NO | 2 | FRANBELL | PLM | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
15327 | Accounting - Dealer EFT | In Production | DEFT | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | ROBRIEN3 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | KDELTA | MVENKA15 | Ford Credit Services | Ford Credit (FMCC) | US & Canada - Electronically moves funds between Dealers bank accounts and Ford/Ford Credit bank accounts. |  |  | YES | 5 | SRAISIN1 | PLM | WAS | TBD | Rewrite | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Java < v21
15326 | Accounting - Customer EFT | In Production | CEFT | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | ROBRIEN3 | Silver | Non S-Ox | 333 | No | Yes | In-House | KDELTA | MVENKA15 | Ford Credit Services | Ford Credit (FMCC) | Electronically transmits retail and Red Carpet Lease (RCL) U.S. and Canada customer payment requests to the banks for processing automatic withdrawals from customers checking/savings accounts. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
15326 | Accounting - Customer EFT | In Production | CEFT | FORD CREDIT | SSINGH14 | MVENKA15 | TLEWIS84 | ROBRIEN3 | Silver | Non S-Ox | 333 | No | Yes | In-House |  |  | Ford Credit Services | Ford Credit (FMCC) | Electronically transmits retail and Red Carpet Lease (RCL) U.S. and Canada customer payment requests to the banks for processing automatic withdrawals from customers checking/savings accounts. |  | Springboot | YES | 2 | SRAISIN1 | PLM | Java < v21 | Q4 2025 | Version Upgrade | Modernize | 2025-12-15 | 2025-12-15 |  | Not Started |  | 2026-03-15 |  | Planned |  | No | [15 empty] | Java < v21
15680 | Accounting - Company Car & COMLIT | In Production | FCCC | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | This asset-based application (based on tag number, VIN, and garage location) provides billing and tax reporting functions for the vehicles leased back to Ford Motor. It is a reporting system for Accounting. | 3 |  | YES | 2 | SRAISIN1 | PLM | Focus - MF | 2027-2028 |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [15 empty] | DA
15680 | Accounting - Company Car & COMLIT | In Production | FCCC | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | S-Ox In Scope | 232 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Finance | Ford Credit (FMCC) | This asset-based application (based on tag number, VIN, and garage location) provides billing and tax reporting functions for the vehicles leased back to Ford Motor. It is a reporting system for Accounting. |  |  | YES | 2 | SRAISIN1 | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
15298 | Accounting - Centralized Check Writing | In Production | CCW | FORD CREDIT | IPANKAJ | RRAJESH8 | SAGILAN2 | RPARAME4 | Silver | S-Ox In Scope | 332 | No | Yes | In-House | IPANKAJ | RRAJESH8 | Ford Credit Services | Ford Credit (FMCC) | This application processes check requests from the Ford Credit branches and other applications and creates an interface file that is sent to the check printing vendor. This application also creates the GL allocation and 1099 interface files along with all the necessary reporting. |  |  | YES | 1 | SRAISIN1 | PLM | Mainframe | TBD | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
19582 | Accountable Document Control System (FOE) | In Production | ADCS | OCETO | TVASU | KBALAS13 | DNATARA1 | WJUSTICE | Copper | Non S-Ox | 111 | No | Yes | COTS | TVASU | NSENTHI1 | Finance | Technology & Enterprise Services (TES) | System monitors and tracks usage and accounting of Accountable Documents as demanded by Finance Manual (build on Dcoumentum EDMS Application & Infrastructure ITMS#19103) |  |  | YES | 1 | TSWEEN16 | PLM | WAS | Q3 2026 | Rewrite | Modernize | 2026-09-15 | 2026-09-15 |  | Not Started |  | 2026-12-14 |  | Planned |  | No | [14 empty] | No | Java < v21
53400 | Account Receivable Workflow | In Production | ARWORKFLOW | I-ERP | SFRANCI8 | SDHANAL3 | PSATHIS3 | LWU14 | Bronze | S-Ox In Scope | 231 | No | Yes | In-House | SFRANCI8 | SDHANAL3 | Finance | - | AR workflow is a third-party application which enables automation of Collection & Cash application processes.AI enabled payment predictor provides early warning alerts on potential delays - helps prioritize 'customer base' requiring attn/ follow-up.Process is automated ilo current process i.e. moving from dependent on human judgement to data based follow-up prioritization.AI based remittance capture from Checks, Emails, EDIs and Websites & Invoice Matching process which enable automatic cash application.Handling/ response to customer queries is automated across languages with in-built translation capabilities..AI payment predictor helps avoid customer follow-ups with a good payment track-record.Worklist Prioritization, repository of customer, follow Ups and ability to track customer queries and timely response by team members.Automated metrics/reports ex: customer ageing, daily sales outstanding, cash flow forecast etc |  |  | YES | 2 | TSWEEN16 | PLM | SQL | TBD | Modernize to Cloud Databases | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | SQL
56321 | Mfg Cost Optimization Suite | In Production | MAOS | GDIA | KLIDDLE | MNOEL2 | TMASLYK1 | GGREEN5 | Bronze | Non S-Ox | 211 | No | Yes | In-House | KLIDDLE | MNOEL2 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | This is a suite of Manufacturing Products that execute models used to optimize production and/or help Ford Manufacturing make optimization planning decisions. | 0 |  | NO | 2 | FRANBELL | PLM | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
22331 | ACCOUNT MANAGER - NORTH AMERICA | In Production | AM - NA | FORD CREDIT | NJOSHI21 | SFRAGAL1 | KUHL1 | ASAXENA8 | Silver | Non S-Ox | 322 | No | Yes | In-House | NJOSHI21 | ABARNA10 | Ford Credit Services | Ford Credit (FMCC) | Customer-facing web site that allows customers to view and update their Ford Credit and Lincoln-AFS accounts. Functionality includes viewing account details, scheduling payments, and exchanging documents electronically with Ford Credit. |  |  | YES | 4 | SRAISIN1 | PLM | Mainframe | TBD |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Mainframe
22331 | ACCOUNT MANAGER - NORTH AMERICA | In Production | AM - NA | FORD CREDIT | NJOSHI21 | SFRAGAL1 | KUHL1 | ASAXENA8 | Silver | Non S-Ox | 322 | No | Yes | In-House | NJOSHI21 | ABARNA10 | Ford Credit Services | Ford Credit (FMCC) | Customer-facing web site that allows customers to view and update their Ford Credit and Lincoln-AFS accounts. Functionality includes viewing account details, scheduling payments, and exchanging documents electronically with Ford Credit. |  |  | YES | 4 | SRAISIN1 | PLM | SQL | Q1 2025 | Modernize to Cloud Databases | Decommission | 2025-03-15 | 2025-03-15 |  | In-Progress | Green | 2025-06-13 |  | Planned |  | No | [15 empty] | SQL
52931 | GDIA Command Center Platform | In Production | GDIA CCPfm | GDIA | EBLOCH | PKHARE2 | HMCCORM7 | GARUNAC1 | Silver | Non S-Ox | 111 | No | Yes | In-House | EBLOCH | PKHARE2 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Platform to support the collection, transformation, and visualization of Data Quality, Data Relevancy, and Operational Metrics to support GDIA Command Center Operations and GDIA products | 0 |  | NO | 3 | FRANBELL | PLM | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
22331 | ACCOUNT MANAGER - NORTH AMERICA | In Production | AM - NA | FORD CREDIT | NJOSHI21 | SFRAGAL1 | KUHL1 | ASAXENA8 | Silver | Non S-Ox | 322 | No | Yes | In-House | NJOSHI21 | ABARNA10 | Ford Credit Services | Ford Credit (FMCC) | Customer-facing web site that allows customers to view and update their Ford Credit and Lincoln-AFS accounts. Functionality includes viewing account details, scheduling payments, and exchanging documents electronically with Ford Credit. |  |  | YES | 4 | SRAISIN1 | PLM | WAS | TBD | Version Upgrade | Decommission |  |  |  | Not Started |  |  |  | Planned |  | No | [15 empty] | Java < v21
9008 | Account Distribution | In Production | ACCDIST | FORD PRO & FCSD TECH | DNANDAN | VKOTESWA | KMUKESH | SDHANAS2 | Gold | S-Ox In Scope | 232 | No | Yes | In-House |  |  | Ford Customer Service | - | Creates various form of Account transactions to account for costs of warranty claims via A/R & G/L transactions to Peoplesoft, GAPS etc. |  |  | YES | 1 | RKENNEL | PLM | Mainframe | TBD | Rewrite apps to GCP | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
23402 | ABC Scale and Commodity Planning | In Production | ABC Scale | ISIT | MNOWICK1 | LSRINIVA | ASHAIK2 | LPATIL | Copper | Non S-Ox | 311 | No | Yes | In-House | MNOWICK1 | LSRINIVA | PD Operations and Quality | Industrial System IT | Complexity Management Tool that facilitates the creation of Modular Toolkits, ABC Complexity Charts and basic Chess Board Reports. Pre Program Engineering can create a Toolkit of Commodity Variants, A Variant being the Base followed by High and Low variants A1, B, B1 etc. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD | Will be Decommissioned | Decommission |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
23779 | GDIA - Informatica Tools | Active | INFA | GDIA | CPELTZE1 | MWILLI20 | MMAES | RPOLLO13 | Silver | Non S-Ox | - | No | Yes | - | MLYONS23 | MJUHASZ | Enterprise Technology | Global Data Insight and Analytics (GDIA) | This tool covers data management, and Self service solutions for GDIA. Includes the following components: Big Data Management (BDM), Enterprise Data Catalog (EDC). and Data Privacy Management (DPM). | 0 |  | NO | 2 | FRANBELL | PLM | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
14820 | 9270 Reporting | In Production | 9270RPTS | M&S TECH | FHIRSH | JEISIMIN | SJINGILI | CKEMPSKI | Silver | Non S-Ox | 111 | No | Yes | In-House | JEISIMIN | SJINGILI | Manufacturing Staffs | Marketing, Sales and Service | The 9270 Reports application is a downstream application of the 9270 mainframe application. It receives daily plant production data for the North American plants and reports the numbers. |  | WAS | YES | 1 | NKANDULA | PLM | WAS | Q4 2026 | Rewrite | Modernize | 2026-12-15 | 2026-12-15 |  | Not Started |  | 2027-03-15 |  | Planned |  | No | [14 empty] | No | Java < v21
9868 | 6-Sigma Project Tracking System (PTS) | In Production | 6-SigmaPTS | ISIT | JDEGUZMA | RMEHTA3 | RJAMBUNA | ISIDDIQ6 | Bronze | Non S-Ox | 111 | No | Yes | In-House | JDEGUZMA | JDEGUZMA | Quality | Industrial System IT | The 6-Sigma Project Tracking System (PTS) system manages projects and resources (skill tracking) to support 6-Sigma projects. It tracks Green Belts and Black Belts and their projects. |  |  | YES | 2 | BWUNNAVA | PLM | Oracle | Q2 2026 | Modernize to Cloud Databases | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | Oracle
94 | ESPS: Extended Service Plan System | In Production | ESPS | FORD PRO & FCSD TECH | DNANDAN | ABANSAL3 | KMUKESH | SDHANAS2 | Silver | S-Ox In Scope | 231 | No | Yes | In-House | ZKOUL | VKOTESWA | Ford Customer Service | FCSD Tech | Extended Service Plan System (ESPS) is an on-line computer system used to support the administration of the Ford Extended Service Plan (ESP). The ESP coverage offers protection against high repair costs after a vehicle is out of its manufacturer warranty period. Dealers sell the ESP product to retail customers. Most sales are from retail customers and often the contract is purchased at the same time they buy the vehicle. Fleets also purchase coverage for their company cars (e.g., Hertz). This application provides for the procesing and maintenance of a significant volume of high margin revenue sales for the Ford Customer Service Division. |  |  | NO | 6 | RKENNEL | Modernize Components (Backlog-2024) | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
56689 | 3DX_iPaaS | Planned | 3DX_IPASS | ISIT | SBONNICI | KRAMMOHA | RHARIKR2 | GRAO3 | Bronze | S-Ox Classification Pending | - | No | Yes | - | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | Used for Data Exchange between 3DX & other sytems like Teamcenter, FEDEBOM & PDO |  | Springboot | YES | 1 | BWUNNAVA | PLM | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
51711 | 3DExperience | In Production | 3DX | ISIT | ACAPONE1 | SGUILLON | SGUILLON | GRAO3 | Bronze | Non S-Ox | 311 | No | Yes | COTS | SBONNICI | KRAMMOHA | Advanced PD and Tech | Industrial System IT | Consists of all applications that are part of basic 3DX platform installation 3D Passport, 3DSwYm, 3DComment, 3DNotification, 3DInxex, 3DDashboard, 3DSpace (CAS, non-CAS), 3DSpaceIndex, File Collaboration Server and 3DOrchestrate |  |  | YES | 2 | BWUNNAVA | PLM | SQL | Q2 2026 | On-Prem | Modernize | 2026-06-15 | 2026-06-15 |  | Not Started | Green | 2026-09-13 |  | Planned |  | No | [14 empty] | No | SQL
23132 | Data Supply Chain | In Production | DSC | GDIA | MLYONS23 | ARAMAKR4 | NSANKAR4 | RPOLLO13 | Silver | Non S-Ox | 311 | No | Yes | In-House | DTERPST1 | ARAMAKR4 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | GDIA Data Supply Chain Analytical repository of all enterprise data. | 0 |  | NO | 3 | FRANBELL | PLM | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
50522 | 2018-372 AP AU BMIT JOYTECH CO., LTD. | In Production | Joytech | ISIT | MFOUNTA1 | AWILDEY1 | ACAJDIN | ACAJDIN | Copper | Non S-Ox | 211 | Yes | No | Managed by 3rd Party Purchased Service | MFOUNTA1 | AWILDEY1 | Advanced PD and Tech | - | The supplier Joytech (GSDB: HG9BA) is IMG VA Package seating Buck / Property build supplier. IMG PD VA team being use Joytech since 2015 for building various program package buck and future product. Ford require to send Confidential 3D CAD data and Joytech to store the data during the project engagement. We are using TCE and SharePoint for the data transmit. Supplier stores the data on a desktop. The desktop links to the milling machine. The supplier will delete all Ford confidential data (CAD / email / data / pictures / etc.) after the delivery and close of the PO. |  |  | YES | 2 | BWUNNAVA | PLM | SQL | TBD |  | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | SQL
50884 | Data Fulfillment Application | In Production | DFA | GDIA | AFRADKIN | PBOSCO3 | KNAWAZ | RPOLLO13 | Silver | Non S-Ox | 311 | No | Yes | COTS | AFRADKIN | PBOSCO3 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Fulfill revenue generating Data Products per business requirements at market speed by enabling an environment with necessary tools and access to internal/external data sources | 0 |  | NO | 3 | FRANBELL | PLM | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
14901 | 1099 Misc Tax System | In Production | 1099-MTS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | AJOGIYAT | Silver | Non S-Ox | 311 | No | Yes | In-House | KHEMANT | RANANDAL | Finance | - | The 1099 Misc. Tax entry system facilitates the collection of the information from the regions for the incentive payments made to the dealership employee and others under certain incentive programs. The collected information is consolidated and passed on to EY Bank to generate the IRS 1099 Misc. forms |  |  | YES | 2 | NKANDULA | PLM | Mainframe | TBD | Optimize MF - MIPs reduction | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe
14901 | 1099 Misc Tax System | In Production | 1099-MTS | M&S TECH | VMUTHUPA | RANANDAL | PP5 | AJOGIYAT | Silver | Non S-Ox | 311 | No | Yes | In-House | KHEMANT | RANANDAL | Finance | - | The 1099 Misc. Tax entry system facilitates the collection of the information from the regions for the incentive payments made to the dealership employee and others under certain incentive programs. The collected information is consolidated and passed on to EY Bank to generate the IRS 1099 Misc. forms |  |  | YES | 2 | NKANDULA | PLM | Mainframe - DB2 |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | Mainframe - DB2
24460 | Attribute Based Access Control | In Production | ABAC | GDIA | CPELTZE1 | ARAMAKR4 | KNAMDEV | RPOLLO13 | Copper | Non S-Ox | 111 | No | Yes | In-House | CPELTZE1 | SS348 | Enterprise Technology | Global Data Insight and Analytics (GDIA) | Application Policy Services (APS) application will continue to be used to manage access requests and approvals, and some roles will have additional information to drive policies in ABAC by user by requested attribute. New attributes represent Source (data table or data file), Country (data row), and PII-level (data column). This enables the user to have access to specific data. The ABAC application will generate the necessary Policies for those users for the role and selected attribute. | 0 |  | NO | 2 | FRANBELL | PLM | VM |  |  | Modernize |  |  |  | Not Started |  |  |  | Planned |  | No | [14 empty] | No | VM
19524 | @Ford Online | In Production | @Ford | OCETO | TSWEEN16 | KADOMKAI | GWHOLIHA | MBALAN2 | Gold | Non S-Ox | 112 | No | Yes | COTS |  |  | Communications | Staffs IT | Single communication website for salaried and hourly employees, retirees, and agency personnel. |  | Springboot | YES | 1 | TSWEEN16 | Modernize Components (Backlog-2024) | Java < v21 | Q1 2026 | Version Upgrade | Modernize | 2026-03-15 | 2026-03-15 |  | Not Started |  | 2026-06-13 |  | Planned |  | No | [14 empty] | No | Java < v21
51458 | Lommel Proving Ground Management System | In Production | LPGMS | ISIT | RTILLEY | GTACKOEN | FBOMANS | JLUCAS1 | Bronze | Non S-Ox | 111 | No | Yes | In-House | GVANNOYE | GTACKOEN | PD Operations and Quality | Industrial System IT | The PGMS controls operation and monitors safety on Proving Ground in Lommel. |  | Java | YES | 1 | BWUNNAVA | Modernize Components (Backlog-2024) | Java < v21 | TBD | Version Upgrade | Modernize |  |  |  | Not Started | Green |  |  | Planned |  | No | [14 empty] | No | Java < v21
Formulas:
Planned Infra. Decommission Date = [Planned Launch Date]+90
Planned Infra. Decommission Date = [Planned Launch Date]
Actual Infra. Decommission Date = [Actual Launch Date]+15
Actual Infra. Decommission Date = [Actual Launch Date]

## Data Validation
Data validation -
| Category | Phase 2 | Planned Launch Date | Actual Launch Date | Overall Status | R/Y/G Status | Planned Infra. Decommission Date | Actual Infra. Decommission Date | Infra. Decommission Status | S-Ox Milestone | Architecture Finalized | Onboarding Pre-Prod | Onboarding Prod | Code Changes Complete | UAT | Prod Launch Complete | Dev Sec Ops | Baseline Date | Pre-Prod Complete Date | Prod Launch Readiness Date | Planned VM for 2025 | Target Platform | Last Modified By | Last Modified | PLM program Lead | Comments | Critical App
[11 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Cloud SQL PostgreSQL
| Decommission | Yes | Date Format | Date Format | Complete | Blue |  |  | Complete | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Cloud SQL SQLServer |  |  | Mate Jayashree |  | Yes
| Modernize | No |  |  | In-Progress | Green |  |  | Planned | Yes | 0.25 | 25 | 25 | 25 | 25 | 25 | 25 |  |  |  |  | BigQuerry |  |  | Hojnacki, Daniel |  | No
[5 empty] | Not Started | Red |  |  |  | No | 0.5 | 50 | 50 | 50 | 50 | 50 | 50 |  |  |  |  | AlloyDB |  |  | Purav, Rajendra
[5 empty] | Planned | Yellow |  |  |  |  | 0.75 | 100 | 100 | 100 | 100 | 100 | 100 |  |  |  |  | MongoDB Atlas |  |  | Omara, Diane
[11 empty] | 1 | [10 empty] | Cloud Run |  |  | Sandhu, Jaspreet
[22 empty] | GCP CaaS |  |  | Wearmouth, Karen
EDC Hypervisor
EDC CaaS
Decommission
SaaS
Java 21
Java 17
Oracle SAAS
Firestore
GCP Migration
SQL
Microsoft SQL on Azure
QlikSense
| Rules/ Formulas - | [8 empty] | Modernization Strategy | Category |  |  | Unique Platforms | [7 empty] | Migrate FOCUS off of Mainframe
1 | have all columns with green header - Read ONLY | [8 empty] | Will be Decommissioned | Decom |  |  | BO | [7 empty] | Webfocus 9
2 | Actual Launch date needs to be later that Planned launched date | [8 empty] | Rewrite | Modernization |  |  | DataStage | [7 empty] | CP4D
3 | Infra. Decom date should be greater than actual lunched date | [8 empty] | Version Upgrade | Modernization |  |  | EBS | [7 empty] | Angular UI
4 | Not modifiable - Last Modified By , Last Modified | [8 empty] | Will be Decommissioned | Decom |  |  | Java < 17 | [7 empty] | Power BI
| Data Validation Rules - | [8 empty] | TBD |  |  |  | Java Struts | [7 empty] | QlikSense + Big Query
| If Category is Decommission, there should not be any data in the milestones columns | [8 empty] | Rewrite apps to GCP | Modernization |  |  | Mainframe | [7 empty] | New Platform altogether
| If Category is Decommissioned, Target Platform should be Decommission | [8 empty] | Optimize MF - MIPs reduction | Modernization |  |  | Mainframe - DB2 | [7 empty] | FOCUS Migration/Modernization Strategy - TBD
| If Category is Decommissioned, S-Ox Milestone should be No | [8 empty] | Migrate/Rewrite ONLY heavy batch/reporting jobs to GCP | Modernization |  |  | Oracle | [7 empty] | Already Migrated
[10 empty] | Move to Pega | Modernization |  |  | SQL
| If Overall Status is Not Planned, there should not be data in the milestone columns | [8 empty] | Move Capabilities to SaaS Solution | SaaS |  |  | VM
5 | If Overall Status is Not Started , there should not be data in the milestone columns | [8 empty] | On-Prem | On Prem |  |  | WAS
| If Launch Status is Complete, there needs date for Planned Launched and Actual Launched | [8 empty] | Modernize to Cloud Databases | Modernization |  |  | Web Focus
| If Launched status In Progress - there needs to have planned launched date, Infrastructure Decom - can not be complete | [8 empty] | Will be Decommissioned | Decom |  |  | WebFocus - MF
| Platform - Planned Launched and actual Launched date should be less than the Program Due date | [8 empty] | Move the VM 2019 until Hypervisor is available for SQL | On-Prem |  |  | VM Distributed
| If Actual launch date is blank, Planned launched date in past - error out | [8 empty] | Modernize to Cloud Databases | Modernization
| If Actual decom date is blank, Planned decom ate in past - error out | [8 empty] | Complete Migration to SaaS | SaaS
[10 empty] | Complete Migration to GCP (Both App & DB) | Modernization
[10 empty] | EDC CaaS | On-Prem
[10 empty] | Partial Migration to GCP | Modernization
[7 empty] | Platform | Program due date |  | EDC New Hypervisor | On-Prem
[7 empty] | BO | 2026-12-31 |  | EDC CaaS and New EDC Hypervisor | On-Prem
[7 empty] | DataStage | 2026-12-31 |  | NA
[7 empty] | EBS | 2027-06-30 |  | Complete Migration to SaaS | SaaS
[7 empty] | Java < v21 | 2027-12-31 |  | App Not found in EAMS
[7 empty] | Java Struts | 2027-12-31
[7 empty] | Mainframe | 2027-12-31
[7 empty] | Mainframe - DB2 | 2027-12-31
[7 empty] | Oracle | 2027-12-31
[7 empty] | SQL | 2027-12-31
[7 empty] | VM | 2027-06-30
[7 empty] | WAS | 2027-12-31
[7 empty] | WebFocus | 2025-12-31
[7 empty] | WebFocus - MF | 2025-12-31
VM Distributed
| Consider (Y/N) | All
| Distinct Count of App ID | Column Labels
|  |  | 2024 | 2025 | 2026 | 2027 | Grand Total
Row Labels
DA
| EPEO | 2 |  | 2 |  |  | 3
| EVDD | 1 |  | 1 |  |  | 1
| Ford Credit | 12 |  | 2 | 3 |  | 17
| Ford Pro & FCSD Tech | 22 | 4 | 9 |  |  | 34
| GDIA | 1 | 1 | 1 |  |  | 3
| I-ERP | 12 | 2 | 7 | 6 |  | 25
| ISIT | 27 | 1 | 6 | 3 |  | 37
| M&S Tech | 25 | 2 | 13 | 4 |  | 41
| OCETO | 4 | 1 | 7 | 1 |  | 13
| OTHERS | 3 |  |  |  |  | 3
| DA Total | 109 | 11 | 48 | 17 |  | 177
Java < v21
| EA | 6 |  | 2 |  |  | 8
| EPEO | 27 | 3 | 2 | 1 |  | 33
| EVDD | 71 |  |  |  |  | 71
| Ford Credit | 12 | 1 | 57 | 41 | 33 | 144
| Ford Pro & FCSD Tech | 20 | 2 | 29 | 27 | 2 | 80
| GDIA | 6 | 1 | 8 | 1 |  | 16
| I-ERP | 18 |  | 33 | 7 | 3 | 61
| ISIT | 89 | 30 | 34 | 29 | 3 | 185
| M&S Tech | 36 | 18 | 31 | 23 | 7 | 115
| OCETO | 21 |  | 50 | 37 | 6 | 114
| OTHERS | 2 |  |  |  |  | 2
| Java < v21 Total | 308 | 55 | 246 | 166 | 54 | 829
Mainframe
| EPEO | 1 |  | 1 |  |  | 2
| Ford Credit | 86 | 1 | 3 | 11 | 2 | 103
| Ford Pro & FCSD Tech | 15 |  | 14 | 11 | 21 | 61
| GDIA | 4 |  |  |  |  | 4
| I-ERP | 17 |  | 10 | 10 | 11 | 48
| ISIT | 34 |  | 2 | 5 | 10 | 51
| M&S Tech | 20 | 1 | 10 | 12 | 20 | 63
| OCETO | 11 |  | 3 |  | 1 | 15
| OTHERS | 2 |  |  |  |  | 2
| Mainframe Total | 190 | 2 | 43 | 49 | 65 | 349
Mainframe - DB2
| Ford Pro & FCSD Tech | 46 |  | 2 |  |  | 48
| I-ERP | 1 |  |  |  |  | 1
| M&S Tech | 46 |  |  |  |  | 46
| Mainframe - DB2 Total | 93 |  | 2 |  |  | 95
Oracle
| EPEO | 17 |  |  |  |  | 17
| EVDD | 4 |  |  |  |  | 4
| Ford Credit | 6 |  | 3 | 1 | 3 | 13
| Ford Pro & FCSD Tech |  | 1 | 11 | 11 | 1 | 24
| GDIA |  |  | 1 |  |  | 1
| I-ERP | 8 |  | 13 | 14 |  | 35
| ISIT | 58 | 2 | 19 | 10 | 5 | 94
| M&S Tech | 5 | 2 | 8 | 9 | 3 | 27
| OCETO | 4 | 4 | 20 | 26 | 17 | 71
| Oracle Total | 102 | 9 | 75 | 71 | 29 | 286
SQL
| EA |  |  | 5 | 1 |  | 6
| EPEO | 71 | 1 | 2 |  |  | 74
| EVDD | 26 |  |  |  |  | 26
| Ford Credit | 32 | 3 | 35 | 8 | 6 | 84
| Ford Pro & FCSD Tech | 11 |  | 24 | 10 | 1 | 46
| GDIA | 11 | 2 | 8 | 1 |  | 22
| I-ERP | 16 | 2 | 14 | 10 | 2 | 44
| ISIT | 124 | 25 | 21 | 18 | 6 | 194
| M&S Tech | 21 | 8 | 34 | 14 | 9 | 86
| OCETO | 18 | 9 | 24 | 24 | 12 | 87
| SQL Total | 330 | 50 | 167 | 86 | 36 | 669
VM
| EA |  |  | 8 | 3 |  | 11
| EPEO | 12 | 2 | 90 | 75 | 3 | 182
| EVDD | 30 |  |  |  |  | 30
| Ford Credit | 10 | 1 | 49 | 28 | 37 | 125
| Ford Pro & FCSD Tech | 12 |  | 37 | 22 | 5 | 76
| GDIA | 10 | 1 | 5 | 2 |  | 18
| I-ERP | 28 | 2 | 16 | 27 | 3 | 76
| ISIT | 157 | 40 | 52 | 51 | 7 | 307
| M&S Tech | 20 | 10 | 66 | 39 | 16 | 151
| OCETO | 26 | 11 | 48 | 57 | 24 | 166
| VM Total | 305 | 67 | 371 | 304 | 95 | 1142
| Grand Total | 956 | 140 | 606 | 465 | 219 | 1730
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: any DB migration that started in2024 but did not finish in 2024 will move to PLM